# Weekly Status Report

## Project Name: Mercury

## Project Manager: Mattias Hallberg

## **Date:** 2012-10-25

(Report Key: **GREEN = good/positive status**, **RED = needs attention/negative status**)

## Summary

* **Internal release for 1.6 was completed on schedule**.
* As of October 24, one week before public open, Rakuten Malaysia has collected 48 merchants,
* About 9000 products, 5246 Facebook fans and 673 Members. Comparing this with Rakuten

Indonesia's Go Live, where we had 28 merchants and 8000 products (books excluded), things are looking pretty good

* A total of 426 test cases were executed during a 5 hour post-deploy test cycle. A few issues were found and one critical fix was completed within one hour after deployment finished
* In preparation for Mall Open, maintenance will be done on both Oct 31 and Nov 1. This will include some enhancements and bug fixes as well
* **Several deferred bugs** (link) **need to be fixed and scheduled for upcoming service releases**
* Project schedule for future releases was updated (link)

## New Initiatives

* [Requirements] JIRA Components hierarchy was updated to enable easy requirements handling
* [Test/Automation] A project was started with the aim to create a test case management tool with integration to JIRA

## Blockers

* Awaiting CEO approval for public open on Nov 1

## Risks

* Due to the latest reorganization, roles and responsibilities are not clear which may cause poor response for Trouble Management. Project Management team will discuss with each group to ensure that the process is fully understood before Mall Open
* Full risk register (link)

## Milestones

* **Release Milestone Target Date Actual Date**
* 1.6 Specification Complete 9/11 9/24
* Code Complete 10/5 10/11
* Test Complete 10/24 10/23
* Internal Release 10/25 10/24
* Mall Open To Public 11/1 -

## Details

* Project Home Page (link)
* Project Schedule (link)
* Product Roadmap (link)
* JIRA Dashboards
  + Development Status (link)
  + Bug Status And Other Details (link)
  + Time Sheet Data (link)
  + Tasks Due (link)
  + Team Load (link)

## Metrics

## Test Status