## Slide 1: Product Backlog
Capability/Item | BV | Baseline
Buy an e-Ticket | 80% | 108SPs
Investigate CUTLASS interface/capabilities |  | 10 SPs
Investigate the basics of Pilot Timesheets | 10% | 20 SPs
Check Status of Flights | 10% | 40 SPs
SouvSite Maintenance |  | 27 SPs
Release Activities |  | 38 SPs
Chores |  | 92 SPs
Total 100% |  | 335 SPs

## Slide 2: Agile EVM
The ratio CPI = (budgeted $/SP) / (actual $/SP)
The ratio SPI = (actual SP/Sprint) / (budgeted SP/Sprint)