## Risk Register
Step 1: Risk Identification |  |  |  |  | Step 2: Risk Assessment |  |  | Step 3: Risk Response |  | Step 4: Monitor & Control
# | Stage | Opportunity / Threat | Risk | Detailed Description | Probability (1-5) | Cost Impact | Time Impact (Weeks) | Risk Owner | Contingency Plan | Status | Date Last Updated | Tracking Comments
1 | Development | Threat | SADAD setup | SADAD Payment gateway setup - SDK kit pending from client side (Bank verification pending from client side) | 3 | - | TBD | Client | Need to check with Bank -for verification process and SDK kit | Active (Ongoing) | Ist Dec
2 | Development | Threat | iPhoneX Support | iOS code base needs to be Supported for latest iPhoneX Devices | 1 | TBD | TBD | Clicklabs team | Find out internally with Tookan product team it this can supported | Active (Not Started)
3 | Development | Threat | iPhoneX Testing | iPhoneX needs to be tested for Agent App | 1 | TBD | TBD | Clicklabs team | Explore option of Simulator Testing | Active (Not Started)