## Sprint -Release Plan
Hourly allocation
Section | Sub Section | Sub Heading | Requirement | Backend | Frontend | iOS | Android
Customer application | IOS Android, Web | Aggregation | Ability to view and select meal category (cuisines) |  | 2 | 2 | 2 | Sprint3 | Release Plan
|  |  | Meal category will be based on the time of the day | 4 | 1 | 1 | 1 |  | Sprint 3 | 16th Oct- 2nd Nov
|  |  | Ability to view list of all the items under selected meal category |  | 2 | 2 | 2 |  | Sprint 4 | 3rd Nov- 20th Nov | Invoice Raised (cash-in done)
|  |  | Ability to select the quantity of an item |  | 2 | 2 | 2 |  | Sprint 5 | 20th Nov- 7th Dec
[9 empty] | Sprint 6 | 8th Dec- 20th Dec | Invoice to Raise
Merchant Panel | Web | Sign up & login | In case of sign up with email, a confirmation mail will be sent | 6 | 4 | 4 | 4
|  |  | OTP is also sent to the email |  | 2 | 2 | 2
|  |  | Once the store sign up successfully an activation email will be sent | 6 | 4 | 4 | 4
|  |  | Ability to add bank account number | 8 | 6 | 6 | 6
|  |  | When the store clicks on forgot password, a link will be sent on the registered email | 1
|  |  | Ability to view and select add ons | 6 | 2 | 2 | 2
|  |  | Add ons are listed by selected restaurant | 6
|  |  | Ability to select an item or add-on and add it to the cart |  | 3 | 3 | 3
|  |  | Ability to add/delete items from the cart |  | 1 | 1 | 1
|  |  | Ability to view total cost |  | 6 | 6 | 6
|  |  | Ability to enter the delivery location manually or by dropping pin on map |  | 2 | 2 | 2
|  |  | Ability to view list of ingredients and specify allergic ingredients in free text field | 6 | 4 | 4 | 4
|  |  | Ability to add instructions |  | 2 | 2 | 2 | Sprint4
|  |  | Ability to place order request | 6 | 4 | 4 | 4
|  | Promo | Ability for customer to apply the promo code | 4 | 2 | 2 | 2
|  |  | Promo codes will be based on either absolute discount or the percentage |  | 1 | 1 | 1
|  |  | Promo codes will be received by customer as push notification email or SMS from service owner | 10 | 4
|  |  | Ability for customer to share referral link |  | 2 | 2 | 2
|  | Matching | Assignment for delivery driver via Tookan | 20
|  |  | Ability to do chat with the restaurant and customer support (Integration with Fugu) | 8 | 6 | 6 | 6
|  | Notifications | A. Order confirmation (Integration with Tookan) | 12 | 8 | 8 | 8
|  |  | B. Delivery status: driver on the way, out for delivery, reached delivery location, delivery ended (Integration with Tookan) | 4 | 2 | 2 | 2
|  |  | C. New promo code | 2 | 1 | 1 | 1
|  |  | D. Invoice, customer will receive invoice of each order via email | 1
|  | Tracking | Ability to track driver via Tookan | 2 | 1 | 1 | 1
|  | Payment | Ability to add CC/DC details by scanning card | 4 | 2 | 2 | 2
|  |  | Ability to make online payment |  | 1 | 1 | 1
|  |  | integration with SADAD | 4 | 1 | 1 | 1
|  |  | Ability to make payment via in app wallet |  | 2 | 2 | 2
|  |  | Ability to make payment via cash | 6 | 8 | 8 | 8
|  | Review | Ability to give star rating and feedback to the delivery driver | 6 | 4 | 4 | 4 | Sprint5
|  |  | Free text box for feedback | 4 | 3 | 3 | 3
|  |  | Ability to add or delete a payment card (CC or DC) |  | 4 | 4 | 4
|  |  | Ability to add credits to in app wallet | 10 | 8 | 8 | 8
|  |  | Ability to view loyalty points pushed by service owner |  | 2 | 2 | 2
|  |  | Ability to view the upcoming orders |  | 2 | 2 | 2
|  |  | Ability to cancel an upcoming order | 4 | 1 | 1 | 1
|  |  | Ability to view the past orders |  | 1 | 1 | 1
|  | Contact us | Ability to view support phone number, support email address, physical address, website link |  | 2 | 2 | 2
|  |  | Ability to click on support phone number and directly place a call |  | 1 | 1 | 1
|  |  | Ability to click on support email address and be redirected to ‘Contact Form’ | 8 | 8 | 8 | 8
|  |  | Ability to do chat with the restaurant and customer support (Integration with Fugu) |  | 2 | 2 | 2
|  | Content | FAQ |  | 2 | 2 | 2
|  |  | Terms & Conditions | 6 | 2 | 2 | 2
|  |  | About us | 6
|  |  | Social network info |  | 3 | 3 | 3
|  | Aggregation | Ability to add driver details | 4 | 2 | 2 | 2
|  |  | Ability to select branch with whom driver is associated |  | 1 | 1 | 1
|  |  | Ability to add drivers on the platform and share login credentials with them | 4 | 1 | 1 | 1
|  |  | Ability to geofence the regions and manually mark operating area on map |  | 2 | 2 | 2
|  |  | Ability to select district from drop down | 6 | 8 | 8 | 8
|  |  | Ability to assign branch and drivers for each geofenced area | 6 | 4 | 4 | 4
|  |  | Ability to add branch details | 4 | 3 | 3 | 3
|  |  | Ability to add location of branch manually or dropping pin on map | 6 | 6 | 6 | 6
|  |  | Ability to select items available at branch | 8 | 8 | 8 | 8
|  |  | Ability to duplicate a branch | 1 | 1 | 1 | 1 | Sprint6
|  |  | Ability to add branch on the platform and share login credentials with them |  | 4 | 4 | 4
|  | View reports | Ability to view daily, weekly and monthly reports based on branch, area, driver, dishes and area delivered based on following KPIs | 10 | 8 | 8 | 8
|  |  | • Orders received • Orders rejected • Orders pending • Order delivered |  | 2 | 2 | 2
|  |  | Ability to view weekly and monthly reports for total sales per branch/ branch manager |  | 2 | 2 | 2
|  |  | Ability to view earnings reconciliation report for total earnings against each branch | 4 | 1 | 1 | 1
|  |  | Ability to view best zone and best branch based upon number of orders |  | 1 | 1 | 1
|  |  | Ability to view best selling meal and time |  | 2 | 2 | 2
|  | List Add-ons | Ability to list add-ons on the platform |  | 1 | 1 | 1
|  |  | Ability to enter details related to each add-on |  | 6 | 6 | 6
|  |  | Restaurant manager can upload excel for adding items |  | 2 | 2 | 2
|  | Role based access to branches | Ability to login with credentials shared by service owner | 6 | 4 | 4 | 4
|  |  | Toggle button to set open and close status for restaurant |  | 2 | 2 | 2
|  |  | Ability to provide reason for closing | 6 | 4 | 4 | 4
|  |  | Total Hours | 235 | 208 | 204 | 204

## Targeted Deliverables
1. Agregation in customer apps and website for restaurants | 27th Sep to 23rd Oct
| Section | Sub Section | Sub Heading | Requirement | Backend | Frontend | iOS | Android
| Customer application | IOS Android, Web | Aggregation | Ability to search for item in the search bar | 4 | 3 | 3 | 3
Green Highlighted : Done |  |  |  | Ability to browse cuisines or select delivery mode. Take away and Request for delivery | 6 | 6 | 6 | 6
|  |  |  | Ability to view list of all the restaurants based on customer’s location | 8 | 8 | 8 | 8
|  |  |  | Restaurant with minimum pick up will be shown on top in the list | 1 | 1 | 1 | 1
|  |  |  | Ability to choose from to view display, list or logos |  | 4 | 4 | 4
|  |  |  | Ability to view profile, restaurant info | 10 | 8 | 8 | 8
|  |  |  | Ability to select a restaurant |  | 2 | 2 | 2
|  |  |  | Ability to view and select meal category (cuisines) |  | 2 | 2 | 2
|  |  |  | Meal category will be based on the time of the day | 4 | 1 | 1 | 1
|  |  |  | Ability to view and select item category/sub category |  | 1 | 1 | 1
|  |  |  | Ability to view list of all the items under selected meal category |  | 2 | 2 | 2
|  |  |  | Ability to view and select item from list |  | 1 | 1 | 1
|  |  |  | Ability to view details related to each item | 8 | 8 | 8 | 8
|  |  |  | Customer can change the view from list to boxes |  | 2 | 2 | 2
|  |  |  | Ability to select the quantity of an item |  | 2 | 2 | 2
| Merchant Panel | Web | Sign up & login | Home page with option signup and login |  | 6 | 6 | 6
|  |  |  | Ability to sign up via email where restaurant manager will enter a valid email address |  | 2 | 2 | 2
|  |  |  | In case of sign up with email, a confirmation mail will be sent | 6 | 4 | 4 | 4
|  |  |  | OTP is also sent to the email |  | 2 | 2 | 2
|  |  |  | Once the store sign up successfully an activation email will be sent | 6 | 4 | 4 | 4
|  |  |  | Ability to set/edit weekly availability | 4 | 2 | 2 | 2
|  |  |  | Restaurant manager will mark available days in week and set opening, closing time against each day |  | 1 | 1 | 1
|  |  |  | Ability to set/edit standard preparation & delivery time | 10 | 4
|  |  |  | Ability to set/edit minimum order amount and delivery fee |  | 2 | 2 | 2
|  |  |  | Ability to view and select service: delivery, pickup & both |  | 2 | 2 | 2
|  |  |  | Ability to add bank account number | 8 | 6 | 6 | 6
|  |  |  | Ability to upload relevant documents | 12 | 8 | 8 | 8
|  |  | Login | Ability to login with email address and password | 4 | 2 | 2 | 2
|  |  |  | Ability to remember credentials | 2 | 1 | 1 | 1
|  |  |  | When the store clicks on forgot password, a link will be sent on the registered email | 1
|  |  |  | Ability to agree on both our terms & condition, service agreement | 2 | 1 | 1 | 1
2. Booking flow and my accounts for customer apps and website | 24th October - 27th Nov
|  |  |  | Ability to view and select add ons | 6 | 2 | 2 | 2
|  |  |  | Add ons are listed by selected restaurant | 6
|  |  |  | Ability to select an item or add-on and add it to the cart |  | 3 | 3 | 3
|  |  |  | Ability to add/delete items from the cart |  | 1 | 1 | 1
|  |  |  | Ability to view total cost |  | 6 | 6 | 6
|  |  |  | Ability to enter the delivery location manually or by dropping pin on map |  | 2 | 2 | 2
|  |  |  | Ability to view list of ingredients and specify allergic ingredients in free text field | 6 | 4 | 4 | 4
|  |  |  | Ability to add instructions |  | 2 | 2 | 2
|  |  |  | Ability to place order request | 6 | 4 | 4 | 4
|  |  | Promo | Ability for customer to apply the promo code | 4 | 2 | 2 | 2
|  |  |  | Promo codes will be based on either absolute discount or the percentage |  | 1 | 1 | 1
|  |  |  | Promo codes will be received by customer as push notification email or SMS from service owner | 10 | 4
|  |  |  | Ability for customer to share referral link |  | 2 | 2 | 2
|  |  | Matching | Customer will manually select a restaurant from list |  | 2 | 2 | 2
|  |  |  | Assignment for delivery driver via Tookan | 20
|  |  |  | Ability to do chat with the restaurant and customer support (Integration with Fugu) | 8 | 6 | 6 | 6
|  |  | Notifications | A. Order confirmation (Integration with Tookan) | 12 | 8 | 8 | 8
|  |  |  | B. Delivery status: driver on the way, out for delivery, reached delivery location, delivery ended (Integration with Tookan) | 4 | 2 | 2 | 2
|  |  |  | C. New promo code | 2 | 1 | 1 | 1
|  |  |  | D. Invoice, customer will receive invoice of each order via email | 1
|  |  | Tracking | Ability to track driver via Tookan | 2 | 1 | 1 | 1
|  |  | Payment | Ability to add CC/DC details by scanning card | 4 | 2 | 2 | 2
|  |  |  | Ability to make online payment |  | 1 | 1 | 1
|  |  |  | integration with SADAD | 4 | 1 | 1 | 1
|  |  |  | Ability to make payment via in app wallet |  | 2 | 2 | 2
|  |  |  | Ability to make payment via cash | 6 | 8 | 8 | 8
|  |  | Review | Ability to give star rating and feedback to the delivery driver | 6 | 4 | 4 | 4
|  |  |  | Free text box for feedback | 4 | 3 | 3 | 3
|  |  | Others (Side menu) | Ability to view profile | 6 | 6 | 6 | 6
|  |  |  | Ability to edit the profile | 8 | 8 | 8 | 8
|  |  |  | Ability to change the password | 1 | 1 | 1 | 1
|  |  |  | Ability to add or delete a payment card (CC or DC) |  | 4 | 4 | 4
|  |  |  | Ability to add credits to in app wallet | 10 | 8 | 8 | 8
|  |  |  | Ability to view loyalty points pushed by service owner |  | 2 | 2 | 2
|  |  |  | Ability to view the upcoming orders |  | 2 | 2 | 2
|  |  |  | Ability to cancel an upcoming order | 4 | 1 | 1 | 1
|  |  |  | Ability to view the past orders |  | 1 | 1 | 1
|  |  | Contact us | Ability to view support phone number, support email address, physical address, website link |  | 2 | 2 | 2
|  |  |  | Ability to click on support phone number and directly place a call |  | 1 | 1 | 1
|  |  |  | Ability to click on support email address and be redirected to ‘Contact Form’ | 8 | 8 | 8 | 8
|  |  |  | Ability to do chat with the restaurant and customer support (Integration with Fugu) |  | 2 | 2 | 2
|  |  | Content | FAQ |  | 2 | 2 | 2
|  |  |  | Terms & Conditions | 6 | 2 | 2 | 2
|  |  |  | About us | 6
|  |  |  | Social network info |  | 3 | 3 | 3
|  |  |  | Sign out |  | 1 | 1 | 1
3. Restaurant panel board and admin full access | 28th November- 22nd December
|  |  | Aggregation | Ability to add driver details | 4 | 2 | 2 | 2
|  |  |  | Ability to select branch with whom driver is associated |  | 1 | 1 | 1
|  |  |  | Ability to add drivers on the platform and share login credentials with them | 4 | 1 | 1 | 1
|  |  |  | Ability to geofence the regions and manually mark operating area on map |  | 2 | 2 | 2
|  |  |  | Ability to select district from drop down | 6 | 8 | 8 | 8
|  |  |  | Ability to assign branch and drivers for each geofenced area | 6 | 4 | 4 | 4
|  |  |  | Ability to add branch details | 4 | 3 | 3 | 3
|  |  |  | Ability to add location of branch manually or dropping pin on map | 6 | 6 | 6 | 6
|  |  |  | Ability to select items available at branch | 8 | 8 | 8 | 8
|  |  |  | Ability to duplicate a branch | 1 | 1 | 1 | 1
|  |  |  | Ability to add branch on the platform and share login credentials with them |  | 4 | 4 | 4
|  |  | View reports | Ability to view daily, weekly and monthly reports based on branch, area, driver, dishes and area delivered based on following KPIs | 10 | 8 | 8 | 8
|  |  |  | • Orders received • Orders rejected • Orders pending • Order delivered |  | 2 | 2 | 2
|  |  |  | Ability to view weekly and monthly reports for total sales per branch/ branch manager |  | 2 | 2 | 2
|  |  |  | Ability to view earnings reconciliation report for total earnings against each branch | 4 | 1 | 1 | 1
|  |  |  | Ability to view best zone and best branch based upon number of orders |  | 1 | 1 | 1
|  |  |  | Ability to view best selling meal and time |  | 2 | 2 | 2
|  |  | Add new item | Ability to view and select meal category |  | 1 | 1 | 1
|  |  |  | Ability to view and select sub category | 8 | 8 | 8 | 8
|  |  |  | Ability to add a new category if category is not listed on the platform |  | 2 | 2 | 2
|  |  |  | Ability to add a new sub-category if category is not listed on the platform |  | 2 | 2 | 2
|  |  |  | Ability to list item on the platform | 6 | 2 | 2 | 2
|  |  | Edit items | Ability to view list of already listed items | 6
|  |  |  | Ability to edit/remove item form list |  | 3 | 3 | 3
|  |  | List Add-ons | Ability to list add-ons on the platform |  | 1 | 1 | 1
|  |  |  | Ability to enter details related to each add-on |  | 6 | 6 | 6
|  |  |  | Restaurant manager can upload excel for adding items |  | 2 | 2 | 2
|  |  | Role based access to branches | Ability to login with credentials shared by service owner | 6 | 4 | 4 | 4
|  |  |  | Toggle button to set open and close status for restaurant |  | 2 | 2 | 2
|  |  |  | Ability to provide reason for closing | 6 | 4 | 4 | 4
[5 empty] | 341 | 319 | 311 | 311

## Task overview
Task Overview- Nov- Dec 2017
Development Plan | Current state- in Progress
Mobile app:
1. Shopping cart
2. Promo code
3. Booking flow
4. All orders in ham menu
5. Edit my account
6. Push notifications
7. Credits UI and data from backend
8. Twilio integration for sms notification
9. Language conversion
Admin panel:
1. Sub categories
2. Products
3. Orders
4. Push notifications
5. Promo codes
6. Customers
7. Suggestion list
Website
frontend - registration, social login
Listing Display
Geo location
8. Restaurant and Branches setup
-Restaurant manager- signup ,- approved by service owner–
- services to use – edit update availablity, weekly etc..
min. Order amount, bank account to add
- can upload excel perdefined format from Service owner- for adding items
- Role base access to branches- recieve order view order etc...
- Star Rating
- Loyalty points
9. Payment gateway
- add cc/dc details by scanning card - card.io integration
- credit debit card: SADAD
- appwallet
- cash
10. Tookan system Integration - Driver App
- Driver Tracking via Tookan
11. Advertisement system
12. Chat Fugu Integration
13. Webhook option (url hit notification) for notification
14. App analytics: client to provide google analytics- Google analytics dashboard

## Dependencies
From client side
Facebook account setup
Payment Gateway-Merchant login details