## Pre-Training
# | Ans |  | # | Ques
1 | C |  | 1 | Agile is
A |  |  | A | Project Management Framework
B |  |  | B | Project Delivery Framework
C |  | x | C | A set of delivery methodologies
D |  |  | D | Mini Waterfall Methodology
2 | D |  | 2 | An Agile project should have minimum ……… phases.
A |  |  | A | 0
B |  |  | B | 1
C |  |  | C | 2
D |  | x | D | Not Applicable
3 | D |  | 3 | Agile Methods are applicable for
A |  |  | A | Small project
B |  |  | B | Medium size project
C |  |  | C | Big Size Project
D |  | x | D | Any Size
4 | B |  | 4 | Agile Manefesto has how many values
A |  |  | A | 2
B |  | x | B | 4
C |  |  | C | 10
D |  |  | D | Not Applicable
5 | D |  | 5 | Agile is applicable when
A |  |  | A | Requirements are unstable
B |  |  | B | Technology is unstable
C |  |  | C | Policies are unstable
D |  | x | D | Any of of the above
6 | D |  | 6 | Agile is suitable for
A |  |  | A | IT Project
B |  |  | B | Construction Project
C |  |  | C | R&D Projects
D |  | x | D | All of Above
E |  |  | E | Can't Say
7 | B |  | 7 | Meaning of Agile practice is same as waterfall processes
A |  |  | A | Yes
B |  | x | B | No
C |  |  | C | Not enough information to answer this
D |  |  | D | May be, may not be
8 | B |  | 8 | Last responsible minute concept of agile (choose the best answer)
A |  |  | A | Do not make mistake on your own let others do it and then learn from others
B |  | x | B | Do not make decision till last moment
C |  |  | C | Do not hurry in project. Go slow initially.
D |  |  | D | Wait till you get all the information
9 | B |  | 9 | Agile projects do not have documentation (choose the best answer)
A |  |  | A | Yes, it is true.
B |  | x | B | No, it is not true.
C |  |  | C | Only if this is requested by stakehodlers
D |  |  | D | Cann't say
10 | D |  | 10 | Agile manifesto has how many principles
A |  |  | A | 9
B |  |  | B | 10
C |  |  | C | 11
D |  | x | D | 12
11 | C,D |  | 11 | Incremental Development Means (more than one options are correct)
A |  |  | A | Develop solution slowly because there is risk
B |  |  | B | Develop many times
C |  | x | C | Deliver high value items first
D |  | x | D | Deliver solution using those requirements which are clearly understood
12 | A,D |  | 12 | Iterative Development means (more than one options are correct)
A |  | x | A | Do not develop solution in only one big step.
B |  |  | B | Deliver high value items first
C |  |  | C | Deliver solution using those requirements which are clearly understood
D |  | x | D | Develop solution slowly because there is risk of poor understanding in the start
13 | A,D |  | 13 | Empirical Process (more than one options are correct)
A |  | x | A | Where output cannot be predicted based on Input
B |  |  | B | Where output can be predicted based on Input
C |  |  | C | Tightly defined process
D |  | x | D | Loosely defined process
14 | C |  | 14 | Self Organizing Team is
A |  |  | A | Value of Agile
B |  |  | B | Principle of Agile
C |  | x | C | Practice in Agile
D |  |  | D | Process in Agile
15 | B |  | 15 | Working extra hours in Agile project is
A |  |  | A | Normal Practice
B |  | X | B | Against the Agile Principle Sustainable Pace
C |  |  | C | Depends upon project
D |  |  | D | Cann't say
16 | A |  | 16 | Iteration Burndown Chart shows
A |  | X | A | Number of remaining hours
B |  |  | B | Number of hours spent
C |  |  | C | Story point remaining
D |  |  | D | Story point completed
17 | B |  | 17 | Velocity is
A |  |  | A | No of user stories done by a person in an iteration
B |  | X | B | No of user stories done in an iteration
C |  |  | C | No of user stories done by a person in an Release
D |  |  | D | No of user stories done in an Release
18 | D |  | 18 | On a particular day Risk burndown chart shows
A |  |  | A | Number of risk remaining
B |  |  | B | Number of risk occurred
C |  |  | C | Number of hours spent in managing risk
D |  | X | D | Number of hours by which a project may be delayed if risk occurred
19 | B |  | 19 | Scrum is
A |  |  | A | Agile principle
B |  | X | B | Agile Method
C |  |  | C | Project Management Best Practice
D |  |  | D | Project Management Approach
20 | B |  | 20 | Daily standup meeting does not have one of these questions
A |  |  | A | What did you do yesterday?
B |  | X | B | How many hours you worked yesterday?
C |  |  | C | What are your planning to do today?
D |  |  | D | Is there any impediments on way today?
21 | D |  | 21 | MoSCoW prioritization does not have one of these
A |  |  | A | Must have
B |  |  | B | Should Have
C |  |  | C | Could Have
D |  | X | D | Would Have
22 | C |  | 22 | A user story is
A |  |  | A | Task which should be done to make software product
B |  |  | B | Functionality which should developed
C |  | X | C | Functionality which has business value
D |  |  | D | Non-functional requirement
23 | E |  | 23 | Which one of these is not scrum meeting
A |  |  | A | Product Grooming
B |  |  | B | Sprint Planning
C |  |  | C | Retrospective Planning
D |  |  | D | Sprint Demo Meeting
E |  | X | E | Sprint Work Review Meeting
24 | C |  | 24 | Daily stand meeting is not
A |  |  | A | 15-20 Meeting Session
B |  |  | B | Information sharing session
C |  | X | C | Reporting Session
D |  |  | D | Only Pigs are allowed to speak
25 | B |  | 25 | One of these is not scrum values
A |  |  | A | Focus
B |  | X | B | Trust
C |  |  | C | Openness
D |  |  | D | Respect
E |  |  | E | Courage
F |  |  | F | Commitment
26 | D |  | 26 | Which one of the following is not role in Scrum
A |  |  | A | Product Owner
B |  |  | B | Scrum Master
C |  |  | C | Development Team
D |  | X | D | Project Manager
27 | C |  | 27 | Which of the following is not agile manifesto principle
A |  |  | A | Individuals and interactions over processes and tools
B |  |  | B | Working software over comprehensive documentation
C |  | X | C | Contract negotiation over customer collaboration
D |  |  | D | Responding to change over following a plan

## Post-Training
# | Ans |  | Ques
1 | B |  | Refactoring is Practice of
A |  |  | Scrum
B |  | x | XP
C |  |  | DSDM
D |  |  | Lean
2 | B |  | Tracer Bullet Solution is
A |  |  | Use and throw solution
B |  | x | Reuse and built and previous solution
C |  |  | Not related to Agile Development
D |  |  | Used in Agile Project for Armed Forces
3 | A, C |  | Technical spike is (more than one options are correct)
A |  | x | Fixed duration work
B |  |  | Work to solve the problem
C |  | x | Work to understand the problem
D |  |  | Estimatable work
4 | D |  | One of the following is NOT the characterstics of daily stand up meeting
A |  |  | Everyday at Same Location
B |  |  | Everyday at Same Time
C |  |  | Everyday Same 3 Question
D |  | x | Depends upon project
5 | A |  | Burndown chart shows
A |  | x | Remaing work
B |  |  | Actual work done
C |  |  | Actual effort spent
D |  |  | Planned work
6 | B |  | Velocity of two projects can be compared
A |  |  | Yes
B |  | x | No
C |  |  | Cann't say
D |  |  | Depends upon PMO
7 | B |  | Risk burndown down chart shows
A |  |  | Number of risks
B |  | x | Expected Impact of remaining risks
C |  |  | Probability of remain risks
D |  |  | Contingency Reserves for managing risk
8 | B |  | Your colleague say to you that they are following all the practices of scrum there for they are doing agile fully. Do you agree?
A |  |  | Yes
B |  | x | No, any project is being managed using agile or not depends whether agile values and principles are implemented in true sprit
C |  |  | Depends upon organization that how they have defined their agile method
9 | A |  | TDD is practices of
A |  | x | XP
B |  |  | Lean
C |  |  | DSDM
D |  |  | FDD
E |  |  | Scrum
10 | A |  | Poka-yoka is about
A |  | x | Mistake proofing
B |  |  | Help your peer in writing better code
C |  |  | Help your tester in writing better test case
D |  |  | Do not disturb development team
11 | B,C |  | User story is (More than one options are correct)
A |  |  | Requirement specification
B |  | x | A promise of PO to the Development team that he will explain the work in details when they start working on this
C |  | x | High level requirement from end user's perspective
D |  |  | Functional requirement
12 | B |  | Story points is
A |  |  | Count of user stories
B |  | x | Sum of complexity of user stories
C |  |  | Count of functional requirements
D |  |  | Sum of efforts required to complete user stories
13 | B |  | At the end of sprint, ideally who should present the product to customer
A |  |  | Product Owner
B |  | x | Scrum Master
C |  |  | Development Team
D |  |  | Testing Team
14 | B |  | You colleague mentioned to you that their latest sprint is complete and now work has been given to testing team for testing the features implemented in this sprint. Do you think your colleague is implementing Agile in his project.
A |  |  | Yes, he is doing agile project management. Product need to tested before delivery.
B |  | x | No, sprint is complete only potentially shippable product is ready
C |  |  | Cann't say
D |  |  | Yes, agile project can have mini teams like testing, development etc.
15 | B |  | Metrics to monitor, control and manage agile and normal project are same
A |  |  | Yes
B |  | x | No
C |  |  | Cann't say
D |  |  | Depends upon PMO