## Slide 1
Project Management Workshop
Trainer : Hari Prasad Thapliyal
(PMP, PMI-ACP, CSM, SPOC, SDC, SAM, MCT, SCT, MBA, MCA, PGDOM, PGDFM, CIC, PRINCE2-Practitioner, ZED Master Trainer)
[PMI-ACP : #318050]
[PMP : #1563385]
PMP, 'PMI-ACP‘ and 'PMI‘ are a registered marks of the Project Management Institute, Inc.
This content is legal only for participants of Toshiba Bangalore Nov’17 Training
Copyright: Vedavit Project Solutions
hari.prasad@vedavit-ps.com

## Slide 2: Workshop Agenda
Day 1:
  PMI & PMP
  Project Management Framework
Day 2:
  PM Framework Continue…
  Project Integration Management
Day 3:
  Project Scope Management
  Project Time Management
Day 4:
  Project Cost Management
  Project Quality Management
Day 5:
  Project Human Resource Management
Day 6:
  Project Communication Management
  Project Stakeholder Management
Day 7:
  Project Risk Management
  Project Procurement Management
  Professional Responsibility
Day 8:
  Review All
  Case Study
  200 Question Exam & Review
  Demo Online Tutorial

## Slide 3: Workshop Agenda
Day 1:
  PMI & PMP
  Project Management Framework
Day 2:
  Project Integration Management
  Project Scope Management
  Project Time Management
Day 3:
  Project Cost Management
  Project Quality Management
  Project Human Resource Management
Day 4:
  Project Communication Management
  Project Risk Management
  Project Procurement Management
  Project Stakeholder Management
  Professional Responsibility

## Slide 4: Introduction

## Slide 5: Project Management Framework

## Slide 7: Topics
Project
Operations
Project Constraints
Project Phases, Milestones, Deliverables, Activities
Project Lifecycle (PLC) & Level of Activities
Typical Costing & Staffing across PLC
Risk, Cost of Change in PLC
Project Boundary
Relationship between Process Group & Phases
Project Management
Program Management
Portfolio Management
Program Management Office
Project Stakeholders
Stakeholder Register
Organization Types & Influence of Project Success
Project Management Methodologies
Configuration Management
Progressive Elaboration
Rolling Wave Planning
Project Documents
Project Management Plan
Organizational Process Assets
Enterprise Environmental Factors
Project Selection Criteria
Expert Judgement
Facilitation Techniques
Analytical Techniques
Meetings
Project Manager Responsibilities
Project Management Knowledge Areas
Process Groups

## Slide 8: What is Project???

## Slide 9: What is Project?
  Project – A temporary endeavor undertaken to create a unique product, service or result
How Temporary?
  Has a definite beginning and end, not an on-going effort
  Ceases when objectives have been attained
  Team is disbanded upon project completion
Unique?
  The product or service is different in some way from other product or services
  Product characteristics are progressively elaborated

## Slide 10: Project has…
Project Characteristics
  Goal (measurable/verifiable) Oriented
  Finite duration with a beginning and end
  Uniqueness to a great extent and related uncertainties
  Coordinated undertaking of interrelated activities
  Performing the activities involve resources
  Resources cost money

## Slide 11: Source of Project?
Need for improvement
Market Competition
Strategic/ Mission/ Vision
Government Regulation
Environmental Forces

## Slide 12: “Projects” different from “operations”?
Contrast Projects & Operations
  Projects
  Permanent Project Charter
  Catalyst for change
  Unique product or service
  Heterogeneous teams
  Start and end date
  Progressive elaboration
  Operations
  Semi-permanent charter
  Maintains status quo
  Standard product or service
  Homogeneous teams
  Ongoing
  Predefined product

## Slide 13: Project Constraints
Scope
Cost
Risk
Schedule
Resource
Project and Product Quality

## Slide 14: Project Phases
Project Phases
Projects are divided into phases where extra control is required to effectively manage the completion of the major deliverables
Collectively, the project phases put together is known as Project life cycle
Each phase is marked by one or more tangible verification work product
The conclusion of a project phase is generally marked by a review
The phase end points are referred to as phase exits, milestones, phase gates, decision gates, stage gates or kill points
Starting a phase before approval of deliverables of a previous phase is called Fast Tracking
Phases are not cyclical they are sequential
Phases are not deliverables but deliverables are part of a Phase
E.g. Product Feasibility, Product Prototyping, Product Design, Development, System Testing, Deployment

## Slide 15: Milestones, Deliverables
Deliverables
  Work product, product component developed by the project team
  E.g. Wireframe, Database ER Diagrams, Sequence Diagram, Test Case, Test Results, Any Feature of the Product.
Milestone
  Zero Duration Activity. Mark of Completion of some set of activities with deliverables
  E.g. Design Complete, Security Testing Complete, Requirement Gathering Complete, Quality Audit Complete, Development Complete, Deployment Complete

## Slide 16: Project Lifecycle (PLC) & Level of Activities
Source PMBOK Guide Version 5.0

## Slide 17: Typical Costing & Staffing across PLC
Source PMBOK Guide Version 5.0

## Slide 18: Risk, Cost of Change in PLC
Source PMBOK Guide Version 5.0

## Slide 19: Project Boundaries are Important!
Source PMBOK Guide Version 5.0
Project Boundaries

## Slide 20: Relationship between Process Group & Phases
Source PMBOK Guide Version 5.0

## Slide 21: Project Management
Project Management
  The application of knowledge, skills, tools and techniques to project activities in order to meet the project requirements

## Slide 22: What is Program?
Project Management Context
Group of related projects managed in a coordinated way to obtain the benefits and control which will not be possible from managing them individually
Scope is least important. Benefit(s) are primary goal. Program manager is not responsible for delivery but for benefit realization. Addition/removal of projects in a program is in the hand of Program Manager
Several projects are required under a program because of different technology, different skills & different kind of teams, parallel work, different type of deliverables.
e.g. Bringing a new product (from conceptualization to Sale all project), New satellite in space, Health improvement of a cancer patient. An IT company want to enter into new market with Cloud Services for the customer.

## Slide 23: Project Portfolio Management
Project Management Context
Collection of projects or programs and other work that are grouped together to facilitate effective management of that work to meet strategic business objectives
CEO (Mission/Vision)
Laptop
Consumer Electronics Company
TV
Servers
OS
Portfolios
Health
Education
Rehabilitation
NGO
Strategy

## Slide 24: Relationship Between PPP
CEO
Portfolio 1
Portfolio 2
Program 1
Project A
Sub Portfolio 1-1
Sub Portfolio 1-2
Program 2
Project 1
Project 2
Program 3
Project 3
Project 4

## Slide 25: What is PMO?
Project Management Office
Managing shared resources across all project administered by PMO
Identifying and developing project management methodology, best practices and standards
Coaching, mentoring, training and oversight
Monitoring compliance with project management standards, policies, procedures and templates via project audits
Developing and managing project policies, procedures, templates and other shared documentation (organizational process assets), and
Coordinating communication across projects

## Slide 26: Who are Stakeholders?
Stakeholders
Source PMBOK Guide Version 5.0
  Persons or organizations who are actively involved in the project or whose interests maybe positively or negatively affected by the performance or completion of the project

## Slide 27: Stakeholders
Source PMBOK Guide Version 5.0

## Slide 28: Stakeholder Register
ID
Name
Department
Internal vs External
Designation
Manager
Power (1-10)
Interest (1-10)
Current Position (Favorable, Against, Neutral)
Needed Position
Person Attributes (food, philosophy, ideology etc)
Person Preferences
Contact Details

## Slide 29: Organizational Types
  Functional
  Matrix
        Weak Matrix
        Balanced Matrix
        Strong matrix
  Projectized

## Slide 30: Functional
Staff
Staff
Functional Manager
Staff
Staff
Functional Manager
Staff
Staff
Staff
Functional Manager
Chief Executive
Project Coordination
Staff
Staff

## Slide 31: Weak Matrix
Staff
Staff
Staff
Functional Manager
Staff
Staff
Functional Manager
Staff
Staff
Staff
Functional Manager
Chief Executive
Project Coordination
Staff

## Slide 32: Balance Matrix
Staff
Staff
Project Manager
Functional Manager
Staff
Functional Manager
Staff
Functional Manager
Chief Executive
Project Coordination
Staff
Staff
Staff
Staff

## Slide 33: Strong Matrix
Staff
Functional Manager
Staff
Functional Manager
Staff
Functional Manager
Chief Executive
Project Coordination
Staff
Manager of Project Managers
Project Manager
Project Manager
Project Manager
Staff
Staff
Staff
Staff
Staff

## Slide 34: Projectized Matrix
Staff
Project Manager
Chief Executive
Project Coordination
Project Manager
Project Manager
Staff
Staff
Staff
Staff
Staff
Staff
Staff
Staff

## Slide 35: Organizational Influence
Source PMBOK Guide Version 5.0

## Slide 36: Project Management Methodologies
All projects are not same. Bases on the project characteristics a project manager need to select a right PMM to deliver a project successfully. Broadly methodologies can be categorized in the 3 groups.
Waterfall Development
Iterative Development
Agile Development

## Slide 37: Configuration Management System
A system to manage project artifacts, project’s product and project’s product’s components.
It helps in versioning, naming, storing, archiving, backup, securing project and product output.
e.g. SVN, VSS, TFS

## Slide 38: Progressive Elaboration
Project scope unfolds during the project execution. Scope of the next phase depends upon the output or success of previous phase.
It is Scope Management Concept.

## Slide 39: Rolling Wave Planning
Activities of any deliverable can be known when we know what need to delivered.
Attribute of the activities can be known only when we know what are the activities and what is deliverable.
It is Time Management Concept.

## Slide 40: Project Documents
Documents being managed by the project team to perform the project
Document provided by customers, vendors, government agencies, management
Documents which are prepared by the team like Design Related, Requirement Related, Issue Register, Risk Register, Change Log
All document must be managed using some Configuration Management Tool.

## Slide 41: Project Management Plan
Project Management Plan includes
  All Subsidiary Plan (Configuration, Cost, Risk etc)
  All Baselines Related to Project
  Project Management Methodology
  Project Lifecycle and Project Phases
  Process Tailored List
  Tailored Process

## Slide 42: Subsidiary Plan
Subsidiary plan need to be developed for each aspect of the project. For every aspect (Scope, Time, Cost, Quality, Resources, Communication, Risk, Stakeholder) you need to know following
What are the activities which need to be done?
Who will perform these? Is any training required to perform these activities.
When these activities will be performed?
How will you measure success?
What tool you will use for this?
How will you execute the work of this aspect?
How will you control this aspect?
Most of these activities are related to Planning of the Plan and NOT of the planning of Execution

## Slide 43: Organizational Process Assets
Process Assets which created by the organization while doing the project in past
Processes, Standards, Guidelines, Checklist, Templates standardized by the Quality Department or PMO
Lessons learned report of the previous projects
Consider them for project Initiation, Planning, Executing, Monitoring & Controlling and Closing. Do not reinvent the wheel in project management.
e.g. Time/Cost/Resource Estimation database, Risk database, Issue Register, Skills Database

## Slide 44: Enterprise Environmental Factors
Constraints which are not in control of a Project Manager and the project manager has to consider them to make project successful.
These constraints are imposed by environment of those enterprises which are involved in the project
Consider them for project Initiation, Planning, Executing, Monitoring & Controlling and Closing
e.g. Skill Availability, Market Condition, Attitude of People, Organization Culture, Climatic Condition, Political Condition, Bosses etc.

## Slide 45: Project Selection Criteria
PBP- Payback Period is a time in which original invest is realized.
PV = FV / (1+ r)^n
  PV= Present Value
  FV= Future Value
  r = Discount Rate
  n = Number of Years
NPV = Inflow – Outflow (Take Positive Value)
IRR = A discount rate at which [Outflow – Inflow =0 ]
BCR = Benefits (Present Value) / Cost (Output)

## Slide 46: Expert Judgement
Being an industry neutral, domain neutral, culture neutral standard PMBOK provides you a unique tool to deliver a successful project. This tool is called expert judgment.
Project managers highly rely on industry specific skills, input from local market experts, those who have done similar work earlier
E.g. SME, A department within Organization, Industry Group, Consultants, Experienced People within Org or Industry

## Slide 47: Facilitation Techniques
Facilitation techniques enable us to conduct the fruitful sessions.
Structured problem solving/decision making
Working in pairs or trios
Three star rating
Round Robin
Ranking
Multi voting
Meta-planning (PostIt Note on Wall)
Ice Breakers
Group Review
Go Wild (wouldn’t it be good if…)
Flipchart
Brainstorming/ Reverse Brainstorming
Action planning

## Slide 48: Analytical Techniques
Analytical techniques enable us to examine complex relationships between variables
Regression Analysis (Dependent/outcome variable is directly affected by one or more independent variables)
Grouping Methods
BCG (Boston) matrix
Brainstorming
Benchmarking
Gap Analysis
Mind Maps
Pareto principle, Pareto principle 80-20 rule
Six Questions
SWOT Analysis
Causal Analysis
Root Cause Analysis
Forecasting Methods (time series, simulation, scenario building etc)
Failure Mode and Effect Analysis (FMEA)
Fault Tree Analysis (FTA)
Reserve Analysis
Trend Analysis
Earned Value Management
Variance Analysis

## Slide 49: Meetings
Meetings with stakeholders helps us understand their viewpoint which is critical for making decisions.
F2F
Virtual
Formal
Informal
Standup Meeting
Kickoff Meetings
Adhoc Meeting
Review Meeting
Off-site Meetings
On-Site Meeting

## Slide 50: PM Competencies
A Framework
Project Manager Competency Development Framework- 2nd Edition, 2007

## Slide 51: Project Manager Responsibilities
Project Manager’s Role
Estimates of size, efforts & schedule
Risk identification, analysis, prioritization, monitoring & control
Resource allocation, resource backup and utilization
Scope management
Communication- reviews, steering committee meetings, stakeholder identification and expectation management
Stakeholder Expectation Management
Defect free product delivery on time within budget
Team motivation, team management, training & development, appreciation, career planning, interview
Deliver as per contract & proposal
Procure as per contract & proposal
Configuration management, data backup
Quality planning
Cost optimization
Presales & proposals
Technical guidance to team – if team members are not available do their work (after project manager has completed his work & he has spare time)

## Slide 52: Project Manager Responsibilities
Project Manager’s Responsibilities in Project Lifecycle
Initiating a Project
  Project aligned with org objectives & customer needs
  High-level risks, assumptions and constraints are understood
  Stakeholders identified and their need are understood
  Project Charter approved
Planning a Project
  Project scope agreed
  Project schedule approved
  Cost budget approved
  Project team identified with roles and responsibilities agreed
  Communication activities agreed
  Quality management process established
  Risk response plan approved
  Integrated change control processes defined
  Procurement plan approved
  Project Plan approved

## Slide 53: Project Manager Responsibilities
Project Manager’s Responsibilities in Project Lifecycle
Executing a Project
  Project scope achieved
  Project stakeholders expectations managed
  Human resource managed
  Quality managed against plan
  Material resources managed
Monitoring & Controlling a Project
  Project tracked and status communicated to stakeholders
  Project change is managed
  Quality is monitored and controlled
  Risk is monitored and controlled
  Project team managed
  Contract administered
Closing a Project
  Project outcomes accepted
  Project resources released
  Stakeholder perceptions measured and analyzed
  Project formally closed

## Slide 54: Project Manager Competencies
Personal Competence
Communication
Leading
Managing
Cognitive Ability
Effectiveness
Professionalism

## Slide 55: Project Management Knowledge Areas
2- Scope
3-Time
4- Cost
5- Quality
6- Human Resources
7- Communication
8- Risk
9- Procurement
10- Stakeholders
1- Integration
Project Manager

## Slide 56: Process Groups
Initiating
Planning
Executing
Monitoring & Controlling
Closing