## Slide 1: Project Time Management

## Slide 2: Project Time Management

## Slide 3: Project Time Management
  “Doing your project without a plan is like watching television with someone else holding the remote control”- Peter Turla
  "I made this letter longer than usual because I lack the time to make it shorter." – Pascal
  “Time is a great teacher, but unfortunately it kills all its pupils." - Hector Louis Berlioz
  "The bad news is time flies. The good news is you're the pilot." - Michael Altshuler

## Slide 4: Project Time Management
  Processes required to manage timely completion of the project.

## Slide 5: Project Time Management
  Plan Schedule Management [PLANNING]
  Define Activities [PLANNING]
  Sequence Activities [PLANNING]
  Estimate Activity Resources [PLANNING]
  Estimate Activity Durations [PLANNING]
  Develop Schedule [PLANNING]
  Control Schedule [M&C]

## Slide 6: 13. Plan Schedule Management
Establishing the policies, procedures and documentation for planning, developing, managing, executing, and controlling the project schedule

## Slide 7: Plan Schedule Management
Project Management Plan
Project Charter
Enterprise Environmental Factors
Organization Process Assets
Expert Judgement
Analytical techniques
Meetings
Schedule Management Plan
Project Time Management
Project Planning

## Slide 8: Schedule Management Plan
It includes
  Scheduling tools to be used
  Level of accuracy
  Units of measure for each resource
  Organizational procedure links
  Process of updating the progress in schedule model
  Control thresholds
  Rules of performance measurement (baselines, %complete, fixed formula etc.)
  Define scheduling reporting format

## Slide 9: 14. Define Activities
Identifying the specific actions to be performed to produce the project deliverables

## Slide 10: Define Activities
Schedule Management Plan
Scope Baseline
Enterprise Environmental Factors
Organization Process Assets
Decomposition
Rolling Wave Planning
Expert Judgement
Activity List
Activity Attributes
Milestone List
Project Time Management
Project Planning

## Slide 11: Activity Attributes
Dependency
Location of performance
Type of dependency
Level of efforts (work contour)
Efforts required
Related Deadline
Related WBS account
Critical activity
Type of task (fixed duration, resources, work)
Resource & skills required
Duration
Lead & Lag

## Slide 12: Discussion/Exercise 12
Write activities & their attributes for previously created 2 level WBS for your project
5 Minutes

## Slide 13: 15. Sequence Activities
Identifying and documenting relationships among the project activities.

## Slide 14: Sequence Activities
Schedule Management Plan
Activity List
Activity Attributes
Milestone List
Project Scope Statement
Enterprise Environmental Factors
Organization Process Assets
Precedence Diagramming Method
Dependency Determination
Leads and Lags
Project Schedule Network Diagrams
Project Documents Updates
Project Time Management
Project Planning

## Slide 15: Discussion/Exercise 13
Sequence Previously activities of your project write FS, SF, FF, SS after the activities
FS- (Finish first to start the next) Documentation – Review
FF- (Finish next to finish the previous) Documentation & Product
SF- (Start next to finish the previous) Shift working environment, changing mortor
SS- (Start next to start previous) Listening & Speaking, Start meeting & Start a topic to discuss
2 Minutes

## Slide 16: Precedence Diagramming Method (PDM)
Also known as Activity on Nodes (AON)
Notes: 134

## Slide 17: Network Development
Precedence Diagramming Method (AON)
Start
D
E
F
A
B
C
Finish

## Slide 18: Network Development
Precedence Diagramming Method (AOA)
Start
Finish
A
B
C
D
E
F

## Slide 19: 16. Estimate Activity Resources
Estimating the type and quantities of material, people, equipment or supplies required to perform each activity.

## Slide 20: Estimate Activity Resources
Schedule Management Plan
Activity List
Activity Attributes
Resource Calendars
Risk Register
Activity Cost Estimates
Enterprise Environmental Factors
Organization Process Assets
Expert Judgement
Alternatives Analysis
Published Estimated Data
Bottom-up estimating
Project Management Software
Activity Resource Requirements
Resource Breakdown Structure
Project Documents Updates
Project Time Management
Project Planning

## Slide 21: Resource Breakdown Structure
Project ABC RBS |  |  |  |  |  |  |  |  |  |  |  | 
Work |  |  |  |  |  |  |  |  |  |  | Material | Expenses
PM (1) | Config Mgmt |  | Technical Leaderhsip |  |  | Dev Team |  |  | Test Team |  |  | 
 | Config Mgr | Release Mgr | Arch (1) | UIExpert (1) | DBA (1) | Sr.Dev (4) | Jr.Dev (3) | TL (1) | Test Mgr | Tester (4) | Laptop (10 Units) | Procurement Team
 |  |  |  |  |  |  |  |  |  |  | Desktop (Units) | Systems Team
 |  |  |  |  |  |  |  |  |  |  | Leaseline (2 Mpbs) | Travel Cost (3 People)
 |  |  |  |  |  |  |  |  |  |  | Servers (2 Units | Boarding Lodging Cost (60 Days)
 |  |  |  |  |  |  |  |  |  |  |  | HR

## Slide 22: Discussion/Exercise 14
Estimate Activity Resources for previously sequenced activities of your project
2 Minutes

## Slide 23: 17. Estimate Activity Durations
Approximating the number of work periods needed to complete individual activities with estimated resources.

## Slide 24: Estimate Activity Durations
Schedule Management Plan
Activity List
Activity Attributes
Activity Resource Requirements
Resource Calendars
Project Scope Statement
Risk Register
Resource Breakdown structure
Enterprise Environmental Factors
Organization Process Assets
Expert Judgement
Analogous Estimating
Parametric Estimating
Three-point estimates
Group Decision Making Techniques
Reserve Analysis
Activity Duration Estimates
Project Documents Updates
Project Time Management
Project Planning

## Slide 25: PERT – Program Evaluation and Review Technique
PERT Estimate = (Optimistic + 4 * Most Likely + Pessimistic)/6
Standard Deviation (using PERT) = (Pessimistic-Optimistic)/6
Variance (using PERT) = ( (Pessimistic - Optimistic)/6)2

## Slide 26: Discussion/Exercise 15
Estimate Activity Duration for activities where resources are identified
5 Minutes

## Slide 27: 18. Develop Schedule
Analyzing activity sequences, durations, resource requirements and schedule constraints to create the project schedule.

## Slide 28: Develop Schedule
Schedule Management Plan
Activity List
Activity Attributes
Project Schedule Network Diagrams
Activity Resource Requirements
Resource Calendars
Activity Duration Estimates
Project Scope Statement
Risk Register
Project staff assignment
Resource Breakdown structure
Enterprise Environmental Factors
Organization Process Assets
Schedule Network Analysis
Critical Path Method
Critical Chain Method
Resource Optimization techniques
Modeling Techniques
Leads and Lags
Schedule Compression
Scheduling Tool
Schedule baseline
Project Schedule
Schedule Data
Project Calendars
Project Management Plan Updates
Project Documents Updates
Project Time Management
Project Planning

## Slide 29: Resource Optimization techniques
Resource Levelling
Ensure resource are not allocated more than their availability for the given project. Can lead to change in critical path.

## Slide 30: Resource Optimization techniques
Resource Smoothing
  Adjust activities in such a way that resources requirement do not exceed than defined limit. No change in critical path. Activities can be delayed within their float (free/total

## Slide 31: Modeling Techniques
What if scenario analysis
  Assess the feasibility of project schedule under adverse conditions. Prepare a contingency plan to overcome the problems. Or prepare mitigation plan to reduce the impact of unexpected situations.
Simulation
  Calculate multiple project duration using tools like Monte Carlo Simulation. In this case use assumptions and distribution constructed using 3 Point estimates.

## Slide 32: 19. Control Schedule
Monitoring the status of the project to update project progress and manage changes to the schedule baseline

## Slide 33: Control Schedule
Project Management Plan
Project Schedule
Work Performance Data
Project Calendars
Schedule Data
Organization Process Assets
Performance Reviews
Project Management Software
Resource Optimization Techniques
Modeling Techniques
Leads and Lags
Schedule Compression
Scheduling Tool
Work Performance Information
Schedule Forecasts
Change Requests
Project Management Plan Updates
Project Documents Updates
Organization Process Assets Updates
Project Time Management
Project Monitoring and Controlling

## Slide 34: Discussion/Exercise 17
Write work performance measures and their values of your project with respect to Schedule Management
5 Minutes

## Slide 35: Big Concepts
Critical Path Method (CPM)
Critical Chain Method (CCM)

## Slide 36: Critical Path Method (CPM)

## Slide 37: Critical Path Method (CPM)
Critical Path method is a planning technique that is used to demonstrate and view the chronological activities of a program or project, and identifies any possible timing risks and can be used to establish the least amount of time to complete a project.

## Slide 38: Critical Path
ES EF
ES EF
ES EF
LS LF
Start
Finish
Duration 7 Task A
LS LF
Duration 6 Task C
LS LF
Duration 3 Task G
LS LF
Duration 2 Task H
ES EF
LS LF
Duration 3 Task B
ES EF
LS LF
Duration 3 Task D
ES EF
LS LF
Duration 3 Task E
ES EF
LS LF
Duration 2 Task F
ES EF
ES EF
ES EF
ES EF

## Slide 39: Critical Path – Longest Path, Zero Float
LS LF
Start
Finish
0
0
7
7
ES EF
LS LF
7
7
13
13
ES EF
LS LF
13
13
16
16
ES EF
LS LF
16
16
18
18
ES EF
LS LF
Duration 3 Task B
0
7
10
3
ES EF
LS LF
Duration 3 Task D
3
10
13
6
ES EF
LS LF
Duration 3 Task E
6
13
16
9
ES EF
LS LF
Duration 2 Task F
3
11
13
5
ES EF
0
0
0
7
7
7
8
0
Duration 7 Task A
Duration 6 Task C
Duration 3 Task G
Duration 2 Task H

## Slide 40: Discussion/Excertise-16
Start
Finish
Duration 4 Task A
ES EF
LS LF
Duration 4 Task B
ES EF
LS LF
Duration 3 Task C
ES EF
LS LF
Duration 10 Task G
ES EF
LS LF
Duration 5 Task E
ES EF
LS LF
Duration 5 Task F
ES EF
LS LF
Duration 7 Task D
ES EF
LS LF
5 Minutes

## Slide 41: Network Exercise - solution
Start
Finish
Duration 4 Task A
0
0
4
4
ES EF
LS LF
Duration 4 Task B
4
7
11
8
ES EF
LS LF
Duration 3 Task C
11
11
14
14
ES EF
LS LF
Duration 10 Task G
14
14
24
24
ES EF
LS LF
Duration 5 Task E
0
4
9
5
ES EF
LS LF
Duration 5 Task F
5
9
14
10
ES EF
LS LF
Duration 7 Task D
4
4
11
11
ES EF
LS LF
Critical Path : ADCG
Notes: Free float: An activity can be delayed without impacting the start of next activity
Total float: As many alternative path that many total float. Total float is available on non critical path. Activities can be delayed without delaying project
Free float on critical path activities is Zero

## Slide 42: Facts/Tips for Critical Path
Total Float is the amount of time the task can delayed without delaying the project finish date.
Free float is the amount of time a task can slip without delaying the early start of any task that immediately follows it
It is possible that a zero float activity may not be on critical path
Longest path & shortest time possible to complete the project
A project can multiple critical paths
Difference between late and early is float
Positive float (the activity can wait to start even after previous activity finishes)
Negative float (the activity must start before previous finishes)
Zero float (the activity must immediately start after the finish of previous one)
Crashing activities to short the overall duration of project
Fast-tracking activities to short the overall duration of project
Be cautious that non-critical activity is not being delayed than the allowed free float
Take care of sub-critical path or non-critical path
Manage critical path resources very closely
Do not overload critical path activity resources
Avoid multitasking for resources working on critical path activities

## Slide 43: Benefits of PERT/CPM
It Provides following information
Expected Project completion time
Probability of completion before a specified date
The critical path activities that directly impact the completion time
The activities that have slack time and that can lend resources to critical path activities
Activity start and end dates

## Slide 44: Critical Chain Method (CCM)

## Slide 45: Background
Eliyahu Goldratt proposed CCM
This is developed based on the TOC framework

## Slide 46: Why CCM is needed?
You have CPM available why CCM is needed?
  You can manage the delays on non-critical path using buffers/floats. BUT
  How do you manage the delays on critical path?

## Slide 47: Principles Behind CCM
Delays accumulate; gains don't advantage
  Sequential Steps: Resources are not available to start early
  Parallel Steps: Three activity each takes 5 days time start in parallel. If one activity takes 10 days and other finish on time, early activities will not be able to take advantage.
  If above sequential and parallel activities are dependent then affect is magnified
Other Time Wasters
  Multitasking
  Student Syndrome
  Parkinson's Law

## Slide 48: Critical Chain Method
CPM is developed using the believe that book as many resource as in advance and they will be available when need because it has been promised
CCM says that if a resource is over booked on any activity he will not be available to work on that activity therefore level the resource on the project activities. Thus resource constrained critical path is critical chain.
CPM is about hoarding, greed. Therefore over-estimation and project management laws like Parkinson law, Murphy law, Student syndrome applies here.
CCM is about believe and assumption that it will available when needed but we need to have proper alert system in place.

## Slide 49: CCM Concepts
Resource Buffer: Notify dependent task resources that when I will finish my work on regularly basis and final notification 1-2 days before. So that resource is available to start the work.
Safety or project buffer should be added at the end of critical-chain as non-activity buffer
Feeding buffer: Add buffer where chain of non-critical activity joins the critical path. This way non critical task can be avoided being critical

## Slide 50: How to estimate in CCM
Resource will give t80, t90 estimate.
Half them to get t50 estimate.
Do not put end date to task and let people finish the task as early as possible.
No penalty for finish beyond t50.
Project Buffer should be 50% of the buffer removed from activity.

## Slide 51: How to manage CCM
If activity finishes late time is borrowed from project buffer.
If activity finishes early, gained time is added to project buffer

## Slide 53
Project Cost Management

## Slide 54: Project Cost Management

## Slide 55: Project Cost Management- A Thought
If you don't plan, it doesn't work. If you do plan, it doesn't work either. Why plan!
The same work under the same conditions will be estimated differently by ten different estimators or by one estimator at ten different times. So why to estimate!
Any project can be estimated accurately (once it's completed).
Nothing is impossible for the person who doesn't have to do it.

## Slide 56: Project Cost Management
  Processes involved in estimating, budgeting, and controlling costs so that the project can be completed within the approved budget

## Slide 57: Project Cost Management
  Plan Cost Management [PLANNING]
  Estimate Costs [PLANNING]
  Determine Budget [PLANNING]
  Control Costs [M&C]

## Slide 58: Components of Contract Price
Contract Price = Material + Labor + Expenses + Overheads + Risk Management Budget + Profit Margins
Who estimates Material cost for your project?
Who estimates Labor cost for your project?
Who estimates Expenses cost for your project?
Who estimates Overhead cost for your project?
Where do you adjust the buffer?
Where do earn profit
What is the price?

## Slide 59: Types of Cost
  Fixed Cost vs Variable Cost
  Direct vs Indirect Cost
  Material, Labour, Services
  Overhead Cost
  Sunk Cost
  Opportunity Cost

## Slide 60: Types of Cost
Direct cost: purchased, used, consumed in the project directly.
Indirect cost: shared cost between project.

## Slide 61: Types of Cost
Sunk Cost- Retrospective cost/ that cannot be recovered/ Cost gone and very low value or zero value was taken out. Plant developed but not of any use now additional money is required but by that money some better work can be done, so not to invest and let already invested money sunk. Software developed but it is not of any use now due any reason.
Perspective Cost- cost to be occurred in future
Allocated Cost- Cost of security service is shared by all division/companies of the building. Spreading the cost among those that use it.

## Slide 62: Types of Cost
Apportioned Cost- To find apportioned cost you should know % of each appraised value (land, building, machine)
Value Added Cost- Sale price of a product and cost price of material is value add
Transfer Cost -Cost of transfer or transaction between two entities
Opportunity cost- Value lose because of exercising an option. It is just economic cost. Does not reflect in financial books

## Slide 63: 20. Plan Cost Management
Establishing policies, procedures and documentation for planning, managing, expending and controlling project costs

## Slide 64: Plan Cost Management
Project Management Plan
Project Charter
Enterprise Environmental Factors
Organization Process Assets
Expert Judgement
Analytical techniques
Meetings
Cost Management Plan
Project Cost Management
Project Planning

## Slide 65: Cost Management Plan
It includes
  Cost management tools to be used
  Level of accuracy (acceptable range +/- 5%)
  Level of precision (US$ 100.01)
  Units of measure for each resource
  Organizational procedure links
  Process of updating the progress in schedule model
  Control thresholds (an allowed variation before some action need to be taken)
  Rules of performance measurement (baselines, %complete, fixed formula etc.)
  Project cost recording process
  Currency exchange rate fluctuation adjustment process
  Define scheduling reporting format

## Slide 66: 21. Estimate Costs
  Developing an approximation of the costs of the resources needed to complete project activities.

## Slide 67: Estimate Cost
Cost Management Plan
Human Resource Management Plan
Scope Baseline
Project Schedule
Risk Register
Enterprise Environmental Factors
Organization Process Assets
Expert Judgement
Analogous Estimating
Parametric Estimating
Bottom-up estimating
Three-point estimates
Reserve Analysis
Cost of Quality
Project Management Software
Vendor Bid Analysis
Group Decision Making Techniques
Activity Cost Estimates
Basis of estimates
Project Documents Updates
Project Cost Management
Project Planning

## Slide 68: Project Cost Estimation Ranges
Cost estimation may include only Direct Cost or in combination of with Indirect Costs
Class Name | % | Range
Definitive | - 5 -> +5% | 10%
Capital Cost | -15 -> +10% | 25%
Appropriation | -25 -> +15% | 40%
Budget Estimates | -10 -> +25% | 35%
Feasibility | -35 -> +25% | 60%
Order of Magnitude | -50 -> +50% | 100%

## Slide 69: Exercise-18
Write Activity cost estimates for 5 activities and their basis of estimates for your project
3 Minutes

## Slide 70: Three Point Estimates
Program Evaluation Review Technique (PERT)
ESTIMATED COST = (Pessimistic + 4*(Most Likely) + Optimistic) / 6

## Slide 71: 22. Determine Budget
  Aggregating the estimated costs of individual activities or work packages to establish an authorized cost baseline

## Slide 72: Determine Budget
Cost Management Plan
Scope Baseline
Activity Cost Estimates
Basis of estimates
Project Schedule
Resource Calendars
Risk Register
Agreements
Organization Process Assets
Expert Judgement
Cost Aggregation
Reserve Analysis
Historical Relationships
Funding Limit Reconciliation
Cost Baseline
Project Funding requirements
Project Documents Updates
Project Cost Management
Project Planning

## Slide 73: Estimation Traps
Customer: “How long will this project take?”
Project Manager: “What is the project about?”
Customer: “It is a systems upgrade project.”
Project Manager: “Can you tell me more about the project?”
Customer: “I don’t know, we will get into that later, but just tell me how long will it take.”

## Slide 74: Five Ways to Avoid Estimation Traps
Provide a range instead of number.
  Ranges reveals level of uncertainty in the scope. Customer will appreciate it if you tell him why that kind of range is given.
  +/- 10 or +/- 50%. You can discuss cone of uncertainty with customer
Highlight underlying assumptions and constraints
  Based on this (current information) assign confidence level or probability
Use objective estimation techniques like 3 Point or PERT
  Don't play estimation games like padding estimates by dubuling and then customer make it halve. Next time you quadruple it. This unnecessarily creates cycle of mistrust.
Use a combination of techniques and solicit multiple perspectives
Track and compare actual results
  Initially everybody fights for getting “accurate estimates” after that people forget about it
Next time you are asked to provide an accurate estimate, don’t fall into the trap. Instead, use it as an opportunity to engage and educate your stakeholders about the reality of estimates.
Notes: http://www.pmi.org/eNews/Post/2011_02-11/NLU_Get-Real-About-Your-Estimates.html

## Slide 75: Exercise-19
Establish cost performance baseline for your project & write funding requirements for your project.
3 Minutes

## Slide 76: 23. Control Costs
  Monitoring the status of the project to update the project budget and managing changes to the cost baseline

## Slide 77: Control Cost
Project Management Plan
Project Funding requirements
Work Performance Data
Organization Process Assets
EVM
Forecasting
TCPI
Performance Reviews
Project Management Software
Reserve Analysis
Work Performance Information
Cost Forecasts
Change Requests
Project Management Plan Updates
Project Documents Updates
Organization Process Assets Updates
Project Cost Management
Project Monitoring & Controlling

## Slide 78: Big Concepts
Earn Value Management

## Slide 79: Earned Value Management – Basic Concepts
Authorized budget assigned to the work to be accomplishes for an activity or work
breakdown structure component.
Earned Value (EV)- BCWP
Actual Cost (AC)- ACWP
Planned Value (PV)- BCWS
Value of work performed expressed in terms of the approved budget assigned to
that work for an activity or work breakdown structure component.
Total cost actually incurred and recorded in accomplishing work performed for an
activity or work breakdown structure component.

## Slide 80: Earn Value Rules
0% - 100%
50% - 50%
20% - 80%
25% - 75%

## Slide 81: Earned Value Management – S Curve
Cost
Progress Review
Time
EV
PV
AC
SV
CV
ΔT

## Slide 82: How project is progressing?

## Slide 83: How project is progressing?

## Slide 84: How project is progressing?

## Slide 85: How project is progressing?

## Slide 86: EVM-Variances
CV (Cost Variance) = EV- AC
CV = 0 => the Project is proceeding as per plan on cost
CV < 0 => the Project is over budget
CV > 0 => the Project is under budget
SV (Schedule Variance) = EV- PV
SV = 0 => the project is on plan, time-wise
SV < 0 => the project is BEHIND schedule
SV > 0 => the project is AHEAD of schedule

## Slide 87: EVM- Indexes
CPI (Cost Performance Index) tells you how much worth of job you are getting for every $ being spent.
CPI = EV/AC
CPI = 1 => the project is on plan, cost wise
CPI < 1 => the project is over budget or under performing
CPI > 1 => the project is under budget or over performing
SPI tells the PM how much worth of job has been completed against planned work
SPI = EV / PV
SPI = 1 => the project is on schedule
SPI < 1 => the project is BEHIND schedule
SPI > 1 => the project is AHEAD of schedule

## Slide 88: EVM- Critical Ratio
CR tells the PM the overall shape of your project
CR= CPI x SPI
CR = 1 => the project is on schedule & within budget
CR < 1 => the project is BEHIND schedule or budget or both
CR > 1 => the project is AHEAD of schedule or budget or both

## Slide 89: CPI & SPI Summary

## Slide 90: Forecasting- ETC
Recalculate it, if original estimate are no longer valid now.
Calculate it manually based on the progress, if original estimates are still valid
  ETC = BAC - EV

## Slide 91: Forecasting- EAC
Estimate at Completion(EAC)
EAC (atypical) = AC + ETC (Re-estimated)
EAC (atypical) = AC + BAC – EV (Estimated based on Progress)
EAC (typical considering CPI & SPI) = AC + ETC/ (CPI x SPI)
EAC (typical)= AC + ETC / CPI = BAC/CPI
  If you feel that you will be able to complete the project on time in spite of current delay then you can consider SPI as 1. In that case CR= SPI

## Slide 92: Forecasting- Variance at Completion
Variance at Completion (VAC)
VAC = BAC – EAC
Variance at Completion (%)
PVAC= (BAC-EAC)/BAC

## Slide 93: Forecasting: TCPI
TCPI (To complete Performance Index) can be calculated using BAC or EAC
TCPI using BAC = (BAC-EV) / (BAC-AC)
TCPI using EAC = (BAC-EV) / (EAC-AC)

## Slide 94: Case Study — Case 1
PV = $ 500
EV = $ 500
AC = $ 500
This is the ideal situation where everything goes as per plan.

## Slide 95: Case Study — Case 2
PV = $ 1,800
EV = $ 1,500
AC = $ 1,700
CV = EV – AC = - $ 200
SV = EV – PV = - $ 300
CPI = EV/AC = 0.88
SPI = EV/PV = 0.83
PV = $ 2,900
EV = $ 2,700
AC = $ 2,500
SV = -200
SPI = 0.92
CV = 200
CPI = 1.08
Calculate CV, SV, SPI, SPI

## Slide 96: EVM- Case 3
PV = $ 1,700
BAC = $ 5000
EV = $ 1,800
AC = $ 1,600
CV = 200
SV = 100
CPI = 1.125
SPI = 1.058
EAC = BAC/ CPI = $4444
ETC =EAC-AC = 4444 – 1600 = $2844 (Org Estimate Incorrect)
ETC = BAC-EV = 5000 – 1800 = $3200 (Org Estimate Correct)
VAC = BAC – EAC= $556
TCPI using BAC = 5000-1800/5000-1600 = 0.941
TCPI using EAC = 5000-1800/4444-1600 = 1.125
Calculate CV, SV, CPI, SPI, EAC (Typical), ETC, VAC, TCPI