## Slide 1
Fundamentals of Project Management
Trainer : Hari Prasad Thapliyal
(MBA, MCA, PGDOM, PGDFM, CIC, PMP, PMI-ACP, CSM, SCPO, SDC
PRINCE2-Trainer, Scrum Certified Trainer, Microsoft Certified Trainer)
[PMI-ACP : #318050]
[PMP : #1563385]
'PMI-ACP', 'PMI', and 'ACP' are a registered marks of the Project Management Institute, Inc.
The Knowledge House
UTC Building & Industrial Systems India

## Slide 2: What are your challenges in managing project?

## Slide 3: What is your learning focus for 3 days?

## Slide 4: Introduction
Max 1 min for one person
Name
Experience Total/PM
Role
Expectations

## Slide 5: Hari Prasad Thapliyal
Education & Certification
  MCA, MBA (Operations), PGDFM
  13 Certifications in Project Management Domain (PMP, PMI-ACP, PRINCE2 Trainer, MCITP, Microsoft Trainer, Scrum Trainer
Experience
  24 years of cross-functional experience in IT Delivery organization, training, consulting.
  Domain: BFSI, Recruitment, NGO, Cargo, LBS, EDMS
  Conducted 250+ PMP, CAPM, MSP, Various Other Project Management Topics
  Training 3000+ professionals globally
  Project Management experience of managing 30+ IT projects
  FPA counting experience of more than 30000 FP
  Setting up and Managing PMO
  Champion in Quality Initiatives like CMMI (1.1, 1.2), ISO9001:2000
  Champion in ISO-20000, ISMS/ ISO-27001 rollout in organization
  Starting and running software development centre
  Product Development
  Scrum/Agile/PMO Consulting/Coaching
Notes: 5

## Slide 6: Hari Prasad Thapliyal
Trained People on project management from
IT, ITES, Banking, Pharma, Power, Defense, Management Consulting, Electronics & Electricity, Telecom, Construction
Membership
PMI (USA),
PMI (Mumbai Chapter),
PMI (Bangalore Chapter),
ScrumAlliance
Axelos
Affiliation
Ex-Board Member of PMI Chennai Chapter & PMI Mumbai Chapter
Ex-Ethics Committee Chair of PMI Mumbai Chapter
Worked with Aurovision, Pyramid IT Consulting, Amsys Infotech
Hobbies
Languages, Reading Scriptures, Yoga, Traveling, Photography, Philosophy, Mythology, History, World Religions, Communication, Cultures
Notes: 6

## Slide 7: Customer I trained/Consulted
CONDUCTED CORPORATES & OPEN HOUSE TRAININGS FOR |  | 
IT (Software) Kale consultants L&T Infotech Microland Sun Guard ITC Intotech LeoTech California software Honeywell Technologies Genpact CGI Intelenet Global Xansa Pata Infotech SXChange Thales Software India EDS Dreamorbit Ellucian Opera Solution ABM Knowledge Ltd Emerio Temenos HDI System Technologies Pharma Sanofi India Pfizer Pharmaceuticals | Telecom Uninor Reliance Communication Qualcomm Nokia Siemens Airtel Smart Telecoms Orange Verizon Wire & Wireless Bank, Insurance, Finance & Securities Standard Charted Bank JP Morgan TATA AIG United Health Group Birla Sunline Insurance ANZ bank HSBC Deutsche Bank ICICI Pru RBS Bank of New York Avaya S & P Capital IQ | Power Vikram Solar Andritz BFL Hydro Power Industrial, Engineering Tyco Fire & Security Wheels India Turner & Toronsent Schneider Electrics Tata Elexi Xerox Emerson Rockwell Federal Mugal ABB HR, Staffing, Training Pyramid IT Future Focus ECCI Allsec Petroleum & Chemical Chemfab Chemicals Tagros Chemicals Gujarat gas Reliance Industries
IT (Software) Tally Solutions TCS SAP Labs Sutherland Wipro NIIT Technologies Limited Mphasis Amadeus Hibu Birlasoft Aurovision Cognizant CSC IBM Capgemini Infinite Computers Infosys HCL | ITES/BPO Service India Real Page WNS Hewitt AXA Technologies Shared Services (Assets Management) Bank of America Continuum Caliber Point Cbay Systems Construction & Infra Zamil Infrastructure L&T TS Arcelor Mittal Gammon India Ltd Allsec | IT (Hardware)/ Electronics Toshiba Embedded Software Kongsberg Dell Infineon Cisco Acer Dubai Ericsson ABB Huwei HP Godrej
Government Mayniland Water Department of Finance (Ph) Consulting Accenture KPMG | Automobiles TOYOTA Mercedes Benz Delphi Media Smart Communications Multi Media Communications | Others INSEAD NICT Flipkart ISKCON VGL Group Netambit Feedback Infra Pepsico ITC Dover India TWISS Reckitt

## Slide 8: Workshop Agenda
Day 1
Project Management Framework
  Understanding the meaning of Project in General Context
  Mindset for Project Management
  Project Success, failure and lessons learned
  Project life cycle (PLC)
  Inter-relationship between Planning, Execution and Control in PLC
  Enterprise Environmental Factors
  Organizational Process Assets
  Stakeholders
Starting a Project
Project Planning
  Scope
  Time

## Slide 9: Workshop Agenda Cont…
Day 2
Planning (Continue)
  Cost
  Quality
  Human Resource
  Risk
  Procurement
  Communication & Stakeholders
Project Execution
  Stakeholder Management
  Team Management
  Team Development
  Conflict Management
  Leadership
  Vendor Selection

## Slide 10: Workshop Agenda Cont…
Day 3
Project Governance
  Project Data Analysis
  Corrective, Preventive Action & Defect Repair
  Project Reporting
  Project Change Management
  Quality Control
  Communication and Stakeholder Engagement Control
  Risk Monitoring & Control
  Contract Management
Project Closing
  Procurement Closure
  Control Closure
  Admin Closure
Agility in Project Management

## Slide 11: Ground Rules
Phone/Electronics-
Corner Talk
During QA wait for you turn
Write questions on note and handover to me
Participate in exercises with your full heart and mind
Free flow of coming and going
Respect time break durations
  Tea break 10:30 (15 min)
  Lunch break 12:30 (45 min)
  Tea Break 15:00 (15 min)

## Slide 12: Understanding this will help us……
Project Management is a huge subject with hundreds of techniques and processes
In 3 days we will try to dig the top surface of this field
Let us not get bog down into technical and business of any project but focus on project management aspects.
Unlearning may also help certain places.
For the time being keep your technical hat off. Wear just leadership and management hat
The workshop is about learning some new terms and PM techniques, align existing PM processes and use standard terms to refer documents, processes or tools in project management domain.
For three days come out of your compartments called department and jump into the huge field called Project.

## Slide 13: Day 1

## Slide 14: Project Management Framework

## Slide 15: Project Management Framework
Understanding the meaning of Project in General Context
Mindset for Project Management
Project Success, failure and lessons learned
Project life cycle (PLC)
Inter-relationship between Planning, Execution and Control in PLC
Enterprise Environmental Factors
Organizational Process Assets
Stakeholders

## Slide 16: Understanding the meaning of Project in General Context
‘A Project is a temporary endeavor undertaken to create a unique product or service’
Temporary : ‘every project has a definite beginning and a definite end’
Unique: ‘the product or service delivered is different from others’
  Organizations resort to Projects to achieve their strategic needs, which cannot otherwise be attained through normal operational means.
Notes: Seven wonders of the world
Pyramids
Product or service or capability to create the product/service(building, business function, org restructuring), research project)
Temporary- end- when proj objectives are met or not met or cannot be met-; need no longer exists-aborted.
Uniqueness- contactor, budget, configuration, location..etc; repititive elements could be there---similar projects or degree of similarity.
Portfolio, Program, Project
Portfolio- L&T Infra dvision—has projects in oil, power, gas, water, airport…(portfolio)-objective to maximize returns; program –within power (projects in power or in airport)
I may have a portfolio of stocks across Banking, Infra, commodities, IT….Banking stocks are from banking program (inter dependencies--)

## Slide 17: Understanding the meaning of Project in General Context
Attribute | Projects | Operations
Charter | Permanent Project Charter | Semi-permanent charter
Change | Catalyst for change | Maintains status quo
Product | Unique product or service | Standard product or service
Team | Heterogeneous teams | Homogeneous teams
Time | Start and end date | Ongoing
Requirments | Progressive elaboration | Predefined product

## Slide 18: Mindset for Project Management

## Slide 19: 10 Aspects of a Project
Scope
Time
Cost
Quality
Human Resource
Communication
Risk
Procurement
Stakeholder
Integration

## Slide 20: How do Projects Arise?
Organizations identify a business need that can be satisfied by executing a Project.
Projects can be ‘Internal’ or ‘External’.
Projects may arise out of many factors including:
  Market/ customer demands.
  Need to improve internal processes.
  Technology upgradation and Legal requirements.
  Social needs.

## Slide 21: Some Project Fail Statistics
Innotas (cloud portfolio management provider) : Fifty percent of businesses had an IT project fail during the 2012
IBM; Nearly 60 percent of projects aimed at achieving business change do not fully meet their objectives.
Harvard Business Review : The brutal fact is that about 70% of all change initiatives fail.
Over 1 in 3 (34%) projects have no baseline. (Source: Wellingtone)

## Slide 22: Choose one between 2, how is life?
A
B
When do you learn identify lessons learned?

## Slide 23: Why Project Fails
Group Activity 1

## Slide 24: Why Project fails?
Lack of User Input/involvement.
Lack of Executive support.
Unrealistic Expectations.
Unclear/changing Goals.
Incomplete Requirements & Specifications.
Changing Requirements and Specifications.
Lack of appropriate methodologies.
Lack of experienced Project Manager.
Lack of skilled staff.
Poor estimation and planning.
Failure to communicate and act as a team.
Poor Risk Management.
Lack of Vendor control.
Abstracted from Standish group report

## Slide 25: Meaning of Project Success
Group Activity 2

## Slide 26: Let’s Select a Project for us!
Shifting your house
Under Govt’s UDAN initiative you get a project to install security & fire safety systems at 10 new tier three 3 city airports

## Slide 27: Project Constraints
Scope
Cost
Risk
Schedule
Resource
Project and Product Quality
Evaluate the competing demands and their impact on project outcomes.

## Slide 28: Project Phases
Project Phases
Projects are divided into phases where extra control is required to effectively manage the completion of the major deliverables
Collectively, the project phases put together is known as Project life cycle
Each phase is marked by one or more tangible verification work product
The conclusion of a project phase is generally marked by a review
The phase end points are referred to as phase exits, milestones, phase gates, decision gates, stage gates or kill points
Starting a phase before approval of deliverables of a previous phase is called Fast Tracking
Your Project Must have Phases

## Slide 29: Example of Phases
Problem Study
Feasibility Study
Prototyping
Designing
Testing
Implementation
Commissioning
Support

## Slide 30: Identify Project Phases
Group Activity 3
Apply project boundary concept.
Break the complete project in different stage

## Slide 31: Who are Stakeholders?
Stakeholders
Source PMBOK Guide Version 5.0
  Persons or organizations who are actively involved in the project or whose interests maybe positively or negatively affected by the performance or completion of the project

## Slide 32: Identify Stakeholders
Maintain a stakeholder register in project
Keep all possible details of every stakeholder
Name, Designation, Location, Interest, Preferences etc.

## Slide 33: Engaging Stakeholders
Engaging the Stakeholders- The RACI Matrix
Responsible, Accountable, Consulted, Informed
Project Phase & Deliverables/Activities | Stakeholders & RACI |  |  |  |  | 
 | Role 1 | Role 2 | Role 3 | Role 4 | Role 5 | Role 6
Phase 1 |  |  |  |  |  | 
Deliverable 1 | R | I | C | A | C | I
Deliverable 2 | A | R | I | I | I | C
Phase 2 |  |  |  |  |  | 
Deliverable 1 | R | A |  | I | C | I
Deliverable 2 | A | R | C |  | C | C
Deliverable 3 | I | A | I |  | R | I
Phase 3 | A | R | I | I | I | C
Deliverable 1 | A | R | C |  | C | C
Deliverable 2 | I | A | I |  | R | I
Notes: In the making of an egg, the hen is involved; in the making of a bacon, the pig is committed; the buck finally stops here;head on the scalp.
Only 1 time in a row..Accountable

## Slide 34: Identify Project Stakeholders
Group Activity 4

## Slide 35: Project Life Cycle

## Slide 36: Understanding Project Lifecycle
Phase II
Phase I
Phase III
Phase IV
a
b
c
Deliverables
Exits
Exits
Exits
d
Closure
Performing Organization/ Stakeholders
Initiation
Notes: What is a lifecycle? Delivery strategy
Conceived, born, childhood, teenage, adult, working adult, married adult, parent, retired, obsolete
(transition from one state to the other needs to be clearly defined--tollgates)
Phase- logical grouping of related tasks, deliverables
Hybrid models
SAP-LIFECYCLE- Proj preparn, Bus blueprint,realizn, Final preparn, Go live and support

## Slide 37: Project Lifecycle (Waterfall)
Waterfall Lifecycle

## Slide 38: The Agile Methodology
Project Vision, Roadmap, Planning
Release 1
Release n
Project Retrospective
Release 2
Release Planning
Iteration/Sprint 1
Iteration/Sprint n
Release Retrospective
Iteration/Sprint 2
Iteration/Sprint Planning
Daily work
Iteration/sprint review, demo, Retrospective
Daily work
Daily work
Daily Standup meetings
Task completion
Update Progress
Task completion
Task completion

## Slide 39: Which Methodology for Your Project?
Group Activity 5

## Slide 40: Enterprise Environmental Factors (EEF)
Constraints from the environment which restricts options of project manager and s/he does not have control over it but they affects the project success.
Climate, Political stability, Organization Culture, organizational systems and processes, attitude of stakeholders, market price of product/services, legal approvals, monopoly, competition, competitor’s strategy

## Slide 41
EEF
Political
Environmental
Social
Technical
Economic
Legal

## Slide 42: Organization Process Assets

## Slide 43: Organizational Process Assets (OPA)
Non-physical assets of organization which are available to project manager and project can get benefited by use of these. It is project manager’s responsibility to refine and further build OPA.
Examples: Estimation database, risk database, skill database, rate database, list of preferred vendors, processes, templates, specs/design from prev. projects, issue register from prev. projects, lessons learned copyrights, org template/checklist/guidelines/forms

## Slide 44: Group Activity 6
For your project
Make a list of 10 EFF
Make a list of 10 OPA

## Slide 45: Project Management Process Groups
Initiating
Closing
Planning
Executing
Monitoring and Controlling

## Slide 46: Starting up a Project

## Slide 47: Initiating Process Group
Finalize document needed to be handed over to PM
Create project charter
Assign PM
Authorize PM
Form an initial project team
Identify Stakeholders & Prepare Stakeholder Register
Conduct a Kickoff Meeting
Notes: Herald – to announce something important – existence of project

## Slide 48: A Project Charter Contains…
Objective: What we want to achieve? Across the product line reduce defects by 90%. It will help improving organization’s brand image, more sales and lessen warranty support.
High level Requirements: What should be done? Perform a through study where improvement possible and can help significantly. Identify points wherever automation possible. Study Process. Automate Process. Training.
Deliverables: As is study document, Solution and Approach Document, Automated Processes, Training Manual, Training
Milestones: As is study completion: 01-May-??
Budget: $ 1,00,000 (+/- 10%). + $ 5,000 Contingency Reserve
Timeline: 6 Months +/- 2 weeks.
Approval Requirement
Risk: Known Project Risk. Inherent Risk of the Project.
Initial Team
Project Manager Name
Sponsor Name
Date of Sign

## Slide 49: Project Kick-off
Present vision, goal to the team
Define ground rule
Understand key risk and dependencies
Understand milestone
?
??
Notes: Yr forum to speak…do yr ground work……share all the context from proposal stage till now…; contractual obligations

## Slide 50: Let’s write a Project Charter
Group Activity 7

## Slide 51
Project Planning
Scope
Time
Cost
Quality
Human Resource
Procurement of Material, Services
Communication, Stakeholders
Risk

## Slide 52: Scope Management

## Slide 53: Scope of Work
While planning consider both
Project Scope "The work that needs to be accomplished to deliver a product, service, or result with the specified features and functions."
Product Scope "The features and functions that characterize a product, service, or result."

## Slide 54: Analyse the work and Develop Solution
Product Analysis
  Product breakdown
  System analysis
  Requirement analysis
  System engineering: Deals with multiple complex systems
  Value engineering: Functions, value, cost
    Retain the function & value and reduce the cost
  Value analysis: Debate the function and its cost
    Discuss the value of function vs the cost
Alternative Identification
  Alternative way of doing work

## Slide 55: The Work Breakdown Structure
The Work Breakdown Structure is a hierarchical chart used to organize the work of a project into related areas
It shows the breakdown of a project depending on the visibility and control needed
Each of these major components are then subdivided into the tasks necessary to reach successful project completion
Each of these major components are then subdivided into the work necessary to reach successful project completion.
Notes: Decomposing till what level of granularity…till duration of the task is not more than 5 working days. Based on project duration/milestone…..if project is 15 days..then daily/agile.
Verbs, specific outputs that are measurable
More the granularity , more the visibility, more is the possibility of control; greater is the PM overhead. But for long durn, weekly may be too much; tied to tracking and reporting needs.
Breakdown to atleast 2 levels
Should be assignable, trackeable, estimatable
But for a new team member, greater; or only at TL level…they will in turn breakdown

## Slide 56: WBS Types
Phase Driven
Department Driven
Milestone Driven
Component Driven
Location Driven
…….

## Slide 57: Definition of Deliverables
A Deliverable is a measurable, tangible, verifiable outcome, result, or item
that must be produced to complete a project or part of a project.
Deliverables may be External or Internal.

## Slide 58: Phase oriented WBS

## Slide 59: Department oriented WBS

## Slide 60: Subproject Oriented WBS

## Slide 61: Let’s Identify Documents Required to Manage Scope and Requirements
Group Activity 8

## Slide 62: Project Scheduling - CPM & PERT

## Slide 63: Steps of Schedule Development
Define Activities
Sequence Activities
Estimate Resources
Estimate Duration
Develop Schedule

## Slide 64: Activity Relationships
Finish to Start
  A- Preparing documenting
  B- Printing document
Start to Start
  A- Shipment of material/parts
  B- Shipment of equipment
Finish to Finish
  A- Data collection & cleaning
  B- Analyse different chart types
Finish to Start
  A- Stop main system
  B- Start new system

## Slide 65: Dependency Types
Mandatory Dependency
Discretionary Dependency
External Dependency
Internal Dependency

## Slide 66: Schedule Constraint
ASAP
ALAP
SNET
SNLT
MSO
MFO
FNET
FNLT

## Slide 67: Define Activities
Know every product and project scope activities
Know the every possible attribute of these activities
List all the internal and external milestones

## Slide 68: Sequence Activities
Sequence activities based on the activity attributes, lead, lag and dependencies between them
Mandatory dependencies – Logical relationships inherent in the set of
activities
Discretionary dependencies – Dependencies which are defined by the
Project team or the Performing organization
External dependencies – relationships between Project and outside
Organization
Lag : The amount of time delay between the completion of one task and the start of its successor task.
Lead: The successor activity starts before the predecessor activity has finished.
Dependency Types : Finish to Start, Start to Start, Finish to Finish, Start to Finish
Notes: Discretionary dependencies– cannot process ahead without milestone review/ qa audit/ baselining/ signoff etc.

## Slide 69: Estimate Resources
Resources required to complete activities may be material, human, equipment, expense
You need to identify every kind of resources and number of resource required to complete every activity
When you are identify human resources that time avoid assigning “named resources”

## Slide 70: Estimate Duration
Techniques of duration estimation already discussed. Therefore use those techniques to estimate duration of each activity

## Slide 71: Develop Schedule
Using following inputs for making schedule
Resource Pool Description - Knowledge of what resources will be available, at what time and in what patterns.
Calendars – When work is allowed. Working and Non-working times. Availability of resources.
Constraints- Imposed Dates. Key Events or Major Milestones.
Notes: Factors considered: convert 5 working day effort to schedule(start Mon…; 1 person working)
-working days(weekends, holidays), part time/full time, dependency /wait time on another activity/resource, time zone-diff, personal leave, effective work hours/per day-org activities, early going, productivity(factored in estimate of 40 working hrs)…
Can finish early..if more hrs/per day/no dependencies, more productive than assumed,….
-

## Slide 72: Develop Schedule : Critical Path
A Critical path for a project is the series of activities that determines the earliest time by which the project can be completed.
The Critical path is the longest path through the network diagram.

## Slide 73: Critical Path
ES EF
ES EF
ES EF
LS LF
Start
Finish
Duration 7 Task A
LS LF
Duration 6 Task C
LS LF
Duration 3 Task G
LS LF
Duration 2 Task H
ES EF
LS LF
Duration 3 Task B
ES EF
LS LF
Duration 3 Task D
ES EF
LS LF
Duration 3 Task E
ES EF
LS LF
Duration 2 Task F
ES EF
ES EF
ES EF
ES EF

## Slide 74: Critical Path – Longest Path, Zero Float
LS LF
Start
Finish
0
0
7
7
ES EF
LS LF
7
7
13
13
ES EF
LS LF
13
13
16
16
ES EF
LS LF
16
16
18
18
ES EF
LS LF
Duration 3 Task B
0
7
10
3
ES EF
LS LF
Duration 3 Task D
3
10
13
6
ES EF
LS LF
Duration 3 Task E
6
13
16
9
ES EF
LS LF
Duration 2 Task F
3
11
13
5
ES EF
0
0
0
7
7
7
8
0
Duration 7 Task A
Duration 6 Task C
Duration 3 Task G
Duration 2 Task H

## Slide 75: Discussion/Excertise-16
Start
Finish
Duration 4 Task A
ES EF
LS LF
Duration 4 Task B
ES EF
LS LF
Duration 3 Task C
ES EF
LS LF
Duration 10 Task G
ES EF
LS LF
Duration 5 Task E
ES EF
LS LF
Duration 5 Task F
ES EF
LS LF
Duration 7 Task D
ES EF
LS LF
5 Minutes

## Slide 76: Network Exercise - solution
Start
Finish
Duration 4 Task A
0
0
4
4
ES EF
LS LF
Duration 4 Task B
4
7
11
8
ES EF
LS LF
Duration 3 Task C
11
11
14
14
ES EF
LS LF
Duration 10 Task G
14
14
24
24
ES EF
LS LF
Duration 5 Task E
0
4
9
5
ES EF
LS LF
Duration 5 Task F
5
9
14
10
ES EF
LS LF
Duration 7 Task D
4
4
11
11
ES EF
LS LF
Critical Path : ADCG
Notes: Free float: An activity can be delayed without impacting the start of next activity
Total float: As many alternative path that many total float. Total float is available on non critical path. Activities can be delayed without delaying project
Free float on critical path activities is Zero

## Slide 77: Facts/Tips for Critical Path
Total Float is the amount of time the task can delayed without delaying the project finish date.
Free float is the amount of time a task can slip without delaying the early start of any task that immediately follows it
It is possible that a zero float activity may not be on critical path
Longest path & shortest time possible to complete the project
A project can multiple critical paths
Difference between late and early is float
Positive float (the activity can wait to start even after previous activity finishes)
Negative float (the activity must start before previous finishes)
Zero float (the activity must immediately start after the finish of previous one)
Crashing activities to short the overall duration of project
Fast-tracking activities to short the overall duration of project
Be cautious that non-critical activity is not being delayed than the allowed free float
Take care of sub-critical path or non-critical path
Manage critical path resources very closely
Do not overload critical path activity resources
Avoid multitasking for resources working on critical path activities

## Slide 78: Let’s write the steps to prepare a project schedule and baseline schedule
Group Activity 9

## Slide 79: Day 2

## Slide 80: Planning : Cost

## Slide 81: Components of Contract Price
Contract Price includes Material, Labor, Expenses, Overheads, Risk Management Budget, Profit Margins
Cost baseline includes contingency reserves
Project budget includes management reserves
Do you know?
Who estimates Material cost for your project?
Who estimates Human Resource cost for your project?
Who estimates Expenses cost for your project?
Who estimates Overhead cost for your project?
How much is contingency reserve for your project?
What are indirect costs to your project?
When can you use contingency funds and who approves that?
How much is profit margin on your project?
What is the price?

## Slide 82: Estimate Cost
Before you start estimating cost, know what all different types of costs you should be included in the estimation
Know the rate of every resources you are going to use

## Slide 83: Project Cost Estimation Ranges
Never ever commit one absolute number to your project sponsor. Always range.
Cost estimation may include only Direct Cost or in combination of with Indirect Costs
Class Name | % | Range
Definitive | - 5 -> +5% | 10%
Capital Cost | -15 -> +10% | 25%
Appropriation | -25 -> +15% | 40%
Budget Estimates | -10 -> +25% | 35%
Feasibility | -35 -> +25% | 60%
Order of Magnitude | -50 -> +50% | 100%

## Slide 84: Determine Budget
Aggregate costs based on the duration
While aggregating also include the money which you pay to vendors for services & contingency reserves
Before you baseline the cost validate the funding requirements with availability of funds.

## Slide 85: Let’s write the steps to prepare a project budget and baseline cost
Group Activity 10

## Slide 86: Planning : Quality

## Slide 87: Plan Quality
Know your metrics, their calculation, data collection method and source
Determine product testing processes, tools
Determine defect fixing or feedback incorporation processes
Develop checklist wherever possible to test the product
Automate testing and review process as much as possible
Do not compromise on quality. Quantity can be sacrificed over quality.
Use 7 basic quality tools for managing project and product quality

## Slide 88: 7 Basic Tools of Quality

## Slide 89: Process Audit
Review your processes with auditors
Show your implementation with proof
Take best practices from auditors
Share your best practices with auditors

## Slide 90: Let’s identify activities to be done to ensure quality of project and quality of product
Group Activity 11

## Slide 91: Human Resource Management

## Slide 92: What are your challenges related to HR
Getting right people
Getting people on time
Commitment of people
Motivation of people
Conflict Management
Addressing Productivity and Efficiency issues
Training need of the team
Skill upgradation
Availability of expert

## Slide 93: Project Risk Management

## Slide 94: Introducing you to the World of Risks
Un-predictable Risks
Known Risks
Management of Uncertainties

## Slide 95: Every Project has risks associated with it!
Commercial viability.
Technical feasibility.
Competitors move ‘faster’.
Customers’ preferences may change.
‘VC’ resources may ‘dry up’.
Project Sponsor changes or may not give continued support.
Attrition.
Project scope, time or cost related issues.
Government regulations.
Notes: Technical risks- lifecycle, product/technology obsolescence
Management risks- Planning, estimation, budgeting, resources
Commercial- exchange rate , payment default
Legal- obligns failure

## Slide 96: What is Risk?
A dictionary definition of risk is “the possibility of loss or injury”.
Project risk involves understanding potential problems that might occur on the project and how they might impede project success.
“Risk is the potential for realization of unwanted negative consequences of an event.”
Project Risk is an uncertain event or condition, that if it occurs, has a positive or negative impact on project objectives. (PMBOK)

## Slide 97: Risk Identification – Information gathering Techniques
  Brainstorming Sessions.
  Interviewing.
  Checklists.
  Assumptions analysis.
  Review of Artifacts (WBS etc).
  SWOT Analysis
  Organization Risk Database.

## Slide 98: Risk Management Process
Risk identification
Risk analysis
Risk prioritization
Risk response planning
Risk resolution
Risk monitoring
Risk Assessment
Risk Control
Risk Database
SDLC
Notes: Self Explanatory slide !

## Slide 99: Risk Event / Impact matrix
Event
Known
Unknown
Known
Unknown
Impact
Planning
Contingency Reserve
Management ‘kept’ Reserve
N.A.
Notes: Unknown unknown- Recession, customer demand/appetite changes, technology changes, new product-game changer has hit the market, farmer agitn –singur—recovery/continuity at Gujarat..
Known-known--- cust may not signoff; team member may leave, resource may not be available..
Known- unknown-----I know customer changes his mind, but don’t know impact;
Unknown-unknown--- don’t know if cycle will change; don’t know if recession might happen; don’t know if suddenly regulations change; don’t know whether customer may delay payment; don’t know if competition announces new changes.

## Slide 100: Risk Estimation

## Slide 101: Risk Prioritization
Rank each Risk based on the exposure

## Slide 102: Risk Response Strategies
Risk Avoidance
Risk Transference
Risk Mitigation
Risk Acceptance

## Slide 103: Risk Monitoring & Control
Keeping track of identified risks
Monitoring of residual risks
Identifying new risks
Ensuring execution of the Risk Plan
Evaluating the effectiveness of the Risk Plan
Will be an ongoing process for the life of the project
Will reassess the priority of the risks periodically.

## Slide 104: Good Risk Management Practices
Acknowledge that risks are inevitable.
Communicate risks openly.
Reward people who prevent crisis, not just those who create crises and then manage them.
Use organization’s risk database for cross project learning.
Take the Expert help whenever needed.
Remember all risks are important .
Notes: Self Explanatory slide !

## Slide 105: Bad excuses in Risk Management
We have no risk.
We deal with problems as they arise.
How can you predict what will happen 6 months from now?
Our job is to develop software, not to fill out bureaucratic forms.
That external interface is not in our risk management program because the interface is not our responsibility.
We deal with problems as they arise.
That method is proven and therefore not a risk. The speaker at the conference said so.
My tech people will rebel if we identify as a risk a lack of skills needed to do development.
We have to bid the lowest cost to win; we'll worry about doing the job when we get it.
(source-The Little book of bad excuses- SPMN)

## Slide 106: Let’s identify activities to be done to manage risk proactively
Group Activity 12

## Slide 107: Project Procurement Management

## Slide 108: Basics of Procurement
Identify your procurement need: Know what is needed by you to complete the project work but your project team cannot produce it. (it may external testing, training, software, hardware, service, material etc)
Specification of each procurement need
Who, when, at what cost
How will you verify the objective is met
Change request

## Slide 109: Execution

## Slide 110: Work Execution
Check the progress of work everyday
Authorize work package according to plan & progress
Coordinate with assigned resources, vendors, consultants in advance
Document the actual progress everyday
Ensure the team is following the processes
Keep team motivated
Keep stakeholders informed
Keep stakeholders engaged
Conflict Management
Servant Leadership. Identify and remove impediments on day to day basis

## Slide 111: Team Management
Together Everyone Achieves More

## Slide 112: Stages of Team Performance
Forming :
  Team members getting to know each other
  Heavy dependence on Leader’s directions
Storming:
  Team members vie for positions of authority/ Power struggles
Norming:
  Team members get to know each others’ strengths and weaknesses
  Agreement and Consensus/ Goal clarity
  Leader – facilitating role
Performing:
  Team has a shared vision
  Conflicts are resolved productively
  Leader – delegating and overseeing role
Notes: Cliques – A group of people or associates

## Slide 113: Maslow’s Need Pyramid

## Slide 114: Motivation
Project is done by people but all people do not have same motivation. So same thing does not motivate all.
Motivation of people change from time to time. Today what is important for one may not be important for him tomorrow.
Remain in touch with team understand their permanent motivation factors and short term motivation factors and need of the project.
As a servant leader create an environment which is free from impediments, external to project.
In the absence of Hygiene factors, Motivation factors does not work.
Hygiene factors does not guarantee the motivation

## Slide 115: Motivation may be
Group 1 (Money)
  More money, promotion,
  Opportunity to travel new place
  Compulsory off
  Worth Prize
Group 2 (Learning)
  Some extra care
  Personal attention
  Dinner with leadership
  Photo on big poster or fame-hall
  Opportunity of getting associated with learned and leaders
  Recognition
Group 3 (Emotions)
  Opportunity to learn
  Opportunity to grow
  Better place to sit and work
  Autonomy or freedom to plan and work

## Slide 116: Group Activity 12
Lets make a resource register with interest and motivation factors (short & long term) of each

## Slide 117: Solving Impediments
Team should recognize that this is a road block
Assign a competent person for that
Ask him possible solution he can give
Assign deadline
Immediate impediment should be resolved on priority within 24 hours
Assigned person should report proactively
If impediment cannot be resolved within allocated time then it should be escalated to higher authority
Keep escalating it till you get the solution
As PM, if you can manage within timeframe with your own resource then do not escalate it
Do not sit on the impediments at the cost of project.

## Slide 118: Conflict Management : Mindset
Understand this is natural
This is because of the team’s dynamics
This is because of individual’s way of working in the team
Nothing is permanent
With sincere efforts we can solve conflicts early
There is a learning opportunity
Have positive mind and positive thoughts
Running away is not a solution
Do not be personal
Do not go to the history
Do not attack the personality
Be very objective. To the point.
Document the event and its learning

## Slide 119: Conflict Management : Techniques
        LOW OBJECTIVE ORIENTATION HIGH
HIGH
LOW
RELATIONSHIP
ORIENTATION
COMPROMISE
SMOOTHING
(ACCOMMODATING)
PROBLEM-SOLVING
(COLLABORATING)
FORCING
(COMPETING)
WITHDRAWAL
(AVOIDING)

## Slide 120: Group Activity 13
Let’s make an impediment register and their solution. This is for day to day update.
Steps - broadly how do solve the impediments
List 10 Reasons of conflict between team members

## Slide 121: Day 3

## Slide 123: Project Data Analysis
Collect all the possible data. Start logging events without interpreting the meaning of data.
Periodically, as per the plan, extract the data from source and look data from all possible angles.
For this you need to identify metrics for your project performance measurement
Also look organization’s perspective when you trying to give meaning to the data
Understand organization’s goal, industry benchmark, stakeholders’ expectation from their perspective
Everything which is important for PM may not be important for org.
Everything which is important for Org must be important for PM.
Use different to tools to track and analyze the data and metrics

## Slide 124: What Metrics are Important for Organization
Profit Margin
Cashflow
EPS
Brand Value
Market Share
Revenue
Variable Expenses
Copyright and Patents Development
Repeat business
Cost of Customer Retention
Cost of Customer Acquisition
CSI
New Technology Adoption
Innovation
Cost Savings
Talent Retention
New skills acquired
Warranty Cost Reduction
Average Value of New Projects
Compliance
Acquisitions / Merger
Reducing cost of testing
Reducing Safety Incidents
Reducing defects
Reducing average customer complaints
Capital to Sales Ratio
Operating Ratio

## Slide 125: Project Metrics
Cost Variance
Schedule Variance
Missed Milestone
Effort Variance
CPI
SPI
VAC
Issues/Defects Reported by Customer
Issues/Defects Reported by QC
Conformance Index
Productivity
Hours in Meeting
Return on Time Invested (ROTI)
Reporting on Time
Cost of Rework
Rework Effort
Resource Attrition
Cost Saving Due to Innovation
Skills Developed

## Slide 126: Corrective, Preventive Action & Defect Repair
Periodically compare the metrics against the benchmark or goal setup
Periodically observe the trends of metrics
Look for process improvement opportunity (Preventive Action)
Fix the product issues timely, before they become irreparable (Corrective action)
If defected product has been shipped then volunteerly recall and fixed it before it hit the brand (Defect Repair)

## Slide 127: Project Reporting
As per communication management plan prepare various type of reports
Minimize the efforts of ad-hoc reporting
Send out reports to stakeholders as per the plan (before they start chasing you)
Broadly there are three types of reports

## Slide 128: Project Change Management
What is the meaning of change?
New Requirement
Requirement Altered
Requirement Wrongly Implemented
Requirement Rightly Implemented but not fit for use
Technology Change
Technically Infeasible
Process Change
Regular changed the rules
Resource change
Cost of Procurement
???

## Slide 129: How do you handle change
Acknowledge there is something which need to be addressed otherwise project’s objective will not be achieved.
Evaluate the change request will help in achieving project objective.
If not implemented what will be the impact on project objective
What is the impact on efforts/cost/quality/time of implementing the change
Can I manage the change with my change budget
Should I take approval from change control board
Bring the change to appropriate CCB and get approval
Update the plan
Implement the change
Verify the change
Demonstrate the change
Deliver the change

## Slide 130: Change Management Steps
Acknowledge
Evaluate impact on business
Evaluate impact on Project Metrics
Approval Required?
CCB Approval
Update Plan
Implement
Verify
Demonstrate
Deliver

## Slide 131: Quality Control
Look for Project & Product Quality both
Measure Quality Against Metrics and Cheklist
Built checklist based on organization’s experience
Refine those checklists and use those to validate the product or results
Manage every defect formally using some defect management system. Tracking to closure is easy.
Always try to look for the global impact of the defect detected
Never ever do the last moment change and then demo the product to customer without QC
Voluntarily use the QC results for process improvement. They are not only to fix the problem

## Slide 132: Communication and Stakeholder Engagement Control
Ensure communication and stakeholder engagement is happening as per the plan
  Do you need to put more efforts in Ad-hoc reports?
  Do you need to waste lots of time in fire-fighting with customer?
  Even after all good work from our side customer is unhappy?
  Customer is not taking interest in the project?
Then time to
  Review your communication and stakeholder engagement plan.

## Slide 133: Risk Monitoring & Control
Use organizational wisdom to populate your risk register
Ignorance is not bliss. Accepting certain risk after know is wisdom.
Keep eyes always on the continuous events on the project. Occurrence of every new event may trigger a new risk, expire a risk or make project more risky
Use risk budget wisely. Don’t use this to address change.
Reassess the project on regular basis against the risk and remaining risk budget

## Slide 134: Contract Management
Customer contract and project progress has attached award, reward and penalty
Vendor contract and vendor work progress also has attached award, reward and penalty
Although contracts are legal document and project are managed in the field with people but ensure contract terms are properly understood by the PMT and followed in the spirit. In adverse time in the court your company need to justify every word and delivery in the court.
Use contract progress reports in preparing project reports
Proactively communicate dependencies of work on regularly basis. People generally do not read email, SMS or open document on regular basis. Express urgencies to them in your own voice.

## Slide 135: Overall Monitoring & Controlling
Know your metrics
Know the allowed threshold limit of each metrics
Get actual data
Compare the data against plan
Calculate your metrics and know your variances
Determine whether variance is without tolerance limit
Corrective and Preventive actions
Defect repair
Validate whether CAPA and Defect repairs recommended are implemented
Prepare reports
Share reports

## Slide 136: Managing Variations
Variation:
The difference between the planned and the actual results. Variation could be with respect to Time, Cost or Quality.
Threshold:
The maximum permissible variation beyond which appropriate corrective action must be taken.
Notes: Talk about:
Explain the definitions of variation and threshold and say that more will be discussed in the subsequent slides

## Slide 137: Earned Value Management
BAC= Variance at completion
PV = Planned Value
AC = Actual Cost
EV = Earned Value
ETC = Estimate to Complete
EAC = Estimate at Completion
SPI = Schedule Performance Index
CPI = Cost Performance Index
VAC = Variance at Completion
ETC = Estimate to Complete
EAC = Estimate at Completion

## Slide 138: Earned Value Rules
0% - 100%
50% - 50%
20% - 80%
25% - 75%

## Slide 139: Types of Reviews/reports
Weekly reviews
Status/Progress reviews
Management reviews
Milestone/phase end reviews
Customer reviews
Vendor reviews

## Slide 140: Project Review outcomes
All reviews must culminate with
  List of Issues Identified.
  List of Action Items decided.
Action items must be tracked to closure.
Issues must be monitored to determine if they are resolved.
Issues need to be escalated as per the defined Escalation procedures.

## Slide 141: Project Dashboard (RAG)

## Slide 142: Issue Management
Log issues and Issue source.
Determine action for resolution.
Establish responsibilities and timeline for action.
Track issue for resolution.
Escalate issue as per escalation procedure.

## Slide 143: Perception Management Steps
Think: How people are perceiving you
Know: How you are actually being perceived
Decide: How you want to be perceived
Story: Create a full end-to-end consistent story, which you want tell to achieve your goal
Meet: Meet to the people and tell your story
Feedback: Ask them questions which helps you in knowing whether your goal is achieved
Confirm: Paraphrase the feedback to confirm whether you understood properly
Thanks: Say thanks to people who have given time to listen your story.
By: Hari Thapliyal

## Slide 144: Project Closure

## Slide 145: Procurement Closure

## Slide 146: Control Closure

## Slide 147: Admin Closure

## Slide 148: What is a Post Project Review?
Looking backing to know how differently we could have done
Looking forward to plan what should we do
Not about the people and blaming their behavior. But about process and opportunities to learn from the interactions of the team members.
Should not wait to end project or phase. But any time when you feel need (like moral is down, productivity is down, team making more mistake etc), you can do project review.
Another purpose of this is to contribute learnings of the project with organization so that future projects can be done in better way

## Slide 149: What’re the Deliverable?
Reuse possibilities
Best Practices
Lessons Learnt
Risks That hit / hurt
Customer / Project / Process / Product measurements
Customer report defect data analysis
  Input for preventing defects in subsequent phases / projects
Customer Satisfaction Survey Analysis. Contributed to organizational repository for further processing

## Slide 150: Ground Rules for Retrospective
Be polite and gracious.
  What happens in you when somebody does not agree with you
  What do you do when you do not agree with someone?
Focus on problems and process.
  What do you do to ensure problem is understood correctly and in right context?
No finger pointing/ No assigning blame.
  How, when and who do you do retrospective?
  Do you think that there is something called perfect plan? What happens when things goes wrong in project?
Let each person have a turn.
Avoid defensiveness.
  How many times and how long you should be humiliated over one mistake?
Respect everyone’s perspective.
  Whose input matters?
  How do you make any decision?

## Slide 151: Project Archival
Ensure that all information is archived in line with the contractual agreements/internal procedures.
Plan for transitioning to warranty / maintenance.

## Slide 152: Agility in Project Management

## Slide 153: Level of Planning

## Slide 154: Daily Standup
Purpose
Format

## Slide 155: Retrospective

## Slide 156: Essential Project Management Tools and Techniques

## Slide 157: Integration
Expert Judgement
Facilitation Techniques
Project Management Information System
Meetings
Change Control Meetings
Analytical techniques

## Slide 158: Scope Management
Interviews
Focus Groups
Observations
Prototypes
Inspection
Facilitated Workshops
Group Creativity Technique
Group Decision Making Techniques
Questionnaires and Surveys
Benchmarking
Context diagrams
Document Analysis
Product Analysis
Alternatives Identification
Decomposition
Variance Analysis

## Slide 159: Time Management
Rolling Wave Planning
Precedence Diagramming Method
Dependency Determination
Leads and Lags
Reserve Analysis
Schedule Network Analysis
Critical Path Method
Schedule Compression
Alternatives Analysis
Published Estimated Data
Critical Chain Method
Resource Optimization techniques
Modeling Techniques
Scheduling Tool

## Slide 160: Cost Management
Bottom-up estimating
Analogous Estimating
Parametric Estimating
Three-point estimates
Vendor Bid Analysis
Cost Aggregation
Historical Relationships
Funding Limit Reconciliation
EVM
Forecasting
TCPI
Cost-benefit analysis
Performance Reviews

## Slide 161: Quality Management
Seven basic quality tools
Cost of Quality
Design of experiments
Statistical sampling
Additional quality planning tools
Quality audits
Process analysis
Approved Change Request Review

## Slide 162: HR Management
Training
Team-building activities
Ground Rules
Pre-assignment
Negotiation
Acquisition
Organization Charts and position descriptions
Networking
Organizational Theory
Virtual Teams
Multi-criteria decision analysis
Interpersonal Skills
Co-location
Recognition and Rewards
Personnel Assessment Tools
Observation & Conversation
Project Performance Appraisals
Conflict Management

## Slide 163: Communication
Communication Requirement Analysis
Communication Technology
Communication Models
Communication Methods
Information Management Systems
Performance Reporting

## Slide 164: Risk Management
Documentation Reviews
Information Gathering Techniques
Checklist Analysis
Assumptions Analysis
Diagramming Techniques
SWOT Analysis
Strategies for Negative risk or threats
Risk Probability and impact assessment
Probability and impact matrix
Risk Categorization
Risk urgency assessment
Risk data quality assessment
Strategies for Positive risks or opportunities
Contingent response strategies
Risk Reassessment
Variance and trend analysis
Data gathering and representation techniques
Quantitative Risk analysis and modelling techniques
Risk Audits
Technical performance measurement

## Slide 165: Procurement Management
Make-or-buy analysis
Market Research
Contract Change Control System
Bidder conferences
Proposal evaluation techniques
Independent estimates
Advertising
Procurement Negotiation
Procurement Performance Reviews
Inspections and Audits
Payment Systems
Claim Administration
Records Management Systems
Procurement Audits

## Slide 166
This document is proprietary and confidential. It remains the property of Vedavit Project Solutions at all times. No part of this document may be used, reproduced, or transmitted in any form or by any means electronic, including photocopying and recording, for any purpose without express consent of Vedavit Project Solutions.

## Slide 167
hari.prasad@vedavit-ps.com
+91 9535999336
http://rarementors.com
https://in.linkedin.com/in/harithapliyal
http://twitter.com/harithapliyal
http://pmlogy.com/
http://facebook.com/harithapliyalpage