## Master
# | Sheet Name |  | Participants
0 | Agenda | 1 | Ajay Dudhedia | ajayd2k@gmail.com
1 | PollQuestion | 2 | AMARNATH K | allnewamar@gmail.com
2 | PM Role & Responsibilities | 3 | Anurag Thakore | anuragthakore@gmail.com
3 | Why Project Fail/get Challenged? | 4 | aravind ashok | aravind182@gmail.com
4 | Your Top 3 Challenges | 5 | Asrar Hussain | asrarhussain.2828@gmail.com
5 | Project Initiation Questions | 6 | Chetan Sarangale | chetan.sarangale@gmail.com
6 | Project Charter | 7 | Chiranjeevi gopalakrishnan | chirug87@gmail.com
7 | OPA-EEF | 8 | digambar jadhav | digambarjadhav1@gmail.com
8 | Project Characterstics | 9 | Gowri Shankar | gowrishnkar@gmail.com
9 | Scope Management | 10 | inderknagpal | inderknagpal@gmail.com
10 | WBS & PBS | 11 | Kavitha S | kavithasathishkumar9@gmail.com
11 | Metrics | 12 | Kirti NG | kirti.ng333@gmail.com
12 |  | 13 | Lakshmana (LK) | Lakshmana.JV@gmail.com
13 |  | 14 | Manish Maurya | mauryamanish21@gmail.com
14 |  | 15 | Manoj Bapat | mnb.bapat@gmail.com
15 |  | 16 | Nalwyn Nessiah | meetnalwyn83@gmail.com
16 |  | 17 | Narayanan Rm | catchnary@gmail.com
17 |  | 18 | Prabhakar Dhamodharan | dsprabhakar@gmail.com
18 |  | 19 | Ramu A | ramu.dhanush@gmail.com
19 |  | 20 | Sarang Kawale | sarang.kawale@gmail.com
20 |  | 21 | Saravanan Govindan | saravanagovind@gmail.com
21 |  | 22 | Semion Alexander | semionalexander@gmail.com
|  | 23 | SUDARSAN SRINIVASAN | sudar1999@gmail.com
|  | 24 | Vineet Saxena | vineetsaxena2005@gmail.com
|  |  | Naresh Prasad | mailnareshprasad@gmail.com
|  |  | Ganesh Kumaran | sganeshkumaran@gmail.com
|  |  | Aravinth Radhakrishnan | aravinth.mca@gmail.com

## 00
Session 1 | Session 2
PART 1 (30 Min)
A.Introduction, Ground Rules and Expectation Setting
B.Objective & Agenda of workshop
C.Project Manager Responsibilities
PART 2 (60 min)
A.Peeing inside the survey
B.Project Initiation
C.Process vs Practices
PART 3 (40 min)
A.Scope Management
B.PO & BA Role
PART 4 (60 Min):
A.Project Monitoring & Controlling
B.Project Estimation
PART 5 (50 Min)
A.Project Scheduling
B.Risk Management

## 02
PM Role & Responsibilities
| Project Manager | Scrum Master
| Stakeholder Management | Facilitator between development team and other stake holder
| Requirement gathering | Daily Standup
| Governance Structure | Boards
| Kick off Meeting | Scrm meetings
| Enagae Stake holders | Scrum ceremonies
| Resource Planning and Management | Estimate Efforts for Sprint items
| Project Charter | Removing Obstacles
| Sprint Planning | Capacity Planning
| Weekly Review status meetings | sprint planning
| Resolving Interpersonal Conflict within Team | Work Items / User Stories
| Identifying Risks in advance and sharing Mitigation to resolve it | Daily stand up meetings
| Creating SOW | Backlogs schedule
| addressing the Pros and Cons | Check on Velocity | <== Via removing impediments
| Identifying Risks well ahead of time | Task Planning
| Resource Planning | status updates
| Planning Demo | Project Status
| Updating client on the project status | scrum calls
This SM work | Burndown chart analysing | Backlog Management
This is Dev Team Work | Sprint Planning | Keep all Parties on Track and Informed
| Project Estimation | Scum meetings
| Providing status updates | ProductBacklog Refinement
|  | handling backlog | <== This is PO's work
| Adhering to Quality Assurance Process | Planning | <== This is Dev team's work
This is PO work | Moving to Backlog items | Interact with Client
| Track Schedule Variance | Facilitation
| Project Status Update | Retrospectives
| Story points assigning | Master of All the Ceremonies
Project completion Report
Ensuring Project outcome/Benefits realization
Technical Support
Risk identification
Weekly Status reporting
Capsity Planning
Risk Mitigation
Address security concerns
Project Environment Readiness and Setup
Monitoring
Motivating team
Monitoring project progress and revisiting project plan
Resolving impediments
Peopel Management
Estimated Vs Actual Analysis
Team's Skill Development
Addressing Concerns
Retrospection
Spike tasks & poc planning
SPOC on both the ends to meet expectations
Cost Overrun
PO work | Backlog Management
Mentor and Guidance
Integrating and Monitoring
CAB Process
Scope and out of scope
Refinement Meeetings planning and participating in estimation
Delivery date Planning with stake holders
Risk Management and Mitigation
Partially Yes | Identify future technology and Provide training
create oppurtunities depending on scenarios
Ensuring Customer Satisfaction
Build Knowledge Base for reference
Regular check of feedback
Sprint Planning & sizing
Retrospective meeting
Timely Communication of things
Resource Allocation and Manage Billing
Create Project Documentation
Leave tracking and Manage resources based on Project Needs
Quality and Time Management
Encourage to Organise different events and Participate
Budget estimation
Daily standup calls
| P&L | Increase Team Productivity
Earned value management

## 05
Project Initiation Questions
Q1 | Q2 | Q3 | Q4 | Q5 | Q6
What a PM is suppose to do in a project? | What prepration you will do in next 24 hours. | What question you will ask to your managers? | After the meeting is over what are the key activites you will do? | How do you select project management methodology? | How do you know the list of all process required to manage project on day to day basis?
| Delivery qulification | Technology need to be used | gap analysis | Duration of project
| Analyse on the technology required | Do we have Domain Knowledge / Prior Experience | Note down the requirement
| understand SOW /BAFO | Do we have Technical Capability | Define Inscope and out Scope
| does customer has clear understanding of deliveriables | Deadline and various phases | Resource availability based on technology
| is there any RFP | Team size | Skills avialibility
| Security aspect | Duration | Resourse planning
| Research on the Domain and its Needs | Compliance Required | risk identificaiton & metigaiton
| HLA | T&M or Fixed Bid | Procuremnet - resoruce, infra check | Does customer have a fixed set of requirement defined
| Try to do some research on requirement by asking what is needed, what is the timeline |  | Resource Manage | Is client flexible to adjust budget and time based on evolving requirements
|  | Automation required - testing | Tech & non-tech Challenges | Continious Integration and Deployment
| mode of delivery onsite/offshore |  | Technology
| Do we have clear list of requirements? |  | check with team if all understood the discussion
| cost management |  | 50K Plan | Change in Requirements
| Who are the stakeholders? |  | Estimation | Iterative approach
|  |  | Project Charter | less planning required
| Prepare a questionnaire to ask based on our assumptions |  | SWOT Analysis | Change Requests
| Analyse for team size |  | prepare deck based on the discussion | New Implementations
| are there any other project depedent on this project |  | Getting information on what we have done in the past (similar thing) and challenges in achieving them | Quick ROI
| Get SCOPE |  | Environment setup and Readiness
Minutes of meeting
| Resource Management |  | Reusable Components
We need to know who is the customer
Identify team members and form a team
Team Analysis
Prior experience/knowledge in the team
Requirement Analysis
| Examine the feasibility |  | Feasibility check
let me read the document and do my estimation.
project charter will be prepared

## 06
Project Charter | Vineet Saxena | Manoj Bapat | Anurag | Manish | Prabhakar | Kirti | Ajay | Sarang | Inder | Nalwyn
Project Objective | Creating an ecommerce website like Amazon for client XYZ Corp | Preparing the SoW | The problem we are trying to solve for the customer to reach the Tier2 and Tier3 Cities in india for retail food products | Site Development for ABC 123 Products | To create an Ecommerce Website | Ecommerce website like amazon | Creating an Ecommerce Website | To create an ecommerce website. The website should allow end users to View Producti Listing categroy wise, search for different products based on names or keywords, sort and filter product listing, place order and track their orders. The website should also allow admin users to upload product listings, manage orders, generate standard reports. to allow day to function | Create a web and mobile application for Digital Therapy | what you plan to achieve by the end of your project
High Level Requirements | Workable ecommerce website with all modules working as required | prepare SRS | Key Dileverables List |  | Homepage/Search menu, PDP, PMP, Checkout page, Review page, Confirmation page | Modules , Sub modules, , Additional Features | Creating a wesite similar to Amazon which will be used for ecommerce purposes. What are the products what are the characteristics, What are the functionalities that are required. What is the delivery date expected What is the budget for the same? What is the target Audience and the Languages in which the same is to be made? What is the Architecture that you are looking for? | View Product LIstings Filter and Sort Product LIstings View Product Details Compare Products Place Orders VIew Order Status Shopping Cart Admin Functions Manage Product Listings | User Onboarding in the application Getting current medical and physical condition of the user Creating therapy plan for the user Monitor the progress of the user alter the therapy program of the user | Product Listing Cost product display Compare Product Adding Cart Reporting
High Level Milestones | Front end, Databases connectivity, testing of all modules etc | Work break down structure | Identify Key Milestones based on Dilevarables |  | WBS, UX, UI, MVP, Phase 2. | Basic Modules in phase I, Additional features required in Phase II | Wh | UI / UX Design FInalization DB Schema Finalization Product Listings Shopping Cart Order Management Upload Product Listing Admin Order Management Reports UAT Release | Application Wireframe Delviery of User onboarding Delivery of the main algo of the therapy program
High Level Risk | Resource Availability, Meeting Deadlines and Budget | Governance plan, RAG reporting | Highlight Risk Areas in terms of People, Schedule, Technology |  | Technology, resources, | Resources, Technolgy stack |  | Performance of website against loarger user load Budget consideration | Readiness of the base algorithm of the therapy program on time All of the exercise videos to be ready
Assumption | Based on the client's requirements, resources availability and budget | User guide | Available resources, SME , ENV |  | schedule, resources | Products which will be available on this wensite will be provided by client |  | Customer signs off on the UI/ UX and its not altered in subsequent phase. Website will be made Mobile Responsive. Will be tested on last 2 versions of Chrome, Firefox, Safari | The base algo is tried and tested on various subjects Complying with the medical legal norms
Budget | Cost estimation | P&L view | Cost Estimation |  | Budgeting, Costing, EV |  |  | Cost based on Resources | $100K
Completion Date | Based on the client's requirements, resources availability and budget | Project plan | Project Plan / Schedule |  | Estimation, Assumptions, SChedule | 3 months after kick off |  | 6 Months | 9 Months
Intial Project Team & Role | PM, Developer | skill matrix vs role & responsibility | List of Roles with People Names and there allocations |  | UX, UI, Angular, Dotnet Core, PM | PM, Tech Lead, UX, UI, QA |  | 1 - PM - Team formation and project plan 1 - UI/UX - Come up with UI/UX suggestions 1 - Tech Lead - Define DB Schema, Code Repo and env setup 1 - Senior FE Developer - Implement FE architecture 1 - Senior BE Developer - Implement BE architecture 1 - QA - Create high level QA plan | 1 UI/UX 2 Backend (1 Architect) 3 UI Developer (1 Tech Team Lead) 1 QA 1 PM
Project Manager | PM |  | PM Name |  | PM | PM Name |  | PM Name | 1
Sponsor | XYZ Corp |  | Sponsor Name | ABC | Acme Pvt Ltd |  |  | Client Name | Client

## 07
OPA-EEF

## 08
Project Characterstics |  | Scale it on 1-10 (1 means increases project success rate, 10 decreases the project success rate)
Technology |  | Anurag | Lakshmana | Manoj | Chetan | Sarang | Kirti | Narayanan | Sudarsan | Semion Alexander
| Stable Technology | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Old but Useful Technology |  | 3 | 2 | 1 | 3 | 2 | 2 | 2 | 2
| Outdated Technology |  | 9 | 5 | 10 | 6 |  | 10 | 10 | 5
| Will retire soon |  | 8 | 2 | 10 | 4 | 2 | 0.7 | 8
| Complex to implement | 4 | 6 | 5 | 2 | 7 | 3 | 5 | 5 | 3
Resources
| Skill Availablity in Market | 5 | 3 | 1 | 3 | 4 | 1 | 5 | 5 | 5
| Training Availablity in Market | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 4
| Available at compititive price vs premium price | 3 | 5 | 3 | 5 | 4 | 5 | 5 |  | 6
| Available with in organization | 3 | 2 | 1 | 3 | 2 | 1 | 3 |  | 5
| Free for the project |  | 2 | 4 | 2 | 3 | 5 | 6 |  | 6
Requirments
| Business rules are well known | 3 | 2 | 2 | 1 | 2 | 3 | 2
| BA knows the business rules | 2 | 2 | 1 | 1 | 3 | 1 | 2
| Functional Requirements are clear and stable | 3 | 2 | 1 | 1 | 2 | 3 | 4
| Non Functional Requirements are clear | 3 | 3 | 2 | 1 | 2 | 3 | 3
Customer
| Availablity of Product Owner | 6 | 3 | 4 | 3 | 3 |  | 3
| Customer knows requirements | 3 | 2 | 1 | 1 | 2 | 1 | 3
| Customer is supportive | 3 | 2 | 1 | 1 | 2 | 1 | 2
Competition
| No local comptetition | 7 | 2 | 6 | 6 | 3 |  | 5
| No international competition | 7 | 2 | 6 | 6 | 2 |  | 5
Goverment Policies
| Goverment can change the tax law | 2 | 5 | 5 | 10 | 6
| Goverment can change the compliance law | 7 | 6 | 5 | 10 | 5
| Goverment can introduce some new framework | 5 | 6 | 5 | 10 | 5
Delivery
| Because of X reasons only one big bang delivery is required | 3 | 6 | 2 | 5 | 5
| Even features of future releases cannot be planned properly | 3 | 7 | 2 | 7 | 5
| We develop and release within 1 week. | 7 | 8 | 5 | 6 | 7
| We develope, hold till MMF and then release after with big announcements. | 6 | 6 | 5 | 6 | 5

## 10
PBS | amazon.in | WBS
Level01 Feature | Level 02 Feature | Level 1 Work | Level 2 Work

## 11
Metrics | Formula | Source of Data | Frequency | Goal | Actual Value | Threshold | Escalation
Usability Index - UI | Effectiveness + Efficiency + Satisfaction | User Feedback
number of change requests accomodated | CR forms count |  | on going
Resoruce utilization | actuals no of hours/total hours | timesheet, project plan | weekly | 100% | 99.73% | +/- 5%
over run, delays | excess man days as of planned |  | weekly, monthly
Burn Rate | Number of hours projected VS number of hours spent | Trend (User Stories Points/ Backlogs)
Capacity - Resource | Capacity Planned Vs Consumed
miestone against invoices
User Stories Planned Vs Delivered
Velocity | Total story points completed from each Sprint | Sprint Board | Every 2 or 4 Weeks
Productivity
Defects - QA | Defect count/Release size | No of Defects per User Story
Cost variance
Defect Density - Prod | Defect count/Release size | No of Defects per User Story | Every Release | 1 defect per KLOC
Task Effort Estimation Vs Actuals
Schedule variance | Earned - Planned
Schedule and Cost | % complete with budget value
Performance of Application | Average Response Time
Cost performance
ROI
Customer satisfaction
employee satisfaction
review efficiency | no of review bugs/ total bugs