## Introduction
DEPLOYING MICROSOFT OFFICE PROJECT SERVER 2007 IN AN ENTERPRISE ENVIRONMENT
Enterprise Implementation Framework Document
EIF Document
Instructions: Use this workbook to record key information for the implementation process and the full details of your implementation plans. Each tab in this workbook is used to record a specific type of information. Each tab is optimized for that type of information.
This workbook is designed to be used with the companion document EIF System Design Guidelines. Follow the instructions in that document to fill out each tab in this workbook.
WARNING: This workbook contains validations which are set up on the last tab, titled Validations. Do not edit this tab. It is locked by default.

## Roles
Microsoft Project 2007 User Roles
User Roles | Imentation Team Roles
Project Manager | Implementation Lead (Customer)
Task Owner | Implementation Lead (Customer)
IT Support Team | Implementation Team Member
Sr.Executive | Implementation Sponsor
Administrator | IT (system architecture)

## Stakeholders
Microsoft Project 2007/Microsoft Project Server Stakeholders
Instructions: List the names and and specified information for each of the key senior managers
Name | Title | E-Mail Address | Phone Number | Role | Roles
Denzil Benjamin | Head- Clinical Operations | denzil.benjamin@clinigeneintl.com | 91 80 2808 2755 |  | Executive
Sorabh Kapoor | Clinical Research Associate-II | sorabh.kapoor@clinigeneintl.com | 91 99867 12704 |  | PM
Vidya Kamath | Clinical Research Associate-II | vidya.Kamath@clinigeneintl.com |  |  | PM

## Implementation Team
Microsoft Project 2007 Implementation Team
Instructions: List the specified information for each member of the implementation team.
Company | Name | E-Mail Address | Phone Number | Implementation Role
AstroWix India | Sujit Das Biswas | sujit.das@astrowix.com |  | Implementation Consultant
AstroWix India | Tripti Kochhar | tripti.agarwal@astrowix.com |  | Implementation Consultant
AstroWix India | Ashish Gedam | ashish.gedam@astrowix.com |  | Implementation Consultant
BioCon | Veena Vasantha | veena.vasantha@biocon.com |  | Implementation Team Member
BioCon | Nanjunda Kumar | nanjunda.kumar@biocon.com |  | Implementation Team Member

## Interviewees
Interviewee List
Instructions: List the specified information about each person interviewed to determine system requirements.
Name | Title | E-Mail Address | Phone Number | User Role
Denzil Benjamin | Head | denzil.benjamin@clinigeneintl.com | 91 80 2808 2755 | Executive
Sorabh Kapoor | PM | sorabh.kapoor@clinigeneintl.com | 91 99867 12704 | PM
Vidya Kamath | PM | vidya.kamath@clinigeneintl.com |  | PM

## PM Training
Project Management / Task Owner/ Administrator Training
Instructions: Based on the Requirements Specification, the Red Flags document, and your analysis of your organization's sophistication re: project management methodology, determine whether individuals in your organization need further training on project management principles and methodology. It's important that project managers understand these principles in order to use Microsoft Project 2007 effectively.
Name | E-Mail Address | Phone Number | User Role
Denzil Benjamin | denzil.benjamin@clinigeneintl.com |  | Executive
Sorabh Kapoor | sorabh.kapoor@clinigeneintl.com |  | Project Manager
Vidya Kamath | vidya.kamath@clinigeneintl.com |  | Project Manager

## Projects
Project Information
Instructions: Review the following questions and, based on the Requirements Specification, fill in your answers in the Value column. Include any further comments in the Comments column and note any supplementary documents in the Reference column.
Project Settings | Value | Comments | Reference
Project definition | Yes
Archived or saved versions | Yes
Capacity
Expected number of projects | 50
Average size of projects (number of tasks) | 160
Largest expected project (number of tasks) | 200
Project/Task Identification
Project numbering/ID system | No | Projects are segregated by phases
WBS format (if non-standard WBS is used) | yes
Task Effort/Duration Calculations
Default task type | Fixed Units
Effort-driven tasks by default | Yes
Interproject Relationships
Do you use external dependencies (cross-project links) in current projects? | Yes
Will you use external dependencies in the future? | Yes
Earned Value
Will you be using earned value? | No
If so, what earned value technique will you be using? | % Complete
Templates
NPP | yes

## Resources
Resource Information
Instructions: Review the following questions and, based on the Requirements Specification, Include any further comments in the Comments column and note any supplementary documents in the Reference column.
Resource Settings | Value | Comments | Reference
Total number of resources
Total number of system users | 50
Will you follow an existing standard resource ID system? | No
What is the convention for naming resources?
Rates and Fees
Will you use resource rates? | No
Rate Table A use | No
Rate Table B use | No
Rate Table C use | No
Rate Table D use | No
Rate Table E use | No
Importing Resource Data
How will you add resources into the system? | [company Name] AD ([company Name] Active Directory)
What specific resource information will you enter/import? | Name / Mail ID
Resource Skills
Will you do skills-based scheduling? | No
Does a skills inventory presently exist? | No
What is the maximum number of skills that can be associated with a single resource? | NA
What is the average number of skills that will be associated with a single resource? | NA
Generic Resources | Generic Resources

## Calendars
Working Time Information
Calendar Settings | Value | Reference
What are your organization's standard working times? | 7:30 AM to 4:00 PM
Is there more than a single standard calendar? | Yes
Do all resources have the same basic working times? | Yes
Base calendar 1: | Clinigene
Base calendar 2: | 7 Days
Will you adjust the maximum units for resources or their working hours per day to accommodate nonproject working time? | No
How many hours per day will you assume users work on project work? | 8 hrs
Where will resource availability information be entered? | Enterprise Resource Pool
What system and fields will be used? | EPM System | Remaining Availablity
Will you use standard task calendars? | Yes
Task calendar 1: | 7 Days
Task calendar 2:

## Codes
Code Definitions
Instructions: Based on the Requirements Specification, for each code that you will define, specify informaton about the code, one code per row.
Enterprise Codes
Applies to? | Type | Project Code | Custom Code Name | Mandatory? | Use Validation List? | Comment | Reference
Project | Text | Project_Status | Project_Status |  | Yes | Formula | Requirement.doc
Project | Text | Project_Type | Project_Type | Yes | Yes |  | Requirement.doc
Project | Text | Project_info | Project_info | Yes | Yes |  | Requirement.doc
Task | Text | Schedule Status | Task Indicator |  | Yes | Formula | Requirement.doc

## CustomViews
Custom Views Definitions
Instructions: Based on the Requirements Specification, for each custom views, informaton about the view and the fields present is specified.
View appears in? | Custom View Name | Category view applies to? (for Project Server Views only) | Restricted to categories? (for Project Server Views only) | Comment | Default table (for Project 2007 Views only) | Sort/Group/Chart Format/Filter (for Project 2007 Views only) | Chart Formatting | Fields
Project Center View | Clinigene DashBoard Summary | Project | NA | NA | Na | Project_Type/Project_Info | Summary (Project Center) | Project Name / % Complete /Project_Status/Start / Finish / Duration / Work / Owner /Project_Type
Project Center View | Clinigene Project Summary | Project | NA | NA | Na | Project_Type/Project_Info | Summary (Project Center) | Project Name / % Complete /Project_Status/Start / Finish / Duration / Work / Owner /Project_Type
Project Center View | Clinigene DashBoard Tracking | Project | NA | NA | Na | Project_Type/Project_Info | Tracking (Project Center) | Project Name / % Complete /Project_Status/Start / Finish / Baseline Start/ Baseline Finish/ Actual Start/ Actual Finish/ Owner /Project_Type
Project Center View | Clinigene Project Tracking | Project | NA | NA | Na | Project_Type/Project_Info | Tracking (Project Center) | Project Name / % Complete /Project_Status/Start / Finish / Baseline Start/ Baseline Finish/ Actual Start/ Actual Finish/ Owner /Project_Type
Project View | Clinigene Milestone Details | Project |  |  |  | Milestone | Gantt Chart (View) | ID/Task Name/ Schedule Status/% Complete/ Start/Finish/ Baseline Start/Baseline Finish
Project View | Clinigene Task Details | Project |  |  |  | Details | Gantt Chart (View) | ID/Task Name/ Schedule Status/% Complete/ Start/Finish/ Baseline Start/Baseline Finish / Start Variance / Finish Varaince
Project View | Clinigene Task Summary Details | Project |  |  |  | Summary filter | Gantt Chart (View) | ID/Task Name/ Schedule Status/% Complete/ Start/Finish/ Baseline Start/Baseline Finish / Start Variance / Finish Varaince
Project View | Clinigene Task Tracking | Project |  |  |  |  | Gantt Chart (View) | ID/Task Name/ Schedule Status/% Complete/ Start/Finish/ Baseline Start/Baseline Finish / Actual Start / Actual Finish / Duration / Actual Duration / Remaining Duration / Actual Work

## Project Document
Sharepoint Document Library Settings
Instructions: Based on the Requirements Specification, define any customizations you will make to the issues. For each list, use one row for each field in the list and enter the information about each field in columns B-F.
Folders;
1 | Confidentiality Agreement
2 | Feasibility Assessment
3 | Site Evaluation
4 | Ethics Committee SOPs
5 | Ethics Committee Membership List
6 | Translation Required(Languages)
7 | Sent for Translations
8 | Translation Received
9 | Sent to Site for Review
10 | Corrections Suggestions Received from Site
11 | Final Copies of Transalations along with Certificates from translation received
12 | Sent for Back translation
13 | No. of Copies for EC submission
14 | EC approval at Site
15 | Copies of EC Submission- Approval in TMF
16 | Local laboratory reference range
17 | Protocol Signature page- Investigator agreement
18 | CV of Prinicipal Investigator
19 | Medical registration certification- No of the principal investigator
20 | CV's of other Study team members
21 | Letter of Undertaking
22 | Insurance - indemnity provided
23 | Site Budget sent to site
24 | Approved site budget received on
25 | Financial Agreement sent to site
26 | Signed Financial Agreement received from Site
27 | Site specific start up presentation
28 | ITF
29 | TMF
30 | Study Drug shipped to site
31 | Non-Drug supplies shipped to site
32 | Site Initiation Visit

## SharePoint Team Services
SharePoint Team Services Custom List Settings
Instructions: Based on the Requirements Specification, define any customizations you will make to the issues. For each list, use one row for each field in the list and enter the information about each field in columns B-F.
Custom list name | Fields | Field type | Typical value | Reference
Site Information
| Site No | Single Line Text
| Site Name | Single Line Text
| Site Address | Single Line Text
Subject Information
| Site No | Lookup |  | Site No from Site Information List
| Subject No | Single Line Text
| Subject Initials | Single Line Text
| Gender | Choice
| Date of Birth | Date/Time
| Screening Date | Date/Time
| Screen failure | Choice
| Planned Enrolled Date | Date/Time | Screening Date+7D
| Actual Enrolled Date | Date/Time
| IC Date | Date/Time
| V-I Planned Date | Date/Time
| V-I Actual Date | Date/Time
| V-II Planned Date | Date/Time
| V-II Actual Date | Date/Time
| DropOut/WithDrawn Date | Date/Time
| DropOut/WithDrawn | Choice
| Evaluable Subjects | Choice
| SAE | Choice
| Study Completed | Choice
Investigator Information
| Site No | Lookup |  | Site No from Site Information List
| Investigator PAN no | Single Line Text
| EC PAN no | Single Line Text
| Institution PAN no | Single Line Text
| Designation | Choice
| Doctor Name | Single Line Text
| Mobile Number | Single Line Text
| Business Phone | Single Line Text
| Home Phone | Single Line Text
| Email ID | Single Line Text
| Fax No | Single Line Text
| Address | Multi-LineText
| City | Single Line Text
SAE Tracking
| Sr No | Single Line Text
| Subject Initials | Lookup |  | Subject Initials from Subject Information
| SAE Report Type | Choice
| Report Date | Date/Time
| Name of Event | Multi-LineText
| SAE Criteria | Choice
| Casuality | Choice
| OutCome | Choice
| EC Notification | Date/Time
| DCGI Notification | Date/Time
| Notification to Sponsor | Date/Time
Recruitment Sheet
| Sr No | Single Line Text
| Site No | Lookup |  | Site No from Site Information List
| Planned Feasibility Evaluation | Number
| Expected Feasibility Evaluation | Number
| Planned Site Evaluation | Number
| Expected Site Evaluation | Number
| Month Of Recruitment | Choice
| Expected patients | Number
| Screened Patients | Number
| Enrolled Patients | Number
Deviation Tracking
| Sr No | Single Line Text
| Subject No | Lookup |  | Subject No from Subject Information
| Deviation Reporting Manager | Person or Group
| Deviation Requester | Person or Group
| Details of Deviation | Multi-LineText
| Deviation Occurrence | Date/Time
| Approved By | Single Line Text
Protocol Tracking Log
| Control Copy No | Single Line Text
| Issued Date | Date/Time
| Site No | Lookup |  | Site No from Site Information List
| Issued By | Person or Group
| Comments/Remarks | Multi-LineText
Team Discussion
| Subject | Single Line Text
| Body | Multi-LineText
| Assigned to | Person or Group
Project Documents
Folder
| Name | Single of text
| Modified | Date/Time
| Owner | Person or Group
| Status | Choice
| Modified By | Date/Time
| Version | Default
| Hospital | Lookup |  | Site No from Site Information List
| Availability | Choice
Version

## Issues
Issue Settings
Instructions: Based on the Requirements Specification, define any customizations you will make to the issues. Use the Fields section to specify additional fields you will define for issues. Use the Custom Views section to define addtional views you will define for issues.
Fields
Field Name | Field type | Typical value | Validation list
Title | Single line of text
Owner | Person or Group
Assigned To | Person or Group
Status | Choice
Category | Choice
Priority | Choice
Due Date | Date/Time
Discussion | Multi-LineText
Resolution | Multi-LineText
Links | Project Link
Created By | Person or Group
Modified By | Person or Group
Custom Views
View Name | Fields in the view | Filter | Group
All Items | Title
All Issues Assigned to Me | Owner | Created by is equals to Me
All Issues Owned by Me | Assigned To | Owner is equals to Me
All Issues Opened by Me | Status | Created by is equals to Me
All Active Issues | Category | Status is equals to Active
All Closed Issues | Priority | Status is equals to Closed
All Postponed Issues | Due Date | Status is equals to Postponed
Discussion
Resolution
Links
Created By
Modified By

## Risk
Risk Settings
Instructions: Based on the Requirements Specification, define any customizations you will make to the issues. Use the Fields section to specify additional fields you will define for issues. Use the Custom Views section to define addtional views you will define for issues.
Fields
Field Name | Field type | Typical value | Validation list
Title | Single line of text
Owner | Person or Group
Assigned To | Person or Group
Status | Choice
Category | Choice
Due Date | Date and Time
Probability | Number
Impact | Number
Exposure | Calculated (calculation based on other columns)
Cost | Currency
Cost Exposure | Calculated (calculation based on other columns)
Description | Multiple lines of text
Mitigation Plan | Multiple lines of text
Contingency Plan | Multiple lines of text
Trigger Description | Multiple lines of text
Trigger | Choice
Links | Project Link
Created By | Person or Group
Modified By | Person or Group
Custom Views
View Name | Fields in the view | Filter | Group
All Items | Title
All Risks Assigned to Me | Owner | Created by is equals to Me
All Risks Owned by Me | Assigned To | Owner is equals to Me
All Risks Opened by Me | Status | Created by is equals to Me
All Active Risks | Category | Status is equals to Active
All Closed Risks | Due Date | Status is equals to Closed
All Postponed Risks | Probability | Status is equals to Postponed
Impact
Exposure
Cost
Cost Exposure
Description
Mitigation Plan
Contingency Plan
Trigger Description
Trigger
Links
Created By
Modified By

## Notifications (hidden)
Custom Notifications
Instructions: Based on the Requirements Specification, define the custom notifications that you want to create.
Description | Publish or subscribe notification? | Notification users | Fields in notification | Notification text | SQL satement

## Project Guide (hidden)
|  | Custom Project Guides |  |  |  | Project Guide
Instructions: Based on the Requirements Specification, define the custom Project Guides that you want to create.
Guide name | Applies only to template? | Description | Toolbar Items | Tasks for toolbar item | View for task | Side pane descripton | URL or Object Model reference | Reference
Maintenance | IT Maintenance | This Project Guide has a simple methodology for tracking maintenance projects for IT. | Open | Initiate | Gantt Chart | Sets up project charge number and PM assigned to
|  |  |  | Requestor | Gantt Chart | Identifies manager of department making the maintenance request
|  |  |  | Delivery Date Requested | Gant Chart | When does the requestor want the change completed?
|  |  | Active | Swich to standard PG | Gantt Chart | Standard PG task panes are used during the execution of the project
|  |  | Closed | Close out date | Gantt Chart | Set close out date for project charges

## IT
IT Requirements
Instructions: Based on the Requirements Specification and working with your IT department, define the system requirements.
Machine | Hardware Configuration | IP Address | OS | Comments
IIS Server for Microsoft Project Server | CPU : Intel Xeon Dual Core 1.8 GHZ RAM : 3 GB Disk: 80 GB Network cards : 10/100 mbps | [IP Address] | Windows 2003 Server Enterprise Edition
SQL Server 2007 Database Server | CPU : Intel Xeon Dual Core 1.8 GHZ RAM : 3 GB Disk: 80 GB Network cards : 10/100 mbps | [IP Address] | Windows 2003 Server Enterprise Edition
Typical project manager workstation | CPU : P4 (1.7 GHz) RAM : 512 MB Disk : 40 GB Network cards : 10/100 mbps |  | Windows XP Professional | For Project Manager those who are using MS Project 2007 Minimum Ram will be 512
Typical Web Access workstation | CPU : P4 (1.7 GHz) RAM : 256 MB Disk : 40 GB Network cards : 10/100 mbps |  | Windows XP Professional
Notification Server (SMTP)
E-mail system

## System Administration
System Administration
Instructions: Based on the Requirements Specification and the Red Flags document, define the key settings for Microsoft Project 2007 Server, Microsoft Project 2007, and Microsoft Project 2007 Web Access. For product versions, list the version name in the Settings Column and provide a description of it in the Comments column. The standard working version, Published, is defined for you. Under Features Not Available to Organization, list the Microsoft Project 2007 Web Access features that you will not use in your organization. Under Project Server, specify the basic information about your project servers. Under Customized Menu Structure, list any customization you will make to the Microsoft Project 2007 Web Access menu structure. Indicate the new or changed Center name in the Value column of the Center row. Under the Center heading, list the menu items the center will include (or the items you are changing under an existing center) and the URL and tooltip for the menu item. Under Customized Categories, in the Values column specify detailed information about the customized category, as indicated.
| Values | Comments | Reference
Enterprise Options:
Publish Master Projects | Yes
Allow local base calendars | No
Single currency | Yes
Microsoft Project Server
Microsoft Project Server Intranet Address | http://bioconepm/clinigene
Microsoft Project Server Extranet Address | NA
Modifications to Categories:
Category Name | Clinigene | Clinigene
Users and groups | Project Manager | CRA(PM)
Permisssions
View projects in Project Center | Yes | Yes
View project tasks in Project views | Yes | Yes
Open project | Yes | Yes
Save project | Yes | Yes
View enterprise resource data | Yes | Yes
Edit enterprise resource data | Yes | Yes
View resource assignments in assignment views | Yes | Yes
View Documents and Issues | Yes | Yes
Viewable projects
All projects | Yes | Yes
Only this list of projects
All projects they manage | Yes | Yes
All projects they are assigned to | Yes | Yes
All projects my staff manages
All projects my staff is assigned to
Project Center views | Yes | Yes
Project views | Yes | Yes
Viewable resources
All resources | Yes | Yes
Only this list of resources | Yes | Yes
View Resource they manage | Yes | Yes
View resources assigned to projects they manage | Yes | Yes
Assignments views | Yes | Yes
Resource Center views | Yes | Yes
Portfolio Analyzer views | Yes | Yes

## Validations
Yes | Fixed Units | Text | Project | Project Center View | Project | To Project | Single Line Text | Windows 2003 Server Enterprise Edition | Publish |  | Physical % Complete
No | Fixed Work | Outline | Resource | Project View | Portfolio | From Project | Multi-LineText | Windows 2003 Advanced Server | Subscribe |  | % Complete
| Fixed Duration | Number | Task |  | Assignment | Both | Number | Windows .Net Server | Both | Microsoft Project Server
|  | Date |  |  | Resource |  | Currency | Windows NT Server |  | Enterprise Resource Pool
|  | Flag |  |  | PortfolioAnalyzer |  | Date/Time | Windows 2000 Professional |  | Another system
|  | Start |  |  |  |  | Lookup | Windows XP Professional
|  | Finish |  |  |  |  | Choice | Windows NT Workstation
|  | Cost |  |  |  |  | Yes/No
|  | Duration |  |  |  |  | Hyperlink/Picture