## Slide 2: Portfolio Strategy
Microsoft Project 2010 Ignite

## Slide 3: Agenda
Introduction
Business Drivers
  Overview
  Explanation
  Demonstration
Portfolio Analyses
  Overview
  Explanation
  Demonstration

## Slide 4: Introduction

## Slide 5: Why is Effective Portfolio Management Important?
Portfolio
Management
Project
Management
50% Value Realized
50% Value Lost
Ability to identify business value potential
66%
75%
Ability to realize business value potential
Project Management
Helps ensure organizations successfully deliver the selected investments and realize the business value
Portfolio Management
Enables organizations to identify and select the investments that will maximize business value

## Slide 6: Unified Project and Portfolio Management Key benefits of Project Server 2010
Common streamlined user interface
Shared platform/architecture
  Leverages scalable queue architecture
  All data available via read/write Project Server Interface (PSI)
  Final selection decisions published to Reporting Database (RDB)
  No gateway required
New Resource Analysis
Unified Project and Portfolio Management
Enhanced Collaboration and Reporting
Simple and Intuitive User Experience
Scalable and Connected Platform

## Slide 7: Process Overview
Business Drivers Definition
Business Drivers Prioritization
Aligning Projects/Proposals to Business Drivers
Projects/Proposals Prioritization
Portfolio Analysis (cost, resource)

## Slide 8: Related Resources
WebCasts - http://www.microsoft.com/events/series/epm.aspx
  TechNet Webcast: Microsoft Project 2010 Portfolio Analysis (Level 200) by Hilde Corbu, Project MVP
Videos and sessions http://www.microsoft.com/showcase/en/US/channels/microsoftproject/
  Project Server 2010 - Portfolio Management by Luke Humphrey and Catalin Olteanu

## Slide 9: Business Drivers

## Slide 10: Business Driver
Business Drivers represent an organization’s business objectives in Project Server 2010
Create drivers in the Business Driver Library
May be associated with zero or more Departments
Drivers are prioritized to reflect organization’s perceived business impact and importance
Notes: Business Drivers not associated with any Department is considered a global driver. When rating a project’s impact on a set of drivers, only drivers that share the same department of the project and all global drivers will be available and/or required for impact ratings. If the project does not have a departmental association, only global drivers will be available for rating.
When a business driver is no longer part of the currently organizational strategy, the driver should either be deleted or inactivated. Choose to inactivate a driver if you no longer want projects to be rated against this driver, but you would like to keep it for historical purposes.

## Slide 11: Driver Prioritizations
Two ways to prioritize business drivers:
  Calculated: Each driver will be compared to every other driver within the prioritization using a fixed seven-point scale. Once every driver has been rated the system will automatically generate relative priority scores
  Manual: Manual prioritizations allow users to specify priority values for each driver directly
Notes: When creating new driver prioritizations, the prioritization’s department selection will filter the list of available drivers to be prioritized by department. Global drivers will be available regardless of the prioritization’s department. If a department is assigned to a prioritization, only drivers that share that departmental association can be included in the prioritization.

## Slide 12: Calculated Driver Prioritization
System calculates the consistency ratio
Inconsistent prioritizations may make sense in some instances but should be reviewed carefully

## Slide 13
 | Driver A | Driver B | Driver C | Driver D
Driver A | 1 | 9 | 6 | 1
Driver B | 1/9 | 1 | 3 | 1/6
Driver C | 1/6 | 1/3 | 1 | 1/3
Driver D | 1 | 6 | 3 | 1
 | Driver A | Driver B | Driver C | Driver D
Driver A | 1 | 9 | 6 | 1
Driver B |  | 1 | 3 | 1/6
Driver C |  |  | 1 | 1/3
Driver D |  |  |  | 1
 | Driver A | Driver B | Driver C | Driver D
Driver A |  | 9 | 6 | 1
Driver B |  |  | 3 | 1/6
Driver C |  |  |  | 1/3
Driver D |  |  |  | 
 | Driver A | Driver B | Driver C | Driver D
Driver A |  | Extremely More | Strongly More | Equal
Driver B |  |  | Moderately More | Strongly Less
Driver C |  |  |  | Moderately Less
Driver D |  |  |  | 
Fill the systemic matrix with the pairwise values
Calculate eigenvector for the matrix
Normalize eigenvector values to 100% to derive relative priorities
Calculated Driver Prioritization Algorithm

## Slide 14
 | Driver A | Driver B | Driver C | Driver D
Driver A | 1 | 9 | 6 | 1
Driver B | 1/9 | 1 | 3 | 1/6
Driver C | 1/6 | 1/3 | 1 | 1/3
Driver D | 1 | 6 | 3 | 1
 | Driver A | Driver B | Driver C | Driver D
Driver A | 1 | 9 | 6 | 1
Driver B |  | 1 | 3 | 1/6
Driver C |  |  | 1 | 1/3
Driver D |  |  |  | 1
 | Driver A | Driver B | Driver C | Driver D
Driver A |  | 9 | 6 | 1
Driver B |  |  | 3 | 1/6
Driver C |  |  |  | 1/3
Driver D |  |  |  | 
Fill the systemic matrix with the pairwise values
Calculate eigenvector for the matrix
Normalize eigenvector values to 100% to derive relative priorities
Calculated Driver Prioritization Algorithm

## Slide 15
 | Driver A | Driver B | Driver C | Driver D
Driver A | 1 | 9 | 6 | 1
Driver B | 1/9 | 1 | 3 | 1/6
Driver C | 1/6 | 1/3 | 1 | 1/3
Driver D | 1 | 6 | 3 | 1
Fill the systemic matrix with the pairwise values
Calculate eigenvector for the matrix
Normalize eigenvector values to 100% to derive relative priorities
Calculated Driver Prioritization Algorithm

## Slide 16
Business Drivers
DEMO

## Slide 17: Portfolio Analyses
Microsoft Project 2010 Ignite

## Slide 18: Portfolio Analyses
Portfolio analyses are a collection of projects that will compete for selection based on their cost relative to their strategic value
Prioritization of Projects:
  By Business Drivers
  By Custom Field

## Slide 19: Unified Project and Portfolio Management Further considerations
Three data points feed into the portfolio analysis process:
  Cost (Number Custom Field) – e.g. Proposal Cost
  Proposal/project impact on business drivers
    Departments are supported to “filter” related Business Drivers
  Time-phased resource requirements
    Proposal will need a Resource Plan or Project Plan

## Slide 20: Project Prioritization
Could use:
  Business drivers impact statements
  Project custom fields with values and relative priorities (manually calculated by user)
    More information Project Server 2010 - Portfolio Management by Luke Humphrey and Catalin Olteanu

## Slide 21
Fill the impact matrix with the numeric values
Multiply matrix with driver priorities
Normalize resulting absolute values to 100% to derive relative priorities
Project Prioritization Using business drivers impact statements
 | Driver A | Driver B | Driver C | Driver D
Project 1 | 0 | 3 | 1 | 9
Project 2 | 9 | 1 | 1 | 0
Project 3 | 1 | 3 | 0 | 3
Project 4 | 0 | 1 | 0 | 1
Project 5 | 1 | 6 | 0 | 0
 | Driver A | Driver B | Driver C | Driver D
Project 1 | None | Moderate | Low | Extreme
Project 2 | Extreme | Low | Low | None
Project 3 | Low | Moderate | None | Moderate
Project 4 | None | Low | None | Low
Project 5 | Low | Strong | None | None

## Slide 22
Fill the impact matrix with the numeric values
Multiply matrix with driver priorities
Normalize resulting absolute values to 100% to derive relative priorities
Project Prioritization Using business drivers impact statements
X
Driver priorities
A: 41%
B: 25%
C: 22%
D: 12%
 | Driver A | Driver B | Driver C | Driver D
Project 1 | 0 | 3 | 1 | 9
Project 2 | 9 | 1 | 1 | 0
Project 3 | 1 | 3 | 0 | 3
Project 4 | 0 | 1 | 0 | 1
Project 5 | 1 | 6 | 0 | 0

## Slide 23
Fill the impact matrix with the numeric values
Multiply matrix with driver priorities
Normalize resulting absolute values to 100% to derive relative priorities
Project Prioritization Using business drivers impact statements
X
=
Driver priorities
A: 41%
B: 25%
C: 22%
D: 12%
Project priorities
P1: 20%
P2: 42%
P3: 15%
P4: 4%
P5: 19%
 | Driver A | Driver B | Driver C | Driver D
Project 1 | 0 | 3 | 1 | 9
Project 2 | 9 | 1 | 1 | 0
Project 3 | 1 | 3 | 0 | 3
Project 4 | 0 | 1 | 0 | 1
Project 5 | 1 | 6 | 0 | 0

## Slide 24: Project Interdependencies
Project dependency relationship will be respected during portfolio selection scenario calculations
There are following types of interdependencies:
  Dependency: If Project A selected, Project B must be selected
  Mutual Inclusion: For a set of projects, if one project is selected, all projects in the set must be selected.
  Mutual Exclusion: For a set of projects, only one project in the set can be selected (Alternatives).
  Finish to Start: Used in Resource Constraint Analysis for identifying scheduling constrains

## Slide 25: Cost constraint analysis

## Slide 26: Constraint Optimization The need for optimization
Available budget: $100
Request: chose the projects that provide maximum value to the business
 | Value | Cost
Project 1 | 30% | $100
Project 2 | 20% | $60
Project 3 | 15% | $40
 | Value | Cost
Project 1 | 30% | $100
Project 2 | 20% | $60
Project 3 | 15% | $40
Total strategic value: 30%
Total strategic value: 35%
Top-down selection
Optimization

## Slide 27
Maximize (x1*v1+x2*v2+x3*v3+ … +xn*vn)
Subject To:
x1*c1+x2*c2+x3*c3+ … +xn*cn <= C
Where
x1, x2… xn = 0 or 1 (algorithm outputs: project in/out)
v1, v2… vn are the project priorities
c1, c2… cn are the constraint values for each project
C is the total constraint value; we have one such row for each constraint
Efficient frontier (based on one constraint):
  For N data points equally spaced between zero and the sum of the constraint
Run Optimization algorithm and determine corresponding portfolio value
Constraint Optimization Algorithm

## Slide 28: Force In/Out
A portfolio may contain projects that must be either selected or not selected, regardless of their cost/value ratio or their dependencies on other projects.
Aliases available for “Force In/Out” per analysis
Examples:
  A non-strategic project that must be implemented because of legal compliance issues will need to be “forced in” the portfolio.
  A very costly project might need to be “forced out” of a portfolio to free up resources for other projects and improve the portfolio’s overall ROI
Notes: ROI = Return on Investment

## Slide 29
Cost Analysis
DEMO

## Slide 30: Resource constraint analysis

## Slide 31: Resource Constraint Analysis Related Portfolio Analysis Configuration
Specify the resource custom field that defines role
Specify the planning horizon dates and granularity
Filter resources by department or RBS value
Consider proposed bookings when calculating capacity for projects outside the analysis (advanced)
Specify how project dates are set
  Respect the project resource plan setting which allows pulling resource requirement data from the project schedule, the resource plan, or a mixture of the two
  Use project date custom fields to specify dates

## Slide 32: Resource Constraint Analysis Simplified Algorithm – Resource Allocation
Portfolios may also be analyzed by their high-level resource requirements combined with their prioritization
Higher priority projects are resourced first, lower priority projects are resourced last.
If resource availability does not meet a given project’s demand for any period for any role, that project is not resourced and the project with the next lowest priority is examined

## Slide 33
Resources Analysis
DEMO

## Slide 34: And when you’re done?

## Slide 35: Portfolio Comparison
Portfolio selections scenarios should be adjusted and recalculated until a scenario is reached that should be finalized or compared with other scenarios
Portfolios may be compared with each other by:
  Projects Selected
  Strategic Value
  Custom Fields (example: ROI )

## Slide 36: Commit Portfolio Analysis Decisions
Once you have completed your portfolio analysis, the final step is to commit your portfolio
Optionally, committed portfolios may kick off a workflow

## Slide 37
Comparing Portfolio Selection Scenarios
DEMO

## Slide 38: Summary
Business Drivers
  Overview
  Explanation
  Demonstration
Portfolio Analyses
  Overview
  Explanation
  Demonstration

## Slide 39: - Resources
Product information and trial download
  http://www.microsoft.com/project
  Project Team Blog http://blogs.msdn.com/project
Interactive content - Videos & Sessions & Webcasts
  http://www.microsoft.com/showcase/en/US/channels/microsoftproject
  http://www.microsoft.com/events/series/epm.aspx
IT Professional related
  TechCenter @ TechNet http://technet.microsoft.com/ProjectServer
  Admin Blog http://blogs.technet.com/projectadministration
Developer related
  Developer center @ MSDN http://msdn.microsoft.com/Project
  Programmability blog http://blogs.msdn.com/project_programmability
Additional questions? Project 2010 Forums!
  http://social.msdn.microsoft.com/Forums/en-US/category/projectserver2010,projectprofessional2010
SharePoint 2010
  http://sharepoint.microsoft.com
FORUMS
Project Professional 2010
General Questions and Answers
Project Server 2010
General Questions and Answers
Setup, Upgrade, Administration and Operation
Customization and Programming

## Slide 40
© 2009 Microsoft Corporation. All rights reserved. Microsoft, Windows, Windows Vista and other product names are or may be registered trademarks and/or trademarks in the U.S. and/or other countries.
The information herein is for informational purposes only and represents the current view of Microsoft Corporation as of the date of this presentation. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information provided after the date of this presentation. MICROSOFT MAKES NO WARRANTIES, EXPRESS, IMPLIED OR STATUTORY, AS TO THE INFORMATION IN THIS PRESENTATION.