## Work Spec
|  | Min (no of man days | Max (no of man days | Estimated Project Schedule
Complete Deployment - Basic |  | 101
Complete Deployment - Advance |  | 112 |  | 86
Least Expensive Deployment |  | 55
Min (Days) | Max (Days) | Optional |  |  | Role
14 |  | N |  |  |  | 1 | Assess and Define Organization’s (Project Management) Requirements and establish target PM Maturity level
3 |  | N |  |  | PC |  | 1.1 | Understand clients PM Readiness (existing PM Maturity Level), Expected PM Maturity Level, needs and expectation from the EPM system; establish a target maturity level viz-a-viz PMI’s OPM3 for instance.
5 |  | N |  |  | PC |  | 1.2 | Understand and agree on Project, Program and Portfolio Management Performance Metrics and Reports to be implemented; in short, identify and freeze Project Report, Busines Intelligence and Analytics requirements, including data source, datapoints and output formats
1 |  | N |  |  | PC |  | 1.3 | Prioritize the (required PM capability and functionality) wish list and finalize the requirements doc and the phases in which they will be achieved.
1 |  | N |  |  | PC |  | 1.4 | Develop Scope of Work Specification; and what is not in the scope.
3 |  | N |  |  | PC |  | 1.5 | Solution Architecture and Design, both logical and physical.
1 |  | N |  |  | PC, TC |  | 1.6 | Establish Solution Size, Performance criteria, and SW licensing requirements.
12 | [5 empty] | 2 | Establish Technology Environment
|  | Y |  |  |  |  | 2.1 | Set up required HW and Network Infrastructure as established through Step 1.e
0 |  | Y |  |  | TC |  |  | 2.1.1 | Set up Servers with required RAID levels.
0 |  | Y |  |  | TC |  |  | 2.1.2 | Set up network connectivity’s between the EPM farm and rest of the network, especially the Active Directory Domain Services, Firewalls etc
1 |  | Y |  |  | TC |  |  | 2.1.3 | Create admin and service accounts
[7 empty] | 2.2 | Install required SW’s
1 |  | Y |  |  | TC |  |  | 2.2.1 | Windows Operating System,
2 |  | N |  |  | TC |  |  | 2.2.2 | SQL Server Database and other components as required viz. SSRS, SSAS etc
0.5 |  | N |  |  | TC |  |  | 2.2.3 | SharePoint Server
0.5 |  | N |  |  | TC |  |  | 2.2.4 | Project Server
0.5 |  | N |  |  | TC |  |  | 2.2.5 | Create Project Web Access Site
0.5 |  | N |  |  | TC |  |  | 2.2.6 | Desktop clients; Project Professional and/or Internet Explorer, MS Office applications as required etc
[7 empty] | 2.3 | Post-Install Configuration
[8 empty] | 2.3.1 | Configure SharePoint Service Applications
0.5 |  | Y |  |  | TC |  |  |  | 2.3.1.1 | Configure PerformancePoint Services for the new Project Server site
0.5 |  | Y |  |  | TC |  |  |  | 2.3.1.2 | Configure Excel Services for the new Project Server site
0.5 |  | Y |  |  | TC |  |  |  | 2.3.1.3 | Configure Secure Store Services for Reporting
[8 empty] | 2.3.2 | Configure the Cube Building Service
0.5 |  | Y |  |  | TC |  |  |  | 2.3.2.1 | Install the SQL Server Native Client and Analysis Management Objects
2 |  | N |  |  | TC |  |  | 2.3.3 | Tune SQL Server for best performance
2 |  | N |  |  | TC |  |  | 2.3.4 | Verify Project Server Functionality
15.6667 |  |  |  |  | PC | 3 | Establish Project, Program and Portfolio Management objectives/processes
47 | [5 empty] | 4 | Configure and Customize the EPM capabilities/functionalities and map them to thus established to Project, Program and Portfolio Management Processes
2 |  | Y |  |  | FC, TC |  | 4.1 | Governance Process Definition
5 |  | Y |  |  | FC, TC |  | 4.2 | Demand (Work Requests) Management
3 |  | Y |  |  | FC, TC |  | 4.3 | Business Case Development
2 |  | Y |  |  | FC, TC |  | 4.4 | Portfolio Prioritization, Optimisation and Selection
2 |  | Y |  |  | FC, TC |  | 4.5 | Capacity Planning (Skill level)
2 |  | N |  |  | FC, TC |  | 4.6 | Project Planning
2 |  | N |  |  | FC, TC |  | 4.7 | Schedule Management
2 |  | N |  |  | FC, TC |  | 4.8 | Resource Management
3 |  | N |  |  | FC, TC |  | 4.9 | Cost Management
3 |  | N |  |  | FC, TC |  | 4.1 | Time and Task Management
2 |  | N |  |  | FC, TC |  | 4.11 | Change Management
2 |  | N |  |  | FC, TC |  | 4.12 | Issue and Risk Management
3 |  | Y |  |  | FC, TC |  | 4.13 | Earned Value Analysis
4 |  | Y |  |  | FC, TC |  | 4.14 | Financial Management
3 |  | N |  |  | FC, TC |  | 4.15 | Communication Management
5 |  | Y |  |  | FC, TC |  | 4.16 | Business Intelligence and Analytics
2 |  | Y |  |  | FC, TC |  | 4.17 | Program Management
16 | [5 empty] | 5 | Project and Portfolio Creation
10 |  | N |  |  | FC |  | 5.1 | Create Project Plan and publish (10 Nos.)
3 |  | Y |  |  | PC, FC |  | 5.2 | Create Program and publish (2 Nos.)
3 |  | Y |  |  | PC |  | 5.3 | Create Portfolio and publish (1 No.)
11 | [5 empty] | 6 | Development
3 |  | Y |  |  | Developer |  |  | Sharepoint Server development
3 |  | Y |  |  | Developer |  |  | Project Server development
5 |  | Y |  |  | Developer |  |  | Custom Report development
5 |  | Y |  |  | TC | 7 | PoC/ProtoType and Solution Functionality Testing with Pilot Team/Project
2 |  | N |  |  | TC | 8 | Solution Performance Testing
1 |  | N |  |  | PC | 9 | User Acceptance Testing
1 |  | N |  |  | TC | 10 | Deploy to production environment
3 | [5 empty] | 11 | Training (Solution oriented Custom Training)
1 |  | Y |  |  | TC |  | 10.1 | For EPM Administrators
0.5 |  | Y |  |  | FC |  | 10.2 | For EPM End Users (other than PM's and Executives)
0.5 |  | Y |  |  | FC |  | 10.3 | For Executives
1 |  | Y |  |  | PC |  | 10.4 | For Project managers
Note on A2: Author: Best Candidate for Vanilla Deployment Complete deployment, including Portfolio and PerformancePoint feature, albiet only what is available out of the box.
Note on A3: Author: Includes development work on SharePoint, ProjectServer integration with ERP/CRM etc, Custom OLAP cubes/Data Mart Development and Custom Report Development
Note on C3: Author: Vsit ProjectPlan-Complete-Adv Tab for a rough implementation plan for this particular type of implementation; the project schedule for best of all two/three tier solution should not be more than 3 months.
Note on A4: Author: Implements ONLY the Mandatory functionalities; enough for a small and medium size Project Management requirement
Note on I9: Author: This activity uses a set of pre defined requirements gathering worksheet
Note on I10: Author: This activity uses a set of pre defined requirements gathering worksheet. alllows clients to pick and choose from pre developed reports, dashboards and scorecards besides routine project analytics
Note on H38: Author: This set of processes and Objectives could be had from an establishes PMO and gathered during PMO set Up activity; duration for which shall depend on PMO maturity at the clients oraganisation Fotr most of the routine implementation, this activity should be impicitly covered in the Activity Category 4; whence PC spends about 1/3rd of the days in cell A40.
Note on I41: Author: This will require PLM definition at the top level; a more granular definition will be followed in the Demand Management step.
Note on I42: Author: 4.1 and 4.2 together will require EPT's i.e Enterprise Project Types to be defined. EPT's definition will include definition of Project Phases, Stages in each phase, Creation of Project Server Objects, Custom Fields, PDP, Plan Template, Workspace site template etc
Note on I43: Author: Define Business Drivers, Impact Statements, etc

## HW Req
Two Server Architecture
| Req Type | Machine | Processor | RAM | HDD | RAID | SW
Project Server Machine | Minimim | 64 Bit | Dual Core; 3 Gz or more | 4 GB | 80 GB |  | Microsoft Internet Explorer 7
| Recommended | 64 Bit | Dual Quad Core; 3 Gz or more | 8 GB | 200 GB | RAID 1 | Microsoft Internet Explorer 8
| Req Type | Machine | Processor | RAM | HDD | RAID | SW
SQL Server Machine | Minimum | 64 Bit | Dual Quad Core; 3 Gz or more |  |  |  | Microsoft SQL Server 2005 with Service Pack 3 (SP3)
| Recommended | 64 Bit | Dual Quad Core; 3 Gz or more |  |  |  | Microsoft SQL Server 2008 with Service Pack 1 (SP1) and Cumulative Update 2 or Microsoft SQL Server 2008 R2

## ProjectPlan-Complete-Adv
Rough Implementation Plan for 2010 complete adv
| Activity Name | Proj Duration |  |  | Predecessors
EPM Implementation - Complete Advance |  | 86 days | 2007-05-25 08:00 | 2007-09-21 17:00
1899-12-31 | Assess and Define Organization’s (Project Management) Requirements and establish target Maturity level | 14 days | 2007-05-25 08:00 | 2007-06-13 17:00
1900-01-01 | Establish Technology Environment | 12 days | 2007-05-25 08:00 | 2007-06-11 17:00
1900-01-02 | Establish Project, Program and Portfolio Management objectives/processes | 16 days | 2007-06-14 08:00 | 2007-07-05 17:00 | 2
1900-01-03 | Configure and Customize the EPM capabilities/functionalities and map them to thus established to Project, Program and Portfolio Management Processes | 31 days | 2007-07-06 08:00 | 2007-08-17 17:00 | 4
1900-01-04 | Project and Portfolio Creation | 16 days | 2007-08-20 08:00 | 2007-09-10 17:00 | 5
1900-01-05 | Development | 11 days | 2007-06-12 08:00 | 2007-06-26 17:00 | 3
1900-01-06 | PoC/ProtoType and Solution Functionality Testing with Pilot Team/Project | 5 days | 2007-09-11 08:00 | 2007-09-17 17:00 | 7,6
1900-01-07 | Solution Performance Testing | 2 days | 2007-09-18 08:00 | 2007-09-19 17:00 | 8
1900-01-08 | User Acceptance Testing | 1 day | 2007-09-20 08:00 | 2007-09-20 17:00 | 9
1900-01-09 | Deploy to production environment | 1 day | 2007-09-21 08:00 | 2007-09-21 17:00 | 10
1900-01-10 | Training (Solution oriented Custom Training) | 3 days | 2007-09-11 08:00 | 2007-09-13 17:00 | 6