## Sheet1
House-1025-Phase1== | House-1025-Phase1 |  |  | Status | Planned End Date | Duration | Actual Duration | Cost | Dependency
Architecture & Design== | Architecture & Design
=House Layout Design= |  | House Layout Design |  | Done |  | 2 | 30
=Foundation Layout Design= |  | Foundation Layout Design |  | Done
=Pillar & Beam work Layout Design= |  | Pillar & Beam work Layout Design |  | Not Started
=Woodwork Layout Design= |  | Woodwork Layout Design |  | Done
=Plumbing Layout Design= |  | Plumbing Layout Design |  | Not Started
=Electric Layout Design= |  | Electric Layout Design |  | Not Started
=Bathroom Layout Design= |  | Bathroom Layout Design |  | Not Started
=Kitchen Layout Design= |  | Kitchen Layout Design |  | Not Started
=AC Layout Design= |  | AC Layout Design |  | Not Started
=TV Layout Design= |  | TV Layout Design |  | Not Started
=Almira Layout Design= |  | Almira Layout Design |  | Not Started
=Staircase Layout Design= |  | Staircase Layout Design |  | Not Started
=Elevation Layout Design= |  | Elevation Layout Design |  | Not Started
=Sitting & Bed Layout Desing= |  | Sitting & Bed Layout Desing |  | Done
Ground Floor== | Ground Floor
=Procurments= |  | Procurments
==Bricks |  |  | Bricks | Done |  |  |  |  | Foundation Layout Design
==Pathankot Sands |  |  | Pathankot Sands | Done | [5 empty] | Broken Stones
==Hosiyarpur Sands |  |  | Hosiyarpur Sands | Done
==Agreegate |  |  | Agreegate | Done
==Broken Stones |  |  | Broken Stones | Done
==Wood |  |  | Wood | Not Started
==Cement |  |  | Cement | Done
==Iron |  |  | Iron | Done
=Contracting= |  | Contracting
==Building Contractor |  |  | Building Contractor | Done
==Sanitoary Contractor |  |  | Sanitoary Contractor | Done
==Wood Contractor |  |  | Wood Contractor | Done
==Marbel Contractor |  |  | Marbel Contractor | Not Started
==Roof Contractor |  |  | Roof Contractor | Not Started
==Electric Contractor |  |  | Electric Contractor | Not Started
==Paint Contractor |  |  | Paint Contractor | Not Started
=Foundation= |  | Foundation
==Digging |  |  | Digging
==Putting Stones |  |  | Putting Stones
==Wall Construction |  |  | Wall Construction
==DPC |  |  | DPC
==Pillar Contruction |  |  | Pillar Contruction
=Wall= |  | Wall
==Bedroom Wall |  |  | Bedroom Wall | Not Started
==Dining wall |  |  | Dining wall | Not Started
==Kitchen wall |  |  | Kitchen wall | Not Started
==Stair Case No#1 |  |  | Stair Case No#1 | Not Started
==Lobby Expending |  |  | Lobby Expending | Not Started
==New Doors to Bedrooms |  |  | New Doors to Bedrooms | Not Started
==MS: Ground work Complete |  |  | MS: Ground work Complete | Not Started
=Beams= |  | Beams
==
==
==
=Woodwork= |  | Woodwork
==Frames of Ground Floor |  |  | Frames of Ground Floor | Not Started
==Beeding |  |  | Beeding | Not Started
==Doors |  |  | Doors | Not Started
==Almira in Dining Hall |  |  | Almira in Dining Hall | Not Started
=Sanitary= |  | Sanitary
==Fitting of Sewerage Pipe |  |  | Fitting of Sewerage Pipe | Not Started
==Fitting of Water Pipe |  |  | Fitting of Water Pipe | Not Started
==Setting up of 3 Bath Rooms |  |  | Setting up of 3 Bath Rooms | Not Started
==Plumbing work in Kitchen |  |  | Plumbing work in Kitchen | Not Started
==Construction of Water Tank |  |  | Construction of Water Tank | Not Started
=Electric work= |  | Electric work
==Laying of Electric wire |  |  | Laying of Electric wire | Not Started
==Fitting of Lights |  |  | Fitting of Lights | Not Started
==Fitting of Fans |  |  | Fitting of Fans | Not Started
==Fitting of Gysers |  |  | Fitting of Gysers | Not Started
==Fitting of AC |  |  | Fitting of AC | Not Started
=Flooring= |  | Flooring
==Selction of Marbel |  |  | Selction of Marbel | Not Started
==Fitting of Marbel |  |  | Fitting of Marbel | Not Started
==Finishing of Marbel |  |  | Finishing of Marbel | Not Started
=Roof work= |  | Roof work
==Selection of Design |  |  | Selection of Design | Not Started
==POP of Work |  |  | POP of Work | Not Started
==Provision of Light and Fan Points |  |  | Provision of Light and Fan Points | Not Started
==Provision of Wood work |  |  | Provision of Wood work | Not Started
=Stair case= |  | Stair case
==Cutting of Roof |  |  | Cutting of Roof | Not Started
==Construciton of Stair case |  |  | Construciton of Stair case | Not Started
==Fitting of Marbel |  |  | Fitting of Marbel | Not Started
==Fitting of Railing |  |  | Fitting of Railing | Not Started
=Kitchen Setup= |  | Kitchen Setup
==Setting of Chimny |  |  | Setting of Chimny | Not Started
==Wood work in Kitchen |  |  | Wood work in Kitchen | Not Started