## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Etihad Airways - AirVision Cargo - Network Module Implementation | 622 days? | 01-02-11 08:00 | 08-07-13 17:00 |  | 0
1 | Yes | Auto Scheduled | Release 2 - Etihad AirVision Cargo - Network Module Implementation | 622 days | 01-02-11 08:00 | 08-07-13 17:00 |  | 1
2 | Yes | Auto Scheduled | Release 2 Due Diligence | 263 days | 01-02-11 08:00 | 02-02-12 17:00 |  | 2
3 | Yes | Auto Scheduled | Proof of Concept | 1 day | 01-02-11 08:00 | 01-02-11 17:00 |  | 3
4 | Yes | Auto Scheduled | Define Target Baseline Proof of Concept Accuracy | 263 days | 01-02-11 08:00 | 02-02-12 17:00 |  | 3
5 | Yes | Auto Scheduled | O&D Accuracy - 25% Error | 1 day | 01-02-11 08:00 | 01-02-11 17:00 | 3 | 4
6 | Yes | Auto Scheduled | Leg Accuracy - 12% Error | 1 day | 02-02-12 08:00 | 02-02-12 17:00 | 3 | 4
7 | Yes | Auto Scheduled | Inputs criteria complete | 28 days | 15-02-11 08:00 | 24-03-11 17:00 | 4 | 3
8 | Yes | Auto Scheduled | Methodology acceptance | 1 day | 25-03-11 08:00 | 25-03-11 17:00 | 7 | 3
9 | Yes | Auto Scheduled | Perform Simluation of Network Module | 17 days | 27-03-11 08:00 | 19-04-11 17:00 | 8 | 3
10 | Yes | Auto Scheduled | Define to-be end-to-end business process | 3 days | 15-05-11 08:00 | 18-05-11 17:00 | 3,8,9 | 3
11 | Yes | Auto Scheduled | Define Acceptance Criteria for end to end | 3 days | 15-05-11 08:00 | 18-05-11 17:00 | 10 | 3
12 | Yes | Auto Scheduled | Release 2 - Re-Engagement (Initiation) Phase | 66 days | 02-01-12 08:00 | 30-03-12 17:00 |  | 2
13 | Yes | Auto Scheduled | Perform Project Set-Up Activities | 45 days | 02-01-12 08:00 | 02-03-12 17:00 |  | 3
14 | Yes | Auto Scheduled | Establish Project/Accounting Codes in Central Systems | 15 days | 13-02-12 08:00 | 02-03-12 17:00 |  | 4
15 | Yes | Auto Scheduled | Create Project Definition Document | 20 days | 30-01-12 08:00 | 24-02-12 17:00 | 2 | 4
16 | Yes | Auto Scheduled | Create Project Processes & Procedures Document | 5 days | 27-02-12 08:00 | 02-03-12 17:00 | 15 | 4
17 | Yes | Auto Scheduled | Negotiate Development Commitments | 30 days | 02-01-12 08:00 | 10-02-12 17:00 | 16 | 4
18 | Yes | Auto Scheduled | Negotiate Testing Commitments | 10 days | 02-01-12 08:00 | 13-01-12 17:00 | 16 | 4
19 | Yes | Auto Scheduled | Create Project Schedule | 43 days | 02-02-12 08:00 | 30-03-12 17:00 |  | 3
20 | Yes | Auto Scheduled | Create High Level Initial Project Schedule | 5 days | 02-02-12 08:00 | 08-02-12 17:00 | 17,18 | 4
21 | Yes | Auto Scheduled | Perform Internal High-Level Project Schedule Review | 4 days | 16-02-12 08:00 | 21-02-12 17:00 | 20 | 4
22 | Yes | Auto Scheduled | Perform Client High-Level Project Schedule Review | 1 day | 22-02-12 08:00 | 22-02-12 17:00 | 21 | 4
23 | Yes | Auto Scheduled | Confirm Client and Client Subcontractor Commitments | 22 days | 23-02-12 08:00 | 22-03-12 17:00 | 22 | 4
24 | Yes | Auto Scheduled | Finalize Project Schedule | 3 days | 23-03-12 08:00 | 27-03-12 17:00 | 23 | 4
25 | Yes | Auto Scheduled | Perform Internal Detail-Level Project Schedule Review | 2 days | 28-03-12 08:00 | 29-03-12 17:00 | 24 | 4
26 | Yes | Auto Scheduled | Perform Client Detail-Level Project Schedule Review | 1 day | 30-03-12 08:00 | 30-03-12 17:00 | 25 | 4
27 | Yes | Auto Scheduled | Baseline Project Schedule | 0 days | 30-03-12 17:00 | 30-03-12 17:00 | 26 | 4
28 | Yes | Auto Scheduled | Perform Project Kick-Off | 46 days | 23-01-12 08:00 | 23-03-12 17:00 |  | 3
29 | Yes | Auto Scheduled | Plan and Perform Customer Project Kick-Off | 46 days | 23-01-12 08:00 | 23-03-12 17:00 |  | 4
30 | Yes | Auto Scheduled | Plan and Perform Customer Project Kick-Off | 1 day | 23-01-12 08:00 | 23-01-12 17:00 | 11 | 5
31 | Yes | Auto Scheduled | Communicate to Stakeholders | 1 day | 23-01-12 08:00 | 23-01-12 17:00 | 30SS | 5
32 | Yes | Auto Scheduled | Establish Initial Customer Access to Community Portal | 5 days | 19-03-12 08:00 | 23-03-12 17:00 |  | 5
33 | Yes | Auto Scheduled | Create Communication Plan | 1 day | 29-02-12 08:00 | 29-02-12 17:00 |  | 5
34 | Yes | Auto Scheduled | Project Re-Engagement Complete | 0 days | 30-03-12 17:00 | 30-03-12 17:00 | 28,19,13 | 2
35 | Yes | Auto Scheduled | Release 2 - Interactive Pilot Phase | 55 days | 16-01-12 08:00 | 29-03-12 17:00 |  | 2
36 | Yes | Auto Scheduled | Perform Interactive Pilot Assessment | 8 days | 24-01-12 08:00 | 02-02-12 17:00 |  | 3
37 | Yes | Auto Scheduled | Perform Data Collection | 8 days | 24-01-12 08:00 | 02-02-12 17:00 | 29 | 4
38 | Yes | Auto Scheduled | Plan and Perform Interactive Pilot Assessment | 8 days | 24-01-12 08:00 | 02-02-12 17:00 | 30 | 4
39 | Yes | Auto Scheduled | Plan Interactive Pilot Workshops | 5 days | 16-01-12 08:00 | 20-01-12 17:00 |  | 3
40 | Yes | Auto Scheduled | Plan and Schedule Interactive Pilot Workshops | 2 days | 16-01-12 08:00 | 17-01-12 17:00 | 29 | 4
41 | Yes | Auto Scheduled | Prepare Interactive Pilot Workshop Components | 3 days | 18-01-12 08:00 | 20-01-12 17:00 | 40 | 4
42 | Yes | Auto Scheduled | Conduct Initial Training | 4 days | 23-02-12 08:00 | 28-02-12 17:00 |  | 3
43 | Yes | Auto Scheduled | Conduct Initial Training (Key User / Train the Trainer) | 4 days | 23-02-12 08:00 | 28-02-12 17:00 | 22 | 4 | This step was satisifed by process walkthroughs the weeks of 29 Jan and 27 Feb 2012
44 | Yes | Auto Scheduled | Perform Interactive Pilot Workshops | 9 days | 23-01-12 08:00 | 02-02-12 17:00 |  | 3
45 | Yes | Auto Scheduled | Perform Interactive Pilot Workshops | 7 days | 25-01-12 08:00 | 02-02-12 17:00 | 29 | 4
46 | Yes | Auto Scheduled | Finalize Interactive Pilot Workshops | 1 day | 02-02-12 08:00 | 02-02-12 17:00 | 29 | 4
47 | Yes | Auto Scheduled | Interactive Pilot Workshops | 9 days | 23-01-12 08:00 | 02-02-12 17:00 |  | 4
48 | Yes | Auto Scheduled | BRD Review Session | 2 days | 23-01-12 08:00 | 24-01-12 17:00 | 45 | 5
49 | Yes | Auto Scheduled | Scenario based process wak-throughs | 5 days | 25-01-12 08:00 | 31-01-12 17:00 | 48 | 5 | The output of this task was the final BRD versions...
50 | Yes | Auto Scheduled | Risk Register Creation | 1 day | 01-02-12 08:00 | 01-02-12 17:00 | 49 | 5
51 | Yes | Auto Scheduled | Deliverable Definition | 1 day | 02-02-12 08:00 | 02-02-12 17:00 | 50 | 5
52 | Yes | Auto Scheduled | Create IPA Report | 36 days | 06-02-12 08:00 | 23-03-12 17:00 | 47,38,37 | 3
53 | Yes | Auto Scheduled | Present IPA Report | 1 day | 26-03-12 08:00 | 26-03-12 17:00 | 52 | 3
54 | Yes | Auto Scheduled | Joint Review of IPA Report | 2 days | 27-03-12 08:00 | 28-03-12 17:00 | 53 | 3
55 | Yes | Auto Scheduled | Publish Final Version of IPA Report | 1 day | 29-03-12 08:00 | 29-03-12 17:00 | 54 | 3
56 | Yes | Auto Scheduled | Consulting Activites | 43 days | 01-02-12 08:00 | 29-03-12 17:00 |  | 3
57 | Yes | Auto Scheduled | On-site Interviews with Pricing Analyst | 1 day | 01-02-12 08:00 | 01-02-12 17:00 | 46 | 4
58 | Yes | Auto Scheduled | Create Organization, Functional and Policy & Procedures recommendations based on Network Module | 34 days | 09-02-12 08:00 | 26-03-12 17:00 | 57,47,37 | 4
59 | Yes | Auto Scheduled | Reivew Recommendations with Etihad Cargo | 2 days | 27-03-12 08:00 | 28-03-12 17:00 | 58 | 4
60 | Yes | Auto Scheduled | Pulbish Final Recommendations | 1 day | 29-03-12 08:00 | 29-03-12 17:00 | 59 | 4
61 | Yes | Auto Scheduled | Create KPI's for Network Module | 37 days | 03-02-12 08:00 | 23-03-12 17:00 | 57,47,37 | 4
62 | Yes | Auto Scheduled | Review and Finalize KPI's for Network Module | 3 days | 26-03-12 08:00 | 28-03-12 17:00 | 61 | 4
63 | Yes | Auto Scheduled | Determine Make-up of Standard Performance Reports | 5 days | 19-03-12 08:00 | 23-03-12 17:00 | 61FF | 4
64 | Yes | Auto Scheduled | Review KPI's and Standard Performance Reports with EY | 2 days | 26-03-12 08:00 | 27-03-12 17:00 | 63 | 4
65 | Yes | Auto Scheduled | Perform the Interactive Pilot End-of-Phase Review | 1 day | 28-03-12 08:00 | 28-03-12 17:00 | 64 | 3
66 | Yes | Auto Scheduled | Release 2 - Interactive Pilot Phase Complete | 0 days | 28-03-12 17:00 | 28-03-12 17:00 | 65 | 2
67 | Yes | Auto Scheduled | Release 2 - Solution Adoption Phase | 292 days | 24-01-12 08:00 | 25-03-13 17:00 |  | 2
68 | Yes | Auto Scheduled | Support Solution Definition and Design | 27 days | 24-01-12 08:00 | 29-02-12 17:00 |  | 3
69 | Yes | Auto Scheduled | Support Detailed Solution Definition | 1 day | 29-02-12 08:00 | 29-02-12 17:00 | 47,2 | 4 | Final Solution Definition was created during the IPA Workshops Task 71...
70 | Yes | Auto Scheduled | Support Detailed Solution Design | 3 days | 24-01-12 08:00 | 26-01-12 17:00 |  | 4
71 | Yes | Auto Scheduled | Determine New GUI Screen Field Details | 2 days | 24-01-12 08:00 | 25-01-12 17:00 | 46 | 5
72 | Yes | Auto Scheduled | Signoff from customer on GUI Fields | 1 day | 26-01-12 08:00 | 26-01-12 17:00 | 71 | 5
73 | Yes | Auto Scheduled | Support Solution Build-Out | 265 days | 01-03-12 08:00 | 25-03-13 17:00 |  | 3
74 | Yes | Auto Scheduled | Support Iteration Planning | 265 days | 01-03-12 08:00 | 25-03-13 17:00 |  | 4
75 | Yes | Auto Scheduled | Support Iteration Planning 1 | 1 day | 01-03-12 08:00 | 01-03-12 17:00 |  | 5
76 | Yes | Auto Scheduled | Support Iteration Planning 2 | 1 day | 15-03-12 08:00 | 15-03-12 17:00 | 75FS+10d | 5
77 | Yes | Auto Scheduled | Support Iteration Planning 3 | 1 day | 30-03-12 08:00 | 30-03-12 17:00 | 76FS+10d | 5
78 | Yes | Auto Scheduled | Support Iteration Planning 4 | 1 day | 16-04-12 08:00 | 16-04-12 17:00 | 77FS+10d | 5
79 | Yes | Auto Scheduled | Support Iteration Planning 5 | 1 day | 01-05-12 08:00 | 01-05-12 17:00 | 78FS+10d | 5
80 | Yes | Auto Scheduled | Support Iteration Planning 6 | 1 day | 16-05-12 08:00 | 16-05-12 17:00 | 79FS+10d | 5
81 | Yes | Auto Scheduled | Support Iteration Planning 7 | 1 day | 31-05-12 08:00 | 31-05-12 17:00 | 80FS+10d | 5
82 | Yes | Auto Scheduled | Support Iteration Planning 8 | 1 day | 15-06-12 08:00 | 15-06-12 17:00 | 81FS+10d | 5
83 | Yes | Auto Scheduled | Support Iteration Planning 9 | 1 day | 02-07-12 08:00 | 02-07-12 17:00 | 82FS+10d | 5
84 | Yes | Auto Scheduled | Support Iteration Planning 10 | 1 day | 17-07-12 08:00 | 17-07-12 17:00 | 83FS+10d | 5
85 | Yes | Auto Scheduled | Support Iteration Planning 11 | 1 day | 01-08-12 08:00 | 01-08-12 17:00 | 84FS+10d | 5
86 | Yes | Auto Scheduled | Support Iteration Planning 12 | 1 day | 16-08-12 08:00 | 16-08-12 17:00 | 85FS+10d | 5
87 | Yes | Auto Scheduled | Support Iteration Planning 13 | 1 day | 31-08-12 08:00 | 31-08-12 17:00 | 86FS+10d | 5
88 | Yes | Auto Scheduled | Support Iteration Planning 14 | 1 day | 17-09-12 08:00 | 17-09-12 17:00 | 87FS+10d | 5
89 | Yes | Auto Scheduled | Support Iteration Planning 15 | 1 day | 02-10-12 08:00 | 02-10-12 17:00 | 88FS+10d | 5
90 | Yes | Auto Scheduled | Support Iteration Planning 16 | 1 day | 17-10-12 08:00 | 17-10-12 17:00 | 89FS+10d | 5
91 | Yes | Auto Scheduled | Support Iteration Planning 17 | 1 day | 01-11-12 08:00 | 01-11-12 17:00 | 90FS+10d | 5
92 | Yes | Auto Scheduled | Support Iteration Planning 18 | 1 day | 16-11-12 08:00 | 16-11-12 17:00 | 91FS+10d | 5
93 | Yes | Auto Scheduled | Support Iteration Planning 19 | 1 day | 07-12-12 08:00 | 07-12-12 17:00 | 92FS+10d | 5
94 | Yes | Auto Scheduled | Support Iteration Planning 20 | 1 day | 07-01-13 08:00 | 07-01-13 17:00 | 93FS+10d | 5
95 | Yes | Auto Scheduled | Support Iteration Planning 21 | 1 day | 22-01-13 08:00 | 22-01-13 17:00 | 94FS+10d | 5
96 | Yes | Auto Scheduled | Support Iteration Planning 22 | 1 day | 06-02-13 08:00 | 06-02-13 17:00 | 95FS+10d | 5
97 | Yes | Auto Scheduled | Support Iteration Planning 23 | 1 day | 21-02-13 08:00 | 21-02-13 17:00 | 96FS+10d | 5
98 | Yes | Auto Scheduled | Support Iteration Planning 24 | 1 day | 08-03-13 08:00 | 08-03-13 17:00 | 97FS+10d | 5
99 | Yes | Auto Scheduled | Support Iteration Planning 25 | 1 day | 25-03-13 08:00 | 25-03-13 17:00 | 98FS+10d | 5
100 | Yes | Auto Scheduled | Support Iteration and Release Planning | 0 days | 01-03-12 08:00 | 01-03-12 08:00 | 47 | 4
101 | Yes | Auto Scheduled | Support Iteration Development / Testing | 0 days | 01-03-12 08:00 | 01-03-12 08:00 | 100 | 4
102 | Yes | Auto Scheduled | Air Vision Cargo Network Module Development Work | 242 days | 01-03-12 08:00 | 20-02-13 17:00 |  | 4
103 | Yes | Auto Scheduled | GUI Design and Cost Module Changes pt I | 50 days | 01-03-12 08:00 | 08-05-12 17:00 |  | 5
104 | Yes | Auto Scheduled | Design GUI Screens | 34 days | 01-03-12 08:00 | 16-04-12 17:00 |  | 6
105 | Yes | Auto Scheduled | Cost Module Changes pt I | 14 days | 12-03-12 08:00 | 29-03-12 17:00 |  | 6
106 | Yes | Auto Scheduled | Booking evaluation changes | 9 days | 30-03-12 08:00 | 11-04-12 17:00 | 105 | 6
107 | Yes | Auto Scheduled | Request build and internal testing | 14 days | 12-04-12 08:00 | 01-05-12 17:00 | 106 | 6
108 | Yes | Auto Scheduled | Workshop to demo new screens | 1 day | 02-05-12 08:00 | 02-05-12 17:00 | 107,104 | 6
109 | Yes | Auto Scheduled | New Screen Demonstration to Etihad | 0 days | 02-05-12 08:00 | 02-05-12 08:00 | 108SS | 6
110 | Yes | Auto Scheduled | Give: Etihad Screen Shot and Cost Module Screen Demos screenshots | 0 days | 02-05-12 08:00 | 02-05-12 08:00 | 109 | 6
111 | Yes | Auto Scheduled | Get: Etihad sign off on screen design | 0 days | 08-05-12 17:00 | 08-05-12 17:00 | 110FS+5d | 6
112 | Yes | Auto Scheduled | Cost Module Changes pt II | 45 days | 12-04-12 08:00 | 13-06-12 17:00 |  | 5
113 | Yes | Auto Scheduled | Cost Module Changes pt II | 12 days | 12-04-12 08:00 | 27-04-12 17:00 | 106 | 6
114 | Yes | Auto Scheduled | Booking Evaluation changes | 14 days | 30-04-12 08:00 | 17-05-12 17:00 | 113 | 6
115 | Yes | Auto Scheduled | Request Build and internal testing | 14 days | 18-05-12 08:00 | 06-06-12 17:00 | 114 | 6
116 | Yes | Auto Scheduled | Workshop to demo Cost Module changes | 1 day | 07-06-12 08:00 | 07-06-12 17:00 | 115 | 6
117 | Yes | Auto Scheduled | Cost Module Demonstration | 0 days | 07-06-12 08:00 | 07-06-12 08:00 | 116SS | 6
118 | Yes | Auto Scheduled | Give: Etihad Cost Module Screen Changes pt II screen shots | 0 days | 07-06-12 08:00 | 07-06-12 08:00 | 117 | 6
119 | Yes | Auto Scheduled | Get: Etihad sign off on cost module screen designs and calcuatlations | 0 days | 13-06-12 17:00 | 13-06-12 17:00 | 118FS+5d | 6
120 | Yes | Auto Scheduled | Network Module Booking Evaluation & Cost Module pt III | 93 days | 18-05-12 08:00 | 25-09-12 17:00 |  | 5
121 | Yes | Auto Scheduled | Cost Module changes pt III | 12 days | 18-05-12 08:00 | 04-06-12 17:00 | 114 | 6
122 | Yes | Auto Scheduled | Modify internal booking evaluation processes | 8 days | 05-06-12 08:00 | 14-06-12 17:00 | 121 | 6
123 | Yes | Auto Scheduled | Modifed Bid Price Find Screen | 16 days | 15-06-12 08:00 | 06-07-12 17:00 | 122 | 6
124 | Yes | Auto Scheduled | Request build and internal testing | 16 days | 09-07-12 08:00 | 30-07-12 17:00 | 123 | 6
125 | Yes | Auto Scheduled | Workshop to demo Booking evaluation changes | 1 day | 31-07-12 08:00 | 31-07-12 17:00 | 124 | 6
126 | Yes | Auto Scheduled | Booking Evaluatoin Demonstration | 0 days | 31-07-12 08:00 | 31-07-12 08:00 | 125SS | 6
127 | Yes | Auto Scheduled | Give: Etihad recording of Booking Evaluation changes demon for signoff | 0 days | 31-07-12 08:00 | 31-07-12 08:00 | 126 | 6
128 | Yes | Auto Scheduled | Get: Etihad signoff on booking evaluation process changes | 0 days | 08-08-12 17:00 | 08-08-12 17:00 | 127FS+7d | 6
129 | Yes | Auto Scheduled | Cost Module and Network Module GUI | 47 days | 09-07-12 08:00 | 11-09-12 17:00 |  | 6
130 | Yes | Auto Scheduled | Cost Module pt IV | 23 days | 09-07-12 08:00 | 08-08-12 17:00 | 123 | 7
131 | Yes | Auto Scheduled | Network Module GUI | 10 days | 09-08-12 08:00 | 22-08-12 17:00 | 130 | 7
132 | Yes | Auto Scheduled | Request build and internal testing | 14 days | 23-08-12 08:00 | 11-09-12 17:00 | 131 | 7
133 | Yes | Auto Scheduled | Workshop to demo Cost Module and GUI changes | 1 day | 12-09-12 08:00 | 12-09-12 17:00 | 132 | 6
134 | Yes | Auto Scheduled | Cost Module Demonstration | 0 days | 12-09-12 08:00 | 12-09-12 08:00 | 133SS | 6
135 | Yes | Auto Scheduled | Give: Etihad Cost and GUI Screen Changes | 0 days | 12-09-12 08:00 | 12-09-12 08:00 | 134 | 6
136 | Yes | Auto Scheduled | Get: Etihad signoff on cost module and NM GUI changes | 0 days | 25-09-12 17:00 | 25-09-12 17:00 | 134FS+10d | 6
137 | Yes | Auto Scheduled | Network Module Interfaces and Technology Changes | 33 days | 23-08-12 08:00 | 08-10-12 17:00 |  | 5
138 | Yes | Auto Scheduled | Create Booking Evaluation Interfaces | 19 days | 23-08-12 08:00 | 18-09-12 17:00 | 131 | 6
139 | Yes | Auto Scheduled | Get: Sample "Booking Evaluation Call" and "Request for Additional Call" messages from CHAMP | 0 days | 18-09-12 17:00 | 18-09-12 17:00 | 138 | 6 | This is required to perform unit testing of the incoming messages before a build is requested. Manually pushing the sample messages through the system will ensure the messages can be consumed correctly prior to GTE testing
140 | Yes | Auto Scheduled | Test sample messages received from CHAMP | 2 days | 19-09-12 08:00 | 20-09-12 17:00 | 139 | 6
141 | Yes | Auto Scheduled | Air Vision Cargo Technology changes (does not include Oracle changes) | 4 days | 21-09-12 08:00 | 26-09-12 17:00 | 140 | 6
142 | Yes | Auto Scheduled | Final build and fixes prior to GTE | 8 days | 27-09-12 08:00 | 08-10-12 17:00 | 141 | 6
143 | Yes | Auto Scheduled | Code Complete | 0 days | 08-10-12 17:00 | 08-10-12 17:00 | 103,112,120,137 | 5
144 | Yes | Auto Scheduled | Internal Testing by GTE team | 30 days | 09-10-12 08:00 | 19-11-12 17:00 |  | 5
145 | Yes | Auto Scheduled | Pass 1 | 10 days | 09-10-12 08:00 | 22-10-12 17:00 | 143 | 6 | Pass 1 includes 3 days for initial code check in and build request...
146 | Yes | Auto Scheduled | Pass 2 | 10 days | 23-10-12 08:00 | 05-11-12 17:00 | 145 | 6 | A more robust until test will be performed using sample messages from CHAMP in the Dev environment. Full integration testing will take place during UVT...
147 | Yes | Auto Scheduled | Pass 3 | 10 days | 06-11-12 08:00 | 19-11-12 17:00 | 146 | 6
148 | Yes | Auto Scheduled | Network Module Development and GTE Testing Complete | 0 days | 19-11-12 17:00 | 19-11-12 17:00 | 144 | 5
149 | Yes | Auto Scheduled | Split shipment BRID | 53 days | 20-11-12 08:00 | 20-02-13 17:00 |  | 5
150 | Yes | Auto Scheduled | Split shipment handling coding | 22 days | 20-11-12 08:00 | 08-01-13 17:00 | 147 | 6
151 | Yes | Auto Scheduled | Request build and internal testing | 1 day | 09-01-13 08:00 | 09-01-13 17:00 | 150 | 6
152 | Yes | Auto Scheduled | GTE Pass 1 | 10 days | 10-01-13 08:00 | 23-01-13 17:00 | 151 | 6
153 | Yes | Auto Scheduled | GTE Pass 2 | 10 days | 24-01-13 08:00 | 06-02-13 17:00 | 152 | 6
154 | Yes | Auto Scheduled | GTE Pass 3 | 10 days | 07-02-13 08:00 | 20-02-13 17:00 | 153 | 6
155 | Yes | Auto Scheduled | Split shipment handling coding complete | 0 days | 20-02-13 17:00 | 20-02-13 17:00 | 154 | 5
156 | Yes | Auto Scheduled | Support On_site Customer Collaboration | 0 days | 19-11-12 17:00 | 19-11-12 17:00 | 144 | 4
157 | Yes | Auto Scheduled | Support Business Process Improvements | 0 days | 19-11-12 17:00 | 19-11-12 17:00 | 56,156 | 4
158 | Yes | Auto Scheduled | Support Solution Validation and Installation | 5 days | 20-11-12 08:00 | 02-12-12 17:00 |  | 3
159 | Yes | Auto Scheduled | Plan and Perform the Installation (For Each Environment As Needed: Training, Validation, etc.) | 5 days | 20-11-12 08:00 | 02-12-12 17:00 | 148 | 4
160 | Yes | Auto Scheduled | System deployed and available for local training | 0 days | 02-12-12 17:00 | 02-12-12 17:00 | 159 | 3
161 | Yes | Auto Scheduled | Consulting Activities | 30 days | 19-11-12 17:00 | 18-01-13 17:00 |  | 3
162 | Yes | Auto Scheduled | Implement agreed recommended processess and practices | 0 days | 19-11-12 17:00 | 19-11-12 17:00 | 157 | 4 | This task does not make logical sense to implement prior to user training and system rollout. This will be performed during the consulting activities in the Project Transition Phase (Task 168)...
163 | Yes | Auto Scheduled | Implementation of Organization structures related to Network Module | 30 days | 20-11-12 08:00 | 18-01-13 17:00 | 56,148 | 4
164 | Yes | Auto Scheduled | Business Training on how KPI's and Standard Performance Reports will be used | 2 days | 20-11-12 08:00 | 21-11-12 17:00 | 56,156,157 | 4
165 | Yes | Auto Scheduled | Perform the Solution Adoption End-of-Phase Review | 1 day | 04-12-12 08:00 | 04-12-12 17:00 | 158FS+1d,148,157,156 | 3
166 | Yes | Auto Scheduled | Release 2 - Solution Adoption Phase Complete | 0 days | 04-12-12 17:00 | 04-12-12 17:00 | 165 | 3
167 | Yes | Auto Scheduled | Release 2 - Project Transition Phase | 201 days | 11-09-12 08:00 | 08-07-13 17:00 |  | 2
168 | Yes | Auto Scheduled | Perform Customer Validation and Training | 201 days | 11-09-12 08:00 | 08-07-13 17:00 |  | 3
169 | Yes | Auto Scheduled | Support Customer Validation | 10 days | 03-12-12 08:00 | 14-12-12 17:00 | 158 | 4
170 | Yes | Auto Scheduled | Build Deployment and Soak (End to End) Testing | 131 days | 11-09-12 08:00 | 01-04-13 17:00 |  | 4
171 | Yes | Auto Scheduled | Calibration Exercise | 30 days | 11-09-12 08:00 | 22-10-12 17:00 | 145FS-30d | 5
172 | Yes | Auto Scheduled | Load Calibration and Cost data in EY Test build | 2 days | 20-11-12 08:00 | 21-11-12 17:00 | 171,159SS | 5 | This task will be carried out in conjunction with Task 145 Plan and Perform Deployment
173 | Yes | Auto Scheduled | GET: CHAMP has deployed build into EY Test Environment | 0 days | 21-11-12 17:00 | 21-11-12 17:00 | 159SS+2d | 5 | The CHAMP system is required to be deployed no later than 11/23/12 to ensure training and testnig can proceed. During the installation phase connectivity will be tested between the systems but actual interface testing will be covered as part of UVT...
174 | Yes | Auto Scheduled | Train the Trainer classroom training for testers | 5 days | 22-11-12 08:00 | 04-12-12 17:00 | 173,172 | 5
175 | Yes | Auto Scheduled | Customer UVT | 74 days | 05-12-12 08:00 | 01-04-13 17:00 |  | 5
176 | Yes | Auto Scheduled | UVT Base System Begin | 0 days | 05-12-12 08:00 | 05-12-12 08:00 | 177SS | 6
177 | Yes | Auto Scheduled | Air Vision Cargo Interface Integration Testing with Cargospot | 10 days | 05-12-12 08:00 | 18-12-12 17:00 | 159,172,173,174 | 6
178 | Yes | Auto Scheduled | Soak Test - Parallel run (Test and Prod) | 36 days | 19-12-12 08:00 | 20-02-13 17:00 | 177 | 6
179 | Yes | Auto Scheduled | Split Shipment Handling Code deployment | 28 days | 21-02-13 08:00 | 01-04-13 17:00 | 178 | 6
180 | Yes | Auto Scheduled | Plan and Perform Split Shipment Handling code deployment | 5 days | 21-02-13 08:00 | 27-02-13 17:00 | 155 | 7
181 | Yes | Auto Scheduled | Validate build successfully deployed | 1 day | 28-02-13 08:00 | 28-02-13 17:00 | 180 | 7
182 | Yes | Auto Scheduled | Train the trainer classroom training for testers | 2 days | 01-03-13 08:00 | 04-03-13 17:00 | 181 | 7
183 | Yes | Auto Scheduled | Soak Test - Parallel run (Test and Prod) | 20 days | 05-03-13 08:00 | 01-04-13 17:00 | 182 | 7
184 | Yes | Auto Scheduled | UVT Base System End | 0 days | 01-04-13 17:00 | 01-04-13 17:00 | 177,183 | 6
185 | Yes | Auto Scheduled | Go/No Go for Production Deployment | 0 days | 01-04-13 17:00 | 01-04-13 17:00 | 184 | 5
186 | Yes | Auto Scheduled | Perform End-User Training | 5 days | 19-03-13 08:00 | 25-03-13 17:00 | 184FS-10d | 4
187 | Yes | Auto Scheduled | Consulting Activities | 75 days | 26-03-13 08:00 | 08-07-13 17:00 |  | 4
188 | Yes | Auto Scheduled | Implement KPI monitoring and utliziation of Standard Performance Reports | 10 days | 26-03-13 08:00 | 08-04-13 17:00 | 186 | 5
189 | Yes | Auto Scheduled | Begin Performance Monitoring | 0 days | 20-05-13 17:00 | 20-05-13 17:00 | 188FS+30d | 5
190 | Yes | Auto Scheduled | Implement agree recommended processes and practices | 10 days | 26-03-13 08:00 | 08-04-13 17:00 | 186 | 5 | This is when task 146 Consulting Activities will actually be performed and not as listed in the WO...
191 | Yes | Auto Scheduled | End Performance Monitoring | 0 days | 01-07-13 17:00 | 01-07-13 17:00 | 189FS+30d | 5 | The will be a recurring activity. Only the first instance is covered in this project schedule
192 | Yes | Auto Scheduled | Present Performance Monitoring Results to Etihad | 5 days | 02-07-13 08:00 | 08-07-13 17:00 | 191 | 5
193 | Yes | Auto Scheduled | Perform Production Cutover and Support | 46 days | 12-03-13 08:00 | 14-05-13 17:00 |  | 3
194 | Yes | Auto Scheduled | Plan Production Cutover | 15 days | 12-03-13 08:00 | 01-04-13 17:00 | 184FS-15d | 4
195 | Yes | Auto Scheduled | Perform Production Cutover | 1 day | 02-04-13 08:00 | 02-04-13 17:00 | 194,185 | 4
196 | Yes | Auto Scheduled | Cutover to Production | 0 days | 02-04-13 17:00 | 02-04-13 17:00 | 195 | 4
197 | Yes | Auto Scheduled | Perform Post-Cutover Customer Support | 30 days | 03-04-13 08:00 | 14-05-13 17:00 | 196 | 4
198 | Yes | Auto Scheduled | Transition to Customer Care | 6 days | 02-04-13 08:00 | 09-04-13 17:00 |  | 3
199 | Yes | Auto Scheduled | Plan Customer Care Transition | 5 days | 02-04-13 08:00 | 08-04-13 17:00 | 194 | 4
200 | Yes | Auto Scheduled | Perform Customer Care Transition | 1 day | 09-04-13 08:00 | 09-04-13 17:00 | 199 | 4
201 | Yes | Auto Scheduled | Perform Project Close-Out and Review | 5 days | 15-05-13 08:00 | 21-05-13 17:00 |  | 3
202 | Yes | Auto Scheduled | Perform Project Close-Out | 3 days | 15-05-13 08:00 | 17-05-13 17:00 | 196,197,200 | 4
203 | Yes | Auto Scheduled | Perform Post-Project Review | 2 days | 20-05-13 08:00 | 21-05-13 17:00 | 202 | 4
204 | Yes | Auto Scheduled | Release 2 - Project Transition Phase Complete | 0 days | 21-05-13 17:00 | 21-05-13 17:00 | 202,203 | 3
205 | Yes | Auto Scheduled | Project Management | 341 days? | 12-01-12 08:00 | 21-05-13 17:00 |  | 1
206 | Yes | Auto Scheduled | Project Planning | 5 days | 12-01-12 08:00 | 18-01-12 17:00 |  | 2 | Components defined as part of this PM Phase are as defined in the contract.
207 | Yes | Auto Scheduled | Project Execution and Control | 305 days? | 23-01-12 08:00 | 10-04-13 17:00 |  | 2
208 | Yes | Auto Scheduled | Manage Project Scope | 1 day? | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
209 | Yes | Auto Scheduled | Manage Project Schedule | 1 day? | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
210 | Yes | Auto Scheduled | Manage Project Issues | 1 day? | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
211 | Yes | Auto Scheduled | Manage Project Risks | 1 day? | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
212 | Yes | Auto Scheduled | Manage Project Quality | 1 day? | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
213 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks | 278 days | 29-02-12 08:00 | 10-04-13 17:00 |  | 3
214 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 1 | 1 day | 29-02-12 08:00 | 29-02-12 17:00 |  | 4
215 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 2 | 1 day | 07-03-12 08:00 | 07-03-12 17:00 |  | 4
216 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 3 | 1 day | 14-03-12 08:00 | 14-03-12 17:00 |  | 4
217 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 4 | 1 day | 21-03-12 08:00 | 21-03-12 17:00 |  | 4
218 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 5 | 1 day | 28-03-12 08:00 | 28-03-12 17:00 |  | 4
219 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 6 | 1 day | 04-04-12 08:00 | 04-04-12 17:00 |  | 4
220 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 7 | 1 day | 11-04-12 08:00 | 11-04-12 17:00 |  | 4
221 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 8 | 1 day | 18-04-12 08:00 | 18-04-12 17:00 |  | 4
222 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 9 | 1 day | 25-04-12 08:00 | 25-04-12 17:00 |  | 4
223 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 10 | 1 day | 02-05-12 08:00 | 02-05-12 17:00 |  | 4
224 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 11 | 1 day | 09-05-12 08:00 | 09-05-12 17:00 |  | 4
225 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 12 | 1 day | 16-05-12 08:00 | 16-05-12 17:00 |  | 4
226 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 13 | 1 day | 23-05-12 08:00 | 23-05-12 17:00 |  | 4
227 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 14 | 1 day | 30-05-12 08:00 | 30-05-12 17:00 |  | 4
228 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 15 | 1 day | 06-06-12 08:00 | 06-06-12 17:00 |  | 4
229 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 16 | 1 day | 13-06-12 08:00 | 13-06-12 17:00 |  | 4
230 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 17 | 1 day | 20-06-12 08:00 | 20-06-12 17:00 |  | 4
231 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 18 | 1 day | 27-06-12 08:00 | 27-06-12 17:00 |  | 4
232 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 19 | 1 day | 04-07-12 08:00 | 04-07-12 17:00 |  | 4
233 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 20 | 1 day | 11-07-12 08:00 | 11-07-12 17:00 |  | 4
234 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 21 | 1 day | 18-07-12 08:00 | 18-07-12 17:00 |  | 4
235 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 22 | 1 day | 25-07-12 08:00 | 25-07-12 17:00 |  | 4
236 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 23 | 1 day | 01-08-12 08:00 | 01-08-12 17:00 |  | 4
237 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 24 | 1 day | 08-08-12 08:00 | 08-08-12 17:00 |  | 4
238 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 25 | 1 day | 15-08-12 08:00 | 15-08-12 17:00 |  | 4
239 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 26 | 1 day | 22-08-12 08:00 | 22-08-12 17:00 |  | 4
240 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 27 | 1 day | 29-08-12 08:00 | 29-08-12 17:00 |  | 4
241 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 28 | 1 day | 05-09-12 08:00 | 05-09-12 17:00 |  | 4
242 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 29 | 1 day | 12-09-12 08:00 | 12-09-12 17:00 |  | 4
243 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 30 | 1 day | 19-09-12 08:00 | 19-09-12 17:00 |  | 4
244 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 31 | 1 day | 26-09-12 08:00 | 26-09-12 17:00 |  | 4
245 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 32 | 1 day | 03-10-12 08:00 | 03-10-12 17:00 |  | 4
246 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 33 | 1 day | 10-10-12 08:00 | 10-10-12 17:00 |  | 4
247 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 34 | 1 day | 17-10-12 08:00 | 17-10-12 17:00 |  | 4
248 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 35 | 1 day | 24-10-12 08:00 | 24-10-12 17:00 |  | 4
249 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 36 | 1 day | 31-10-12 08:00 | 31-10-12 17:00 |  | 4
250 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 37 | 1 day | 07-11-12 08:00 | 07-11-12 17:00 |  | 4
251 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 38 | 1 day | 14-11-12 08:00 | 14-11-12 17:00 |  | 4
252 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 39 | 1 day | 21-11-12 08:00 | 21-11-12 17:00 |  | 4
253 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 40 | 1 day | 05-12-12 08:00 | 05-12-12 17:00 |  | 4
254 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 41 | 1 day | 12-12-12 08:00 | 12-12-12 17:00 |  | 4
255 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 42 | 1 day | 19-12-12 08:00 | 19-12-12 17:00 |  | 4
256 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 43 | 1 day | 09-01-13 08:00 | 09-01-13 17:00 |  | 4
257 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 44 | 1 day | 16-01-13 08:00 | 16-01-13 17:00 |  | 4
258 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 45 | 1 day | 23-01-13 08:00 | 23-01-13 17:00 |  | 4
259 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 46 | 1 day | 30-01-13 08:00 | 30-01-13 17:00 |  | 4
260 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 47 | 1 day | 06-02-13 08:00 | 06-02-13 17:00 |  | 4
261 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 48 | 1 day | 13-02-13 08:00 | 13-02-13 17:00 |  | 4
262 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 49 | 1 day | 20-02-13 08:00 | 20-02-13 17:00 |  | 4
263 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 50 | 1 day | 27-02-13 08:00 | 27-02-13 17:00 |  | 4
264 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 51 | 1 day | 06-03-13 08:00 | 06-03-13 17:00 |  | 4
265 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 52 | 1 day | 13-03-13 08:00 | 13-03-13 17:00 |  | 4
266 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 53 | 1 day | 20-03-13 08:00 | 20-03-13 17:00 |  | 4
267 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 54 | 1 day | 27-03-13 08:00 | 27-03-13 17:00 |  | 4
268 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 55 | 1 day | 03-04-13 08:00 | 03-04-13 17:00 |  | 4
269 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 56 | 1 day | 10-04-13 08:00 | 10-04-13 17:00 |  | 4
270 | Yes | Auto Scheduled | Manage Delivery as an Integrated Portfolio | 1 day | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
271 | Yes | Auto Scheduled | Manage Project Budget And Invoicing | 1 day | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
272 | Yes | Auto Scheduled | Perform Project Metrics Tracking | 1 day | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
273 | Yes | Auto Scheduled | Perform Project Status Reporting | 278 days | 29-02-12 08:00 | 10-04-13 17:00 |  | 3
274 | Yes | Auto Scheduled | Perform Project Status Reporting 1 | 1 day | 29-02-12 08:00 | 29-02-12 17:00 |  | 4
275 | Yes | Auto Scheduled | Perform Project Status Reporting 2 | 1 day | 07-03-12 08:00 | 07-03-12 17:00 |  | 4
276 | Yes | Auto Scheduled | Perform Project Status Reporting 3 | 1 day | 14-03-12 08:00 | 14-03-12 17:00 |  | 4
277 | Yes | Auto Scheduled | Perform Project Status Reporting 4 | 1 day | 21-03-12 08:00 | 21-03-12 17:00 |  | 4
278 | Yes | Auto Scheduled | Perform Project Status Reporting 5 | 1 day | 28-03-12 08:00 | 28-03-12 17:00 |  | 4
279 | Yes | Auto Scheduled | Perform Project Status Reporting 6 | 1 day | 04-04-12 08:00 | 04-04-12 17:00 |  | 4
280 | Yes | Auto Scheduled | Perform Project Status Reporting 7 | 1 day | 11-04-12 08:00 | 11-04-12 17:00 |  | 4
281 | Yes | Auto Scheduled | Perform Project Status Reporting 8 | 1 day | 18-04-12 08:00 | 18-04-12 17:00 |  | 4
282 | Yes | Auto Scheduled | Perform Project Status Reporting 9 | 1 day | 25-04-12 08:00 | 25-04-12 17:00 |  | 4
283 | Yes | Auto Scheduled | Perform Project Status Reporting 10 | 1 day | 02-05-12 08:00 | 02-05-12 17:00 |  | 4
284 | Yes | Auto Scheduled | Perform Project Status Reporting 11 | 1 day | 09-05-12 08:00 | 09-05-12 17:00 |  | 4
285 | Yes | Auto Scheduled | Perform Project Status Reporting 12 | 1 day | 16-05-12 08:00 | 16-05-12 17:00 |  | 4
286 | Yes | Auto Scheduled | Perform Project Status Reporting 13 | 1 day | 23-05-12 08:00 | 23-05-12 17:00 |  | 4
287 | Yes | Auto Scheduled | Perform Project Status Reporting 14 | 1 day | 30-05-12 08:00 | 30-05-12 17:00 |  | 4
288 | Yes | Auto Scheduled | Perform Project Status Reporting 15 | 1 day | 06-06-12 08:00 | 06-06-12 17:00 |  | 4
289 | Yes | Auto Scheduled | Perform Project Status Reporting 16 | 1 day | 13-06-12 08:00 | 13-06-12 17:00 |  | 4
290 | Yes | Auto Scheduled | Perform Project Status Reporting 17 | 1 day | 20-06-12 08:00 | 20-06-12 17:00 |  | 4
291 | Yes | Auto Scheduled | Perform Project Status Reporting 18 | 1 day | 27-06-12 08:00 | 27-06-12 17:00 |  | 4
292 | Yes | Auto Scheduled | Perform Project Status Reporting 19 | 1 day | 04-07-12 08:00 | 04-07-12 17:00 |  | 4
293 | Yes | Auto Scheduled | Perform Project Status Reporting 20 | 1 day | 11-07-12 08:00 | 11-07-12 17:00 |  | 4
294 | Yes | Auto Scheduled | Perform Project Status Reporting 21 | 1 day | 18-07-12 08:00 | 18-07-12 17:00 |  | 4
295 | Yes | Auto Scheduled | Perform Project Status Reporting 22 | 1 day | 25-07-12 08:00 | 25-07-12 17:00 |  | 4
296 | Yes | Auto Scheduled | Perform Project Status Reporting 23 | 1 day | 01-08-12 08:00 | 01-08-12 17:00 |  | 4
297 | Yes | Auto Scheduled | Perform Project Status Reporting 24 | 1 day | 08-08-12 08:00 | 08-08-12 17:00 |  | 4
298 | Yes | Auto Scheduled | Perform Project Status Reporting 25 | 1 day | 15-08-12 08:00 | 15-08-12 17:00 |  | 4
299 | Yes | Auto Scheduled | Perform Project Status Reporting 26 | 1 day | 22-08-12 08:00 | 22-08-12 17:00 |  | 4
300 | Yes | Auto Scheduled | Perform Project Status Reporting 27 | 1 day | 29-08-12 08:00 | 29-08-12 17:00 |  | 4
301 | Yes | Auto Scheduled | Perform Project Status Reporting 28 | 1 day | 05-09-12 08:00 | 05-09-12 17:00 |  | 4
302 | Yes | Auto Scheduled | Perform Project Status Reporting 29 | 1 day | 12-09-12 08:00 | 12-09-12 17:00 |  | 4
303 | Yes | Auto Scheduled | Perform Project Status Reporting 30 | 1 day | 19-09-12 08:00 | 19-09-12 17:00 |  | 4
304 | Yes | Auto Scheduled | Perform Project Status Reporting 31 | 1 day | 26-09-12 08:00 | 26-09-12 17:00 |  | 4
305 | Yes | Auto Scheduled | Perform Project Status Reporting 32 | 1 day | 03-10-12 08:00 | 03-10-12 17:00 |  | 4
306 | Yes | Auto Scheduled | Perform Project Status Reporting 33 | 1 day | 10-10-12 08:00 | 10-10-12 17:00 |  | 4
307 | Yes | Auto Scheduled | Perform Project Status Reporting 34 | 1 day | 17-10-12 08:00 | 17-10-12 17:00 |  | 4
308 | Yes | Auto Scheduled | Perform Project Status Reporting 35 | 1 day | 24-10-12 08:00 | 24-10-12 17:00 |  | 4
309 | Yes | Auto Scheduled | Perform Project Status Reporting 36 | 1 day | 31-10-12 08:00 | 31-10-12 17:00 |  | 4
310 | Yes | Auto Scheduled | Perform Project Status Reporting 37 | 1 day | 07-11-12 08:00 | 07-11-12 17:00 |  | 4
311 | Yes | Auto Scheduled | Perform Project Status Reporting 38 | 1 day | 14-11-12 08:00 | 14-11-12 17:00 |  | 4
312 | Yes | Auto Scheduled | Perform Project Status Reporting 39 | 1 day | 21-11-12 08:00 | 21-11-12 17:00 |  | 4
313 | Yes | Auto Scheduled | Perform Project Status Reporting 40 | 1 day | 05-12-12 08:00 | 05-12-12 17:00 |  | 4
314 | Yes | Auto Scheduled | Perform Project Status Reporting 41 | 1 day | 12-12-12 08:00 | 12-12-12 17:00 |  | 4
315 | Yes | Auto Scheduled | Perform Project Status Reporting 42 | 1 day | 19-12-12 08:00 | 19-12-12 17:00 |  | 4
316 | Yes | Auto Scheduled | Perform Project Status Reporting 43 | 1 day | 09-01-13 08:00 | 09-01-13 17:00 |  | 4
317 | Yes | Auto Scheduled | Perform Project Status Reporting 44 | 1 day | 16-01-13 08:00 | 16-01-13 17:00 |  | 4
318 | Yes | Auto Scheduled | Perform Project Status Reporting 45 | 1 day | 23-01-13 08:00 | 23-01-13 17:00 |  | 4
319 | Yes | Auto Scheduled | Perform Project Status Reporting 46 | 1 day | 30-01-13 08:00 | 30-01-13 17:00 |  | 4
320 | Yes | Auto Scheduled | Perform Project Status Reporting 47 | 1 day | 06-02-13 08:00 | 06-02-13 17:00 |  | 4
321 | Yes | Auto Scheduled | Perform Project Status Reporting 48 | 1 day | 13-02-13 08:00 | 13-02-13 17:00 |  | 4
322 | Yes | Auto Scheduled | Perform Project Status Reporting 49 | 1 day | 20-02-13 08:00 | 20-02-13 17:00 |  | 4
323 | Yes | Auto Scheduled | Perform Project Status Reporting 50 | 1 day | 27-02-13 08:00 | 27-02-13 17:00 |  | 4
324 | Yes | Auto Scheduled | Perform Project Status Reporting 51 | 1 day | 06-03-13 08:00 | 06-03-13 17:00 |  | 4
325 | Yes | Auto Scheduled | Perform Project Status Reporting 52 | 1 day | 13-03-13 08:00 | 13-03-13 17:00 |  | 4
326 | Yes | Auto Scheduled | Perform Project Status Reporting 53 | 1 day | 20-03-13 08:00 | 20-03-13 17:00 |  | 4
327 | Yes | Auto Scheduled | Perform Project Status Reporting 54 | 1 day | 27-03-13 08:00 | 27-03-13 17:00 |  | 4
328 | Yes | Auto Scheduled | Perform Project Status Reporting 55 | 1 day | 03-04-13 08:00 | 03-04-13 17:00 |  | 4
329 | Yes | Auto Scheduled | Perform Project Status Reporting 56 | 1 day | 10-04-13 08:00 | 10-04-13 17:00 |  | 4
330 | Yes | Auto Scheduled | Perform Project Status Reporting | 1 day? | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
331 | Yes | Auto Scheduled | Perform Project Steering | 1 day? | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
332 | Yes | Auto Scheduled | Manage Project Stakeholder Communications | 1 day? | 23-01-12 08:00 | 23-01-12 17:00 |  | 3
333 | Yes | Auto Scheduled | Project Closure | 0 days | 21-05-13 17:00 | 21-05-13 17:00 | 202,203 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | Windows User Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Sabre SME | S | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Sabre OR | S | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Sabre PM | S | Work |  |  |  |  | 100% | $0.00/h | 0
4 | EY Business | E | Work |  |  |  |  | 100% | $0.00/h | 0
5 | EY Cargo | E | Work |  |  |  |  | 100% | $0.00/h | 0
6 | EY IT | E | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Sabre PM & SME | S | Work |  |  |  |  | 100% | $0.00/h | 0
8 | EY Cargo & IT | E | Work |  |  |  |  | 100% | $0.00/h | 0
9 | CHAMP | C | Work |  |  |  |  | 100% | $0.00/h | 0
10 | Sabre Dev | S | Work |  |  |  |  | 100% | $0.00/h | 0
11 | All | A | Work |  |  |  |  | 100% | $0.00/h | 0
12 | Sabre Dec | S | Work |  |  |  |  | 100% | $0.00/h | 0
13 | Sabre Agile Customer | S | Work |  |  |  |  | 100% | $0.00/h | 0
14 | Pete Calloway | P | Work |  |  |  |  | 100% | $0.00/h | 0
15 | Sabre GTE | S | Work |  |  |  |  | 100% | $0.00/h | 0
16 | Sabre Adv Support | S | Work |  |  |  |  | 100% | $0.00/h | 0
17 | Sabre Tech SME | S | Work |  |  |  |  | 100% | $0.00/h | 0
18 | Sabre Cargo | S | Work |  |  |  |  | 100% | $0.00/h | 0
19 | Sabre IT | S | Work |  |  |  |  | 100% | $0.00/h | 0
20 | EY PM | E | Work |  |  |  |  | 100% | $0.00/h | 0
21 | EY IT PM | E | Work |  |  |  |  | 100% | $0.00/h | 0
22 | Sabre Dev Sabre GTE | S | Work |  |  |  |  | 100% | $0.00/h | 0
23 | Sabre Advance Support | S | Work |  |  |  |  | 100% | $0.00/h | 0
24 | Sabre SaaS | S | Work |  |  |  |  | 100% | $0.00/h | 0
25 | SaaS | S | Work |  |  |  |  | 100% | $0.00/h | 0
26 | SME Tech SME | S | Work |  |  |  |  | 100% | $0.00/h | 0
27 | Sabre Tech PM | S | Work |  |  |  |  | 100% | $0.00/h | 0
28 | Stakeholders | S | Work |  |  |  |  | 100% | $0.00/h | 0
29 | Sabre AD | S | Work |  |  |  |  | 100% | $0.00/h | 0
30 | Sabre Pgrm Mgr | S | Work |  |  |  |  | 100% | $0.00/h | 0
31 | Sabre Solutions | S | Work |  |  |  |  | 100% | $0.00/h | 0
32 | EY Caargo | E | Work |  |  |  |  | 100% | $0.00/h | 0
33 | EY Test | E | Work |  |  |  |  | 100% | $0.00/h | 0
34 | Sabre CC | S | Work |  |  |  |  | 100% | $0.00/h | 0
35 | Sabre | S | Work |  |  |  |  | 100% | $0.00/h | 0
36 | SabreSME | S | Work |  |  |  |  | 100% | $0.00/h | 0
37 | EY | E | Work |  |  |  |  | 100% | $0.00/h | 0
38 | IT | I | Work |  |  |  |  | 100% | $0.00/h | 0
39 | Sabre PM | S | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Proof of Concept | Sabre OR | 1 | 8h | 100%
Proof of Concept | EY Cargo | 1 | 8h | 100%
Proof of Concept | Sabre Cargo | 1 | 8h | 100%
O&D Accuracy - 25% Error | Sabre OR | 1 | 8h | 100%
O&D Accuracy - 25% Error | Sabre SME | 1 | 8h | 100%
O&D Accuracy - 25% Error | EY Cargo | 1 | 8h | 100%
Leg Accuracy - 12% Error | Sabre OR | 1 | 8h | 100%
Leg Accuracy - 12% Error | Sabre SME | 1 | 8h | 100%
Leg Accuracy - 12% Error | EY Cargo | 1 | 8h | 100%
Methodology acceptance | Sabre OR | 1 | 8h | 100%
Methodology acceptance | Sabre SME | 1 | 8h | 100%
Methodology acceptance | EY Cargo | 1 | 8h | 100%
Perform Simluation of Network Module | Sabre OR | 1 | 136h | 100%
Define to-be end-to-end business process | Sabre OR | 1 | 24h | 100%
Define to-be end-to-end business process | Sabre SME | 1 | 24h | 100%
Define to-be end-to-end business process | Sabre PM | 1 | 24h | 100%
Define to-be end-to-end business process | EY Cargo | 1 | 24h | 100%
Define to-be end-to-end business process | EY IT | 1 | 24h | 100%
Define to-be end-to-end business process | CHAMP | 1 | 24h | 100%
Define Acceptance Criteria for end to end | Sabre OR | 1 | 24h | 100%
Define Acceptance Criteria for end to end | Sabre SME | 1 | 24h | 100%
Define Acceptance Criteria for end to end | EY Cargo | 1 | 24h | 100%
Define Acceptance Criteria for end to end | EY IT | 1 | 24h | 100%
Establish Project/Accounting Codes in Central Systems | Sabre PM | 1 | 120h | 100%
Create Project Definition Document | Sabre PM & SME | 0.94999998807907104 | 160h | 100%
Create Project Processes & Procedures Document | Sabre PM & SME | 0.94999998807907104 | 40h | 100%
Negotiate Development Commitments | Sabre Dev | 1 | 240h | 100%
Negotiate Development Commitments | Sabre PM | 1 | 240h | 100%
Negotiate Testing Commitments | Sabre GTE | 1 | 80h | 100%
Negotiate Testing Commitments | Sabre Dev | 1 | 80h | 100%
Create High Level Initial Project Schedule | Sabre PM | 1 | 40h | 100%
Create High Level Initial Project Schedule | Sabre Dev | 1 | 40h | 100%
Perform Internal High-Level Project Schedule Review | Sabre PM | 1 | 5.33h | 67%
Perform Internal High-Level Project Schedule Review | Sabre Dev | 1 | 5.33h | 67%
Perform Internal High-Level Project Schedule Review | Sabre Pgrm Mgr | 1 | 5.33h | 67%
Perform Client High-Level Project Schedule Review | Sabre PM | 1 | 8h | 100%
Perform Client High-Level Project Schedule Review | Sabre SME | 1 | 8h | 100%
Confirm Client and Client Subcontractor Commitments | EY PM | 1 | 176h | 100%
Finalize Project Schedule | Sabre PM | 0.75 | 16.08h | 67%
Finalize Project Schedule | Sabre Dev | 0.75 | 16.08h | 67%
Finalize Project Schedule | Sabre Pgrm Mgr | 0.75 | 16.08h | 67%
Perform Internal Detail-Level Project Schedule Review | Sabre PM | 0 | 10.72h | 67%
Perform Internal Detail-Level Project Schedule Review | Sabre Dev | 0 | 10.72h | 67%
Perform Internal Detail-Level Project Schedule Review | Sabre Pgrm Mgr | 0 | 10.72h | 67%
Perform Client Detail-Level Project Schedule Review | Sabre PM | 0 | 8h | 100%
Perform Client Detail-Level Project Schedule Review | Sabre Pgrm Mgr | 0 | 8h | 100%
Perform Client Detail-Level Project Schedule Review | EY Cargo | 0 | 8h | 100%
Perform Client Detail-Level Project Schedule Review | EY IT | 0 | 8h | 100%
Baseline Project Schedule | Sabre PM | 0 | 0h | 100%
Baseline Project Schedule | EY PM | 0 | 0h | 100%
Plan and Perform Customer Project Kick-Off | Sabre PM | 1 | 8h | 100%
Plan and Perform Customer Project Kick-Off | Sabre SME | 1 | 8h | 100%
Communicate to Stakeholders | Sabre SME | 1 | 8h | 100%
Communicate to Stakeholders | Sabre PM | 1 | 8h | 100%
Communicate to Stakeholders | EY Cargo | 1 | 8h | 100%
Communicate to Stakeholders | EY IT | 1 | 8h | 100%
Communicate to Stakeholders | EY IT PM | 1 | 8h | 100%
Communicate to Stakeholders | Stakeholders | 1 | 8h | 100%
Establish Initial Customer Access to Community Portal | Sabre PM | 0 | 40h | 100%
Create Communication Plan | Sabre PM | 0 | 8h | 100%
Create Communication Plan | EY PM | 0 | 8h | 100%
Perform Data Collection | Sabre SME | 1 | 64h | 100%
Perform Data Collection | Sabre OR | 1 | 64h | 100%
Plan and Perform Interactive Pilot Assessment | Sabre PM | 1 | 64h | 100%
Plan and Perform Interactive Pilot Assessment | Sabre SME | 1 | 64h | 100%
Plan and Schedule Interactive Pilot Workshops | Sabre PM | 1 | 16h | 100%
Plan and Schedule Interactive Pilot Workshops | Sabre SME | 1 | 16h | 100%
Prepare Interactive Pilot Workshop Components | Sabre PM | 1 | 24h | 100%
Prepare Interactive Pilot Workshop Components | Sabre SME | 1 | 24h | 100%
Conduct Initial Training (Key User / Train the Trainer) | Sabre PM | 0 | 32h | 100%
Conduct Initial Training (Key User / Train the Trainer) | Sabre SME | 0 | 32h | 100%
Conduct Initial Training (Key User / Train the Trainer) | Sabre Solutions | 0 | 32h | 100%
Conduct Initial Training (Key User / Train the Trainer) | EY Cargo | 0 | 32h | 100%
Conduct Initial Training (Key User / Train the Trainer) | EY IT | 0 | 32h | 100%
Conduct Initial Training (Key User / Train the Trainer) | CHAMP | 0 | 32h | 100%
Perform Interactive Pilot Workshops | Sabre PM | 1 | 56h | 100%
Perform Interactive Pilot Workshops | Sabre SME | 1 | 56h | 100%
Perform Interactive Pilot Workshops | EY Cargo | 1 | 56h | 100%
Finalize Interactive Pilot Workshops | Sabre PM | 1 | 8h | 100%
Finalize Interactive Pilot Workshops | Sabre SME | 1 | 8h | 100%
Finalize Interactive Pilot Workshops | EY Cargo | 1 | 8h | 100%
Finalize Interactive Pilot Workshops | EY PM | 1 | 8h | 100%
BRD Review Session | Sabre PM | 1 | 16h | 100%
BRD Review Session | Sabre SME | 1 | 16h | 100%
BRD Review Session | EY Cargo | 1 | 16h | 100%
BRD Review Session | EY PM | 1 | 16h | 100%
Scenario based process wak-throughs | Sabre PM | 1 | 30h | 75%
Scenario based process wak-throughs | Sabre SME | 1 | 30h | 75%
Scenario based process wak-throughs | EY Cargo | 1 | 30h | 75%
Scenario based process wak-throughs | CHAMP | 1 | 30h | 75%
Risk Register Creation | Sabre PM | 1 | 8h | 100%
Risk Register Creation | Sabre SME | 1 | 8h | 100%
Risk Register Creation | EY Cargo | 1 | 8h | 100%
Risk Register Creation | EY PM | 1 | 8h | 100%
Deliverable Definition | Sabre PM | 1 | 8h | 100%
Deliverable Definition | Sabre SME | 1 | 8h | 100%
Deliverable Definition | EY Cargo | 1 | 8h | 100%
Deliverable Definition | EY PM | 1 | 8h | 100%
Create IPA Report | Sabre PM | 1 | 288h | 100%
Create IPA Report | Sabre SME | 1 | 288h | 100%
Present IPA Report | Sabre PM | 1 | 8h | 100%
Present IPA Report | Sabre SME | 1 | 8h | 100%
Joint Review of IPA Report | Sabre PM | 1 | 16h | 100%
Joint Review of IPA Report | Sabre SME | 1 | 16h | 100%
Joint Review of IPA Report | EY Cargo | 1 | 16h | 100%
Joint Review of IPA Report | EY PM | 1 | 16h | 100%
Publish Final Version of IPA Report | Sabre PM | 1 | 8h | 100%
Publish Final Version of IPA Report | EY PM | 1 | 8h | 100%
On-site Interviews with Pricing Analyst | Sabre SME | 1 | 8h | 100%
On-site Interviews with Pricing Analyst | EY Cargo | 1 | 8h | 100%
Create Organization, Functional and Policy & Procedures recommendations based on Network Module | Sabre SME | 1 | 272h | 100%
Reivew Recommendations with Etihad Cargo | Sabre SME | 1 | 16h | 100%
Reivew Recommendations with Etihad Cargo | EY Cargo | 1 | 16h | 100%
Pulbish Final Recommendations | Sabre PM | 1 | 8h | 100%
Pulbish Final Recommendations | EY PM | 1 | 8h | 100%
Create KPI's for Network Module | Sabre SME | 0 | 296h | 100%
Create KPI's for Network Module | EY Cargo | 0 | 296h | 100%
Review and Finalize KPI's for Network Module | Sabre SME | 0 | 24h | 100%
Review and Finalize KPI's for Network Module | EY Cargo | 0 | 24h | 100%
Determine Make-up of Standard Performance Reports | Sabre SME | 0 | 40h | 100%
Determine Make-up of Standard Performance Reports | EY Caargo | 0 | 40h | 100%
Review KPI's and Standard Performance Reports with EY | Sabre SME | 0 | 16h | 100%
Review KPI's and Standard Performance Reports with EY | EY Cargo | 0 | 16h | 100%
Perform the Interactive Pilot End-of-Phase Review | Sabre PM | 0 | 8h | 100%
Perform the Interactive Pilot End-of-Phase Review | Sabre SME | 0 | 8h | 100%
Perform the Interactive Pilot End-of-Phase Review | EY Cargo | 0 | 8h | 100%
Perform the Interactive Pilot End-of-Phase Review | EY PM | 0 | 8h | 100%
Release 2 - Interactive Pilot Phase Complete | Sabre PM | 0 | 0h | 100%
Support Detailed Solution Definition | EY Cargo & IT | 1 | 8h | 100%
Support Detailed Solution Definition | Sabre Cargo | 1 | 8h | 100%
Determine New GUI Screen Field Details | EY Cargo & IT | 1 | 16h | 100%
Determine New GUI Screen Field Details | Sabre Cargo | 1 | 16h | 100%
Signoff from customer on GUI Fields | EY Cargo | 1 | 8h | 100%
Support Iteration Planning 1 | Sabre Agile Customer | 1 | 8h | 100%
Support Iteration Planning 2 | Sabre Agile Customer | 1 | 8h | 100%
Support Iteration Planning 3 | Sabre Agile Customer | 1 | 8h | 100%
Support Iteration Planning 4 | Sabre Agile Customer | 1 | 8h | 100%
Support Iteration Planning 5 | Sabre Agile Customer | 1 | 8h | 100%
Support Iteration Planning 6 | Sabre Agile Customer | 1 | 8h | 100%
Support Iteration Planning 7 | Sabre Agile Customer | 1 | 8h | 100%
Support Iteration Planning 8 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 9 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 10 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 11 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 12 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 13 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 14 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 15 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 16 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 17 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 18 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 19 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 20 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 21 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 22 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 23 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 24 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration Planning 25 | Sabre Agile Customer | 0 | 8h | 100%
Support Iteration and Release Planning | Sabre Agile Customer | 0 | 0h | 100%
Support Iteration Development / Testing | Sabre Agile Customer | 0 | 0h | 100%
Support Iteration Development / Testing | Sabre GTE | 0 | 0h | 100%
Design GUI Screens | Sabre Dev | 0 | 272h | 100%
Cost Module Changes pt I | EY Cargo | 0.41999998688697815 | 112h | 100%
Cost Module Changes pt I | Sabre Cargo | 0.41999998688697815 | 112h | 100%
Request build and internal testing | Sabre Dev | 1 | 112h | 100%
Workshop to demo new screens | EY Cargo | 1 | 8h | 100%
Workshop to demo new screens | Sabre PM | 1 | 8h | 100%
Workshop to demo new screens | Sabre SME | 1 | 8h | 100%
Workshop to demo new screens | Sabre Dev | 1 | 8h | 100%
Give: Etihad Screen Shot and Cost Module Screen Demos screenshots | Sabre PM | 1 | 0h | 100%
Get: Etihad sign off on screen design | EY Cargo | 1 | 0h | 100%
Cost Module Changes pt II | Sabre Dev | 1 | 96h | 100%
Request Build and internal testing | Sabre Dev | 1 | 112h | 100%
Workshop to demo Cost Module changes | Sabre Dev | 1 | 8h | 100%
Workshop to demo Cost Module changes | Sabre PM | 1 | 8h | 100%
Workshop to demo Cost Module changes | EY Cargo | 1 | 8h | 100%
Give: Etihad Cost Module Screen Changes pt II screen shots | Sabre PM | 0 | 0h | 100%
Get: Etihad sign off on cost module screen designs and calcuatlations | EY Cargo | 0 | 0h | 100%
Modify internal booking evaluation processes | Sabre Dev | 0 | 64h | 100%
Request build and internal testing | Sabre Dev | 0 | 128h | 100%
Workshop to demo Booking evaluation changes | Sabre Dev | 0 | 8h | 100%
Workshop to demo Booking evaluation changes | Sabre SME | 0 | 8h | 100%
Workshop to demo Booking evaluation changes | Sabre PM | 0 | 8h | 100%
Workshop to demo Booking evaluation changes | EY Cargo | 0 | 8h | 100%
Give: Etihad recording of Booking Evaluation changes demon for signoff | Sabre | 0 | 0h | 100%
Get: Etihad signoff on booking evaluation process changes | EY Cargo & IT | 0 | 0h | 100%
Create Booking Evaluation Interfaces | Sabre Dev | 0 | 152h | 100%
Get: Sample "Booking Evaluation Call" and "Request for Additional Call" messages from CHAMP | Sabre Dev | 0 | 0h | 100%
Get: Sample "Booking Evaluation Call" and "Request for Additional Call" messages from CHAMP | CHAMP | 0 | 0h | 100%
Test sample messages received from CHAMP | Sabre Dev | 0 | 16h | 100%
Test sample messages received from CHAMP | Sabre GTE | 0 | 16h | 100%
Air Vision Cargo Technology changes (does not include Oracle changes) | Sabre Dev | 0 | 32h | 100%
Final build and fixes prior to GTE | Sabre Dev | 0 | 64h | 100%
Pass 1 | Sabre GTE | 0 | 80h | 100%
Pass 2 | Sabre GTE | 0 | 40h | 50%
Pass 2 | EY Test | 0 | 40h | 50%
Pass 3 | Sabre GTE | 0 | 80h | 100%
Pass 3 | EY Test | 0 | 80h | 100%
Support On_site Customer Collaboration | Sabre SME | 0 | 0h | 100%
Support On_site Customer Collaboration | Sabre PM | 0 | 0h | 100%
Support Business Process Improvements | Sabre SME | 0 | 0h | 100%
Plan and Perform the Installation (For Each Environment As Needed: Training, Validation, etc.) | Sabre PM | 0 | 40h | 100%
Plan and Perform the Installation (For Each Environment As Needed: Training, Validation, etc.) | Sabre Tech SME | 0 | 40h | 100%
Implement agreed recommended processess and practices | Sabre SME | 0 | 0h | 100%
Implement agreed recommended processess and practices | EY Cargo | 0 | 0h | 100%
Implementation of Organization structures related to Network Module | Sabre SME | 0 | 240h | 100%
Implementation of Organization structures related to Network Module | EY Cargo | 0 | 240h | 100%
Business Training on how KPI's and Standard Performance Reports will be used | Sabre SME | 0 | 16h | 100%
Business Training on how KPI's and Standard Performance Reports will be used | EY Cargo | 0 | 16h | 100%
Perform the Solution Adoption End-of-Phase Review | Sabre Cargo | 0 | 8h | 100%
Perform the Solution Adoption End-of-Phase Review | EY Cargo | 0 | 8h | 100%
Perform the Solution Adoption End-of-Phase Review | EY PM | 0 | 8h | 100%
Support Customer Validation | Sabre Tech SME | 0 | 80h | 100%
Support Customer Validation | Sabre SME | 0 | 80h | 100%
Support Customer Validation | Sabre OR | 0 | 80h | 100%
Calibration Exercise | Sabre OR | 0 | 240h | 100%
Calibration Exercise | Sabre SME | 0 | 240h | 100%
Calibration Exercise | EY Cargo | 0 | 240h | 100%
Load Calibration and Cost data in EY Test build | EY IT | 0 | 8h | 50%
Load Calibration and Cost data in EY Test build | Sabre Adv Support | 0 | 8h | 50%
Load Calibration and Cost data in EY Test build | Sabre Tech SME | 0 | 8h | 50%
GET: CHAMP has deployed build into EY Test Environment | EY IT | 0 | 0h | 100%
GET: CHAMP has deployed build into EY Test Environment | Sabre PM | 0 | 0h | 100%
Train the Trainer classroom training for testers | Sabre SME | 0 | 40h | 100%
Train the Trainer classroom training for testers | EY Cargo | 0 | 40h | 100%
Air Vision Cargo Interface Integration Testing with Cargospot | EY Cargo | 0 | 80h | 100%
Air Vision Cargo Interface Integration Testing with Cargospot | EY IT | 0 | 40h | 50%
Air Vision Cargo Interface Integration Testing with Cargospot | CHAMP | 0 | 60h | 75%
Air Vision Cargo Interface Integration Testing with Cargospot | Sabre SME | 0 | 80h | 100%
Soak Test - Parallel run (Test and Prod) | Sabre SME | 0 | 68.07h | 24%
Soak Test - Parallel run (Test and Prod) | EY Cargo | 0 | 170.18h | 59%
Soak Test - Parallel run (Test and Prod) | EY IT | 0 | 68.07h | 24%
Soak Test - Parallel run (Test and Prod) | CHAMP | 0 | 68.07h | 24%
Plan and Perform Split Shipment Handling code deployment | Sabre SME | 0 | 40h | 100%
Plan and Perform Split Shipment Handling code deployment | EY IT | 0 | 40h | 100%
Validate build successfully deployed | Sabre SME | 0 | 8h | 100%
Validate build successfully deployed | EY IT | 0 | 8h | 100%
Train the trainer classroom training for testers | Sabre SME | 0 | 16h | 100%
Train the trainer classroom training for testers | EY Cargo | 0 | 16h | 100%
Soak Test - Parallel run (Test and Prod) | EY Cargo | 0 | 160h | 100%
Soak Test - Parallel run (Test and Prod) | EY | 0 | 160h | 100%
Soak Test - Parallel run (Test and Prod) | IT | 0 | 160h | 100%
Soak Test - Parallel run (Test and Prod) | Sabre SME | 0 | 160h | 100%
Soak Test - Parallel run (Test and Prod) | Sabre PM | 0 | 160h | 100%
Go/No Go for Production Deployment | Sabre Cargo | 0 | 0h | 100%
Go/No Go for Production Deployment | EY Cargo | 0 | 0h | 100%
Go/No Go for Production Deployment | EY IT | 0 | 0h | 100%
Perform End-User Training | Sabre SME | 0 | 40h | 100%
Perform End-User Training | EY Cargo | 0 | 40h | 100%
Implement KPI monitoring and utliziation of Standard Performance Reports | Sabre SME | 0 | 80h | 100%
Implement KPI monitoring and utliziation of Standard Performance Reports | EY Cargo | 0 | 80h | 100%
Begin Performance Monitoring | Sabre SME | 0 | 0h | 100%
Begin Performance Monitoring | EY Cargo | 0 | 0h | 100%
Implement agree recommended processes and practices | Sabre SME | 0 | 80h | 100%
Implement agree recommended processes and practices | EY Cargo | 0 | 80h | 100%
End Performance Monitoring | SabreSME | 0 | 0h | 100%
Present Performance Monitoring Results to Etihad | Sabre SME | 0 | 40h | 100%
Present Performance Monitoring Results to Etihad | EY Cargo | 0 | 40h | 100%
Plan Production Cutover | Sabre Tech SME | 0 | 120h | 100%
Plan Production Cutover | Sabre PM | 0 | 120h | 100%
Plan Production Cutover | EY IT | 0 | 120h | 100%
Plan Production Cutover | EY Cargo | 0 | 120h | 100%
Perform Production Cutover | Sabre Tech SME | 0 | 8h | 100%
Perform Production Cutover | EY IT | 0 | 8h | 100%
Perform Post-Cutover Customer Support | Sabre SME | 0 | 240h | 100%
Plan Customer Care Transition | Sabre PM | 0 | 40h | 100%
Perform Customer Care Transition | Sabre PM | 0 | 8h | 100%
Perform Customer Care Transition | Sabre CC | 0 | 8h | 100%
Perform Customer Care Transition | EY Cargo | 0 | 8h | 100%
Perform Customer Care Transition | EY IT | 0 | 8h | 100%
Perform Project Close-Out | Sabre PM | 0 | 24h | 100%
Perform Project Close-Out | EY PM | 0 | 24h | 100%
Perform Project Close-Out | EY Cargo | 0 | 24h | 100%
Perform Post-Project Review | Sabre PM | 0 | 16h | 100%
Perform Post-Project Review | EY PM | 0 | 16h | 100%
Perform Post-Project Review | EY Cargo | 0 | 16h | 100%
Project Planning | Sabre PM | 1 | 40h | 100%
Project Planning | EY PM | 1 | 40h | 100%
Project Planning | Sabre SME | 1 | 40h | 100%
Manage Project Scope | Sabre PM | 0 | 8h | 100%
Manage Project Scope | EY PM | 0 | 8h | 100%
Manage Project Schedule | Sabre PM | 0 | 8h | 100%
Manage Project Schedule | EY PM | 0 | 8h | 100%
Manage Project Issues | Sabre PM | 0 | 8h | 100%
Manage Project Issues | EY PM | 0 | 8h | 100%
Manage Project Risks | Sabre PM | 0 | 8h | 100%
Manage Project Risks | EY PM | 0 | 8h | 100%
Manage Project Quality | Sabre PM | 0 | 8h | 100%
Manage Project Quality | EY PM | 0 | 8h | 100%
Manage Project Scope, Schedule, Issues & Risks | Sabre PM | 0 | 2,224h | 100%
Manage Project Scope, Schedule, Issues & Risks | EY PM | 0 | 2,224h | 100%
Manage Project Scope, Schedule, Issues & Risks | EY Cargo | 0 | 2,224h | 100%
Manage Delivery as an Integrated Portfolio | Sabre PM | 0 | 8h | 100%
Manage Delivery as an Integrated Portfolio | EY PM | 0 | 8h | 100%
Manage Project Budget And Invoicing | Sabre PM | 0 | 8h | 100%
Manage Project Budget And Invoicing | EY PM | 0 | 8h | 100%
Perform Project Metrics Tracking | Sabre PM | 0 | 8h | 100%
Perform Project Metrics Tracking | EY PM | 0 | 8h | 100%
Perform Project Status Reporting | Sabre PM | 0 | 2,224h | 100%
Perform Project Status Reporting | EY PM | 0 | 2,224h | 100%
Perform Project Status Reporting | EY Cargo | 0 | 2,224h | 100%
Perform Project Status Reporting | Sabre PM | 0 | 8h | 100%
Perform Project Status Reporting | EY PM | 0 | 8h | 100%
Perform Project Steering | Stakeholders | 0 | 8h | 100%
Perform Project Steering | Sabre PM | 0 | 8h | 100%
Perform Project Steering | EY PM | 0 | 8h | 100%
Manage Project Stakeholder Communications | Sabre PM | 0 | 8h | 100%
Manage Project Stakeholder Communications | EY PM | 0 | 8h | 100%
Project Closure | Sabre PM | 0 | 0h | 100%
Project Closure | EY PM | 0 | 0h | 100%