## Task_Costs
ID | Active | Task_Mode | Task_Name | Fixed_Cost | Total_Cost | Baseline_Cost | Cost_Variance | Actual_Cost | Remaining_Cost
0 | Yes | Auto Scheduled | Etihad Airways - AirVision Cargo - Network Module Implementation | 0 | 0 | 0 | 0 | 0 | 0
1 | Yes | Auto Scheduled | Release 2 - Etihad AirVision Cargo - Network Module Implementation | 0 | 0 | 0 | 0 | 0 | 0
2 | Yes | Auto Scheduled | Release 2 Due Diligence | 0 | 0 | 0 | 0 | 0 | 0
3 | Yes | Auto Scheduled | Proof of Concept | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Cargo | 0 | 0 | 0 | 0 | 0 | 0
4 | Yes | Auto Scheduled | Define Target Baseline Proof of Concept Accuracy | 0 | 0 | 0 | 0 | 0 | 0
5 | Yes | Auto Scheduled | O&D Accuracy - 25% Error | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
6 | Yes | Auto Scheduled | Leg Accuracy - 12% Error | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
7 | Yes | Auto Scheduled | Inputs criteria complete | 0 | 0 | 0 | 0 | 0 | 0
8 | Yes | Auto Scheduled | Methodology acceptance | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
9 | Yes | Auto Scheduled | Perform Simluation of Network Module | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
10 | Yes | Auto Scheduled | Define to-be end-to-end business process | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | CHAMP | 0 | 0 | 0 | 0 | 0 | 0
11 | Yes | Auto Scheduled | Define Acceptance Criteria for end to end | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
12 | Yes | Auto Scheduled | Release 2 - Re-Engagement (Initiation) Phase | 0 | 0 | 0 | 0 | 0 | 0
13 | Yes | Auto Scheduled | Perform Project Set-Up Activities | 0 | 0 | 0 | 0 | 0 | 0
14 | Yes | Auto Scheduled | Establish Project/Accounting Codes in Central Systems | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
15 | Yes | Auto Scheduled | Create Project Definition Document | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM & SME | 0 | 0 | 0 | 0 | 0 | 0
16 | Yes | Auto Scheduled | Create Project Processes & Procedures Document | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM & SME | 0 | 0 | 0 | 0 | 0 | 0
17 | Yes | Auto Scheduled | Negotiate Development Commitments | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
18 | Yes | Auto Scheduled | Negotiate Testing Commitments | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre GTE | 0 | 0 | 0 | 0 | 0 | 0
19 | Yes | Auto Scheduled | Create Project Schedule | 0 | 0 | 0 | 0 | 0 | 0
20 | Yes | Auto Scheduled | Create High Level Initial Project Schedule | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
21 | Yes | Auto Scheduled | Perform Internal High-Level Project Schedule Review | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Pgrm Mgr | 0 | 0 | 0 | 0 | 0 | 0
22 | Yes | Auto Scheduled | Perform Client High-Level Project Schedule Review | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
23 | Yes | Auto Scheduled | Confirm Client and Client Subcontractor Commitments | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
24 | Yes | Auto Scheduled | Finalize Project Schedule | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Pgrm Mgr | 0 | 0 | 0 | 0 | 0 | 0
25 | Yes | Auto Scheduled | Perform Internal Detail-Level Project Schedule Review | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Pgrm Mgr | 0 | 0 | 0 | 0 | 0 | 0
26 | Yes | Auto Scheduled | Perform Client Detail-Level Project Schedule Review | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Pgrm Mgr | 0 | 0 | 0 | 0 | 0 | 0
27 | Yes | Auto Scheduled | Baseline Project Schedule | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
28 | Yes | Auto Scheduled | Perform Project Kick-Off | 0 | 0 | 0 | 0 | 0 | 0
29 | Yes | Auto Scheduled | Plan and Perform Customer Project Kick-Off | 0 | 0 | 0 | 0 | 0 | 0
30 | Yes | Auto Scheduled | Plan and Perform Customer Project Kick-Off | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
31 | Yes | Auto Scheduled | Communicate to Stakeholders | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Stakeholders | 0 | 0 | 0 | 0 | 0 | 0
32 | Yes | Auto Scheduled | Establish Initial Customer Access to Community Portal | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
33 | Yes | Auto Scheduled | Create Communication Plan | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
34 | Yes | Auto Scheduled | Project Re-Engagement Complete | 0 | 0 | 0 | 0 | 0 | 0
35 | Yes | Auto Scheduled | Release 2 - Interactive Pilot Phase | 0 | 0 | 0 | 0 | 0 | 0
36 | Yes | Auto Scheduled | Perform Interactive Pilot Assessment | 0 | 0 | 0 | 0 | 0 | 0
37 | Yes | Auto Scheduled | Perform Data Collection | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
38 | Yes | Auto Scheduled | Plan and Perform Interactive Pilot Assessment | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
39 | Yes | Auto Scheduled | Plan Interactive Pilot Workshops | 0 | 0 | 0 | 0 | 0 | 0
40 | Yes | Auto Scheduled | Plan and Schedule Interactive Pilot Workshops | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
41 | Yes | Auto Scheduled | Prepare Interactive Pilot Workshop Components | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
42 | Yes | Auto Scheduled | Conduct Initial Training | 0 | 0 | 0 | 0 | 0 | 0
43 | Yes | Auto Scheduled | Conduct Initial Training (Key User / Train the Trainer) | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | CHAMP | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Solutions | 0 | 0 | 0 | 0 | 0 | 0
44 | Yes | Auto Scheduled | Perform Interactive Pilot Workshops | 0 | 0 | 0 | 0 | 0 | 0
45 | Yes | Auto Scheduled | Perform Interactive Pilot Workshops | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
46 | Yes | Auto Scheduled | Finalize Interactive Pilot Workshops | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
47 | Yes | Auto Scheduled | Interactive Pilot Workshops | 0 | 0 | 0 | 0 | 0 | 0
48 | Yes | Auto Scheduled | BRD Review Session | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
49 | Yes | Auto Scheduled | Scenario based process wak-throughs | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | CHAMP | 0 | 0 | 0 | 0 | 0 | 0
50 | Yes | Auto Scheduled | Risk Register Creation | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
51 | Yes | Auto Scheduled | Deliverable Definition | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
52 | Yes | Auto Scheduled | Create IPA Report | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
53 | Yes | Auto Scheduled | Present IPA Report | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
54 | Yes | Auto Scheduled | Joint Review of IPA Report | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
55 | Yes | Auto Scheduled | Publish Final Version of IPA Report | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
56 | Yes | Auto Scheduled | Consulting Activites | 0 | 0 | 0 | 0 | 0 | 0
57 | Yes | Auto Scheduled | On-site Interviews with Pricing Analyst | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
58 | Yes | Auto Scheduled | Create Organization, Functional and Policy & Procedures recommendations based on Network Module | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
59 | Yes | Auto Scheduled | Reivew Recommendations with Etihad Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
60 | Yes | Auto Scheduled | Pulbish Final Recommendations | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
61 | Yes | Auto Scheduled | Create KPI's for Network Module | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
62 | Yes | Auto Scheduled | Review and Finalize KPI's for Network Module | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
63 | Yes | Auto Scheduled | Determine Make-up of Standard Performance Reports | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Caargo | 0 | 0 | 0 | 0 | 0 | 0
64 | Yes | Auto Scheduled | Review KPI's and Standard Performance Reports with EY | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
65 | Yes | Auto Scheduled | Perform the Interactive Pilot End-of-Phase Review | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
66 | Yes | Auto Scheduled | Release 2 - Interactive Pilot Phase Complete | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
67 | Yes | Auto Scheduled | Release 2 - Solution Adoption Phase | 0 | 0 | 0 | 0 | 0 | 0
68 | Yes | Auto Scheduled | Support Solution Definition and Design | 0 | 0 | 0 | 0 | 0 | 0
69 | Yes | Auto Scheduled | Support Detailed Solution Definition | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo & IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Cargo | 0 | 0 | 0 | 0 | 0 | 0
70 | Yes | Auto Scheduled | Support Detailed Solution Design | 0 | 0 | 0 | 0 | 0 | 0
71 | Yes | Auto Scheduled | Determine New GUI Screen Field Details | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo & IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Cargo | 0 | 0 | 0 | 0 | 0 | 0
72 | Yes | Auto Scheduled | Signoff from customer on GUI Fields | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
73 | Yes | Auto Scheduled | Support Solution Build-Out | 0 | 0 | 0 | 0 | 0 | 0
74 | Yes | Auto Scheduled | Support Iteration Planning | 0 | 0 | 0 | 0 | 0 | 0
75 | Yes | Auto Scheduled | Support Iteration Planning 1 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
76 | Yes | Auto Scheduled | Support Iteration Planning 2 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
77 | Yes | Auto Scheduled | Support Iteration Planning 3 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
78 | Yes | Auto Scheduled | Support Iteration Planning 4 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
79 | Yes | Auto Scheduled | Support Iteration Planning 5 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
80 | Yes | Auto Scheduled | Support Iteration Planning 6 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
81 | Yes | Auto Scheduled | Support Iteration Planning 7 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
82 | Yes | Auto Scheduled | Support Iteration Planning 8 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
83 | Yes | Auto Scheduled | Support Iteration Planning 9 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
84 | Yes | Auto Scheduled | Support Iteration Planning 10 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
85 | Yes | Auto Scheduled | Support Iteration Planning 11 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
86 | Yes | Auto Scheduled | Support Iteration Planning 12 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
87 | Yes | Auto Scheduled | Support Iteration Planning 13 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
88 | Yes | Auto Scheduled | Support Iteration Planning 14 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
89 | Yes | Auto Scheduled | Support Iteration Planning 15 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
90 | Yes | Auto Scheduled | Support Iteration Planning 16 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
91 | Yes | Auto Scheduled | Support Iteration Planning 17 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
92 | Yes | Auto Scheduled | Support Iteration Planning 18 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
93 | Yes | Auto Scheduled | Support Iteration Planning 19 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
94 | Yes | Auto Scheduled | Support Iteration Planning 20 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
95 | Yes | Auto Scheduled | Support Iteration Planning 21 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
96 | Yes | Auto Scheduled | Support Iteration Planning 22 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
97 | Yes | Auto Scheduled | Support Iteration Planning 23 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
98 | Yes | Auto Scheduled | Support Iteration Planning 24 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
99 | Yes | Auto Scheduled | Support Iteration Planning 25 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
100 | Yes | Auto Scheduled | Support Iteration and Release Planning | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
101 | Yes | Auto Scheduled | Support Iteration Development / Testing | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Agile Customer | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre GTE | 0 | 0 | 0 | 0 | 0 | 0
102 | Yes | Auto Scheduled | Air Vision Cargo Network Module Development Work | 0 | 0 | 0 | 0 | 0 | 0
103 | Yes | Auto Scheduled | GUI Design and Cost Module Changes pt I | 0 | 0 | 0 | 0 | 0 | 0
104 | Yes | Auto Scheduled | Design GUI Screens | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
105 | Yes | Auto Scheduled | Cost Module Changes pt I | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Cargo | 0 | 0 | 0 | 0 | 0 | 0
106 | Yes | Auto Scheduled | Booking evaluation changes | 0 | 0 | 0 | 0 | 0 | 0
107 | Yes | Auto Scheduled | Request build and internal testing | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
108 | Yes | Auto Scheduled | Workshop to demo new screens | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
109 | Yes | Auto Scheduled | New Screen Demonstration to Etihad | 0 | 0 | 0 | 0 | 0 | 0
110 | Yes | Auto Scheduled | Give: Etihad Screen Shot and Cost Module Screen Demos screenshots | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
111 | Yes | Auto Scheduled | Get: Etihad sign off on screen design | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
112 | Yes | Auto Scheduled | Cost Module Changes pt II | 0 | 0 | 0 | 0 | 0 | 0
113 | Yes | Auto Scheduled | Cost Module Changes pt II | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
114 | Yes | Auto Scheduled | Booking Evaluation changes | 0 | 0 | 0 | 0 | 0 | 0
115 | Yes | Auto Scheduled | Request Build and internal testing | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
116 | Yes | Auto Scheduled | Workshop to demo Cost Module changes | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
117 | Yes | Auto Scheduled | Cost Module Demonstration | 0 | 0 | 0 | 0 | 0 | 0
118 | Yes | Auto Scheduled | Give: Etihad Cost Module Screen Changes pt II screen shots | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
119 | Yes | Auto Scheduled | Get: Etihad sign off on cost module screen designs and calcuatlations | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
120 | Yes | Auto Scheduled | Network Module Booking Evaluation & Cost Module pt III | 0 | 0 | 0 | 0 | 0 | 0
121 | Yes | Auto Scheduled | Cost Module changes pt III | 0 | 0 | 0 | 0 | 0 | 0
122 | Yes | Auto Scheduled | Modify internal booking evaluation processes | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
123 | Yes | Auto Scheduled | Modifed Bid Price Find Screen | 0 | 0 | 0 | 0 | 0 | 0
124 | Yes | Auto Scheduled | Request build and internal testing | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
125 | Yes | Auto Scheduled | Workshop to demo Booking evaluation changes | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
126 | Yes | Auto Scheduled | Booking Evaluatoin Demonstration | 0 | 0 | 0 | 0 | 0 | 0
127 | Yes | Auto Scheduled | Give: Etihad recording of Booking Evaluation changes demon for signoff | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre | 0 | 0 | 0 | 0 | 0 | 0
128 | Yes | Auto Scheduled | Get: Etihad signoff on booking evaluation process changes | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo & IT | 0 | 0 | 0 | 0 | 0 | 0
129 | Yes | Auto Scheduled | Cost Module and Network Module GUI | 0 | 0 | 0 | 0 | 0 | 0
130 | Yes | Auto Scheduled | Cost Module pt IV | 0 | 0 | 0 | 0 | 0 | 0
131 | Yes | Auto Scheduled | Network Module GUI | 0 | 0 | 0 | 0 | 0 | 0
132 | Yes | Auto Scheduled | Request build and internal testing | 0 | 0 | 0 | 0 | 0 | 0
133 | Yes | Auto Scheduled | Workshop to demo Cost Module and GUI changes | 0 | 0 | 0 | 0 | 0 | 0
134 | Yes | Auto Scheduled | Cost Module Demonstration | 0 | 0 | 0 | 0 | 0 | 0
135 | Yes | Auto Scheduled | Give: Etihad Cost and GUI Screen Changes | 0 | 0 | 0 | 0 | 0 | 0
136 | Yes | Auto Scheduled | Get: Etihad signoff on cost module and NM GUI changes | 0 | 0 | 0 | 0 | 0 | 0
137 | Yes | Auto Scheduled | Network Module Interfaces and Technology Changes | 0 | 0 | 0 | 0 | 0 | 0
138 | Yes | Auto Scheduled | Create Booking Evaluation Interfaces | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
139 | Yes | Auto Scheduled | Get: Sample "Booking Evaluation Call" and "Request for Additional Call" messages from CHAMP | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | CHAMP | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
140 | Yes | Auto Scheduled | Test sample messages received from CHAMP | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre GTE | 0 | 0 | 0 | 0 | 0 | 0
141 | Yes | Auto Scheduled | Air Vision Cargo Technology changes (does not include Oracle changes) | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
142 | Yes | Auto Scheduled | Final build and fixes prior to GTE | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Dev | 0 | 0 | 0 | 0 | 0 | 0
143 | Yes | Auto Scheduled | Code Complete | 0 | 0 | 0 | 0 | 0 | 0
144 | Yes | Auto Scheduled | Internal Testing by GTE team | 0 | 0 | 0 | 0 | 0 | 0
145 | Yes | Auto Scheduled | Pass 1 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre GTE | 0 | 0 | 0 | 0 | 0 | 0
146 | Yes | Auto Scheduled | Pass 2 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre GTE | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Test | 0 | 0 | 0 | 0 | 0 | 0
147 | Yes | Auto Scheduled | Pass 3 | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre GTE | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Test | 0 | 0 | 0 | 0 | 0 | 0
148 | Yes | Auto Scheduled | Network Module Development and GTE Testing Complete | 0 | 0 | 0 | 0 | 0 | 0
149 | Yes | Auto Scheduled | Split shipment BRID | 0 | 0 | 0 | 0 | 0 | 0
150 | Yes | Auto Scheduled | Split shipment handling coding | 0 | 0 | 0 | 0 | 0 | 0
151 | Yes | Auto Scheduled | Request build and internal testing | 0 | 0 | 0 | 0 | 0 | 0
152 | Yes | Auto Scheduled | GTE Pass 1 | 0 | 0 | 0 | 0 | 0 | 0
153 | Yes | Auto Scheduled | GTE Pass 2 | 0 | 0 | 0 | 0 | 0 | 0
154 | Yes | Auto Scheduled | GTE Pass 3 | 0 | 0 | 0 | 0 | 0 | 0
155 | Yes | Auto Scheduled | Split shipment handling coding complete | 0 | 0 | 0 | 0 | 0 | 0
156 | Yes | Auto Scheduled | Support On_site Customer Collaboration | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
157 | Yes | Auto Scheduled | Support Business Process Improvements | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
158 | Yes | Auto Scheduled | Support Solution Validation and Installation | 0 | 0 | 0 | 0 | 0 | 0
159 | Yes | Auto Scheduled | Plan and Perform the Installation (For Each Environment As Needed: Training, Validation, etc.) | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Tech SME | 0 | 0 | 0 | 0 | 0 | 0
160 | Yes | Auto Scheduled | System deployed and available for local training | 0 | 0 | 0 | 0 | 0 | 0
161 | Yes | Auto Scheduled | Consulting Activities | 0 | 0 | 0 | 0 | 0 | 0
162 | Yes | Auto Scheduled | Implement agreed recommended processess and practices | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
163 | Yes | Auto Scheduled | Implementation of Organization structures related to Network Module | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
164 | Yes | Auto Scheduled | Business Training on how KPI's and Standard Performance Reports will be used | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
165 | Yes | Auto Scheduled | Perform the Solution Adoption End-of-Phase Review | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
166 | Yes | Auto Scheduled | Release 2 - Solution Adoption Phase Complete | 0 | 0 | 0 | 0 | 0 | 0
167 | Yes | Auto Scheduled | Release 2 - Project Transition Phase | 0 | 0 | 0 | 0 | 0 | 0
168 | Yes | Auto Scheduled | Perform Customer Validation and Training | 0 | 0 | 0 | 0 | 0 | 0
169 | Yes | Auto Scheduled | Support Customer Validation | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Tech SME | 0 | 0 | 0 | 0 | 0 | 0
170 | Yes | Auto Scheduled | Build Deployment and Soak (End to End) Testing | 0 | 0 | 0 | 0 | 0 | 0
171 | Yes | Auto Scheduled | Calibration Exercise | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre OR | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
172 | Yes | Auto Scheduled | Load Calibration and Cost data in EY Test build | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Adv Support | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Tech SME | 0 | 0 | 0 | 0 | 0 | 0
173 | Yes | Auto Scheduled | GET: CHAMP has deployed build into EY Test Environment | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
174 | Yes | Auto Scheduled | Train the Trainer classroom training for testers | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
175 | Yes | Auto Scheduled | Customer UVT | 0 | 0 | 0 | 0 | 0 | 0
176 | Yes | Auto Scheduled | UVT Base System Begin | 0 | 0 | 0 | 0 | 0 | 0
177 | Yes | Auto Scheduled | Air Vision Cargo Interface Integration Testing with Cargospot | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | CHAMP | 0 | 0 | 0 | 0 | 0 | 0
178 | Yes | Auto Scheduled | Soak Test - Parallel run (Test and Prod) | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | CHAMP | 0 | 0 | 0 | 0 | 0 | 0
179 | Yes | Auto Scheduled | Split Shipment Handling Code deployment | 0 | 0 | 0 | 0 | 0 | 0
180 | Yes | Auto Scheduled | Plan and Perform Split Shipment Handling code deployment | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
181 | Yes | Auto Scheduled | Validate build successfully deployed | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
182 | Yes | Auto Scheduled | Train the trainer classroom training for testers | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
183 | Yes | Auto Scheduled | Soak Test - Parallel run (Test and Prod) | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
184 | Yes | Auto Scheduled | UVT Base System End | 0 | 0 | 0 | 0 | 0 | 0
185 | Yes | Auto Scheduled | Go/No Go for Production Deployment | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Cargo | 0 | 0 | 0 | 0 | 0 | 0
186 | Yes | Auto Scheduled | Perform End-User Training | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
187 | Yes | Auto Scheduled | Consulting Activities | 0 | 0 | 0 | 0 | 0 | 0
188 | Yes | Auto Scheduled | Implement KPI monitoring and utliziation of Standard Performance Reports | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
189 | Yes | Auto Scheduled | Begin Performance Monitoring | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
190 | Yes | Auto Scheduled | Implement agree recommended processes and practices | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
191 | Yes | Auto Scheduled | End Performance Monitoring | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | SabreSME | 0 | 0 | 0 | 0 | 0 | 0
192 | Yes | Auto Scheduled | Present Performance Monitoring Results to Etihad | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
193 | Yes | Auto Scheduled | Perform Production Cutover and Support | 0 | 0 | 0 | 0 | 0 | 0
194 | Yes | Auto Scheduled | Plan Production Cutover | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Tech SME | 0 | 0 | 0 | 0 | 0 | 0
195 | Yes | Auto Scheduled | Perform Production Cutover | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre Tech SME | 0 | 0 | 0 | 0 | 0 | 0
196 | Yes | Auto Scheduled | Cutover to Production | 0 | 0 | 0 | 0 | 0 | 0
197 | Yes | Auto Scheduled | Perform Post-Cutover Customer Support | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
198 | Yes | Auto Scheduled | Transition to Customer Care | 0 | 0 | 0 | 0 | 0 | 0
199 | Yes | Auto Scheduled | Plan Customer Care Transition | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
200 | Yes | Auto Scheduled | Perform Customer Care Transition | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY IT | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre CC | 0 | 0 | 0 | 0 | 0 | 0
201 | Yes | Auto Scheduled | Perform Project Close-Out and Review | 0 | 0 | 0 | 0 | 0 | 0
202 | Yes | Auto Scheduled | Perform Project Close-Out | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
203 | Yes | Auto Scheduled | Perform Post-Project Review | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
204 | Yes | Auto Scheduled | Release 2 - Project Transition Phase Complete | 0 | 0 | 0 | 0 | 0 | 0
205 | Yes | Auto Scheduled | Project Management | 0 | 0 | 0 | 0 | 0 | 0
206 | Yes | Auto Scheduled | Project Planning | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre SME | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
207 | Yes | Auto Scheduled | Project Execution and Control | 0 | 0 | 0 | 0 | 0 | 0
208 | Yes | Auto Scheduled | Manage Project Scope | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
209 | Yes | Auto Scheduled | Manage Project Schedule | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
210 | Yes | Auto Scheduled | Manage Project Issues | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
211 | Yes | Auto Scheduled | Manage Project Risks | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
212 | Yes | Auto Scheduled | Manage Project Quality | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
213 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
214 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 1 | 0 | 0 | 0 | 0 | 0 | 0
215 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 2 | 0 | 0 | 0 | 0 | 0 | 0
216 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 3 | 0 | 0 | 0 | 0 | 0 | 0
217 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 4 | 0 | 0 | 0 | 0 | 0 | 0
218 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 5 | 0 | 0 | 0 | 0 | 0 | 0
219 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 6 | 0 | 0 | 0 | 0 | 0 | 0
220 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 7 | 0 | 0 | 0 | 0 | 0 | 0
221 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 8 | 0 | 0 | 0 | 0 | 0 | 0
222 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 9 | 0 | 0 | 0 | 0 | 0 | 0
223 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 10 | 0 | 0 | 0 | 0 | 0 | 0
224 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 11 | 0 | 0 | 0 | 0 | 0 | 0
225 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 12 | 0 | 0 | 0 | 0 | 0 | 0
226 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 13 | 0 | 0 | 0 | 0 | 0 | 0
227 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 14 | 0 | 0 | 0 | 0 | 0 | 0
228 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 15 | 0 | 0 | 0 | 0 | 0 | 0
229 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 16 | 0 | 0 | 0 | 0 | 0 | 0
230 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 17 | 0 | 0 | 0 | 0 | 0 | 0
231 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 18 | 0 | 0 | 0 | 0 | 0 | 0
232 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 19 | 0 | 0 | 0 | 0 | 0 | 0
233 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 20 | 0 | 0 | 0 | 0 | 0 | 0
234 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 21 | 0 | 0 | 0 | 0 | 0 | 0
235 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 22 | 0 | 0 | 0 | 0 | 0 | 0
236 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 23 | 0 | 0 | 0 | 0 | 0 | 0
237 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 24 | 0 | 0 | 0 | 0 | 0 | 0
238 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 25 | 0 | 0 | 0 | 0 | 0 | 0
239 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 26 | 0 | 0 | 0 | 0 | 0 | 0
240 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 27 | 0 | 0 | 0 | 0 | 0 | 0
241 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 28 | 0 | 0 | 0 | 0 | 0 | 0
242 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 29 | 0 | 0 | 0 | 0 | 0 | 0
243 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 30 | 0 | 0 | 0 | 0 | 0 | 0
244 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 31 | 0 | 0 | 0 | 0 | 0 | 0
245 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 32 | 0 | 0 | 0 | 0 | 0 | 0
246 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 33 | 0 | 0 | 0 | 0 | 0 | 0
247 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 34 | 0 | 0 | 0 | 0 | 0 | 0
248 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 35 | 0 | 0 | 0 | 0 | 0 | 0
249 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 36 | 0 | 0 | 0 | 0 | 0 | 0
250 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 37 | 0 | 0 | 0 | 0 | 0 | 0
251 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 38 | 0 | 0 | 0 | 0 | 0 | 0
252 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 39 | 0 | 0 | 0 | 0 | 0 | 0
253 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 40 | 0 | 0 | 0 | 0 | 0 | 0
254 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 41 | 0 | 0 | 0 | 0 | 0 | 0
255 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 42 | 0 | 0 | 0 | 0 | 0 | 0
256 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 43 | 0 | 0 | 0 | 0 | 0 | 0
257 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 44 | 0 | 0 | 0 | 0 | 0 | 0
258 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 45 | 0 | 0 | 0 | 0 | 0 | 0
259 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 46 | 0 | 0 | 0 | 0 | 0 | 0
260 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 47 | 0 | 0 | 0 | 0 | 0 | 0
261 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 48 | 0 | 0 | 0 | 0 | 0 | 0
262 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 49 | 0 | 0 | 0 | 0 | 0 | 0
263 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 50 | 0 | 0 | 0 | 0 | 0 | 0
264 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 51 | 0 | 0 | 0 | 0 | 0 | 0
265 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 52 | 0 | 0 | 0 | 0 | 0 | 0
266 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 53 | 0 | 0 | 0 | 0 | 0 | 0
267 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 54 | 0 | 0 | 0 | 0 | 0 | 0
268 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 55 | 0 | 0 | 0 | 0 | 0 | 0
269 | Yes | Auto Scheduled | Manage Project Scope, Schedule, Issues & Risks 56 | 0 | 0 | 0 | 0 | 0 | 0
270 | Yes | Auto Scheduled | Manage Delivery as an Integrated Portfolio | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
271 | Yes | Auto Scheduled | Manage Project Budget And Invoicing | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
272 | Yes | Auto Scheduled | Perform Project Metrics Tracking | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
273 | Yes | Auto Scheduled | Perform Project Status Reporting | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY Cargo | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
274 | Yes | Auto Scheduled | Perform Project Status Reporting 1 | 0 | 0 | 0 | 0 | 0 | 0
275 | Yes | Auto Scheduled | Perform Project Status Reporting 2 | 0 | 0 | 0 | 0 | 0 | 0
276 | Yes | Auto Scheduled | Perform Project Status Reporting 3 | 0 | 0 | 0 | 0 | 0 | 0
277 | Yes | Auto Scheduled | Perform Project Status Reporting 4 | 0 | 0 | 0 | 0 | 0 | 0
278 | Yes | Auto Scheduled | Perform Project Status Reporting 5 | 0 | 0 | 0 | 0 | 0 | 0
279 | Yes | Auto Scheduled | Perform Project Status Reporting 6 | 0 | 0 | 0 | 0 | 0 | 0
280 | Yes | Auto Scheduled | Perform Project Status Reporting 7 | 0 | 0 | 0 | 0 | 0 | 0
281 | Yes | Auto Scheduled | Perform Project Status Reporting 8 | 0 | 0 | 0 | 0 | 0 | 0
282 | Yes | Auto Scheduled | Perform Project Status Reporting 9 | 0 | 0 | 0 | 0 | 0 | 0
283 | Yes | Auto Scheduled | Perform Project Status Reporting 10 | 0 | 0 | 0 | 0 | 0 | 0
284 | Yes | Auto Scheduled | Perform Project Status Reporting 11 | 0 | 0 | 0 | 0 | 0 | 0
285 | Yes | Auto Scheduled | Perform Project Status Reporting 12 | 0 | 0 | 0 | 0 | 0 | 0
286 | Yes | Auto Scheduled | Perform Project Status Reporting 13 | 0 | 0 | 0 | 0 | 0 | 0
287 | Yes | Auto Scheduled | Perform Project Status Reporting 14 | 0 | 0 | 0 | 0 | 0 | 0
288 | Yes | Auto Scheduled | Perform Project Status Reporting 15 | 0 | 0 | 0 | 0 | 0 | 0
289 | Yes | Auto Scheduled | Perform Project Status Reporting 16 | 0 | 0 | 0 | 0 | 0 | 0
290 | Yes | Auto Scheduled | Perform Project Status Reporting 17 | 0 | 0 | 0 | 0 | 0 | 0
291 | Yes | Auto Scheduled | Perform Project Status Reporting 18 | 0 | 0 | 0 | 0 | 0 | 0
292 | Yes | Auto Scheduled | Perform Project Status Reporting 19 | 0 | 0 | 0 | 0 | 0 | 0
293 | Yes | Auto Scheduled | Perform Project Status Reporting 20 | 0 | 0 | 0 | 0 | 0 | 0
294 | Yes | Auto Scheduled | Perform Project Status Reporting 21 | 0 | 0 | 0 | 0 | 0 | 0
295 | Yes | Auto Scheduled | Perform Project Status Reporting 22 | 0 | 0 | 0 | 0 | 0 | 0
296 | Yes | Auto Scheduled | Perform Project Status Reporting 23 | 0 | 0 | 0 | 0 | 0 | 0
297 | Yes | Auto Scheduled | Perform Project Status Reporting 24 | 0 | 0 | 0 | 0 | 0 | 0
298 | Yes | Auto Scheduled | Perform Project Status Reporting 25 | 0 | 0 | 0 | 0 | 0 | 0
299 | Yes | Auto Scheduled | Perform Project Status Reporting 26 | 0 | 0 | 0 | 0 | 0 | 0
300 | Yes | Auto Scheduled | Perform Project Status Reporting 27 | 0 | 0 | 0 | 0 | 0 | 0
301 | Yes | Auto Scheduled | Perform Project Status Reporting 28 | 0 | 0 | 0 | 0 | 0 | 0
302 | Yes | Auto Scheduled | Perform Project Status Reporting 29 | 0 | 0 | 0 | 0 | 0 | 0
303 | Yes | Auto Scheduled | Perform Project Status Reporting 30 | 0 | 0 | 0 | 0 | 0 | 0
304 | Yes | Auto Scheduled | Perform Project Status Reporting 31 | 0 | 0 | 0 | 0 | 0 | 0
305 | Yes | Auto Scheduled | Perform Project Status Reporting 32 | 0 | 0 | 0 | 0 | 0 | 0
306 | Yes | Auto Scheduled | Perform Project Status Reporting 33 | 0 | 0 | 0 | 0 | 0 | 0
307 | Yes | Auto Scheduled | Perform Project Status Reporting 34 | 0 | 0 | 0 | 0 | 0 | 0
308 | Yes | Auto Scheduled | Perform Project Status Reporting 35 | 0 | 0 | 0 | 0 | 0 | 0
309 | Yes | Auto Scheduled | Perform Project Status Reporting 36 | 0 | 0 | 0 | 0 | 0 | 0
310 | Yes | Auto Scheduled | Perform Project Status Reporting 37 | 0 | 0 | 0 | 0 | 0 | 0
311 | Yes | Auto Scheduled | Perform Project Status Reporting 38 | 0 | 0 | 0 | 0 | 0 | 0
312 | Yes | Auto Scheduled | Perform Project Status Reporting 39 | 0 | 0 | 0 | 0 | 0 | 0
313 | Yes | Auto Scheduled | Perform Project Status Reporting 40 | 0 | 0 | 0 | 0 | 0 | 0
314 | Yes | Auto Scheduled | Perform Project Status Reporting 41 | 0 | 0 | 0 | 0 | 0 | 0
315 | Yes | Auto Scheduled | Perform Project Status Reporting 42 | 0 | 0 | 0 | 0 | 0 | 0
316 | Yes | Auto Scheduled | Perform Project Status Reporting 43 | 0 | 0 | 0 | 0 | 0 | 0
317 | Yes | Auto Scheduled | Perform Project Status Reporting 44 | 0 | 0 | 0 | 0 | 0 | 0
318 | Yes | Auto Scheduled | Perform Project Status Reporting 45 | 0 | 0 | 0 | 0 | 0 | 0
319 | Yes | Auto Scheduled | Perform Project Status Reporting 46 | 0 | 0 | 0 | 0 | 0 | 0
320 | Yes | Auto Scheduled | Perform Project Status Reporting 47 | 0 | 0 | 0 | 0 | 0 | 0
321 | Yes | Auto Scheduled | Perform Project Status Reporting 48 | 0 | 0 | 0 | 0 | 0 | 0
322 | Yes | Auto Scheduled | Perform Project Status Reporting 49 | 0 | 0 | 0 | 0 | 0 | 0
323 | Yes | Auto Scheduled | Perform Project Status Reporting 50 | 0 | 0 | 0 | 0 | 0 | 0
324 | Yes | Auto Scheduled | Perform Project Status Reporting 51 | 0 | 0 | 0 | 0 | 0 | 0
325 | Yes | Auto Scheduled | Perform Project Status Reporting 52 | 0 | 0 | 0 | 0 | 0 | 0
326 | Yes | Auto Scheduled | Perform Project Status Reporting 53 | 0 | 0 | 0 | 0 | 0 | 0
327 | Yes | Auto Scheduled | Perform Project Status Reporting 54 | 0 | 0 | 0 | 0 | 0 | 0
328 | Yes | Auto Scheduled | Perform Project Status Reporting 55 | 0 | 0 | 0 | 0 | 0 | 0
329 | Yes | Auto Scheduled | Perform Project Status Reporting 56 | 0 | 0 | 0 | 0 | 0 | 0
330 | Yes | Auto Scheduled | Perform Project Status Reporting | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
331 | Yes | Auto Scheduled | Perform Project Steering | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Stakeholders | 0 | 0 | 0 | 0 | 0 | 0
332 | Yes | Auto Scheduled | Manage Project Stakeholder Communications | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0
333 | Yes | Auto Scheduled | Project Closure | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | Sabre PM | 0 | 0 | 0 | 0 | 0 | 0
0 | Yes |  | EY PM | 0 | 0 | 0 | 0 | 0 | 0

## Resource_Costs
Actual_Cost | Actual_Work | Assignment_Owner
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 1,046h
0 | 8h
0 | 8h
0 | 8h
0 | 24h
0 | 24h
0 | 8h
0 | 8h
0 | 8h
0 | 64h
0 | 64h
0 | 16h
0 | 24h
0 | 0h
0 | 56h
0 | 8h
0 | 16h
0 | 30h
0 | 8h
0 | 8h
0 | 288h
0 | 8h
0 | 16h
0 | 8h
0 | 272h
0 | 16h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 8h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 40h
0 | 280h
0 | 8h
0 | 8h
0 | 8h
0 | 8h
0 | 136h
0 | 24h
0 | 24h
0 | 64h
0 | 0h
0 | 0h
0 | 1,079.4h
0 | 24h
0 | 120h
0 | 240h
0 | 40h
0 | 5.33h
0 | 8h
0 | 12.07h
0 | 0h
0 | 0h
0 | 0h
0 | 8h
0 | 8h
0 | 0h
0 | 0h
0 | 64h
0 | 16h
0 | 24h
0 | 0h
0 | 56h
0 | 8h
0 | 16h
0 | 30h
0 | 8h
0 | 8h
0 | 288h
0 | 8h
0 | 16h
0 | 8h
0 | 8h
0 | 0h
0 | 0h
0 | 8h
0 | 0h
0 | 8h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 40h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 325.03h
0 | 8h
0 | 8h
0 | 8h
0 | 8h
0 | 24h
0 | 24h
0 | 0h
0 | 8h
0 | 0h
0 | 56h
0 | 8h
0 | 16h
0 | 30h
0 | 8h
0 | 8h
0 | 16h
0 | 8h
0 | 16h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 8h
0 | 47.03h
0 | 8h
0 | 0h
0 | 8h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 56h
0 | 24h
0 | 24h
0 | 0h
0 | 8h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 190h
0 | 152h
0 | 38h
0 | 24h
0 | 8h
0 | 16h
0 | 0h
0 | 54h
0 | 24h
0 | 0h
0 | 30h
0 | 0h
0 | 0h
0 | 0h
0 | 713.4h
0 | 240h
0 | 80h
0 | 40h
0 | 5.33h
0 | 12.07h
0 | 0h
0 | 0h
0 | 112h
0 | 8h
0 | 96h
0 | 112h
0 | 8h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 56h
0 | 8h
0 | 8h
0 | 8h
0 | 8h
0 | 8h
0 | 8h
0 | 8h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 80h
0 | 80h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 79.03h
0 | 8h
0 | 8h
0 | 16h
0 | 47.03h
0 | 0h
0 | 0h
0 | 0h
0 | 288h
0 | 176h
0 | 0h
0 | 0h
0 | 8h
0 | 16h
0 | 8h
0 | 8h
0 | 16h
0 | 8h
0 | 8h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 40h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 8h
0 | 8h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 8h
0 | 8h
0 | 0h
0 | 0h
0 | 17.4h
0 | 5.33h
0 | 12.07h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h
0 | 0h

## Assignment_Costs
Resource_Name | Actual_Cost
Sabre OR | 0
EY Cargo | 0
Sabre Cargo | 0
Sabre OR | 0
Sabre SME | 0
EY Cargo | 0
Sabre OR | 0
Sabre SME | 0
EY Cargo | 0
Sabre OR | 0
Sabre SME | 0
EY Cargo | 0
Sabre OR | 0
Sabre OR | 0
Sabre SME | 0
Sabre PM | 0
EY Cargo | 0
EY IT | 0
CHAMP | 0
Sabre OR | 0
Sabre SME | 0
EY Cargo | 0
EY IT | 0
Sabre PM | 0
Sabre PM & SME | 0
Sabre PM & SME | 0
Sabre Dev | 0
Sabre PM | 0
Sabre GTE | 0
Sabre Dev | 0
Sabre PM | 0
Sabre Dev | 0
Sabre PM | 0
Sabre Dev | 0
Sabre Pgrm Mgr | 0
Sabre PM | 0
Sabre SME | 0
EY PM | 0
Sabre PM | 0
Sabre Dev | 0
Sabre Pgrm Mgr | 0
Sabre PM | 0
Sabre Dev | 0
Sabre Pgrm Mgr | 0
Sabre PM | 0
Sabre Pgrm Mgr | 0
EY Cargo | 0
EY IT | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
Sabre SME | 0
Sabre SME | 0
Sabre PM | 0
EY Cargo | 0
EY IT | 0
EY IT PM | 0
Stakeholders | 0
Sabre PM | 0
Sabre PM | 0
EY PM | 0
Sabre SME | 0
Sabre OR | 0
Sabre PM | 0
Sabre SME | 0
Sabre PM | 0
Sabre SME | 0
Sabre PM | 0
Sabre SME | 0
Sabre PM | 0
Sabre SME | 0
Sabre Solutions | 0
EY Cargo | 0
EY IT | 0
CHAMP | 0
Sabre PM | 0
Sabre SME | 0
EY Cargo | 0
Sabre PM | 0
Sabre SME | 0
EY Cargo | 0
EY PM | 0
Sabre PM | 0
Sabre SME | 0
EY Cargo | 0
EY PM | 0
Sabre PM | 0
Sabre SME | 0
EY Cargo | 0
CHAMP | 0
Sabre PM | 0
Sabre SME | 0
EY Cargo | 0
EY PM | 0
Sabre PM | 0
Sabre SME | 0
EY Cargo | 0
EY PM | 0
Sabre PM | 0
Sabre SME | 0
Sabre PM | 0
Sabre SME | 0
Sabre PM | 0
Sabre SME | 0
EY Cargo | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
Sabre SME | 0
EY Cargo | 0
Sabre SME | 0
Sabre SME | 0
EY Cargo | 0
Sabre PM | 0
EY PM | 0
Sabre SME | 0
EY Cargo | 0
Sabre SME | 0
EY Cargo | 0
Sabre SME | 0
EY Caargo | 0
Sabre SME | 0
EY Cargo | 0
Sabre PM | 0
Sabre SME | 0
EY Cargo | 0
EY PM | 0
Sabre PM | 0
EY Cargo & IT | 0
Sabre Cargo | 0
EY Cargo & IT | 0
Sabre Cargo | 0
EY Cargo | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre Agile Customer | 0
Sabre GTE | 0
Sabre Dev | 0
EY Cargo | 0
Sabre Cargo | 0
Sabre Dev | 0
EY Cargo | 0
Sabre PM | 0
Sabre SME | 0
Sabre Dev | 0
Sabre PM | 0
EY Cargo | 0
Sabre Dev | 0
Sabre Dev | 0
Sabre Dev | 0
Sabre PM | 0
EY Cargo | 0
Sabre PM | 0
EY Cargo | 0
Sabre Dev | 0
Sabre Dev | 0
Sabre Dev | 0
Sabre SME | 0
Sabre PM | 0
EY Cargo | 0
Sabre | 0
EY Cargo & IT | 0
Sabre Dev | 0
Sabre Dev | 0
CHAMP | 0
Sabre Dev | 0
Sabre GTE | 0
Sabre Dev | 0
Sabre Dev | 0
Sabre GTE | 0
Sabre GTE | 0
EY Test | 0
Sabre GTE | 0
EY Test | 0
Sabre SME | 0
Sabre PM | 0
Sabre SME | 0
Sabre PM | 0
Sabre Tech SME | 0
Sabre SME | 0
EY Cargo | 0
Sabre SME | 0
EY Cargo | 0
Sabre SME | 0
EY Cargo | 0
Sabre Cargo | 0
EY Cargo | 0
EY PM | 0
Sabre Tech SME | 0
Sabre SME | 0
Sabre OR | 0
Sabre OR | 0
Sabre SME | 0
EY Cargo | 0
EY IT | 0
Sabre Adv Support | 0
Sabre Tech SME | 0
EY IT | 0
Sabre PM | 0
Sabre SME | 0
EY Cargo | 0
EY Cargo | 0
EY IT | 0
CHAMP | 0
Sabre SME | 0
Sabre SME | 0
EY Cargo | 0
EY IT | 0
CHAMP | 0
Sabre SME | 0
EY IT | 0
Sabre SME | 0
EY IT | 0
Sabre SME | 0
EY Cargo | 0
EY Cargo | 0
EY | 0
IT | 0
Sabre SME | 0
Sabre PM | 0
Sabre Cargo | 0
EY Cargo | 0
EY IT | 0
Sabre SME | 0
EY Cargo | 0
Sabre SME | 0
EY Cargo | 0
Sabre SME | 0
EY Cargo | 0
Sabre SME | 0
EY Cargo | 0
SabreSME | 0
Sabre SME | 0
EY Cargo | 0
Sabre Tech SME | 0
Sabre PM | 0
EY IT | 0
EY Cargo | 0
Sabre Tech SME | 0
EY IT | 0
Sabre SME | 0
Sabre PM | 0
Sabre PM | 0
Sabre CC | 0
EY Cargo | 0
EY IT | 0
Sabre PM | 0
EY PM | 0
EY Cargo | 0
Sabre PM | 0
EY PM | 0
EY Cargo | 0
Sabre PM | 0
EY PM | 0
Sabre SME | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
EY Cargo | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
EY Cargo | 0
Sabre PM | 0
EY PM | 0
Stakeholders | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0
Sabre PM | 0
EY PM | 0