## All_Tasks
Overdue_Flag | Project_Status | Expected_Percent_Complete | Percent_Complete | Late_Finish | Project_Manager | Task_Name | Start_Date | Finish_Date | Actual_Start | Actual_Finish | Baseline_Start | Baseline_Finish | Red_Overdue_Reason | Action_Planned_Required | Red_Action_Due_Date | Red_Action_Risk_if_not_complete | Summary | External_Task | Critical | Workstream | Sub_Program_Name | Life_Cycle
| Red | 100% | 0.23000000000000001 | 6/11/2014 3:00:00 PM |  | Etihad Airways-Cargo Master Schedule | 2/1/2011 8:00:00 AM | 6/11/2014 3:00:00 PM | 2/1/2011 8:00:00 AM | 12:00:00 AM | 2/1/2011 8:00:00 AM | 6/11/2014 3:00:00 PM |  |  |  |  | Yes | No | Yes
| Red | 100% | 0.23999999999999999 | 6/11/2014 3:00:00 PM |  | Etihad Airways - AirVision Cargo - Network Module Implementation | 2/1/2011 8:00:00 AM | 6/11/2014 3:00:00 PM | 2/1/2011 8:00:00 AM | 12:00:00 AM | 2/1/2011 8:00:00 AM | 6/11/2014 3:00:00 PM |  |  |  |  | Yes | No | Yes
Overdue | No BL | 100% | 0.25 | 6/11/2014 3:00:00 PM |  | Release 2 - Etihad AirVision Cargo - Network Module Implementation | 2/1/2011 8:00:00 AM | 6/11/2014 3:00:00 PM | 2/1/2011 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | Yes
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Release 2 Due Diligence | 2/1/2011 8:00:00 AM | 2/2/2012 5:00:00 PM | 2/1/2011 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
| Complete | 100% | 1 | 2/1/2011 5:00:00 PM |  | Proof of Concept | 2/1/2011 8:00:00 AM | 2/1/2011 5:00:00 PM | 2/1/2011 8:00:00 AM | 2/1/2011 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Define Target Baseline Proof of Concept Accuracy | 2/1/2011 8:00:00 AM | 2/2/2012 5:00:00 PM | 2/1/2011 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 2/1/2011 5:00:00 PM |  | O&D Accuracy - 25% Error | 2/1/2011 8:00:00 AM | 2/1/2011 5:00:00 PM | 2/1/2011 8:00:00 AM | 2/1/2011 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Leg Accuracy - 12% Error | 2/2/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 2/2/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 3/24/2011 5:00:00 PM |  | Inputs criteria complete | 2/15/2011 8:00:00 AM | 3/24/2011 5:00:00 PM | 2/15/2011 8:00:00 AM | 3/24/2011 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 3/25/2011 5:00:00 PM |  | Methodology acceptance | 3/25/2011 8:00:00 AM | 3/25/2011 5:00:00 PM | 3/25/2011 8:00:00 AM | 3/25/2011 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 4/19/2011 5:00:00 PM |  | Perform Simluation of Network Module | 3/27/2011 8:00:00 AM | 4/19/2011 5:00:00 PM | 3/27/2011 8:00:00 AM | 4/19/2011 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 5/18/2011 5:00:00 PM |  | Define to-be end-to-end business process | 5/15/2011 8:00:00 AM | 5/18/2011 5:00:00 PM | 5/15/2011 8:00:00 AM | 5/18/2011 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 5/18/2011 5:00:00 PM |  | Define Acceptance Criteria for end to end | 5/15/2011 8:00:00 AM | 5/18/2011 5:00:00 PM | 5/15/2011 8:00:00 AM | 5/18/2011 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0.29999999999999999 | 6/11/2014 3:00:00 PM |  | Release 2 - Re-Engagement (Initiation) Phase | 1/2/2012 8:00:00 AM | 1/16/2014 3:00:00 PM | 1/2/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0.97999999999999998 | 6/11/2014 3:00:00 PM |  | Perform Project Set-Up Activities | 1/2/2012 8:00:00 AM | 3/2/2012 5:00:00 PM | 1/2/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 3/2/2012 5:00:00 PM |  | Establish Project/Accounting Codes in Central Systems | 2/13/2012 8:00:00 AM | 3/2/2012 5:00:00 PM | 2/13/2012 8:00:00 AM | 3/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0.94999999999999996 | 6/11/2014 12:00:00 PM |  | Create Project Definition Document | 1/30/2012 8:00:00 AM | 2/24/2012 5:00:00 PM | 1/30/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0.94999999999999996 | 6/11/2014 3:00:00 PM |  | Create Project Processes & Procedures Document | 2/27/2012 8:00:00 AM | 3/2/2012 5:00:00 PM | 2/27/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 2/10/2012 5:00:00 PM |  | Negotiate Development Commitments | 1/2/2012 8:00:00 AM | 2/10/2012 5:00:00 PM | 1/2/2012 8:00:00 AM | 2/10/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 1/13/2012 5:00:00 PM |  | Negotiate Testing Commitments | 1/2/2012 8:00:00 AM | 1/13/2012 5:00:00 PM | 1/2/2012 8:00:00 AM | 1/13/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0.12 | 6/11/2014 3:00:00 PM |  | Create Project Schedule | 2/2/2012 8:00:00 AM | 1/16/2014 3:00:00 PM | 2/2/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 2/8/2012 5:00:00 PM |  | Create High Level Initial Project Schedule | 2/2/2012 8:00:00 AM | 2/8/2012 5:00:00 PM | 2/2/2012 8:00:00 AM | 2/8/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 2/21/2012 5:00:00 PM |  | Perform Internal High-Level Project Schedule Review | 2/16/2012 8:00:00 AM | 2/21/2012 5:00:00 PM | 2/16/2012 8:00:00 AM | 2/21/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 2/22/2012 5:00:00 PM |  | Perform Client High-Level Project Schedule Review | 2/22/2012 8:00:00 AM | 2/22/2012 5:00:00 PM | 2/22/2012 8:00:00 AM | 2/22/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 3/22/2012 5:00:00 PM |  | Confirm Client and Client Subcontractor Commitments | 2/23/2012 8:00:00 AM | 3/22/2012 5:00:00 PM | 2/23/2012 8:00:00 AM | 3/22/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0.01 | 9/4/2013 3:00:00 PM |  | Finalize Project Schedule | 3/23/2012 8:00:00 AM | 4/11/2013 3:00:00 PM | 3/23/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0 | 9/9/2013 3:00:00 PM |  | Perform Internal Detail-Level Project Schedule Review | 4/12/2013 3:00:00 PM | 4/16/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Client Detail-Level Project Schedule Review | 1/15/2014 3:00:00 PM | 1/16/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Baseline Project Schedule | 1/16/2014 3:00:00 PM | 1/16/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0.25 | 6/11/2014 3:00:00 PM |  | Perform Project Kick-Off | 1/23/2012 8:00:00 AM | 5/10/2013 3:00:00 PM | 1/23/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0.25 | 6/11/2014 3:00:00 PM |  | Plan and Perform Customer Project Kick-Off | 1/23/2012 8:00:00 AM | 5/10/2013 3:00:00 PM | 1/23/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 1/23/2012 5:00:00 PM |  | Plan and Perform Customer Project Kick-Off | 1/23/2012 8:00:00 AM | 1/23/2012 5:00:00 PM | 1/23/2012 8:00:00 AM | 1/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
| Complete | 100% | 1 | 1/23/2012 5:00:00 PM |  | Communicate to Stakeholders | 1/23/2012 8:00:00 AM | 1/23/2012 5:00:00 PM | 1/23/2012 8:00:00 AM | 1/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Establish Initial Customer Access to Community Portal | 5/3/2013 3:00:00 PM | 5/10/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Create Communication Plan | 5/2/2013 3:00:00 PM | 5/3/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Re-Engagement Complete | 1/16/2014 3:00:00 PM | 1/16/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Iniation
Overdue | No BL | 100% | 0.68999999999999995 | 6/11/2014 3:00:00 PM |  | Release 2 - Interactive Pilot Phase | 1/16/2012 8:00:00 AM | 3/31/2014 3:00:00 PM | 1/16/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Interave Pilot
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Perform Interactive Pilot Assessment | 1/24/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 1/24/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Perform Data Collection | 1/24/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 1/24/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Plan and Perform Interactive Pilot Assessment | 1/24/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 1/24/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 1/20/2012 5:00:00 PM |  | Plan Interactive Pilot Workshops | 1/16/2012 8:00:00 AM | 1/20/2012 5:00:00 PM | 1/16/2012 8:00:00 AM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 1/17/2012 5:00:00 PM |  | Plan and Schedule Interactive Pilot Workshops | 1/16/2012 8:00:00 AM | 1/17/2012 5:00:00 PM | 1/16/2012 8:00:00 AM | 1/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 1/20/2012 5:00:00 PM |  | Prepare Interactive Pilot Workshop Components | 1/18/2012 8:00:00 AM | 1/20/2012 5:00:00 PM | 1/18/2012 8:00:00 AM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Conduct Initial Training | 1/31/2014 3:00:00 PM | 2/6/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Conduct Initial Training (Key User / Train the Trainer) | 1/31/2014 3:00:00 PM | 2/6/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Perform Interactive Pilot Workshops | 1/23/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 1/23/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Perform Interactive Pilot Workshops | 1/25/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 1/25/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Finalize Interactive Pilot Workshops | 2/2/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 2/2/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Interactive Pilot Workshops | 1/23/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 1/23/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 1/24/2012 5:00:00 PM |  | BRD Review Session | 1/23/2012 8:00:00 AM | 1/24/2012 5:00:00 PM | 1/23/2012 8:00:00 AM | 1/24/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 1/31/2012 5:00:00 PM |  | Scenario based process wak-throughs | 1/25/2012 8:00:00 AM | 1/31/2012 5:00:00 PM | 1/25/2012 8:00:00 AM | 1/31/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 2/1/2012 5:00:00 PM |  | Risk Register Creation | 2/1/2012 8:00:00 AM | 2/1/2012 5:00:00 PM | 2/1/2012 8:00:00 AM | 2/1/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 2/2/2012 5:00:00 PM |  | Deliverable Definition | 2/2/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 2/2/2012 8:00:00 AM | 2/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 3/23/2012 5:00:00 PM |  | Create IPA Report | 2/6/2012 8:00:00 AM | 3/23/2012 5:00:00 PM | 2/6/2012 8:00:00 AM | 3/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 3/26/2012 5:00:00 PM |  | Present IPA Report | 3/26/2012 8:00:00 AM | 3/26/2012 5:00:00 PM | 3/26/2012 8:00:00 AM | 3/26/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 3/28/2012 5:00:00 PM |  | Joint Review of IPA Report | 3/27/2012 8:00:00 AM | 3/28/2012 5:00:00 PM | 3/27/2012 8:00:00 AM | 3/28/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 3/29/2012 5:00:00 PM |  | Publish Final Version of IPA Report | 3/29/2012 8:00:00 AM | 3/29/2012 5:00:00 PM | 3/29/2012 8:00:00 AM | 3/29/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0.45000000000000001 | 3/11/2014 3:00:00 PM |  | Consulting Activites | 2/1/2012 8:00:00 AM | 2/11/2014 3:00:00 PM | 2/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 2/1/2012 5:00:00 PM |  | On-site Interviews with Pricing Analyst | 2/1/2012 8:00:00 AM | 2/1/2012 5:00:00 PM | 2/1/2012 8:00:00 AM | 2/1/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 3/26/2012 5:00:00 PM |  | Create Organization, Functional and Policy & Procedures recommendations based on Network Module | 2/9/2012 8:00:00 AM | 3/26/2012 5:00:00 PM | 2/9/2012 8:00:00 AM | 3/26/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 3/28/2012 5:00:00 PM |  | Reivew Recommendations with Etihad Cargo | 3/27/2012 8:00:00 AM | 3/28/2012 5:00:00 PM | 3/27/2012 8:00:00 AM | 3/28/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
| Complete | 100% | 1 | 3/29/2012 5:00:00 PM |  | Pulbish Final Recommendations | 3/29/2012 8:00:00 AM | 3/29/2012 5:00:00 PM | 3/29/2012 8:00:00 AM | 3/29/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0 | 2/11/2014 3:00:00 PM |  | Create KPI's for Network Module | 11/22/2013 3:00:00 PM | 1/14/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0 | 3/11/2014 3:00:00 PM |  | Review and Finalize KPI's for Network Module | 2/6/2014 3:00:00 PM | 2/11/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0 | 3/7/2014 3:00:00 PM |  | Determine Make-up of Standard Performance Reports | 1/14/2014 3:00:00 PM | 1/21/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0 | 3/11/2014 3:00:00 PM |  | Review KPI's and Standard Performance Reports with EY | 1/21/2014 3:00:00 PM | 1/23/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform the Interactive Pilot End-of-Phase Review | 3/28/2014 3:00:00 PM | 3/31/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Release 2 - Interactive Pilot Phase Complete | 3/31/2014 3:00:00 PM | 3/31/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Interactive Pilot
Overdue | No BL | 100% | 0.13 | 6/11/2014 3:00:00 PM |  | Release 2 - Solution Adoption Phase | 1/24/2012 8:00:00 AM | 5/14/2014 3:00:00 PM | 1/24/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 2/29/2012 5:00:00 PM |  | Support Solution Definition and Design | 1/24/2012 8:00:00 AM | 2/29/2012 5:00:00 PM | 1/24/2012 8:00:00 AM | 2/29/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 2/29/2012 5:00:00 PM |  | Support Detailed Solution Definition | 2/29/2012 8:00:00 AM | 2/29/2012 5:00:00 PM | 2/29/2012 8:00:00 AM | 2/29/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 1/26/2012 5:00:00 PM |  | Support Detailed Solution Design | 1/24/2012 8:00:00 AM | 1/26/2012 5:00:00 PM | 1/24/2012 8:00:00 AM | 1/26/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 1/25/2012 5:00:00 PM |  | Determine New GUI Screen Field Details | 1/24/2012 8:00:00 AM | 1/25/2012 5:00:00 PM | 1/24/2012 8:00:00 AM | 1/25/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 1/26/2012 5:00:00 PM |  | Signoff from customer on GUI Fields | 1/26/2012 8:00:00 AM | 1/26/2012 5:00:00 PM | 1/26/2012 8:00:00 AM | 1/26/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0.13 | 6/11/2014 3:00:00 PM |  | Support Solution Build-Out | 3/1/2012 8:00:00 AM | 2/11/2014 3:00:00 PM | 3/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0.28000000000000003 | 6/11/2014 3:00:00 PM |  | Support Iteration Planning | 3/1/2012 8:00:00 AM | 3/25/2013 5:00:00 PM | 3/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 3/1/2012 5:00:00 PM |  | Support Iteration Planning 1 | 3/1/2012 8:00:00 AM | 3/1/2012 5:00:00 PM | 3/1/2012 8:00:00 AM | 3/1/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 3/15/2012 5:00:00 PM |  | Support Iteration Planning 2 | 3/15/2012 8:00:00 AM | 3/15/2012 5:00:00 PM | 3/15/2012 8:00:00 AM | 3/15/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 3/30/2012 5:00:00 PM |  | Support Iteration Planning 3 | 3/30/2012 8:00:00 AM | 3/30/2012 5:00:00 PM | 3/30/2012 8:00:00 AM | 3/30/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 4/16/2012 5:00:00 PM |  | Support Iteration Planning 4 | 4/16/2012 8:00:00 AM | 4/16/2012 5:00:00 PM | 4/16/2012 8:00:00 AM | 4/16/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 5/1/2012 5:00:00 PM |  | Support Iteration Planning 5 | 5/1/2012 8:00:00 AM | 5/1/2012 5:00:00 PM | 5/1/2012 8:00:00 AM | 5/1/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 5/16/2012 5:00:00 PM |  | Support Iteration Planning 6 | 5/16/2012 8:00:00 AM | 5/16/2012 5:00:00 PM | 5/16/2012 8:00:00 AM | 5/16/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 5/31/2012 5:00:00 PM |  | Support Iteration Planning 7 | 5/31/2012 8:00:00 AM | 5/31/2012 5:00:00 PM | 5/31/2012 8:00:00 AM | 5/31/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 9/23/2013 3:00:00 PM |  | Support Iteration Planning 8 | 6/15/2012 8:00:00 AM | 6/15/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 10/8/2013 3:00:00 PM |  | Support Iteration Planning 9 | 7/2/2012 8:00:00 AM | 7/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 10/23/2013 3:00:00 PM |  | Support Iteration Planning 10 | 7/17/2012 8:00:00 AM | 7/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 11/7/2013 3:00:00 PM |  | Support Iteration Planning 11 | 8/1/2012 8:00:00 AM | 8/1/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 11/22/2013 3:00:00 PM |  | Support Iteration Planning 12 | 8/16/2012 8:00:00 AM | 8/16/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 12/9/2013 3:00:00 PM |  | Support Iteration Planning 13 | 8/31/2012 8:00:00 AM | 8/31/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 12/24/2013 3:00:00 PM |  | Support Iteration Planning 14 | 9/17/2012 8:00:00 AM | 9/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 1/8/2014 3:00:00 PM |  | Support Iteration Planning 15 | 10/2/2012 8:00:00 AM | 10/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 1/23/2014 3:00:00 PM |  | Support Iteration Planning 16 | 10/17/2012 8:00:00 AM | 10/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 2/7/2014 3:00:00 PM |  | Support Iteration Planning 17 | 11/1/2012 8:00:00 AM | 11/1/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 2/24/2014 3:00:00 PM |  | Support Iteration Planning 18 | 11/16/2012 8:00:00 AM | 11/16/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 3/11/2014 3:00:00 PM |  | Support Iteration Planning 19 | 12/7/2012 8:00:00 AM | 12/7/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 3/26/2014 3:00:00 PM |  | Support Iteration Planning 20 | 1/7/2013 8:00:00 AM | 1/7/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/10/2014 3:00:00 PM |  | Support Iteration Planning 21 | 1/22/2013 8:00:00 AM | 1/22/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/25/2014 3:00:00 PM |  | Support Iteration Planning 22 | 2/6/2013 8:00:00 AM | 2/6/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/12/2014 3:00:00 PM |  | Support Iteration Planning 23 | 2/21/2013 8:00:00 AM | 2/21/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/27/2014 3:00:00 PM |  | Support Iteration Planning 24 | 3/8/2013 8:00:00 AM | 3/8/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Support Iteration Planning 25 | 3/25/2013 8:00:00 AM | 3/25/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Support Iteration and Release Planning | 3/1/2012 8:00:00 AM | 3/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Support Iteration Development / Testing | 3/1/2012 8:00:00 AM | 3/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0.13 | 9/3/2013 3:00:00 PM |  | Air Vision Cargo Network Module Development Work | 3/12/2012 8:00:00 AM | 8/27/2013 3:00:00 PM | 3/12/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 8.9999999999999997E-2 | 5/2/2013 3:00:00 PM |  | GUI Design and Cost Module Changes pt I | 3/12/2012 8:00:00 AM | 4/23/2013 8:57:36 AM | 3/12/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/2/2013 3:00:00 PM |  | Design GUI Screens | 6/20/2012 8:00:00 AM | 8/6/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0.02 | 5/2/2013 3:00:00 PM |  | Cost Module Changes pt I | 3/12/2012 8:00:00 AM | 4/23/2013 8:57:36 AM | 3/12/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 4/11/2012 5:00:00 PM |  | Booking evaluation changes | 3/30/2012 8:00:00 AM | 4/11/2012 5:00:00 PM | 3/30/2012 8:00:00 AM | 4/11/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 5/1/2012 5:00:00 PM |  | Request build and internal testing | 4/12/2012 8:00:00 AM | 5/1/2012 5:00:00 PM | 4/12/2012 8:00:00 AM | 5/1/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 5/2/2012 5:00:00 PM |  | Workshop to demo new screens | 5/2/2012 8:00:00 AM | 5/2/2012 5:00:00 PM | 5/2/2012 8:00:00 AM | 5/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 5/2/2012 8:00:00 AM |  | New Screen Demonstration to Etihad | 5/2/2012 8:00:00 AM | 5/2/2012 8:00:00 AM | 5/2/2012 8:00:00 AM | 5/2/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 5/2/2012 8:00:00 AM |  | Give: Etihad Screen Shot and Cost Module Screen Demos screenshots | 5/2/2012 8:00:00 AM | 5/2/2012 8:00:00 AM | 5/2/2012 8:00:00 AM | 5/2/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 5/8/2012 5:00:00 PM |  | Get: Etihad sign off on screen design | 5/8/2012 5:00:00 PM | 5/8/2012 5:00:00 PM | 5/8/2012 5:00:00 PM | 5/8/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0.98999999999999999 | 5/2/2013 3:00:00 PM |  | Cost Module Changes pt II | 4/12/2012 8:00:00 AM | 6/13/2012 5:00:00 PM | 4/12/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 4/27/2012 5:00:00 PM |  | Cost Module Changes pt II | 4/12/2012 8:00:00 AM | 4/27/2012 5:00:00 PM | 4/12/2012 8:00:00 AM | 4/27/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 5/17/2012 5:00:00 PM |  | Booking Evaluation changes | 4/30/2012 8:00:00 AM | 5/17/2012 5:00:00 PM | 4/30/2012 8:00:00 AM | 5/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 6/6/2012 5:00:00 PM |  | Request Build and internal testing | 5/18/2012 8:00:00 AM | 6/6/2012 5:00:00 PM | 5/18/2012 8:00:00 AM | 6/6/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 6/7/2012 5:00:00 PM |  | Workshop to demo Cost Module changes | 6/7/2012 8:00:00 AM | 6/7/2012 5:00:00 PM | 6/7/2012 8:00:00 AM | 6/7/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
| Complete | 100% | 1 | 6/7/2012 8:00:00 AM |  | Cost Module Demonstration | 6/7/2012 8:00:00 AM | 6/7/2012 8:00:00 AM | 6/7/2012 8:00:00 AM | 6/7/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/25/2013 3:00:00 PM |  | Give: Etihad Cost Module Screen Changes pt II screen shots | 6/7/2012 8:00:00 AM | 6/7/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/2/2013 3:00:00 PM |  | Get: Etihad sign off on cost module screen designs and calcuatlations | 6/13/2012 5:00:00 PM | 6/13/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 5.0000000000000003E-2 | 5/2/2013 3:00:00 PM |  | Network Module Booking Evaluation & Cost Module pt III | 5/18/2012 8:00:00 AM | 5/2/2013 3:00:00 PM | 5/18/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0.40000000000000002 | 6/4/2012 5:00:00 PM |  | Cost Module changes pt III | 5/18/2012 8:00:00 AM | 6/4/2012 5:00:00 PM | 5/18/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/19/2012 5:00:00 PM |  | Modify internal booking evaluation processes | 6/8/2012 8:00:00 AM | 6/19/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 7/11/2012 5:00:00 PM |  | Modifed Bid Price Find Screen | 6/20/2012 8:00:00 AM | 7/11/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 8/28/2012 5:00:00 PM |  | Request build and internal testing | 8/7/2012 8:00:00 AM | 8/28/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/24/2013 3:00:00 PM |  | Workshop to demo Booking evaluation changes | 4/23/2013 3:00:00 PM | 4/24/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/23/2013 3:00:00 PM |  | Booking Evaluatoin Demonstration | 4/23/2013 3:00:00 PM | 4/23/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/23/2013 3:00:00 PM |  | Give: Etihad recording of Booking Evaluation changes demon for signoff | 4/23/2013 3:00:00 PM | 4/23/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/2/2013 3:00:00 PM |  | Get: Etihad signoff on booking evaluation process changes | 5/2/2013 3:00:00 PM | 5/2/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/18/2013 3:00:00 PM |  | Cost Module and Network Module GUI | 7/12/2012 8:00:00 AM | 9/14/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 3/1/2013 5:00:00 PM |  | Cost Module pt IV | 7/12/2012 8:00:00 AM | 8/13/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 3/15/2013 5:00:00 PM |  | Network Module GUI | 8/14/2012 8:00:00 AM | 8/27/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/18/2013 3:00:00 PM |  | Request build and internal testing | 8/28/2012 8:00:00 AM | 9/14/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/19/2013 3:00:00 PM |  | Workshop to demo Cost Module and GUI changes | 9/17/2012 8:00:00 AM | 9/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/18/2013 3:00:00 PM |  | Cost Module Demonstration | 9/17/2012 8:00:00 AM | 9/17/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/2/2013 3:00:00 PM |  | Give: Etihad Cost and GUI Screen Changes | 9/17/2012 8:00:00 AM | 9/17/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/2/2013 3:00:00 PM |  | Get: Etihad signoff on cost module and NM GUI changes | 9/28/2012 5:00:00 PM | 9/28/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/2/2013 3:00:00 PM |  | Network Module Interfaces and Technology Changes | 8/29/2012 8:00:00 AM | 10/12/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/12/2013 3:00:00 PM |  | Create Booking Evaluation Interfaces | 8/29/2012 8:00:00 AM | 9/24/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/12/2013 3:00:00 PM |  | Get: Sample "Booking Evaluation Call" and "Request for Additional Call" messages from CHAMP | 9/24/2012 5:00:00 PM | 9/24/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/16/2013 3:00:00 PM |  | Test sample messages received from CHAMP | 9/25/2012 8:00:00 AM | 9/26/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 4/22/2013 3:00:00 PM |  | Air Vision Cargo Technology changes (does not include Oracle changes) | 9/27/2012 8:00:00 AM | 10/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/2/2013 3:00:00 PM |  | Final build and fixes prior to GTE | 10/3/2012 8:00:00 AM | 10/12/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/2/2013 3:00:00 PM |  | Code Complete | 5/2/2013 3:00:00 PM | 5/2/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/13/2013 3:00:00 PM |  | Internal Testing by GTE team | 5/2/2013 3:00:00 PM | 6/13/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/16/2013 3:00:00 PM |  | Pass 1 | 5/2/2013 3:00:00 PM | 5/16/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 5/30/2013 3:00:00 PM |  | Pass 2 | 5/16/2013 3:00:00 PM | 5/30/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/13/2013 3:00:00 PM |  | Pass 3 | 5/30/2013 3:00:00 PM | 6/13/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/13/2013 3:00:00 PM |  | Network Module Development and GTE Testing Complete | 6/13/2013 3:00:00 PM | 6/13/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 9/3/2013 3:00:00 PM |  | Split shipment BRID | 6/13/2013 3:00:00 PM | 8/27/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 7/22/2013 3:00:00 PM |  | Split shipment handling coding | 6/13/2013 3:00:00 PM | 7/15/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 7/23/2013 3:00:00 PM |  | Request build and internal testing | 7/15/2013 3:00:00 PM | 7/16/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 8/6/2013 3:00:00 PM |  | GTE Pass 1 | 7/16/2013 3:00:00 PM | 7/30/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 8/20/2013 3:00:00 PM |  | GTE Pass 2 | 7/30/2013 3:00:00 PM | 8/13/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 9/3/2013 3:00:00 PM |  | GTE Pass 3 | 8/13/2013 3:00:00 PM | 8/27/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 9/3/2013 3:00:00 PM |  | Split shipment handling coding complete | 8/27/2013 3:00:00 PM | 8/27/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 3/11/2014 3:00:00 PM |  | Support On_site Customer Collaboration | 6/13/2013 3:00:00 PM | 6/13/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 3/11/2014 3:00:00 PM |  | Support Business Process Improvements | 2/11/2014 3:00:00 PM | 2/11/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/20/2013 3:00:00 PM |  | Support Solution Validation and Installation | 6/13/2013 3:00:00 PM | 6/20/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/20/2013 3:00:00 PM |  | Plan and Perform the Installation (For Each Environment As Needed: Training, Validation, etc.) | 6/13/2013 3:00:00 PM | 6/20/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | System deployed and available for local training | 6/20/2013 3:00:00 PM | 6/20/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Consulting Activities | 2/11/2014 3:00:00 PM | 5/14/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Implement agreed recommended processess and practices | 2/11/2014 3:00:00 PM | 2/11/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Implementation of Organization structures related to Network Module | 3/31/2014 3:00:00 PM | 5/12/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Business Training on how KPI's and Standard Performance Reports will be used | 5/12/2014 3:00:00 PM | 5/14/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform the Solution Adoption End-of-Phase Review | 2/11/2014 3:00:00 PM | 2/12/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Release 2 - Solution Adoption Phase Complete | 2/12/2014 3:00:00 PM | 2/12/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Solution Adoption
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Release 2 - Project Transition Phase | 4/24/2013 3:00:00 PM | 6/11/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Customer Validation and Training | 4/24/2013 3:00:00 PM | 6/11/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Support Customer Validation | 5/14/2014 3:00:00 PM | 5/28/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Build Deployment and Soak (End to End) Testing | 4/24/2013 3:00:00 PM | 10/11/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/13/2013 3:00:00 PM |  | Calibration Exercise | 4/24/2013 3:00:00 PM | 6/5/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/24/2013 3:00:00 PM |  | Load Calibration and Cost data in EY Test build | 6/20/2013 3:00:00 PM | 6/24/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/24/2013 3:00:00 PM |  | GET: CHAMP has deployed build into EY Test Environment | 6/17/2013 3:00:00 PM | 6/17/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 7/1/2013 3:00:00 PM |  | Train the Trainer classroom training for testers | 6/24/2013 3:00:00 PM | 7/1/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Customer UVT | 7/1/2013 3:00:00 PM | 10/11/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | UVT Base System Begin | 7/1/2013 3:00:00 PM | 7/1/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 7/15/2013 3:00:00 PM |  | Air Vision Cargo Interface Integration Testing with Cargospot | 7/1/2013 3:00:00 PM | 7/15/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 9/3/2013 3:00:00 PM |  | Soak Test - Parallel run (Test and Prod) | 7/15/2013 3:00:00 PM | 9/3/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 10/11/2013 3:00:00 PM |  | Split Shipment Handling Code deployment | 9/3/2013 3:00:00 PM | 10/11/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | Yes
Overdue | No BL | 100% | 0 | 9/10/2013 3:00:00 PM |  | Plan and Perform Split Shipment Handling code deployment | 9/3/2013 3:00:00 PM | 9/10/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes
Overdue | No BL | 100% | 0 | 9/11/2013 3:00:00 PM |  | Validate build successfully deployed | 9/10/2013 3:00:00 PM | 9/11/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes
Overdue | No BL | 100% | 0 | 9/13/2013 3:00:00 PM |  | Train the trainer classroom training for testers | 9/11/2013 3:00:00 PM | 9/13/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes
Overdue | No BL | 100% | 0 | 10/11/2013 3:00:00 PM |  | Soak Test - Parallel run (Test and Prod) | 9/13/2013 3:00:00 PM | 10/11/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes
Overdue | No BL | 100% | 0 | 10/11/2013 3:00:00 PM |  | UVT Base System End | 10/11/2013 3:00:00 PM | 10/11/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 12/18/2013 3:00:00 PM |  | Go/No Go for Production Deployment | 10/11/2013 3:00:00 PM | 10/11/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 10/18/2013 3:00:00 PM |  | Perform End-User Training | 10/11/2013 3:00:00 PM | 10/18/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Consulting Activities | 10/18/2013 3:00:00 PM | 6/11/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 3/12/2014 3:00:00 PM |  | Implement KPI monitoring and utliziation of Standard Performance Reports | 10/18/2013 3:00:00 PM | 11/1/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 4/23/2014 3:00:00 PM |  | Begin Performance Monitoring | 12/13/2013 3:00:00 PM | 12/13/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Implement agree recommended processes and practices | 5/28/2014 3:00:00 PM | 6/11/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | Yes |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/4/2014 3:00:00 PM |  | End Performance Monitoring | 1/24/2014 3:00:00 PM | 1/24/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Present Performance Monitoring Results to Etihad | 1/24/2014 3:00:00 PM | 1/31/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 4/18/2014 3:00:00 PM |  | Perform Production Cutover and Support | 11/1/2013 3:00:00 PM | 3/25/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 12/18/2013 3:00:00 PM |  | Plan Production Cutover | 11/1/2013 3:00:00 PM | 11/22/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 12/19/2013 3:00:00 PM |  | Perform Production Cutover | 11/22/2013 3:00:00 PM | 11/25/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 12/19/2013 3:00:00 PM |  | Cutover to Production | 11/25/2013 3:00:00 PM | 11/25/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 4/18/2014 3:00:00 PM |  | Perform Post-Cutover Customer Support | 2/11/2014 3:00:00 PM | 3/25/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 4/18/2014 3:00:00 PM |  | Transition to Customer Care | 11/22/2013 3:00:00 PM | 1/15/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 2/28/2014 5:00:00 PM |  | Plan Customer Care Transition | 11/22/2013 3:00:00 PM | 11/29/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 4/18/2014 3:00:00 PM |  | Perform Customer Care Transition | 1/14/2014 3:00:00 PM | 1/15/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Close-Out and Review | 3/25/2014 3:00:00 PM | 5/16/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 4/23/2014 3:00:00 PM |  | Perform Project Close-Out | 3/25/2014 3:00:00 PM | 3/28/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Post-Project Review | 5/14/2014 3:00:00 PM | 5/16/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Release 2 - Project Transition Phase Complete | 5/16/2014 3:00:00 PM | 5/16/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Transistion
Overdue | No BL | 100% | 4.0000000000000001E-2 | 6/11/2014 3:00:00 PM |  | Project Management | 1/12/2012 8:00:00 AM | 5/16/2014 3:00:00 PM | 1/12/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Management
| Complete | 100% | 1 | 1/18/2012 5:00:00 PM |  | Project Planning | 1/12/2012 8:00:00 AM | 1/18/2012 5:00:00 PM | 1/12/2012 8:00:00 AM | 1/18/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Execution and Control | 2/29/2012 8:00:00 AM | 5/2/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope | 4/16/2013 3:00:00 PM | 4/17/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Schedule | 4/17/2013 3:00:00 PM | 4/18/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Issues | 4/18/2013 3:00:00 PM | 4/19/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Risks | 4/19/2013 3:00:00 PM | 4/22/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Quality | 4/22/2013 3:00:00 PM | 4/23/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks | 2/29/2012 8:00:00 AM | 4/10/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 1 | 2/29/2012 8:00:00 AM | 2/29/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 2 | 3/7/2012 8:00:00 AM | 3/7/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 3 | 3/14/2012 8:00:00 AM | 3/14/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 4 | 3/21/2012 8:00:00 AM | 3/21/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 5 | 3/28/2012 8:00:00 AM | 3/28/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 6 | 4/4/2012 8:00:00 AM | 4/4/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 7 | 4/11/2012 8:00:00 AM | 4/11/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 8 | 4/18/2012 8:00:00 AM | 4/18/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 9 | 4/25/2012 8:00:00 AM | 4/25/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 10 | 5/2/2012 8:00:00 AM | 5/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 11 | 5/9/2012 8:00:00 AM | 5/9/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 12 | 5/16/2012 8:00:00 AM | 5/16/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 13 | 5/23/2012 8:00:00 AM | 5/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 14 | 5/30/2012 8:00:00 AM | 5/30/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 15 | 6/6/2012 8:00:00 AM | 6/6/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 16 | 6/13/2012 8:00:00 AM | 6/13/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 17 | 6/20/2012 8:00:00 AM | 6/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 18 | 6/27/2012 8:00:00 AM | 6/27/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 19 | 7/4/2012 8:00:00 AM | 7/4/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 20 | 7/11/2012 8:00:00 AM | 7/11/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 21 | 7/18/2012 8:00:00 AM | 7/18/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 22 | 7/25/2012 8:00:00 AM | 7/25/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 23 | 8/1/2012 8:00:00 AM | 8/1/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 24 | 8/8/2012 8:00:00 AM | 8/8/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 25 | 8/15/2012 8:00:00 AM | 8/15/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 26 | 8/22/2012 8:00:00 AM | 8/22/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 27 | 8/29/2012 8:00:00 AM | 8/29/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 28 | 9/5/2012 8:00:00 AM | 9/5/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 29 | 9/12/2012 8:00:00 AM | 9/12/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 30 | 9/19/2012 8:00:00 AM | 9/19/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 31 | 9/26/2012 8:00:00 AM | 9/26/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 32 | 10/3/2012 8:00:00 AM | 10/3/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 33 | 10/10/2012 8:00:00 AM | 10/10/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 34 | 10/17/2012 8:00:00 AM | 10/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 35 | 10/24/2012 8:00:00 AM | 10/24/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 36 | 10/31/2012 8:00:00 AM | 10/31/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 37 | 11/7/2012 8:00:00 AM | 11/7/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 38 | 11/14/2012 8:00:00 AM | 11/14/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 39 | 11/21/2012 8:00:00 AM | 11/21/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 40 | 12/5/2012 8:00:00 AM | 12/5/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 41 | 12/12/2012 8:00:00 AM | 12/12/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 42 | 12/19/2012 8:00:00 AM | 12/19/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 43 | 1/9/2013 8:00:00 AM | 1/9/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 44 | 1/16/2013 8:00:00 AM | 1/16/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 45 | 1/23/2013 8:00:00 AM | 1/23/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 46 | 1/30/2013 8:00:00 AM | 1/30/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 47 | 2/6/2013 8:00:00 AM | 2/6/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 48 | 2/13/2013 8:00:00 AM | 2/13/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 49 | 2/20/2013 8:00:00 AM | 2/20/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 50 | 2/27/2013 8:00:00 AM | 2/27/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 51 | 3/6/2013 8:00:00 AM | 3/6/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 52 | 3/13/2013 8:00:00 AM | 3/13/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 53 | 3/20/2013 8:00:00 AM | 3/20/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 54 | 3/27/2013 8:00:00 AM | 3/27/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 55 | 4/3/2013 8:00:00 AM | 4/3/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope, Schedule, Issues & Risks 56 | 4/10/2013 8:00:00 AM | 4/10/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Delivery as an Integrated Portfolio | 4/24/2013 3:00:00 PM | 4/25/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Budget And Invoicing | 4/25/2013 3:00:00 PM | 4/26/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Metrics Tracking | 4/26/2013 3:00:00 PM | 4/29/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting | 2/29/2012 8:00:00 AM | 4/10/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 1 | 2/29/2012 8:00:00 AM | 2/29/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 2 | 3/7/2012 8:00:00 AM | 3/7/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 3 | 3/14/2012 8:00:00 AM | 3/14/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 4 | 3/21/2012 8:00:00 AM | 3/21/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 5 | 3/28/2012 8:00:00 AM | 3/28/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 6 | 4/4/2012 8:00:00 AM | 4/4/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 7 | 4/11/2012 8:00:00 AM | 4/11/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 8 | 4/18/2012 8:00:00 AM | 4/18/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 9 | 4/25/2012 8:00:00 AM | 4/25/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 10 | 5/2/2012 8:00:00 AM | 5/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 11 | 5/9/2012 8:00:00 AM | 5/9/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 12 | 5/16/2012 8:00:00 AM | 5/16/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 13 | 5/23/2012 8:00:00 AM | 5/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 14 | 5/30/2012 8:00:00 AM | 5/30/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 15 | 6/6/2012 8:00:00 AM | 6/6/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 16 | 6/13/2012 8:00:00 AM | 6/13/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 17 | 6/20/2012 8:00:00 AM | 6/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 18 | 6/27/2012 8:00:00 AM | 6/27/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 19 | 7/4/2012 8:00:00 AM | 7/4/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 20 | 7/11/2012 8:00:00 AM | 7/11/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 21 | 7/18/2012 8:00:00 AM | 7/18/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 22 | 7/25/2012 8:00:00 AM | 7/25/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 23 | 8/1/2012 8:00:00 AM | 8/1/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 24 | 8/8/2012 8:00:00 AM | 8/8/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 25 | 8/15/2012 8:00:00 AM | 8/15/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 26 | 8/22/2012 8:00:00 AM | 8/22/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 27 | 8/29/2012 8:00:00 AM | 8/29/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 28 | 9/5/2012 8:00:00 AM | 9/5/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 29 | 9/12/2012 8:00:00 AM | 9/12/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 30 | 9/19/2012 8:00:00 AM | 9/19/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 31 | 9/26/2012 8:00:00 AM | 9/26/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 32 | 10/3/2012 8:00:00 AM | 10/3/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 33 | 10/10/2012 8:00:00 AM | 10/10/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 34 | 10/17/2012 8:00:00 AM | 10/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 35 | 10/24/2012 8:00:00 AM | 10/24/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 36 | 10/31/2012 8:00:00 AM | 10/31/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 37 | 11/7/2012 8:00:00 AM | 11/7/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 38 | 11/14/2012 8:00:00 AM | 11/14/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 39 | 11/21/2012 8:00:00 AM | 11/21/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 40 | 12/5/2012 8:00:00 AM | 12/5/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 41 | 12/12/2012 8:00:00 AM | 12/12/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 42 | 12/19/2012 8:00:00 AM | 12/19/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 43 | 1/9/2013 8:00:00 AM | 1/9/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 44 | 1/16/2013 8:00:00 AM | 1/16/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 45 | 1/23/2013 8:00:00 AM | 1/23/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 46 | 1/30/2013 8:00:00 AM | 1/30/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 47 | 2/6/2013 8:00:00 AM | 2/6/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 48 | 2/13/2013 8:00:00 AM | 2/13/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 49 | 2/20/2013 8:00:00 AM | 2/20/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 50 | 2/27/2013 8:00:00 AM | 2/27/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 51 | 3/6/2013 8:00:00 AM | 3/6/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 52 | 3/13/2013 8:00:00 AM | 3/13/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 53 | 3/20/2013 8:00:00 AM | 3/20/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 54 | 3/27/2013 8:00:00 AM | 3/27/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 55 | 4/3/2013 8:00:00 AM | 4/3/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting 56 | 4/10/2013 8:00:00 AM | 4/10/2013 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting | 4/29/2013 3:00:00 PM | 4/30/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Steering | 4/30/2013 3:00:00 PM | 5/1/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Stakeholder Communications | 5/1/2013 3:00:00 PM | 5/2/2013 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Closure | 5/16/2014 3:00:00 PM | 5/16/2014 3:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No |  |  | Project Management
Overdue | Red | 100% | 0 | 6/11/2014 3:00:00 PM |  | Etihad Airways - AirVision CargoMax - Allotment Management Implementation | 1/1/2012 8:00:00 AM | 1/24/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 1/1/2012 8:00:00 AM | 1/24/2012 5:00:00 PM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 5/21/2014 3:00:00 PM |  | Release 3 - Interactive Pilot Phase | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 5/21/2014 3:00:00 PM |  | Interface Specification & BRD Review | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 5/21/2014 3:00:00 PM |  | Review Interface Specifications with EY and CHAMP | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Release 3 - Solution Adoption Phase | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 5/21/2014 3:00:00 PM |  | Allotment Module Development Work | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 5/21/2014 3:00:00 PM |  | Input from Cargospot | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 5/21/2014 3:00:00 PM |  | Output to Cargospot | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 5/21/2014 3:00:00 PM |  | Allotment Development Work Complete | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 5/21/2014 3:00:00 PM |  | Internal Testing of AMM | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Solution Adoption Phase Complete Phase Gate Check | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Release 3 - Project Transistion Phase | 1/20/2012 5:00:00 PM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform end user training | 1/20/2012 5:00:00 PM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Customer UAT | 1/20/2012 5:00:00 PM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Production Cutover | 1/20/2012 5:00:00 PM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Allotment Module Cutover to Production | 1/20/2012 5:00:00 PM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Transition Allotment Module Phase Gate Check | 1/20/2012 5:00:00 PM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Management | 1/2/2012 8:00:00 AM | 1/24/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Planning | 1/2/2012 8:00:00 AM | 1/6/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Execution and Control | 1/9/2012 8:00:00 AM | 1/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope | 1/9/2012 8:00:00 AM | 1/9/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Schedule | 1/10/2012 8:00:00 AM | 1/10/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Issues | 1/11/2012 8:00:00 AM | 1/11/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Risks | 1/12/2012 8:00:00 AM | 1/12/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Quality | 1/13/2012 8:00:00 AM | 1/13/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Delivery as an Integrated Portfolio | 1/16/2012 8:00:00 AM | 1/16/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Budget And Invoicing | 1/17/2012 8:00:00 AM | 1/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Metrics Tracking | 1/18/2012 8:00:00 AM | 1/18/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting | 1/19/2012 8:00:00 AM | 1/19/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Steering | 1/20/2012 8:00:00 AM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Stakeholder Communications | 1/23/2012 8:00:00 AM | 1/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Closure | 1/24/2012 8:00:00 AM | 1/24/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | Red | 100% | 0 | 6/11/2014 3:00:00 PM |  | Etihad Airways - AirVision Cargo - SaaS Migration | 1/1/2012 8:00:00 AM | 1/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 1/1/2012 8:00:00 AM | 1/23/2012 5:00:00 PM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Release 4 - SaaS Migration | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Review SaaS BRD with EY | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | SaaS Product Deployment Planning | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Saas Environment Setup and Configuration | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Saas Environment Setup and Configuration Complete | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Sabre Interface Review & Changes - to ensure SaaS compatibility | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Interface Development work complete | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Prepare CERT Environment | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Perform Deployment in CERT | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | CERT Environment Setup Complete | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Prepare PROD Environment | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Perform Production Cutover | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Milestone: SaaS Migration Complete | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/10/2014 3:00:00 PM |  | Begin Transition to Customer Care | 1/1/2012 8:00:00 AM | 1/1/2012 8:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Transition to Customer Care Phase Gate Check Complete | 1/2/2012 8:00:00 AM | 1/2/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Management | 1/2/2012 8:00:00 AM | 1/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Planning | 1/9/2012 8:00:00 AM | 1/9/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Execution and Control | 1/2/2012 8:00:00 AM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | Yes | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Scope | 1/10/2012 8:00:00 AM | 1/10/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Schedule | 1/11/2012 8:00:00 AM | 1/11/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Issues | 1/2/2012 8:00:00 AM | 1/4/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Risks | 1/12/2012 8:00:00 AM | 1/12/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Quality | 1/13/2012 8:00:00 AM | 1/13/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Delivery as an Integrated Portfolio | 1/16/2012 8:00:00 AM | 1/16/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Budget And Invoicing | 1/17/2012 8:00:00 AM | 1/17/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Metrics Tracking | 1/5/2012 8:00:00 AM | 1/6/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Status Reporting | 1/18/2012 8:00:00 AM | 1/18/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Perform Project Steering | 1/19/2012 8:00:00 AM | 1/19/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Manage Project Stakeholder Communications | 1/20/2012 8:00:00 AM | 1/20/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No
Overdue | No BL | 100% | 0 | 6/11/2014 3:00:00 PM |  | Project Closure | 1/23/2012 8:00:00 AM | 1/23/2012 5:00:00 PM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM | 12:00:00 AM |  |  |  |  | No | No | No