## Slide 1: Project Integration Management

## Slide 4: Project Integration Management
  Processes and activities needed to identify, define, combine, unify, and coordinate the various processes and project management activities within the Project Management Process Groups

## Slide 5: Project Integration Management
  Develop Project Charter [INITIATING]
  Develop Project Management Plan [PLANNING]
  Direct and Manage Project Execution [EXECUTING]
  Manage Project Knowledge [EXECUTING]
  Monitor and Control Project Work [M&C]
  Perform Integrated Change Control [M&C]
  Close Project or Phase [CLOSING]

## Slide 6: 1. Develop Project Charter
The process of developing a document that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities.

## Slide 7: Develop Project Charter
.1 Business documents
  • Business case
  • Benefits management plan
.2 Agreements
.3 EEFs
.4 OPA
.1 Expert judgment
.2 Data gathering
  • Brainstorming
  • Focus groups
  • Interviews
.3 Interpersonal and team skills
  • Conflict management
  • Facilitation
  • Meeting management
.4 Meetings
.1 Project charter
.2 Assumption log
PIM
INIT

## Slide 8: Project Charter Template
Project purpose or justification
Measurable project objectives and related success criteria
High – Level Requirements
High – Level Project description
High – Level Risks
Summary milestone schedule
Summary Budget
Project approval requirements
Assigned project manager, responsibility, and authority level
Name and authority of the sponsor or other person(s) authorizing the project charter

## Slide 9: Exercise-1
Prepare Project Charter for your Project
15 Minutes

## Slide 10: 2. Develop Project Management Plan
The process of defining, preparing, and coordinating all plan components and consolidating them into an integrated project management plan.

## Slide 11: Develop Project Management Plan
.1 Expert judgment
.2 Data gathering
  • Brainstorming
  • Checklists
  • Focus groups
  • Interviews
.3 Interpersonal and team skills
  • Conflict management
  • Facilitation
  • Meeting management
.4 Meetings
.1 Project charter
.2 Outputs from other processes
.3 EEFs
.4 OPAs
.1 Project management plan
PIM
PLAN

## Slide 12: Exercise-2
  Write name of all type of subsidiary plans for your Project
5 Minutes

## Slide 13: 3. Direct & Manage Project Work
The process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives.

## Slide 14: Direct and Manage Project Work
.1 Expert judgment
.2 Project management information system
.3 Meetings
.1 Project management plan
• Any component
.2 Project documents
  • Change log
  • Lessons learned register
  • Milestone list
  • Project communications
  • Project schedule
  • RTM
  • Risk register
  • Risk report
.3 Approved change requests
.4 EEFs
.5 OPAs
.1 Deliverables
.2 Work performance data
.3 Issue log
.4 Change requests
.5 PMP updates
• Any component
.6 Project documents updates
  • Activity list
  • Assumption log
  • Lessons learned register
  • Requirements Docs.
  • Risk register
  • Stakeholder register
.7 OPAs Updates
PIM
EXEC

## Slide 15: Exercise-3
  Write name of Deliverables & Name of work performance information for your Project
5 Minutes

## Slide 16: 4. Manage Project Knowledge
The process of using existing knowledge and creating new knowledge to achieve the project’s objectives and contribute to organizational learning.

## Slide 17: Manage Project Knowledge
.1 Expert judgment
.2 Knowledge management
.3 Information management
.4 Interpersonal and team skills
  • Active listening
  • Facilitation
  • Leadership
  • Networking
  • Political awareness
.1 Project management plan
• All components
.2 Project documents
  • Lessons learned register
  • Project team assignments
  • Resource breakdown structure
  • Source selection criteria
  • Stakeholder register
.3 Deliverables
.4 EEFs
.5 OPAs
.1 Lessons learned register
.2 Project management plan
updates
• Any component
.3 OPAs updates
PIM
EXEC

## Slide 18: 5. Monitor & Control Project Work
The process of tracking, reviewing, and reporting overall progress to meet the performance objectives defined in the project management plan.

## Slide 19: Monitor and Control Project Work
.1 Expert judgment
.2 Data analysis
  • Alternatives analysis
  • Cost-benefit analysis
  • Earned value analysis
  • Root cause analysis
  • Trend analysis
  • Variance analysis
.3 Decision making
.4 Meetings
.1 Project management plan
  • Any component
.2 Project documents
  • Assumption log
  • Basis of estimates
  • Cost forecasts
  • Issue log
  • Lessons learned register
  • Milestone list
  • Quality reports
  • Risk register
  • Risk report
  • Schedule forecasts
.3 Work performance information
.4 Agreements
.5 EEFs
.6 OPA
.1 Work performance reports
.2 Change requests
.3 PMP updates
• Any component
.4 Project documents updates
  • Cost forecasts
  • Issue log
  • Lessons learned register
  • Risk register
  • Schedule forecasts
PIM
M&C

## Slide 20: Exercise-4
  Write type & name of a few change requests for your Project
5 Minutes

## Slide 21: 6. Perform Integrated Change Control
The process of reviewing all change requests; approving changes and managing changes to deliverables, organizational process assets, project documents, and the project management plan; and communicating the decisions.

## Slide 22: Perform Integrated Change Control
.1 Expert judgment
.2 Change control tools
.3 Data analysis
  • Alternatives analysis
  • Cost-benefit analysis
.4 Decision making
  • Voting
  • Autocratic decision making
  • Multicriteria decision analysis
.5 Meetings
.1 Project management plan
  • Change management plan
  • Configuration management plan
  • Scope baseline
  • Schedule baseline
  • Cost baseline
.2 Project documents
  • Basis of estimates
  • Requirements traceability matrix
  • Risk report
.3 Work performance reports
.4 Change requests
.5 EEFs
.6 OPAs
.1 Approved change requests
.2 PMP updates
  • Any component
.3 Project documents updates
  • Change log
PIM
M&C

## Slide 23: Exercise-5
  Write change management process for your Project OR
  Prepare a format of change request report for your project
5 Minutes

## Slide 24: 7. Close Project or Phase
The process of finalizing all activities for the project, phase, or contract.

## Slide 25: Close Project or Phase
.1 Project charter
.2 Project management plan
  • All components
.3 Project documents
  • Assumption log
  • Basis of estimates
  • Change log
  • Issue log
  • Lessons learned register
  • Milestone list
  • Project communications
  • Quality control measurements
  • Quality reports
  • Requirements
  documentation
  • Risk register
  • Risk report
.4 Accepted deliverables
.5 Business documents
  • Business case
  • Benefits management plan
.6 Agreements
.7 Procurement documentation
.8 OPA
.1 Expert judgment
.2 Data analysis
  • Document analysis
  • Regression analysis
  • Trend analysis
  • Variance analysis
.3 Meetings
.1 Project documents updates
  • Lessons learned register
.2 Final product, service, or result transition
.3 Final report
.4 OPA updates
PIM
Closing

## Slide 26: Exercise-6
  Write name of documents submitted to organization deliveries made to customer for your Project at the end of your project or project phase.
5 Minutes

## Slide 28: Project Scope Management

## Slide 30: Level of Detailing in Scope

## Slide 31
How the customer explained it
How the Project Leader understood it
How the Architect Designed it
How the Programmer wrote it
How the Business Consultant described it
How the project was documented
How operations installed it
How the customer was billed
How it was supported
What the customer really needed

## Slide 32: Scope
Project Scope "The work that needs to be accomplished to deliver a product, service, or result with the specified features and functions."
Product Scope "The features and functions that characterize a product, service, or result."

## Slide 33: Project Scope Management
  Processes required to ensure that the project includes all the work required, and ONLY the work required to complete the project successfully

## Slide 34: Project Scope Management
  Plan Scope Management [PLANNING]
  Collect Requirements [PLANNING]
  Define Scope [PLANNING]
  Create WBS [PLANNING]
  Validate Scope [M&C]
  Control Scope [M&C]

## Slide 35: 8. Plan Scope Management
Documenting how the project scope will be defined, validated and controlled

## Slide 36: Plan Scope Management
.1 Project charter
.2 Project management plan
  • Quality management plan
  • Project life cycle description
  • Development approach
.3 EEFs
.4 OPAs
.1 Expert judgment
.2 Data analysis
  • Alternatives analysis
.3 Meetings
.1 Scope management plan
.2 Requirements management plan
PSM
PLAN

## Slide 37: Plan Scope Management IO
Scope Management Plan includes
  Process for preparing project scope statement (PSS)
  Process that enable creation of WBS from PSS
  Process that specifies how formal acceptance be obtained
  Process to control changes to details PSS
Requirement Management Plan includes
  Process of analyzing, documenting and managing requirements
  Process of requirement prioritization
  Product measurement metrics and their rationale
  RTM structure
  Configuration management activities related to product

## Slide 38: 9. Collect Requirements
  The process of determining, documenting, and managing stakeholder needs and requirements to meet project objectives.

## Slide 39: Collect Requirements
.1 Project charter
.2 Project management plan
  • Scope management plan
  • Requirements management plan
  • Stakeholder engagement plan
.3 Project documents
  • Assumption log
  • Lessons learned register
  • Stakeholder register
.4 Business documents
  • Business case
.5 Agreements
.6 EEFs
.7 OPAs
.1 Expert judgment
.2 Data gathering
  • Brainstorming
  • Interviews
  • Focus groups
  • Questionnaires and surveys
  • Benchmarking
.3 Data analysis
  • Document analysis
.4 Decision making
  • Voting
  • Multicriteria decision analysis
.5 Data representation
  • Affinity diagrams
  • Mind mapping
.6 Interpersonal and team skills
  • Nominal group technique
  • Observation/conversation
  • Facilitation
.7 Context diagram
.8 Prototypes
.1 Requirements documentation
.2 Requirements traceability matrix
PSM
PLAN

## Slide 40: Collect Requirements
Focus groups
  Guided by moderator, group’s final opinion is taken
Group creativity techniques
    Brain storming
    Nominal group techniques: Brainstorming only on most voted
    Delphi Techniques: Only selected experts answers. Who answered what is not shared
    Idea Mapping techniques: Individuals ideas mapped on single map
    Affinity diagrams: Grouping and sorting of ideas for discussion
Group decision making techniques
  Majority, Unanimity, Plurality, Dictatorship

## Slide 41: Requirement Traceability Matrix
Tracing Requirements to
  Business needs, opportunities, goals & objectives
  Project objectives
  Project scope/WBS deliverables
  Product design
  product development
  Test strategy and test scenarios
Traces high-level requirements to more detailed requirements.
Attributes in RTM can be
  Unique identified
  Textual description of requirement
  Rationale for inclusion
  Owner
  Source
  Priority
  Version
  Current Status (active, cancelled, differed, added, approved)
  Date completed
  Stability
  Complexity
  Acceptance Criteria

## Slide 42: Requirement vs Scope
Scope and requirement are two different things.
Requirements are only those, which are in scope!
Requirements are driven from scope
Boundaries are defined first (using SOW), requirements are collected next
Requirement must be measurable, testable, traceable, complete, consistent and acceptable to key stakeholders.

## Slide 43: Requirement Documentation includes
Business need or opportunity to be seized, describing the limitation of the current situation and why the project has been undertaken
Business and project objectives for traceability
Functional requirements, describing business process, information, and interaction with the product, as appropriate which can be documented textually in a requirements list, in models, or both
Non-functional requirements like SLA, performance, safety, security, compliance, supportability, retention/purge
Quality requirements
Acceptance criteria
Business rules stating the guiding principles
Impacts to other organizational areas call centre, technology centre, sales force
Impacts to other entities inside or outside the performing organization
Support and training requirements
Requirements assumptions and constraints

## Slide 44: Discussion/Exercise-7
How to collect, analyze, document, prioritize, manage req; how change should be initiated and impact analysis done; Tracking changes, configuration management activities, RTM structure
  Write Requirement Management Plan for your projects OR
  Write Columns of RTM for your project
5 Minutes

## Slide 45: 10. Define Scope
Developing a detailed description of the project and product.

## Slide 46: Define Scope
.1 Project charter
.2 Project management plan
  • Scope management plan
.3 Project documents
  • Assumption log
  • Requirements documentation
  • Risk register
.4 EEFs
.5 OPAs
.1 Expert judgment
.2 Data analysis
  • Alternatives analysis
.3 Decision making
  • Multicriteria decision analysis
.4 Interpersonal and team skills
  • Facilitation
.5 Product analysis
.1 Project scope statement
.2 Project documents updates
  • Assumption log
  • Requirements documentation
  • Requirements traceability matrix
  • Stakeholder register
PSM
PLAN

## Slide 47: Define Scope
Product Analysis
  Product breakdown
  System analysis
  Requirement analysis
  System engineering: Deals with multiple complex systems
  Value engineering: Functions, value, cost
    Retain the function & value and reduce the cost
  Value analysis: Debate the function and its cost
    Discuss the value of function vs the cost
Alternative Identification
  Alternative way of doing work

## Slide 48: Scope Statement
Scope statement has following sections
  Product Scope Description
  Product Acceptance Criteria
  Project Deliverables
  Project Exclusions
  Project Constraints (budget, imposed date, scheduled milestones, contractual provisions)
  Project Assumptions
  Organizational policies
  Available skilled resources

## Slide 49: Discussion/Exercise 8
Product Scope Description, Product Acceptance Criteria, Project Deliverables
Project Exclusions, Project Constraints (budget, imposed date, scheduled milestones, contractual provisions), Project Assumptions, Organizational policies, Available skilled resources
Write Project Scope Statement for your project
5 Minutes

## Slide 50: 11. Create WBS
Subdividing project deliverables and project work into smaller, more manageable components.

## Slide 51: Create WBS
.1 Project management plan
  • Scope management plan
.2 Project documents
  • Project scope statement
  • Requirements documentation
.3 EEFs
.4 OPAs
.1 Expert judgment
.2 Decomposition
1 Scope baseline
.2 Project documents updates
  • Assumption log
  • Requirements documentation
PSM
PLAN

## Slide 52: Scope baseline
Scope baseline is part of PMP, Scope baseline includes
  Project Scope Statements
  WBS
  WBS Dictionary

## Slide 53: WBS Types
Phase Driven
Department Driven
Milestone Driven
Component Driven
Location Driven
…….

## Slide 54: Phase oriented WBS

## Slide 55: Department oriented WBS

## Slide 56: Subproject Oriented WBS

## Slide 57: Discussion/Exercise 9
Write 2 Level WBS & WBS Dictionary with min 5 deliverables for your project
5 Minutes

## Slide 58: 12. Validate Scope
Formalizing acceptance of the completed project deliverables.

## Slide 59: Validate Scope
.1 Project management plan
  • Scope management plan
  • Requirements management plan
  • Scope baseline
.2 Project documents
  • Lessons learned register
  • Quality reports
  • Requirements documentation
  • Requirements traceability matrix
.3 Verified deliverables
.4 Work performance data
.1 Inspection
.2 Decision making
  • Voting
.1 Accepted deliverables
.2 Work performance information
.3 Change requests
.4 Project document updates
  • Lessons learned register
  • Requirements documentation
  • Requirements traceability matrix
PSM
M&C

## Slide 60: Discussion/Exercise 10
Write verify scope activities for your project; also write the name of deliverables verified.
5 Minutes

## Slide 61: 13. Control Scope
Monitoring the status of the project and product scope and managing changes to the scope baseline.

## Slide 62: Control Scope
.1 Project management plan
  • Scope management plan
  • Requirements management plan
  • Change management plan
  • Configuration management plan
  • Scope baseline
  • Performance measurement baseline
.2 Project documents
  • Lessons learned register
  • Requirements documentation
  • Requirements traceability matrix
.3 Work performance data
.4 OPAs
.1 Data analysis
  • Variance analysis
  • Trend analysis
.1 Work performance information
.2 Change requests
.3 PMP updates
  • Scope management plan
  • Scope baseline
  • Schedule baseline
  • Cost baseline
  • Performance measurement baseline
.4 Project documents updates
  • Lessons learned register
  • Requirements documentation
  • Requirements traceability matrix
PSM
M&C

## Slide 63: Discussion/Exercise-11
Write work performance measurement metrics and their values for your project
5 Minutes