## Slide 1: Project Communication Management

## Slide 2: Project Communications Management

## Slide 3: Project Communication Management
  Processes required to ensure timely and appropriate generation, collection, distribution, storage, retrieval and ultimate disposition of project information.

## Slide 4: Project Communications Management
  Plan Communications [PLANNING]
  Manage Communication[EXECUTING]
  Monitor Communications[M&C]

## Slide 5: 33. Plan Communications
Determining the project stakeholder information needs and defining a communication approach.

## Slide 6: Plan Communication Management
.1 Expert judgment
.2 Communication requirements analysis
.3 Communication technology
.4 Communication models
.5 Communication methods
.6 Interpersonal and team skills
  • Communication styles assessment
  • Political awareness
  • Cultural awareness
.7 Data representation
  • Stakeholder engagement assessment matrix
.8 Meetings
.1 Project charter
.2 Project management plan
  • Resource management plan
  • Stakeholder engagement plan
.3 Project documents
  • Requirements documentation
  • Stakeholder register
.4 EEFs
.5 OPAs
.1 Communications management plan
.2 PMP updates
  • Stakeholder engagement plan
.3 Project documents updates
• Project schedule
• Stakeholder register
PCOM
PLAN

## Slide 7: Communication Requirements Analysis
  Project resources should be expended only on communicating information that contributes to success or where a lack of communication can lead to failure.
  Depends upon the responsibilities and relationship between performing organization and stakeholder.
  Depends upon disciplines, departments, and specialties involved in the project.
  Depends upon logistics of how many individuals will be involved with the project and at which locations.
  Depends upon internal and External communication needs

## Slide 8: Number of Communication Channels
  N(N-1)/2
Two People, One Channel
Three People, Three Channel
Four People, Six Channel
Six People, Fifteen Channel

## Slide 9: Communication Methods
  Which communication technology should be used depends upon what communication method is the needed
  Three Communication Methods
  Interactive Communication
    Phone, audio/video conferences, moderator lead discussion, workshop
  Push Communication
    Letters, memos, reports, emails, faxes, voice mail, press releases
  Pull Communication
    e-learning, knowledge repository, unknown people

## Slide 10: Communication Model
Receiver
Decoding
Message
channel
Encoding
Source
Feedback
Noise

## Slide 11: 34. Manage Communication
As per the communication management plan creating, collecting, distributing, storing, retrieving and ultimate disposition of project information

## Slide 12: Manage Communications
.1 Communication technology
.2 Communication methods
.3 Communication skills
  • Communication competence
  • Feedback
  • Nonverbal
  • Presentations
.4 PMIS
.5 Project reporting
.6 Interpersonal and team skills
  • Active listening
  • Conflict management
  • Cultural awareness
  • Meeting management
  • Networking
  • Political awareness
.7 Meetings
.1 Project management plan
  • Resource management plan
  • Communications management plan
  • Stakeholder engagement plan
.2 Project documents
  • Change log
  • Issue log
  • Lessons learned register
  • Quality report
  • Risk report
  • Stakeholder register
.3 WPR
.4 EEFs
.5 OPAs
.1 Project communications
.2 PMP updates
  • Communications management plan
  • Stakeholder engagement plan
.3 Project documents updates
  • Issue log
  • Lessons learned register
  • Project schedule
  • Risk register
  • Stakeholder register
.4 OPAs updates
PCOM
EXEC

## Slide 13: Communication Methods
  Individual Meetings
  Group Meetings
  Audio & Video conferences
  Computer chats
  Remote communication methods

## Slide 14: Information distribution tools
  Hardcopy distribution, manual filing systems, press released, shared access to electronic database
  Electronic communication & conferencing tool: email, fax, voice mail, telephone, video, web conferencing, websites and web publishing
  Electronic tools for project management web interfaces to scheduling and project management software, meeting and virtual office software, portals and collaborating work management tool

## Slide 15: Distribute Information
Top Mgmt /Client/Sponsor
Team Members/ Contr./Sub-Contr.
Funct. Mgr/
Other.Mgrs.
Ext.Stk.Holder/
Reg.Agencies/
Press
Proj.Mgr.
Up
Down
Horizontal
Horizontal

## Slide 16: 35. Control Communications
Monitoring and controlling communication throughout project life cycle to ensure the information needs of the project stakeholders are met

## Slide 17: Monitor Communications
.1 Expert judgment
.2 PMIS
.3 Data analysis
  • Stakeholder engagement assessment matrix
.4 Interpersonal and team skills
  • Observation/ conversation
.5 Meetings
.1 Project management plan
  • Resource management plan
  • Communications management plan
  • Stakeholder engagement plan
.2 Project documents
  • Issue log
  • Lessons learned register
  • Project communications
.3 Work performance data
.4 EEFs
.5 OPAs
.1 Work performance
  information
.2 Change requests
.3 PMP updates
  • Communications management plan
  • Stakeholder engagement plan
.4 Project documents updates
  • Issue log
  • Lessons learned register
  • Stakeholder register
PCOM
M&C

## Slide 18: Communication Types
Informal | Meeting, Conversation | Email, Status Update, Memos
Formal | Speech, Presentation | Project Plan, Contract, Charter
 | Verbal | Written

## Slide 19: Communication Management
Filtering – A phenomenon that occurs when a large portion of the message is lost in vertical/horizontal communication
Nonverbal communication carries 55% of the message
Progress Reports generally show problems after they have occurred.
A communication matrix is an excellent tool to identify the stakeholders and their requirements for communication.

## Slide 20: Communication Management
Other Factors
  Ambiguity in language
  Culture
  Semantics
  Knowledge Base
  Message Content – hidden agendas
  Probable Factors
  Senders reputation
  Status within the organization
  Environmental Background
  Dysfunctional emotional behaviors
  Situational Consideration – Predefined Mindset
  Historical Consideration in message interpretation

## Slide 21: Cross Cultural Problems
  Project may require inputs from individual and groups from different countries
  Relevant concerns are -
  Differences in culture
  Differences in project environments.
  Attitude – perceiving others using one’s own standards rather than other’s.
  Stereotypes – sticking to a particular culture to apply in any situation
  Thought patterns – differing culture across geographical distances/organizations
  Time sense – differing sense of urgency

## Slide 22: Exercise 25
Prepare Communication Management Plan for your project
  Information to be shared
  Report formats (Name & Identifiers)
  Reporting frequency
  Reporting Technology
  Purpose of Communication
  Presenter
  Audience (Name & Number)
Prepare different reporting formats
  Progress Reports
  Status Reports
  Forecast Reports
30 Min

## Slide 24: Project Risk Management

## Slide 28: Project Risk Management
  Processes for conducting risk management planning, identification, analysis, response planning and monitoring and control on a project.

## Slide 29: Project Risk Management
  Plan Risk Management [PLANNING]
  Identify Risks [PLANNING]
  Perform Qualitative Risk Analysis [PLANNING]
  Perform Quantitative Risk Analysis [PLANNING]
  Plan Risk Responses [PLANNING]
  Implement Risk Responses [EXECUTING]
  Control Risks [M&C]

## Slide 30: Personal Attitude to Risk
  Individuals fall into one of the three categories
  Risks Averse
  Risk Seeking
  Risk Neutral

## Slide 31: 36. Plan Risk Management
Defining how to conduct risk management activities for a project .

## Slide 32: Plan Risk Management
.1 Expert judgment
.2 Data analysis
  • Stakeholder analysis
.3 Meetings
.1 Project charter
.2 Project management plan
  • All components
.3 Project documents
  • Stakeholder register
.4 EEFs
.5 OPAs
.1 Risk management plan
PRKM
PLAN

## Slide 33: Risk Breakdown Structure
Source : PMI PMBOK® Fourth Edition

## Slide 34: Definition of Impact
Source : PMI PMBOK® Fourth Edition

## Slide 35: 37. Identify Risks
Determining which risks may affect the project and documenting their characteristics

## Slide 36: Identify Risks
.1 Expert judgment
.2 Data gathering
  • Brainstorming
  • Checklists
  • Interviews
.3 Data analysis
  • Root cause analysis
  • Assumption and constraint analysis
  • SWOT analysis
  • Document analysis
.4 Interpersonal and team skills
  • Facilitation
.5 Prompt lists
.6 Meetings
.1 Project management plan
  • Requirements management plan
  • Schedule management plan
  • Cost management plan
  • Quality management plan
  • Resource management plan
  • Risk management plan
  • Scope baseline
  • Schedule baseline
  • Cost baseline
.2 Project documents
  • Assumption log
  • Cost estimates
  • Duration estimates
  • Issue log
  • Lessons learned register
  • Requirements documentation
  • Resource requirements
  • Stakeholder register
.3 Agreements
.4 Procurement documentation
.5 EEFs
.6 OPAs
.1 Risk register
.2 Risk report
.3 Project documents updates
  • Assumption log
  • Issue log
  • Lessons learned register
PRKM
PLAN

## Slide 37: Diagramming Techniques
Cause and effect diagrams
System or process flow charts
Influence Diagram

## Slide 38: 38. Perform Qualitative Risk Analysis
Prioritizing risks for further analysis or action by assessing and combining their probability of occurrence and impact.

## Slide 39: Perform Qualitative Risk Analysis
.1 Expert judgment
.2 Data gathering
  • Interviews
.3 Data analysis
  • Risk data quality assessment
  • Risk probability and impact assessment
  • Assessment of other risk parameters
.4 Interpersonal and team skills
  • Facilitation
.5 Risk categorization
.6 Data representation
  • Probability and impact matrix
  • Hierarchical charts
.7 Meetings
.1 Project management plan
  • Risk management plan
.2 Project documents
  • Assumption log
  • Risk register
  • Stakeholder register
.3 EEFs
.4 OPAs
.1 Project documents updates
  • Assumption log
  • Issue log
  • Risk register
  • Risk report
PRKM
PLAN

## Slide 40: Probability Impact Matrix
Source : PMI PMBOK® Fourth Edition
    Define Threshold
    High risk (“red condition”)
    Medium risk (“yellow condition”)
    Low risk (“green condition”)

## Slide 41: 39. Perform Quantitative Risk Analysis
Numerically analyzing the effect of identified risks on overall project objectives.

## Slide 42: Perform Quantitative Risk Analysis
.1 Expert judgment
.2 Data gathering
  • Interviews
.3 Interpersonal and team skills
  • Facilitation
.4 Representations of
  uncertainty
.5 Data analysis
  • Simulations
  • Sensitivity analysis
  • Decision tree analysis
  • Influence diagrams
.1 Project management plan
  • Risk management plan
  • Scope baseline
  • Schedule baseline
  • Cost baseline
.2 Project documents
  • Assumption log
  • Basis of estimates
  • Cost estimates
  • Cost forecasts
  • Duration estimates
  • Milestone list
  • Resource requirements
  • Risk register
  • Risk report
  • Schedule forecasts
.3 EEFs
.4 OPAs
.1 Project documents updates
  • Risk report
PRKM
PLAN

## Slide 43: PQnRA- Tools & Techniques
Data Gathering & Representation Techniques
  Interview
  Probability Distribution (Normal, Beta, Triangular)
Quantitative Risk Analysis Modeling Techniques
  Sensitivity analysis- helps to determine which risks have the most potential impact- Tornado diagrams (compare relative importance and impact of variables of high degree of uncertainty)
  Expected monetary value analysis (EMV)- Calculates average outcome of future scenarios that may or may not happen
  Modeling & Simulation- Monte Carlo techniques

## Slide 44: Formulae
Probability = Number of Occurrences / Total Number occurrences
= Frequency of Related Events / Total Number of Events
Probability = Frequency of Related Events /
Total Number of Possible Events
Expected Monetary Value (EMV) = Risk Event Probability X Risk Event Value
The sum of their probabilities of occurrence is 1.0

## Slide 45: Decision Tree

## Slide 46: Decision Tree
A Fixed Price Contract worth $150,000 has a clause of $1000 penalty per day of schedule delay. The following estimates for Cost and Schedule are provided:
Self-execute
    Cost can vary : with a likelihood 80%  120,000 vs. with a likelihood of 20%  140,000
    Schedule: can vary : 95% on time, 5% possibility of 2 days delay
Subcontract
    Cost can vary : with a likelihood of 60%  110,000 vs. with a likelihood of 40%  120,000
    Schedule can vary:: 80% on time, 20% possibility of 20 days delay

## Slide 47: Decision Tree- Solution
Self -execute
Subcontract
Cost
.4
.6
.8
.2
Schedule
Probability
.95
.05
.95
.05
.8
.2
.8
.2
.76
.04
.19
.01
.48
.12
.32
.08
Profit Potential
150,000-120,000 = 30,000
150,000-(120,000+20,000) = 10,000
150,000-120,000 = 30,000
150,000-(110,000+20,000) = 20,000
150,000-110,000 = 40,000
150,000-(140,000+2000) = 8,000
150,000-140,000 = 10,000
150,000-(120,000+2000) = 28,000
22,800
1,120
1,900
80
19,200
2,400
9,600
800
25,900
32,000

## Slide 48: 40. Plan Risk Response
Developing options and actions to enhance opportunities and reduce threats to project objectives.

## Slide 49: Plan Risk Response
.1 Expert judgment
.2 Data gathering
  • Interviews
.3 Interpersonal and team skills
  • Facilitation
.4 Strategies for threats
.5 Strategies for opportunities
.6 Contingent response strategies
.7 Strategies for overall project risk
.8 Data analysis
  • Alternatives analysis
  • Cost-benefit analysis
.9 Decision making
  • Multicriteria decision analysis
.1 Project management plan
  • Resource management plan
  • Risk management plan
  • Cost baseline
.2 Project documents
  • Lessons learned register
  • Project schedule
  • Project team assignments
  • Resource calendars
  • Risk register
  • Risk report
  • Stakeholder register
.3 EEFs
.4 OPAs
.1 Change requests
.2 PMP updates
  • Schedule management plan
  • Cost management plan
  • Quality management plan
  • Resource management plan
  • Procurement management plan
  • Scope baseline
  • Schedule baseline
  • Cost baseline
.3 Project documents updates
  • Assumption log
  • Cost forecasts
  • Lessons learned register
  • Project schedule
  • Project team assignments
  • Risk register
  • Risk report
PRKM
PLAN

## Slide 50: Risk Response Strategies
Risk Responses: Threats & Opportunities
Threats or Negative Risk Positive Risk or Opportunities
Avoid Exploit
Mitigate Enhance
Transfer Share
Acceptance Acceptance

## Slide 51: Negative Risk Responses
Avoid
Risk avoidance involves changing the project management plan to eliminate the threat posed by an adverse risk, to isolate the project objectives from the risk’s impact or to relax the objective that is in jeopardy, such as extending the schedule or reducing scope.
Transfer
It requires shifting the negative impact of a threat, along with ownership of the response, to a third party.
Mitigate
It implies a reduction in the probability and / or impact of an adverse risk event to an acceptable threshold. Transference is a form of mitigation.

## Slide 52: Positive Risk Responses
Exploit
  It seeks to eliminate the uncertainty associated with a particular upside risk by making the opportunity definitely happen. It may be selected for opportunities where the organization wishes to ensure that it is realized.
  Examples include assigning more talented resources to the project to reduce time to completion or to provide better quality than originally planned.
  - It is analogous to ‘avoidance’
Share
  It involves allocating ownership to a third-party who is best able to capture the opportunity for the benefit of the project.
  Examples include forming risk-sharing partnerships or joint ventures.
  - It is analogous to ‘transference’.

## Slide 53: Positive Risk Responses
Enhance
  It modifies the ‘size’ of an opportunity by Increasing probability and / or positive impacts and identifying and maximizing key drivers of positive- impact risks.
  It seeks to facilitate or strengthen the cause of the opportunity and proactively target and reinforce it’s trigger conditions to increase the probability.
  It is analogous to ‘mitigation’.

## Slide 54: +/- Risk Responses
Accept
  It is a strategy that is adopted because it is seldom possible to eliminate all risk from a project.
  It indicates that the project team
  Has decided not to change the project management plan to deal with risk or
  Is unable to identify any other suitable response strategy.
Active Acceptance most commonly involves establishing a
‘contingency reserve’, including amounts of time, money or resources to handle known or unknown threats or opportunities.
Passive Acceptance requires no action, leaving the project team to deal with threats or opportunities as they occur.

## Slide 55: Understanding Reserves
      Contingency reserves : Known – Unknown
      It is designed for use only if certain events occur or only under certain predefined conditions, provided there is sufficient warning to implement the response.
      Examples of events that may trigger the contingency response include missing intermediate milestones or gaining higher priority with a supplier.
      Events triggering the contingency response should be triggered and tracked.
      Management reserves: Unknown – Unknown
      It is defined for use only if ‘the events that occur or only under certain conditions’, where information about the event & its occurrence is absolutely NOT available.

## Slide 56: 41. Implement Risk Responses
The process of implementing agreed-upon risk response plans.

## Slide 57: Implement Risk Responses
.1 Expert judgment
.2 Interpersonal and team skills
  • Influencing
.3 PMIS
.1 Project management plan
  • Risk management plan
.2 Project documents
  • Lessons learned register
  • Risk register
  • Risk report
.3 OPAs
.1 Change requests
.2 Project documents updates
  • Issue log
  • Lessons learned register
  • Project team assignments
  • Risk register
  • Risk report
PRKM
EXEC

## Slide 58: 42. Monitor Risks
The process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project.

## Slide 59: Control Risks
.1 Data analysis
  • Technical performance analysis
  • Reserve analysis
.2 Audits
.3 Meetings
.1 Project management plan
  • Risk management plan
.2 Project documents
  • Issue log
  • Lessons learned register
  • Risk register
  • Risk report
.3 Work performance data
.4 Work performance reports
.1 Work performance information
.2 Change requests
.3 Project management plan updates
  • Any component
.4 Project documents updates
  • Assumption log
  • Issue log
  • Lessons learned register
  • Risk register
  • Risk report
.5 OPAs updates
PRKM
M&C

## Slide 60: Risk Management Terms
Contingency Reserve
  A separately planned quantity used to allow for future situations which may be planned for only in part (sometimes called “Known-unknowns”)
  Intended to reduce the impact of missing cost or schedule objectives
  Normally included in the project costs
Management Reserves
  “A separately planned quantity used to allow for future situations which are impossible to predict (sometimes called “Unknown- unknowns”)
  Intended to reduce the risk of missing cost or schedule objectives
  Use of Management reserves requires a change to the project’s cost baseline
Residual Risks
  Residual risks are those that remain after response measures have been taken.
  Include minor risks that have been accepted and addressed. E.g., By adding contingency amounts to the cost or by allowing time
Secondary risks
  Risks that arise as a result of implementing risk response
  Should be identified and responses planned

## Slide 61: Exercise 26
Prepare Risk Management Plan for your project
  Setup a template to capture all the information to manage risk
  Training content for risk awareness
  Training audience
  Roles & Responsibilities for Risk Management Activities
  Risk assessment techniques & tools
  Risk Manager, Risk Audits Frequency, Risk Auditor
  Define Impact Table
  Define Probability and Impact Table/ Risk Tolerances of Stakeholders
Prepare Risk Register
  Analyse Assumptions, Constraints, Dependencies of your project
  Identify Risk for your projects
Prepare Risk Response Plan
  Prepare Risk Response Strategy for every risk which cannot be tolerated
  Establish Contingency Fund
  Discuss Unknown-Unknown and Management Reserve
30 Min