## Slide 1: Project Procurement Management

## Slide 3: Project Procurement Management
  Processes necessary to purchase or acquire products, services or results needed from outside the project team.

## Slide 4: Another look @ Procurement Management
PROCUREMENT
MANAGEMENT
Cost
Objectives
Availability
Productivity
PROJECT
MANAGEMENT
INTEGRATION
SCOPE
TIME
HUMAN
RESOURCES
COST
COMMUNICATION
QUALITY
RISK
Project
Definitions
Risk Contracting
Performance, Service, Materials
Life Cycle
Environment Variations
Directives
Data Exchange
Specification
Assurance
Time
Objectives
STAKEHOLDER
Expectations

## Slide 5: Project Procurement Management
  Plan Procurement Management [PLANNING]
  Conduct Procurements [EXECUTING]
  Control Procurements [M&C]

## Slide 6: Project Manager’s Role
Identifying project procurement needs
Determine contract types and potential providers
Identify/select procurement source
Assessing quality and completeness of contract
Verify product/service acceptance
Structured review of the procurement process

## Slide 7: 43. Plan Procurement Management
Documenting project purchasing decisions, specifying the approach and identifying potential sellers.

## Slide 8: Plan Procurement
.1 Expert judgment
.2 Data gathering
  • Market research
.3 Data analysis
  • Make-or-buy analysis
.4 Source selection analysis
.5 Meetings
.1 Project charter
.2 Business documents
  • Business case
  • Benefits management plan
.3 Project management plan
  • Scope management plan
  • Quality management plan
  • Resource management plan
  • Scope baseline
.4 Project documents
  • Milestone list
  • Project team assignments
  • Requirements
  documentation
  • Requirements traceability
  matrix
  • Resource requirements
  • Risk register
  • Stakeholder register
.5 EEFs
.6 OPAs
.1 Procurement management
  plan
.2 Procurement strategy
.3 Bid documents
.4 Procurement statement of
  work
.5 Source selection criteria
.6 Make-or-buy decisions
.7 Independent cost estimates
.8 Change requests
.9 Project documents updates
  • Lessons learned register
  • Milestone list
  • Requirements documentation
  • Requirements traceability matrix
  • Risk register
  • Stakeholder register
.10 OPAs
PPM
PLAN

## Slide 9: Procurement Management Plan
Describes how the procurement processes will be managed
  Types of Contracts to be used
  Managing Multiple Providers
  Coordination with other project aspects

## Slide 10: Source selection criteria
Understanding of need
Overall or life-cycle cost
Technical capability
Risk
Management Approach
Technical Approach
Warranty
Financial Capacity
Production Capacity and interest
Business size and type
Past performance of sellers
References
Intellectual property rights
Proprietary rights

## Slide 11: 44. Conduct Procurements
Process involves obtaining seller responses, selecting a seller and awarding a contract

## Slide 12: Conduct Procurement
.1 Expert judgment
.2 Advertising
.3 Bidder conferences
.4 Data analysis
  • Proposal evaluation
.5 Interpersonal and team skills
  • Negotiation
.1 Project management plan
  • Scope management plan
  • Requirements management plan
  • Communications management plan
  • Risk management plan
  • Procurement management plan
  • Configuration management plan
  • Cost baseline
.2 Project documents
  • Lessons learned register
  • Project schedule
  • Requirements documentation
  • Risk register
  • Stakeholder register
.3 Procurement documentation
.4 Seller proposals
.5 EEFs
.6 OPAs
.1 Selected sellers
.2 Agreements
.3 Change requests
.4 PMP Updates
  • Requirements management plan
  • Quality management plan
  • Communications management plan
  • Risk management plan
  • Procurement management plan
  • Scope baseline
  • Schedule baseline
  • Cost baseline
.5 Project documents updates
  • Lessons learned register
  • Requirements documentation
  • Requirements traceability matrix
  • Resource calendars
  • Risk register
  • Stakeholder register
.6 OPAs
PPM
EXEC

## Slide 13: 45. Control Procurement
Managing procurement relationships, monitoring contract performance and making changes and corrections as needed.

## Slide 14: Control Procurement
.1 Expert judgment
.2 Claims administration
.3 Data analysis
  • Performance reviews
  • Earned value analysis
  • Trend analysis
.4 Inspection
.5 Audits
.1 Project management plan
  • Requirements management plan
  • Risk management plan
  • Procurement management plan
  • Change management plan
  • Schedule baseline
.2 Project documents
  • Assumption log
  • Lessons learned register
  • Milestone list
  • Quality reports
  • Requirements documentation
  • Requirements traceability matrix
  • Risk register
  • Stakeholder register
.3 Agreements
.4 Procurement documentation
.5 Approved change requests
.6 Work performance data
.7 EEFs
.8 OPAs
.1 Closed procurements
.2 Work performance information
.3 Procurement documentation updates
.4 Change requests
.5 PMP updates
  • Risk management plan
  • Procurement management plan
  • Schedule baseline
  • Cost baseline
.6 Project documents updates
  • Lessons learned register
  • Resource requirements
  • Requirements traceability matrix
  • Risk register
  • Stakeholder register
.7 OPAs updates
PPM
M&C

## Slide 15: Claim Administration
Contested changes or potential constructive changes are those requested changes where buyer and seller cannot reach to an agreement for payment.
Settle through negotiation
Follow the ADR (alternative dispute resolution) method established in contract.

## Slide 16: Procurement: Tips for PMP® Exam
Questions are written from buyer’s perspective
Seller is not supplying people to adjunct the buyer’s team (seller remains external to the project team)
Contracts require formality
All product and project management requirements should be specifically stated in the contract
If it is not in a contract, it can be done if a change is issued
If it is in the contract, it must be done or a change order, signed by both parties issued
Changes must be in writing

## Slide 17: Procurement: Tips for PMP® Exam
Contracts are legally binding
Contracts should help diminish project risk
Most governments back all contracts by providing a court system for dispute resolution
Questions are written by government contracting specialists of USA
Exam has very few references to International contracts
In many parts of the world (including India), contracts are informal and relationships between parties is more important than the contract
It is important to take a more formal approach to the procurement process when answering questions

## Slide 18: Big Concepts
Contract Structure
Contract Types
Legal Requirement on Contracts
Contract Change Control

## Slide 19: Contract Structure

## Slide 20: Sections of Contract
  SOW or Deliverables
  Schedule Baseline
  Performance Reporting
  Period of Performance
  Roles & Responsibilities
  Seller's Place of Performance
  Pricing
  Payment Terms
  Place of delivery
  Inspection and acceptance criteria

## Slide 21: Sections of Contract
  Warranty
  Product Support
  Limitation of liability
  Fees and retainage
  Penalties
  Incentives
  Insurance and performance bonds
  Subordinate subcontractors approvals
  Change request handling
  Termination and alternative dispute resolution Mechanism

## Slide 22: Contract Types

## Slide 23: Procurement Contract Types
Different types of contracts are more or less appropriate for different types of purchases.
  Time and material contracts
  Unit Price contracts
  Fixed Price or lump sum contracts
  Cost reimbursable contracts

## Slide 24: Contract type & Risk
Buyer
Seller
100%
0%
Risk
CPPC
CPFF
CPAF
CPIF
T&M
FPEPA
FP
FPIF

## Slide 25: Types of Contracts
Continued …
  T & M – Time & Materials
  The seller is paid for the amount of time it takes to accomplish the work & also reimbursed for the materials to complete the work
  Unit Price – Fixed Price
  The seller is paid a fixed price for an agreed upon Unit of Supply

## Slide 26: Types of Contracts- Fix Price Plus
  FFP – Firm Fixed Price
  Lump sum/firm Fixed Price. Seller at most risk
FPIF – Fixed Price Incentive Fee
Most difficult to administer. It contains a number of cost/profit schemes like, cost, target profit, target price, ceiling price and share ratio. if seller maximizes profits, an incentive is offered to reduce costs and improve efficiency price, seller effort. but no profit
FP-EPA— Fixed Price with Economic Price Adjustment
The seller is paid a fixed price. The contract is reviewed at pre-defined intervals in the project for adjustments to the contract price based on certain parameters

## Slide 27: Types of Contracts- Cost Plus
CPFF— Cost Plus Fixed Fee Not desirable from buyer’s point of view. The contractor is reimbursed its cost + a fixed fee
CPAF-Cost Plus Award Fee
Not desirable from buyer's point of view. The contractor is influenced to increase costs.
CPIF— Cost Plus Incentive Fee
Seller is reimbursed for an agreed upon performance cost along with a pre established fee plus an incentive bonus. The buyer and seller share the uncertainty to a certain degree

## Slide 28
Contract Examples
&
Exercises

## Slide 29: Contract type Example: Fixed Price
Fixed Price (FP)
  Contract = $1,100,000
  It is fixed regardless of any other information
Fixed Price Economic Price Adjustment (FPEPA)
  Contract = $1,100,000 but a price increase will be allowed in year two based on the U.S. Consumer Price Increase report for year one; or
  Contract = $1,100,000 but a price increase will be allowed in year two to account for increases in specific material costs

## Slide 30: Fixed Price Incentive Fee (FPIF)
Simple Case
  Contract = $1,100,000. For every month early the project is completed, an additional $10,000 is paid to the seller. For every month late the project is completed a penalty of $20,000 is levied on the seller
  If project is completed 2 months early, Contract = $1,120,000
  If project is completed 2 months late, Contract = $1,060,000
Complex Case
  PTA is a point on cost line upto where buyer pays the money for the service which buyer is buying. If Cost is more then PTA Profit starts dipping because customer is not paying any cost. So profits starts dipping and after some profit washes away and seller start making loss.
  PTA = [Ceiling Price - Target Price]/ Buyer's Ratio + Target Cost
  Note: Target Price = Target Cost + Target Profit

## Slide 31: Point of Total Assumption

## Slide 32: CPIF- Complex Case
Input Data for Question
Target Cost = $ 300,000 (Finish the work in this budget)
Target Profit = $ 50,000 (if seller do then he gets $50,000 for his good work)
Target Price = Target Cost + Target Profit
Ceiling Price = $ 370,000 (Seller will not spend more than in any condition else he has to bare the every extra from his pocket)
Share/Buyer-Seller Ratio = 70/30 (Share the profit or over expense in this ratio until they are below ceiling price)
If actual cost of the project is $335,000 then how much is the profit?
Calculations
PTA= ((Ceiling Price – Target Price)/buyer’s Share Ratio) + Target Cost
PTA = (370,000 - 350,000) / .7 + 300,000 => 328,571
Cost over run above PTA = PTA – Target Cost = 28,571
Between Target Cost and PTA spending (cost) will be split between the parties like this
Buyer's share (70% of 28,571) = 20,000 , Seller's share (30% of 28,571) = 8,571
Seller has to pay for extra spending over PTA ie. Actual Cost- PTA = 335,000 – 328,571 = 6,429
Profit will dip by Seller’s Share of Loss + Over Spending above PTA = 8,571 + 6,429 = 15000
Final Profit = 50,000 – 15,000 = $35,000

## Slide 33: Contract type Example: Cost Reimbursable
Cost-Plus-Percentage of Cost (CPPC)
  Contract = Cost plus 12% of costs as fee
  If seller cost = 1,000,000
    Then, Contract = $1,120,000
Cost-Plus-Fixed-Fee (CPFF)
  Contract = Cost plus a fee of $100,000
  If seller cost = 1,000,000
    Then, Contract = $1,100,000

## Slide 34: Contract type Example: Cost Reimbursable
Cost-Plus-Incentive-Fee (CPIF)
If ceiling price is not defined then
Final payout = Target cost + Fixed fee + Buyer share ratio * (Actual Cost - Target Cost)
If ceiling price is defined then
Final payout = Target cost + Fixed fee + Buyer share ratio * (Ceiling Price - Target Cost)
  Fixed fee (Target Profit) $100,000. Target cost of $1,000,000, the buyer to seller benefit/cost share ratio is 60/40. Minimum fee is $75,000, Maximum fee is $150,000.
  If project is completed at a cost of $900,000, Final Payout= $1,040,000.
  If project is completed at a cost of $1,100,000, Final Payout = $1,175,000.
Note: “Target Profit” and “Fixed Fee” are interchangeable words

## Slide 35: CPIF Example
Final payout = Target cost + Fixed fee + Buyer share ratio * (Actual Cost - Target Cost) |  |  |  | 
Final payout = Target cost + Fixed fee + Buyer share ratio * (Ceiling Price - Target Cost) |  |  |  | 
Minimum Fee: nnn, Maxmum Fee: mmm |  |  |  | 
Min Fee | NA | NA | 50 | NA
Max Fee | NA | NA | 90 | NA
Ceiling Price | NA | 1100 | NA | NA
Target Cost | 1000 | 1000 | 1000 | 1000
Fixed Feed (Target Profit) | 100 | 100 | 100 | 100
Buyer/Seller Benefit/cost sharing | 80% /20% | 80% /20% | 80% /20% | 60% / 40%
Actual Cost | 900 | 900 |  | 900
Contract Value | 1020 | 1020 |  | 1040
Profit | 120 | 120 |  | 140
Actual Cost | 1200 | 1200 | 1200 | 1100
Contract Value | 1260 | 1100 | 1190 | 1160
Profit/Loss | 60 | -160 | -70 | 60

## Slide 36: Contract type Example: Time & Material
Contract = Material $1000/CuM of concrete, Labour $200/CuM of concrete
  If actual quantity 100 CuM then Contract = $120,000
  If actual quantity 75 CuM then Contract = $90,000

## Slide 37: Legal Requirements on Contracts
  Performing the promises in the contract between seller and buyer
  Essential elements of a contract
    Offer – clearly stated in a manner that can be understood by a reasonable person
    Contract must be between competent persons (mental state, age)
    Contract must have lawful objectives

## Slide 38: Legal Requirements on Contracts
  Acceptance by the buyer, based on genuine assent of both parties
  Consideration – Most important part of the contract. It means something of value is received by the seller in exchange for meeting the promise
  Follows all laws where the contract execution occurs

## Slide 39: Procurement Management: Few More Concepts
Acronyms
  IFB- Invitation for Bid,
  RFB- Request for Bid,
  LOI- Letter of Intent,
  RFQ- Request for Quotation
  RFP- Request for Proposal
IFB or RFB/P :
  Single Price,
  High $ Value
RFQ used :
  Per Item/Hour Price,
  Lower $ Value,
  May be used to develop info in RFP.

## Slide 40: Procurement Management: Few More Concepts
T& M Used when you must begin work immediately without a procurement statement of work
If seller need to do more work in cost plus fixed fee contract then he should negotiate to change in contract. Otherwise seller will not get more than fixed fee, no matter how much he works.
An IFB is typically a request for a sealed document that lists the seller’s firm price to complete the detailed work.
A letter of intent is not binding in a court of law, it does make the seller feel more comfortable about expending funds before a contract is signed.

## Slide 41: Contract Change Control System (CCCS)
CCCS is a process for modifying the contract.
Contract change control system (CCCS) is part of integrated change control system
PM should focus on Buyer Seller relationship
Following are part of CCCS
  Paperwork
  Tracking Systems
  Dispute resolution processes
  Approval Levels necessary for authorizing changes

## Slide 43: Project Stakeholder Management

## Slide 44: Project Communications Management
  Identify Stakeholders [INITIATING]
  Plan Stakeholder Management [PLANNING]
  Manage Stakeholder Engagement [EXECUTING]
  Control Stakeholder Engagements [M&C]

## Slide 45: 46. Identify Stakeholders
Identifying all people, group or organizations that could be impacted by the project and documenting relevant information regarding their interests, involvement and impact on project success.

## Slide 46: Identify Stakeholders
.1 Expert judgment
.2 Data gathering
  • Questionnaires and surveys
  • Brainstorming
.3 Data analysis
  • Stakeholder analysis
  • Document analysis
.4 Data representation
  • Stakeholder mapping/ representation
.5 Meetings
.1 Project charter
.2 Business documents
  • Business case
  • Benefits management plan
.3 PMP
  • Communications management plan
  • Stakeholder engagement
plan
.4 Project documents
  • Change log
  • Issue log
  • Requirements documentation
.5 Agreements
.6 EEFs
.7 OPAs
.1 Stakeholder register
.2 Change requests
.3 PMP updates
  • Requirements management plan
  • Communications management plan
  • Risk management plan
  • Stakeholder engagement plan
.4 Project documents updates
  • Assumption log
  • Issue log
  • Risk register
PSTM
INIT

## Slide 47: Sample Stakeholder Analysis Matrix
 | Stakeholders |  |  |  | 
 | Ahmed | Susan | Erik | Mark | David
Organization | Internal Senior Management | Project team | Project Team | Hardware Vendor | Project manager for other internal project
Role on project | Sponsor of project and one of the compnay's founder | DBA sequencing expert | Lead Programmer | Supplies some istrument hardware | Competing for company resources
Unique Facts | Demanding, likes details, business focus, stanford MBA | Very smart, Ph.D. in biology, easy to work with, has a toddler | Best Programmer I know, weird sense of humor | Start-up company, he knows we can make him rich if this works | Nice guy, one of oldest people at company, has 3 kids in college
Level of interest | Very high | Very high | High | Very high | Low to medium
Level of Influence | Very high, can call the shots | SME, critical to success | High; hard to replace | Low; other vendors available | Low to medium
Suggestions on managing relationship | Keep informed, let him lead conversations, do as he says and quickly | Make sure she reviews specifications and leads testing; can do some work from home | Keep him happy so he stays; emphasize stock options; likes mexican food | Give him enough leads time to deliver hardware | He knows his project takes a back seat to this one, but can learn from him

## Slide 48: Sample Stakeholder Analysis Matrix
Stakeholder | Stakeholder Interest(s) in the Project | Assessment of Impact | Potential Strategies for Gaining Support or Reducing Obstacles

## Slide 49: Power/Interest Grid with stakeholders
Vendor
Sponsor, Team
Regulatory Authorities
Individual Citizens

## Slide 50: 47. Plan Stakeholder Management
Developing appropriate management strategies to effectively engage stakeholders throughout the project lifecycle

## Slide 51: Plan Stakeholders Management
.1 Expert judgment
.2 Data gathering
  • Benchmarking
.3 Data analysis
  • Assumption and constraint analysis
  • Root cause analysis
.4 Decision making
  • Prioritization/ranking
.5 Data representation
  • Mind mapping
  • Stakeholder engagement assessment matrix
.6 Meetings
.1 Project charter
.2 Project management plan
  • Resource management plan
  • Communications
  management plan
  • Risk management plan
.3 Project documents
  • Assumption log
  • Change log
  • Issue log
  • Project schedule
  • Risk register
  • Stakeholder register
.4 Agreements
.5 EEFs
.6 OPAs
.1 Stakeholder engagement plan
PSTM
PLAN

## Slide 52: 48. Manage Stakeholder Engagements
Process of communicating and working with stakeholders to meet their needs and addressing issues as they occur.

## Slide 53: Manage Stakeholders Engagements
.1 Expert judgment
.2 Communication skills
  • Feedback
.3 Interpersonal and team skills
  • Conflict management
  • Cultural awareness
  • Negotiation
  • Observation/ conversation
  • Political awareness
.4 Ground rules
.5 Meetings
.1 PMP
  • Communications management plan
  • Risk management plan
  • Stakeholder engagement plan
  • Change management plan
.2 Project documents
  • Change log
  • Issue log
  • Lessons learned register
  • Stakeholder register
.3 EEFs
.4 OPAs
.1 Change requests
.2 PMP updates
  • Communications management plan
  • Stakeholder engagement plan
.3 Project documents updates
  • Change log
  • Issue log
  • Lessons learned register
  • Stakeholder register
PSTM
EXEC

## Slide 54: Interpersonal Skills
A project manager works with team. He need to ensure that stakeholders are aligned with project. The skills which helps him in managing group of people…
Leadership
Team Building
Motivation
Communication
Influencing
Decision Making
Political & Cultural Awareness
Negotiation

## Slide 55: Management Skills
Presentation Skills
Negotiating Skills
Writing Skills
Public Speaking Skills

## Slide 56: 49. Monitor Stakeholder Engagements
Monitoring overall project stakeholder relationships and adjusting strategies and plans to engage stakeholders.

## Slide 57: Monitor Stakeholder Engagements
.1 Data analysis
  • Alternatives analysis
  • Root cause analysis
  • Stakeholder analysis
.2 Decision making
  • Multicriteria decision
  analysis
  • Voting
.3 Data representation
  • Stakeholder engagement assessment matrix
.4 Communication skills
  • Feedback
  • Presentations
.5 Interpersonal and team skills
  • Active listening
  • Cultural awareness
  • Leadership
  • Networking
  • Political awareness
.6 Meetings
.1 PMP
  • Resource management plan
  • Communications management plan
  • Stakeholder engagement plan
.2 Project documents
  • Issue log
  • Lessons learned register
  • Project communications
  • Risk register
  • Stakeholder register
.3 Work performance data
.4 EEFs
.5 OPAs
.1 Work performance information
.2 Change requests
.3 PMP updates
  • Resource management plan
  • Communications management plan
  • Stakeholder engagement plan
.4 Project documents updates
  • Issue log
  • Lessons learned register
  • Risk register
  • Stakeholder register
PSTM
M&C

## Slide 59
Professional
Responsibility
As
Integrated part of
Complete project
life cycle
Notes: PMP Preparation Processes
www.Compulinkgroup.com
412

## Slide 63: Honesty
Honesty is our duty to understand the truth and act in a Truthful manner both in our communication and in our conduct
We earnestly seek to understand the truth
We are truthful in our communications and conduct and provide in timely manner
We make commitments and promises in good faith ( implied & explicit)
We do not engage on or condone behavior that is designated to deceive others
We do not engage in dishonest behavior with the intention of personal gain or at the expense of other.

## Slide 64: Responsibility
Responsibility is our duty to take ownership for the decisions we make or fail to make, the actions we take or fail to take & the consequences that result
Make decisions and take actions based on the BEST interests of society, Public safety and the environment
We accept those assignments that are consistent with our background, experience, skills and qualifications
We inform ourselves and uphold the policies, rules and regulations and laws that governs our work, professional and volunteer activities
We report unethical or illegal conduct to appropriate management & if necessary to those affected by the conduct
We bring violations of this Code to the attention of the appropriate body for resolution. We only file ethics complaints when they are substantiated by facts.
Notes: PMP Preparation Processes
www.Compulinkgroup.com
417

## Slide 65: Respect
Respect is our duty to show a high regard for ourselves, others and the resources entrusted to us
We inform ourselves about norms and customs of others and avoid engaging in behaviors they might consider disrespectful
We listen to others points of view , seeking to understand them
We approach directly those persons with whom we have conflict
We conduct ourselves in a professional manner
We negotiate in good faith, do not exercise the power of our expertise or position to influence decisions

## Slide 66: Fairness
Fairness is our duty to make decisions and act impartially & Objectively. Our conduct must be free from competing self interest , Prejudice and favoritism.
We demonstrate transparency in decision making and constantly re-examine our impartiality .
We provide equal access to information to those authorized & equal opportunities to qualified candidates
We do not discriminate against others based on, but not limited to , Gender, Race, Age, Religion, Disability, Nationality or Sexual orientation.

## Slide 67: Fairness
Conflict of Interest:
We proactively and fully disclose any real or potential conflicts of interest to the appropriate stakeholders.
When we realize that we have a real or potential conflict of interest :
  We refrain from engaging in the decision making process or otherwise
  attempting to influence outcome s, unless or until we have made full
  disclosure to the affected stakeholders.
We do not hire or fire, reward or punish, or award or deny contracts based on personal considerations. Including but not limited to Favoritism, Nepotism, or Bribery.

## Slide 68: Ethics Quick Test
  Texas Instruments “Ethics Quick Test” for making ethical decisions
  Is the action legal?
  Does it comply with your understanding of company values?
  If you do it, will you feel bad?
  How will it look in the newspaper?
  If you know it is wrong, do not do it.
  If you are not sure, ask.
  Keep asking until you get an answer.
Notes: What are some examples of projects?

## Slide 69: Project Manager’s Oath of Professional Responsibility

## Slide 70: Professional Responsibility
  Ensure individual integrity
  Adhere to legal requirements and ethical standards
  Protect Stakeholders
  Share lessons learned and other relevant information
  Build capabilities of colleagues
  Advance project management professionalism
  Improve competencies as project manager
  Balance stakeholder interests in project
  Respect cultural ethnic and personal differences
  Ensure collaborative project management environment
  Comply with all organizational rules and policies
Notes: What are some examples of projects?

## Slide 71: Professional Responsibility
  Provide accurate and truthful representations in cost estimates
  Provide accurate and truthful representations in project reports
  Report violations of policies, procedures and code of ethics
  Strive for fair resolutions
  Satisfy competing needs and objectives
  Interact with others in a professional manner
  Be responsible for satisfying the complete scope and objectives of customer requirements
  Maintain and respect confidential information
Notes: What are some examples of projects?

## Slide 72: Professional Responsibility
  Ensure that a conflict of interest does not interfere with professional judgment
  Disclose conflict of interest to customer
  Disclose circumstances that could be construed as conflicts of interest
  Refrain from offering or accepting inappropriate payments, gifts, or other forms of compensation
  Adhere to all applicable laws or customs of the country where services are being provided
  Respect intellectual property developed or owned by others
  Act in a accurate, truthful and competent manner
Notes: What are some examples of projects?

## Slide 74
Hari P Thapliyal,
PMP, PMI-ACP, MCITP, Princ2 Practitioner, CSM, MBA, MCA, CIC, PGDFM
PMO Architect & Project Management Evangelist
Profile: http://in.linkedin.com/in/harithapliyal
For content related queries please contact me via
hari.Prasad@vedavit-ps.com
This document is proprietary and confidential. It remains the property of Vedavit Project Solutions at all times. No part of this document may be used, reproduced, or transmitted in any form or by any means electronic, including photocopying and recording, for any purpose without express consent of Vedavit Project Solutions.