## Sheet4
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | Integration | Scope | Schedule | Cost | Quality | Resources | Communication | Risk | Procurement | Stakeholder
Data Gathering Tools and Techniques
1 | Benchmarking | 5: 5.2; 8: 8.1; 13: 13.2
2 | Brainstorming | 4: 4.1,4.2; 5: 5.2; 8: 8.1; 11: 11.2; 13: 13.1
3 | Check-sheets | 8: 8.3
4 | Checklists | 4: 4.2; 8: 8.2,8.3; 11: 11.2
5 | Focus-groups | 4: 4.1,4.2; 5: 5.2
6 | Interviews | 4: 4.1,4.2; 5: 5.2; 8: 8.1; 11: 11.2,11.3,11.4,11.5
7 | Market-research | 12: 12.1
8 | Questionnaires-and-surveys | 5: 5.2; 13: 13.1
9 | Statistical-sampling | 8: 8.3
Data Analysis Tools and Techniques
1 | Alternatives-analysis | 4.5, 4.6 | 5.1, 5.4 | 6.1, 6.4 | 7.1, 7.2 | 8.2 | 9.2, 9.6 |  | 11.5 |  | 13.4
2 | Assessment of other risk parameters | 11: 11.3
3 | Assumption and constraint analysis | 7: 7.2; 8: 8.1; 11: 11.2
4 | Cost of quality
5 | Cost-bene t analysis | 4: 4.5, 4.6; 8: 8.1; 9: 9.6; 11: 11.5
6 | Decision tree analysis | 11: 11.4
7 | Document analysis | 4: 4.7; 5: 5.2; 8: 8.2; 11: 11.2; 13: 13.1
8 | Earned value analysis | 4: 4.5; 6: 6.6; 7: 7.4; 12: 12.3
9 | In uence diagrams | 11: 11.4
10 | Iteration burndown chart | 6: 6.6
11 | Make-or-buy analysis | 12: 12.1
12 | Performance reviews | 6: 6.6; 8: 8.3; 9: 9.6; 12: 12.3
13 | Process analysis | 5: 8.2
14 | Proposal evaluation | 4: 12.2
15 | Regression analysis | 4: 4.7
16 | Reserve analysis | 6: 6.4; 7: 7.2,7.3,7.4; 11: 11.6
17 | Risk data quality assessment | 11: 11.3
18 | Risk probability and impact assessment | 11: 11.3
19 | Root cause analysis | 4: 4.5; 8: 8.2,8.3; 11: 11.2; 13: 13.2,13.4
20 | Sensitivity analysis | 11: 11.4
21 | Simulation | 6: 6.5; 11: 11.4
22 | Stakeholder analysis | 11: 11.1; 13: 13.1,13.4
23 | SWOT analysis | 11: 11.2; 13: 13.2
24 | Technical performance analysis | 11: 11.7
25 | Trend analysis | 4.5,4.7 | 5.6 | 6.6 | 7.4 |  | 9.6 |  |  | 12.3
26 | Variance analysis | 4: 4.5,4.7; 5: 5.6; 6: 6.6; 7: 7.4
27 | What-if scenario analysis | 6: 6.5, 6.6
Data Representation Tools and Techniques
1 | Afi nity diagrams | 5: 5.2; 8: 8.2
2 | Cause-and-effect diagrams | 8: 8.2, 8.3
3 | Control charts | 8: 8.3
4 | Flowcharts | 8: 8.1,8.2
5 | Hierarchical charts | 9: 9.1
6 | Histograms | 8: 8.2,8.3
7 | Logical data model | 8: 8.1
8 | Matrix diagrams | 8: 8.1,8.2
9 | Matrix-based charts | 9: 9.1
10 | Mind mapping | 5: 5.2; 8: 8.1; 13: 13.2
11 | Probability and impact matrix | 11: 11.3
12 | Scatter diagrams | 8: 8.2,8.3
13 | Stakeholder engagement assessment matrix | 10: 10.1,10.3; 13: 13.2,13.4
14 | Stakeholder mapping/ representation | 13: 13.1
15 | Text-oriented formats | 9: 9.1
Decision-Making Tools and Techniques
1 | Multicriteria decision analysis | 4.6 | 5.2, 5.3 |  |  | 8.1, 8.2 | 9.3 |  | 11.5 |  | 13.4
2 | Voting | 4: 4.5,4.6; 6: 5.2,5.5; 7: 6.4; 8: 7.2; 13: 13.4
Communication Skills Tools and Techniques
1 | Feedback | 10: 10.2; 13: 13.4
2 | Presentations | 10: 10.2; 13: 13.4
Interpersonal and Team Skills Tools and Techniques
1 | Active listening | 4: 4.4; 10: 10.2; 13: 13.4
2 | Communication styles assessment | 10: 10.1
3 | Con ict management | 4: 4.1, 4.2; 9: 9.4, 9.5; 10: 10.2; 13: 13.3
4 | Cultural awareness | 4: 10.1,; 10: 10.2; 13: 13.3,13.4
5 | Decision making | 9: 9.5
6 | Emotional intelligence | 9: 9.5
7 | Facilitation | 4: 4.1,4.2,4.4; 5: 5.2, 5.3; 12: 11.2,11.3,11.4
8 | In uencing | 9: 9.4,9.5,9.6; 11: 11.6
9 | Leadership | 4: 4.4; 9: 9.5; 13: 13.4
10 | Meeting management | 4: 4.1, 4.2; 10: 10.2
11 | Motivation | 9: 9.4
12 | Negotiation | 9: 9.3,9.4,9.6; 12: 12.2; 13: 13.3
13 | Networking | 4: 4.4; 10: 10.2; 13: 13.4
14 | Nominal group technique | 5: 5.2
15 | Observation/ conversation | 5: 5.2; 10: 10.3; 13: 13.3
16 | Political awareness | 4: 4.4; 10: 10.1,10.2; 13: 13.3,13.4
17 | Team building | 9: 9.4
Ungrouped Tools and Techniques
1 | Advertising | 12: 12.2
2 | Agile release planning | 6: 6.5
3 | Analogous estimating | 6: 6.4; 7: 7.2; 9: 9.2
4 | Audits | 8: 8.2; 11: 11.7; 12: 12.3
5 | Bidder conferences | 12: 12.2
6 | Bottom-up estimating | 6: 6.4; 7: 7.2; 9: 9.2
7 | Change control tools | 4: 4.6
8 | Claims administration | 12: 12.3
9 | Colocation | 5: 9.4
10 | Communication methods | 10: 10.1,10.2
11 | Communication models | 10: 10.1
12 | Communication requirements analysis | 10: 10.1
13 | Communication technology | 9: 9.4; 10: 10.1,10.2
14 | Context diagram | 5: 5.2
15 | Contingent response strategies | 11: 11.5
16 | Cost aggregation | 7: 7.3
17 | Critical path method | 6: 6.5,6.6
18 | Decomposition | 5: 5.4; 6: 6.3
19 | Dependency determination and integration | 6: 6.3
20 | Design for X | 8: 8.2
21 | Expert judgment | 4.1,4.2,4.4,4.5,4.6,4.7 | 5.1,5.2,5.3,5.4 | 6.1,6.2,6.4 | 7.1,7.2,7.3,7.4 | 8.1 | 9.1,9.2 | 10.1,10.3 | 11.1,11.2,11.3,11.4,11.5,11.6 | 12.1,12.2,12.3 | 13.1,13.2,13.3
22 | Financing | 7: 7.3
23 | Funding limit reconciliation | 7: 7.3
24 | Ground rules | 13: 13.3
25 | Historical information review | 7: 7.3
26 | Individual and team assessments | 9: 9.4
27 | Information management | 4: 4.4
28 | Inspections | 5: 5.5; 8: 8.3; 12: 12.3; 13: 13.3
29 | Knowledge management | 4: 4.4; 6: 6.3,6.5,6.6
30 | Leads and lags
31 | Meetings | 4.1,4.2,4.3,4.5,4.6,4.7 | 5.1 | 6.1,6.2,6.4 | 7.1 | 8.1,8.3 | 9.1,9.2,9.4 | 10.1,10,2,10.3 | 11.1,11.2,11.3,11.6 | 12.1 | 13.1,13.2,13.3,13.4
32 | Organizational theory | 9: 9.1
33 | Parametric estimating | 6: 6.4; 7: 7.2; 9: 9.2
34 | Pre-assignment | 9: 9.3
35 | Precedence
36 | Precedence diagramming method | 6: 6.3
37 | Problem solving | 8: 8.2; 9: 9.6
38 | Product analysis | 5: 5.3
39 | Project management information system | 4.3 |  | 6.3,6.5,6.6 | 7.2,7.4 |  | 9.2,9.5,9.6 | 10.2,10.3 | 11.6
40 | Project reporting | 8: 8.2
41 | Prompt lists | 11: 11.2
42 | Prototypes | 5: 5.2
43 | Quality improvement methods | 8: 8.2; 9: 9.4
44 | Recognition and rewards
45 | Representations of uncertainty | 11: 11.4
46 | Resource optimization | 6: 6.5, 6.6
47 | Risk categorization | 11: 11.3
48 | Rolling wave planning | 6: 6.2
49 | Schedule compression | 6: 6.5, 6.6
50 | Schedule network analysis | 6: 6.5
51 | Source selection analysis | 12: 12.1
52 | Strategies for opportunities | 11: 11.5
53 | Strategies for overall project risk | 11: 11.5
54 | Strategies for threats | 11: 11.5
55 | Test and inspection planning | 8: 8.1
56 | Testing/product evaluations | 8: 8.3
57 | Three-point estimating | 6: 6.4; 7: 7.2
58 | To-complete performance index | 7: 7.4
59 | Training | 9: 9.4
60 | Virtual teams | 9: 9.3,9.4