## Sheet3
| Business Case |  | Organization |  | Quality |  | Plans |  | Risk |  | Change |  | Progress
Starting Up a Project (SU) | During start up an outline Business case is compiled together with the Project End Product. This is used to judge the viablity and feasiblity of the project | Starting Up a Project (SU) | During start Up the first action is to appoint a Project Executive and a Project Manager. After examining lessons from earlier projects the project management team (PMT) is designed and appointed | Starting Up a Project (SU) | The Quality Theme is triggered during SU when the Project Product Description is made with Quality Expectations and Acceptance Criteria | Starting Up a Project (SU) | The last step during SU is the making of the Initiation Stage Plan. | Starting Up a Project (SU) | During SU some major risks may be identified as part of the outline Business Case. | Starting Up a Project (SU) | The Quality Expectaions in the Project Prodct Description may provide clues to implemeting this theme during initiation | Starting Up a Project (SU) | Project tolerance are set by Corporate or Program Management
Directing A Project (DP) | Consecutive versions of the Business Case are approved during: Authorize Initiation, Authorize Project, Authorize Stage or Exception Plan | Directing A Project (DP) | The PMT structure and roles are approved as part of the Project Brief and the PID | Directing A Project (DP) | Project Product Description (SU) and Product Descriptions (IP) are approved (Baselined) by the Project Board | Directing A Project (DP) | Approval of: Initiation Stage Plan (SU), Project Plan (IP), Stage Plan (MSB), Exception Plan (MSB) Updated Project Plan (MSB), Benefits Review Plan (IP, MSB) | Directing A Project (DP) | Approval of Risk Management Strategy, Risk planning, Risk Tolerances and Risk Budget | Directing A Project (DP) | Approval of Configuration Management Strategy & setting the Change Budget | Directing A Project (DP) | Stage tolerances are set by the Project Board
Initiating A Project (IP) | After planning the project and setting-up project controls the Detailed Business Case is created together with the Benefits Review Plan | Initiating A Project (IP) | During IP some extra roles may be described in the strategies for Quality, Risk and Configuration Management | Initiating A Project (IP) | A Quality Management Strategy is created. The Project Product Description is improved and Product Descriptions are generated also the Quality Register is created | Initiating A Project (IP) | Plans are designed and overall Project Plan is created | Initiating A Project (IP) | Prepare the Risk Management Strategy | Initiating A Project (IP) | Prepare the Configuration Management Strategy & establish procedures for Configuration Management, issue & change control | Initiating A Project (IP) | Define Management Stages, establish event driven and time-driven controls. Format highlight and checkpoint reports
Managing Stage Boundaries (MSB) | After the next stage is planned The project Plan and Business Case are updated including the Benefits Review Plan | Managing Stage Boundaries (MSB) | Some role adjustments are possible for a following stage | Managing Stage Boundaries (MSB) | Product Descriptions are made or updated. Quality review is planned and the Quality Register is updated | Managing Stage Boundaries (MSB) | Stage or Exception Plan is Created | Managing Stage Boundaries (MSB) | Manage Risk | Managing Stage Boundaries (MSB) | Manage issues | Managing Stage Boundaries (MSB) | Update Project Plan & set stage tolerances in Stage Plan
Controlling a Stage (CS) | The business case is verified against issues and risks | Controlling a Stage (CS) |  | Controlling a Stage (CS) | Quality issues are dealt with within tolerances or escalated to the Project Board | Controlling a Stage (CS) | Stage Plan and Project Plan are used to control progress Work Packages are Created | Controlling a Stage (CS) | Manage Risk | Controlling a Stage (CS) | Manage issues | Controlling a Stage (CS) | Monitor Progress against Stage Plan

## Sheet2
| Starting Up a Project (SU) | Directing A Project (DP) | Initiating A Project (IP) | Managing Stage Boundaries (MSB) | Controlling a Stage (CS) | Managing Product Delivery (MP) | Closing a project (CP)
Business Case | During start up an outline Business case is compiled together with the Project End Product. This is used to judge the viablity and feasiblity of the project | Consecutive versions of the Business Case are approved during: Authorize Initiation, Authorize Project, Authorize Stage or Exception Plan | After planning the project and setting-up project controls the Detailed Business Case is created together with the Benefits Review Plan | After the next stage is planned The project Plan and Business Case are updated including the Benefits Review Plan | The business case is verified against issues and risks | Issues are identified that may impact the Business Case (See Controlling A Stage) (CS) | The Benefits Review Plan is updated
Organization | During start Up the first action is to appoint a Project Executive and a Project Manager. After examining lessons from earlier projects the project management team (PMT) is designed and appointed | The PMT structure and roles are approved as part of the Project Brief and the PID | During IP some extra roles may be described in the strategies for Quality, Risk and Configuration Management | Some role adjustments are possible for a following stage |  |  | Once the Project Board confirmed project closure the resources can be released from the project. A review of team performance will be part of the project evaluation
Quality | The Quality Theme is triggered during SU when the Project Product Description is made with Quality Expectations and Acceptance Criteria | Project Product Description (SU) and Product Descriptions (IP) are approved (Baselined) by the Project Board | A Quality Management Strategy is created. The Project Product Description is improved and Product Descriptions are generated also the Quality Register is created | Product Descriptions are made or updated. Quality review is planned and the Quality Register is updated | Quality issues are dealt with within tolerances or escalated to the Project Board | Quality Review Technique is used to accept products | Acceptance records are Obtained
Plans | The last step during SU is the making of the Initiation Stage Plan. | Approval of: Initiation Stage Plan (SU), Project Plan (IP), Stage Plan (MSB), Exception Plan (MSB) Updated Project Plan (MSB), Benefits Review Plan (IP, MSB) | Plans are designed and overall Project Plan is created | Stage or Exception Plan is Created | Stage Plan and Project Plan are used to control progress Work Packages are Created | Work Packages are accepted and optional Team Plans are created | Project Plan is updated
Risk | During SU some major risks may be identified as part of the outline Business Case. | Approval of Risk Management Strategy, Risk planning, Risk Tolerances and Risk Budget | Prepare the Risk Management Strategy | Manage Risk | Manage Risk | Manage Risk | Handover of Risk Register, evaluate and feed Lessons Learned
Change | The Quality Expectaions in the Project Prodct Description may provide clues to implemeting this theme during initiation | Approval of Configuration Management Strategy & setting the Change Budget | Prepare the Configuration Management Strategy & establish procedures for Configuration Management, issue & change control | Manage issues | Manage issues | Manage issues | Handover of products according to the Configuration Management Strategy
Progress | Project tolerance are set by Corporate or Program Management | Stage tolerances are set by the Project Board | Define Management Stages, establish event driven and time-driven controls. Format highlight and checkpoint reports | Update Project Plan & set stage tolerances in Stage Plan | Monitor Progress against Stage Plan | Monitor Progress against Stage and optional Team Plan | Evaluate project and feed Lessons Learned