## Sheet1
| SU |  | 6 |  | IP |  | 8
Mgmt Product? | What? | Who Produces? | Process | Mgmt Product? | What? | Who Produces? | Process
DL |  |  | Appoint Exec/PM | RMS | C |  | Prep RMS
Exec Role Desc | C & Confirm |  |  | RR | C | PS
PM Role Desc | C & Confirm |  |  | CnMS | C |  | Prep Con MS
Project Mandate | Provide |  |  | CIR | C | PS
LL | C |  | Capture Prev Lessons | IR | C | PS
DL |  |  | Design & Appoint PMT | QMS | C |  | Prep QMS
PMT Role | C |  |  | QR | C | PS
PMT Struc | C |  |  | CmMS | C |  | Prep Com MS
Appoint PMT | Confirm |  |  | Proj Controls | C |  | Setup Proj Controls
OBC | C | Exec | Prepare OBC | Role Descr | U
PPD | C | PM |  | PMT Stru | U
DL | U |  |  | PP | C |  | Create PP
Proj Approach | C/Select |  | Select Approach & Assemble PB | PD | C
Additional R&R | C |  |  | CIR | C/A | PS
PB | Assemble |  |  | PMT Stru | U
DL | U |  |  | Role Descr | U
SP | C |  | Plan IS | BRP | C |  | Refine BC
DL | U |  |  | Detail BC | C
|  |  |  | PID | Assemble |  | Assemble PID
| DP |  | 5 |  | MSB |  | 5
Mgmt Product? | What? | Who Produces? | Process | Mgmt Product? | What? | Who Produces? | Process
PB | Approve |  | Authorize Init | PID | U |  | Plan Next Stage
Init Stage Plan | Approve |  |  | SP | U
LL | Review |  | Authorize Proj | CIR | C/U
PID | Approve |  |  | R Reg | U
BRP | Approve |  |  | I Reg | U
Specialized Prod | Approve |  | Authorize Stage/EP | Q Reg | U
ESR | Approve |  |  | PP | U |  | Update PP
LR | Distribute |  |  | I Reg | U
Followon Action Reco | Distribute |  |  | R Reg | U
SP+1 | Approve |  |  | BC | U |  | Update BC
EP | Approve |  |  | BRP | U
Updated PID | Approve |  |  | R Reg | U
Updated BRP | Approve |  |  | I Reg | U
HLR | Inspect |  | Give Adhoc Dir | ESR | C |  | Report Stage End
ER | Respond |  |  | LR | C
Issue | Raise |  |  | Followon Action Recm | C
EPR | Approve |  | Authorise Proj Closure | PID | U |  | Product Exception Plan
LR | Distribute |  |  | EP | C
Followon Action Reco | Distribute |  |  | CIR | C/U
Updated BC | Confirm |  |  | R Reg | U
Updated BRP | Approve |  |  | I Reg | U
|  |  |  | Q Reg | U
| CS |  | 8 |  | MPD |  | 3
Mgmt Product? | What? | Who Produces? | Process | Mgmt Product? | What? | Who Produces? | Process
WP | C/A | PM | Authorize WP | TP | C |  | Accepting WP
CIR | C/U | PS |  | Risk | Raise
Q Reg | U | PS |  | Q Reg | U
R Reg | U |  |  | WP | Approve
I Reg | U |  |  | Specialist Prod | C |  | Execute WP
TP | R | TM |  | Q Reg | U | PS
SP | U |  |  | CIR | U | PS
CPR | R | TM | Review WP | TP | U
TP | R | TM |  | CPR | C
SP | U |  |  | Issue | Raise
CIR | U | PS |  | Risk | Raise
R Reg | U |  |  | Approval Record | Obtain
I Reg | U |  |  | WP | U | TM | Deliver WP
CIR | Confirm | PS | Receive Completed WP | TP | U | TM
SP | U
R Reg | U |  | Review Stage Status |  | CP |  | 5
I Reg | U |  |  | Mgmt Product? | What? | Who Produces? | Process
SP | U |  |  | PP | U |  | Prep Planned Closure
LL | U |  |  | PSA | C | PS
IR | U |  |  | I Reg | U |  | Prep Premature Closure
HLR | C |  | Report Highlights | PP | U
DL | U |  | Capture & Examine I&R | PSA | C
IR | C |  |  | Additional Work Estimate | C
I Reg | U |  |  | Followon Action Recm | C/U |  | Handover Product
R Reg | U |  |  | CIR | U
ER | C |  | Escalate I&R | BRP | U
I Reg | U |  |  | Acceptance Records | Obtain
R Reg | U |  |  | ERP | C |  | Evaluate Proj
IR | U |  |  | LR | C
I Reg | U |  | Take Corrective Actions | I Reg | Close |  | Recommend Project Closure
R Reg | U |  |  | R Reg | Close
IR | U |  |  | Q Reg | Close
SP | U |  |  | DL | Close
CIR | U |  |  | LL | Close
DL | U |  |  | Draft Project Closure Notification | Prepare