## Slide 1: Quiz
  Which is the purpose of Risk Register
Capture risks that may occur during the project
Record how risk management activities will be undertaken on the project
Record the risk tolerance for the project
Capture issues which are impacting on the delivery of the project objectives
Correct Answer: A
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 2: Quiz
  Which process provides the information required to decide whether to authorize the delivery of the project?
Directing a project
Initiating a project
Managing Product Delivery
Starting up a project
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 3: Quiz
  What product forms the ‘contract’ between the Project Board and the Project Manager
  Project Brief
  Project Mandate
  Project Plan
  Project Initiation Documentation
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 4: Quiz
  What product identifies the management stages and other major control points in a project?
  Business Case
  Project Plan
  Work Package
  Project Brief
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 5: Quiz
  Which should be funded by a Change Budget
Increase in agreed scope
Initiation stage
Change Authority
Handover activities
Correct Answer: A
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 6: Quiz
  Which regular report provides the Project Board with a summary of stage status
Communication Management Strategy
Project Brief
Highlight Report
Checkpoint Report
Correct Answer: C ( Time driven Report )
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 7: Quiz
  What is the purpose of the Change Theme ?
Prevent changes to baselined products
Identify, assess and control any potential and approved changes to the baselined product
Establish the mechanism to monitor and compare actual achievements against those planned
Assess and control uncertainty
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 8: Quiz
  Which is the purpose of the Risk theme?
Establish as procedure to ensure that every change is agreed by the relevant authority before it takes place
Establish a cost effective procedure to identify, assess and control uncertainty
Establish a mechanism to control any unacceptable deviation from plan
Establish mechanism to manage risks at the corporate or programme level of an organsation
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 9: Quiz
  Which activity does NOT have to take place before the initiation of a project is authorized
Appoint at least the Executive
Define the quality techniques to be applied during the project
Prepare an outline Business Case
Assemble the project Brief
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 10: Quiz
  Which is shown in product break down structure?
Management stages, major products and control points
In which order should the products be created
The major products that are to be developed in a plan
What resources are required to develop the products
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 11: Quiz
  Which does the Executive need to ensure is in place before the project is initiated?
All work packages are authorized
An understanding of how the project will contribute to corporate objectives
The project plan has been approved
The project initiation document is complete
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 12: Quiz
  Why should the project manager escalate an issue to the project board
The project board is responsible for determining the priority of all issues
Direction is required on the best response for preventing the issue from occurring
The issue is forecast to cause a deviation beyond stage tolerance and advice is required
Escalating issues is a means of providing project board with a regular update on their status
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 13: Quiz
  Which is a typical core activity within a configuration management procedure?
Quality Assurance
Risk Management
Verification and audit
Progress reporting
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 14: Quiz
  Which is the purpose of the Plan theme?
Define the means by which products will be verified as fit for purpose
Establish the project’s structure of accountability
Assesses and control uncertainty
Understand whether the targets are achievable
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 15: Quiz
  When considering risk, which describes an opportunity in the project?
An uncertain event that could have a negative impact on objectives
An uncertain event that could have a favorable impact on objectives
An event that has occurred resulting in a negative impact on objectives
An event that has occurred resulting in a favorable impact on objectives
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 16: Quiz
  Which of the following describes a use of a Configuration Item Record
To record how changes to a product will be controlled
To provide information on the approval procedure for the work package
To record the history of a product
To pass responsibility for the delivery of a product to a team manager
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 17: Quiz
  Which of the following is a type of issue
  Problem / concern
  Request for change
  External product
  Off-specification
1, 2, 3
1, 2, 4
1, 3, 4
2, 3, 4
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 18: Quiz
  Which is a product description used for?
To define any inherent risks in a product
To record the results of any quality checks carried out on a product
To define the quality criteria for a product
To record acceptance of a product following its quality check(s)
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 19: Quiz
  Which role is responsible for the management of risk assigned to it?
Project Support
Risk Owner
Risk Actionee
Project Assurance
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 20: Quiz
  Which theme provides the controls to escalate any forecast beyond tolerance to the next management level?
Business Case
Plans
Progress
Quality
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 21: Quiz
  If the Work package tolerance is forecast to be exceeded to whom should the Team Manager Report?
Corporate Management
Project Board
Project Assurance
Project Manager
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 22: Quiz
  In which product would you find quality tolerance defined?
Product Description
Project Plan
Quality Register
Configuration Item Record
Correct Answer: A
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 23: Quiz
  Identify the missing words in the following sentence. During the initiating a project process the [?] before a project is authorized.
Minimum necessary is done to decide if a project is worth while
Aim is to establish sound foundation to achieve a successful project
Project Brief is assembled and approved
Project approach appropriate for delivering a project is selected
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 24: Quiz
  Which describes risk impact
Timeframe within which the risk might occur
The trigger that occurred giving rise to the risk
The effect of risk on the delivery of project objectives
How likely the risk is to occur in the given project situation
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 25: Quiz
  Which of the following is true for a project plan?
Used by the project board to monitor project process
Identifies the major control points
Used as the basis for day-to-day control by the project manager
Should align to the corporate or programme management plan
1, 2, 3
1, 2, 4
1, 3, 4
2, 3, 4
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 26: Quiz
  When considering how long the management stages should be, which might be a reason for one stage to be longer than others?
A substantial amount of the project budget is spent
More human resources are required than in other stages
The risk is lower
No changes to the project management team are envisaged
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 27: Quiz
  Which risk response type is NOT recommended to respond to an opportunity
Accept
Exploit
Share
Reject
Correct Answer: A
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 28: Quiz
  Identify the missing words in the following sentence. The [?] is one of the levels of plan recommended by PRINCE2.
Benefit Review Plan
Exception Plan
Product Status Account
Stage Plan
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 29: Quiz
  Which describes the “Identify Risks” steps within the recommended risk management procedure
Identify responses to risks documented in the Business Case
Gather information about the project environment and objectives
Identify the roles to be involved in risk management activities
Identify uncertainties that may impact the delivery of the project objectives
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 30: Quiz
  When are project closure activities planned?
During the initiation stage
When the stage plan for the final management stage is produced
As the first activity in the closing a project process
In the last work package allocated to a Team Manager
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 31: Quiz
  Which is the purpose of Lessons Report?
Improve the project management method for future projects
Details open issues and risks that need to be managed after the project has closed
Compare the actual performance of the final stage against its plan
Provide a summary of the benefits realized during the project
Correct Answer: A
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 32: Quiz
  Which may be funded from a risk budget?
Corrections due to off-specifications
Impact analysis of request for change
Implementation of a fallback plan
Preparation of the Risk Management Strategy
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 33: Quiz
  What is described as an organization's unique attitude towards risk taking ?
Risk appetite
Risk management
Risk evaluation
Risk tolerance
Correct Answer: A
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 34: Quiz
  Which is a typical core activity with in a configuration management procedure
  Assessment
  Communication
  Quality control
  Status accounting
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 35: Quiz
  Which is a risk cause?
  The actions required to resolve a risk
  The impact that the risk would have on a project if it materializes
  The likelihood of a risk occurring
  The source of a risk
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 36: Quiz
  Which statement describes the responsibilities of a risk actionee?
  Identifying risk to the project that might occur in their department
  Owning and authorizing the use of the risk budget to fund risk responses
  Managing, monitoring and controlling of all aspects of an assigned risk
  Carrying out a risk response action to respond to a particular risk
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 37: Quiz
  Which is a purpose of the initiating a project process?
  Produce a stage plan for each stage of a multi-stage project
  Enable the project board to decide whether it is worthwhile to initiate a project
  Provide a fixed point at which acceptance for the project product is confirmed
  Enable the organization to understand the work that needs to be done to deliver the projects product
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 38: Quiz
  What product provides details about the latest version numbers of a project’s products?
Project Product Description
Product Status Account
Project Plan
Issue register
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 39: Quiz
  What product identifies the management stages and other major control points in a project?
Business Case
Project plan
Work package
Project brief
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 40: Quiz
  Which of the following would be recorded in the Issue Register?
  Problems that require formal management
  Risks with high probability
  Suggested improvements to baselined products
  Requested additions to scope
1, 2, 3
1, 2, 4
1, 3, 4
2, 3, 4
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 41: Quiz
  In which product does a project manager define the time and cost tolerance for the work to be done by a team manager?
Product description
Team Plan
Work package
Stage plan
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 42: Quiz
  Which is the purpose of an End Stage Report?
Support the project board’s decision on what action to take next
Summarize how the project performed against the version of the project initiation document used to authorize it
Provide the detailed analysis of a deviation and offer options for the way to proceed
Provide a plan for the next stage of the project
Correct Answer: A
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 43: Quiz
  Which step in the issue and change control procedure evaluates options to respond to an issue that is being managed formally?
Capture
Examine
Propose
Decide
Correct Answer: C ( Capture, Examine, Propose, Decide, Implement )
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 44: Quiz
  Which role does NOT set tolerances?
Corporate or Programme management
Project Board
Change Authority
Project Manager
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 45: Quiz
  Which process provides progress information on a team’s work to the Project Manager?
Controlling a stage
Directing a stage
Managing a stage boundary
Managing product delivery
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 46: Quiz
  What is the first task of product based planning?
Produce the initiation stage plan
Write the project product description
Identify dependencies
Create the product breakdown structure
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 47: Quiz
  Why is it crucial that the project product description clearly defines acceptable methods?
Enables project assurance to authorize quality activities
Defines how all project products will be reviewed and approved
Defines how it will be proven that the completed project product meets the customer’s expectations
Provides confirmation that all project products have met their quality criteria
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 48: Quiz
  Which is the change authority role permitted to authorize?
Risks to the project
Adjustments to the limits on the change budget
Changes the stage tolerance
Changes to the project that do not exceed a defined budget
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 49: Quiz
  Which does the Change theme consider a prerequisite for effective issue and change control?
Configuration management system
Manage by exception
Quality planning
Information needs for stakeholders
Correct Answer: A
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 50: Quiz
  Which is NOT undertaken during the Initiating a project process
Review why the project is needed
Identify if the project is sufficiently aligned with corporate objectives
Show how the outcome is to be achieved
Appoint an Executive and project manager
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 51: Quiz
  Which describes risk appetite?
An organizations unique attitude towards risk taking
The risk to the expected benefits
A common set of risk categories, risk scales and evaluation techniques
The budget set side for potential changes to the scope of the project
Correct Answer: A
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 52: Quiz
  What is a type of issue?
A Lesson
A request for change
An exception report
A risk with an estimated high impact
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 53: Quiz
  Identify the missing word[s] in the following sentence.
  PRINCE2 recommends three levels of [?] to reflect needs of the different levels of management involved in the project.
Management strategies
Plan
Stakeholders interests
Time driven controls
Correct Answer: B ( Project Plan, Stage Plan, Team Plan-Optional )
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 54: Quiz
  Which risk response type is appropriate to respond to a threat?
Exploit
Enhance
Reject
Transfer
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 55: Quiz
  Which of the following is NOT identified in a product description?
The quality specification to which a product must be produced
The purpose of the product must fulfill
The skills required to undertake quality control of a product
The time and cost tolerances for a creation of a product
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 56: Quiz
  Identify the missing words in the following sentence?
  At the end of a stage, the [?] should be used to check whether there is a requirement to send the copies of the end stage report to external interested parties
Stage Plan
Communication Management Strategy
Follow-on action recommendations
Quality Management strategy
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 57: Quiz
  Which theme provides the controls to escalate any forecast beyond tolerance to the next management level?
Business Case
Plan
Progress
Quality
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 58: Quiz
  Which provides a single source of reference that may be used by people joining a project after it has been initiated so they can quickly and easily find out how the project is being managed ?
Project Brief
Project Initiation Document
Project Mandate
Project Product Description
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 59: Quiz
  During the initiating a project process, which product is updated to incorporate the estimated time and cost from the project plan?
Project Product description
Business Case
Project Brief
Project Mandate
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 60: Quiz
  Which is the purpose of Risk Theme?
Establish a procedure to ensure that every change is agreed by the relevant authority before it takes place
Establish a cost-effective procedure to identify, assess and control uncertainty
Establish a mechanism to control any unacceptable deviation from plan
Establish mechanism to manage risks at the corporate or programme level of an organization
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 61: Quiz
  Which is a task of product – based planning
Design the plan
Create the product flow diagram
Analyze the risk
Prepare the schedule
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 62: Quiz
  Which is the purpose of the “Plan” step within the recommended risk management procedure?
Identify the roles and responsibilities for all risk management activities
Prepare and agree the risk management strategy with the project board
Plan the communication management strategy to keep the stakeholders updated on the risk management activities
Identify possible responses to be implemented to manage a risk should it occur
Correct Answer: D
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 63: Quiz
  Which describes the risk impact?
Timeframe within which the risk might occur
The trigger that occurred giving rise to the risk
The effect of the risk on the delivery of the project objectives
How likely the risk is to occur in the given situation
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 64: Quiz
  Which should be funded from a change budget?
The starting up a project process
A fallback plan
An agreed change to the scope of a project
A change to a plan, within allocated tolerance, due to poor estimating
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 65: Quiz
  Which is a true statement about PRINCE2 event-driven controls?
Event driven controls take place at predefined periodic intervals
Event-driven controls are produced at the frequency defined in a work package
Event driven controls are used for decision making
Checkpoint reports are event driven controls
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 66: Quiz
  What theme estimates the cost of delivering the project?
Business Case
Change
Plans
Progress
Correct Answer: C
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 67: Quiz
  Identify the missing word in the following sentence. A risk consists of the [?] of threat occurring and its impact
Outcome
Probability
Dis-benefit
proximity
Correct Answer: B
Notes: Product vs Service
Product – one time kind of thing
Service – ongoing

## Slide 68: Thanks