## Appendix A
PRODUCT DESCRIPTION
A.1 | BENEFITS REVIEW PLAN | BASELINE Management Products | Purpose
A.2 | BUSINESS CASE | BASELINE Management Products | Composition
A.3 | CHECKPOINT REPORT | Reports-Time Driven | Derivation
A.4 | COMMUNICATION MANAGEMENT STRATEGY | BASELINE Management Products | Format and Presentation
A.5 | CONFIGURATION ITEM RECORD | Records - Dynamic Management Products | Quality Criteria
A.6 | CONFIGURATION MANAGEMENT STRATEGY | BASELINE Management Products
A.7 | DAILY LOG | Records - Dynamic Management Products
A.8 | END PROJECT REPORT | Reports-Event Driven
A.9 | END STAGE REPORT | Reports-Event Driven
A.10 | EXCEPTION REPORT | Reports-Event Driven
A.11 | HIGHLIGHT REPORT | Reports-Time Driven
A.12 | ISSUE REGISTER | Records - Dynamic Management Products
A.13 | ISSUE REPORT | Reports-Event Driven
A.14 | LESSON LOG | Records - Dynamic Management Products
A.15 | LESSON REPORT | Reports-Event Driven
A.16 | PLAN | BASELINE Management Products
PRODUCT BREAKDOWN STRUCTURE
PRODUCT CHECKLIST
A.17 | PRODUCT DESCRIPTION | BASELINE Management Products
PRODUCT FLOW DIAGRAM
A.18 | PRODUCT STATUS ACCOUNT
A.19 | PROJECT BRIEF | BASELINE Management Products
A.20 | PROJECT INITIATION DOCUMENT | BASELINE Management Products
PROJECT MANDATE
A.21 | PROJECT PRODUCT DESCRIPTION | BASELINE Management Products
A.22 | QUALITY MANAGEMENT STRATEGY | BASELINE Management Products
A.23 | QUALITY REGISTER | Records - Dynamic Management Products
A.24 | RISK MANAGEMENT STRATEGY | BASELINE Management Products
A.25 | RISK REGISTER | Records - Dynamic Management Products
A.26 | WORK PACKAGE | BASELINE Management Products

## Process&ManagementProduct
Starting up a Project (SU) |  | Initiating a Project (IP) |  | Directing a Project (DP)
Appoint Executive | Corporate/Programmer | Prepare the Quality Management Startegy | Project Manager/Project Assurance | Authorize Initiation | Project Board<-Project Board/Project Assurance
Appoint Project Manager | Executive | Prepare the Risk Management Startegy | Project Manager / Project Board ( Ext Risk) | Authorize a Project | Project Board<-Project Assurance
Capture previous Lessons | Project Manager | Prepare the Configuration Management Strategy | Project Manager/Project Assurance | Authorize a stage or Exception Plan | Project Board<-Project Board/Project Assurance
Design and Appoint Project Management Team | Executive->Project Manager | Prepare the Communication Management Strategy | Project Manager/Project Assurance | Give AD HOC Direction | Project Board
Prepare the Outline Business Case | Executive->Project Manager | Create the Project Plan | Project Manager/Project Assurance | Authorize Project Closure | Project Board<-Project Board/Project Assurance
Select the project approach and assemble the project brief | Project Manager | Refine the Business Case | Executive->Project Manager
Plan the Initiation Stage | Project Manager | Setup the project controls | Project Manager (Project Board)
|  | Assemble the Project Initiation Document | Project Manager/Project Assurance/Project Support
Controlling a Stage(CS) |  | Managing Product Delivery(DP) |  | Manage a stage boundary(SB)
Authorize work package | Project Manager | Accept a work package | Team Manager/Project Manager | Plan a stage | Project Manager<-Project support/Prject Board/Project Assurance/Team Managers
Review the Work Package Status | Project Manager (Project Support) | Execute a work package | Team Manager | Update a Project Plan | Project Manager (Project Support)
Receive Completed Work Package | Project Manager (Project Support) | Deliver a work package | Team Manager | Update the Business Case | Project Manager->Executive
Review Stage Status | Project Manager ->Project Board |  |  | Report the Stage End | Project Manager
Report Highlights | Project Manager |  |  | Produce an Exception Plan | Project Manager/Project Assurance
Capture and Examine Risks | Project Manager (Project Support)
Escalate Issues and Risk | Project Manager/Project Assurance
Take corrective action | Project Board<-Project Board/Project Assurance
Clsoing a Project (CP)
Prepare Planned Closure | Project Manager/Project Support
Prepare Premature Closure | Project Manager/Project Assurance
Handover products | Project Manager
Evaluate the Project | Project Manager/Project Assurance/Project Support
Recommend Project Closure | Project Manager/Project Assurance/Project Support

## Sample Paper Day 1
33 | 32
Sample Paper 1-33 | Sample Paper 2-32
Question No | Question No
1 | 1
2 | 2
3 | 3
9 | 5
10 | 10
13 | 12
14 | 13
19 | 14
20 | 15
23 | 18
24 | 21
26 | 25
29 | 27
30 | 29
31 | 32
32 | 33
33 | 34
36 | 35
41 | 39
42 | 41
43 | 45
45 | 48
46 | 49
51 | 54
52 | 56
55 | 57
57 | 61
62 | 65
63 | 66
66 | 71
68 | 73
69 | 75
74

## Sample Paper Day 2
28 | 26 | 54
Day 2 | Day 2
Sample Paper 1-28 | Sample Paper 2-26
Question No | Question No
4 | 6
7 | 11
8 | 16
12 | 17
15 | 20
17 | 22
22 | 24
25 | 28
27 | 30
28 | 31
37 | 36
40 | 37
44 | 38
47 | 42
48 | 43
49 | 46
50 | 47
53 | 51
56 | 58
58 | 59
59 | 60
60 | 64
64 | 67
70 | 69
71 | 70
72 | 72
73
75

## Sample Paper Day 3
14 | 17 | 31
Day 3 | Day 3
Sample Paper 1-14 | Sample Paper 2-17
Question No | Question No
5 | 4
6 | 7
11 | 8
16 | 9
18 | 19
21 | 23
34 | 26
35 | 40
38 | 44
39 | 50
54 | 52
61 | 53
65 | 55
67 | 62
63
68
74