## Sheet1
PRINCE2 (42) | Controlling a Stage (8)
1. Starting up a Project (6) | Event/Decision (PM & Board)
2. Directing a Project (5) | Exception Plan Approved
3. Initiating a Project (10) | Stage Authorization
4. Controlling a Stage (8) | Exception Raised
5. Managing Product Delivery (3) | Request for Advice
6. Managing a Stage Boundary (5) | Project Board Advice
7. Closing a Project (5) | Project End Approaching (CP)
Stage boundary approaching (MSB)
Starting up a Project (6) | Event/Decision (PM & TM)
Event/Decision (Prog Mgmt & Board & PM) | Completed work package
Project Mandate | Authority to deliver work package
Processes | New Issue
1. Appoint the Executive and the Project Manager
2. Capture previous lessons | Processes
3. Design and appoint the project management team | Work Packages:
4. Prepare the outline Business Case | 1. Authorize a Work Package
5. Select the project approach and assemble the Project Brief | 2. Review Work Package status
6. Plan the initiation stage | 3. Receive completed Work Packages
Monitoring and reporting:
Event/Decision (PM & Board) | 1. Review the stage status
Request to Initiate a Project | 2. Report highlights
Issues:
Directing a Project (5) | 1. Capture and examine issues and risks
2. Escalate issues and risks
Event/Decision (Program Mgmt & Board) | 3. Take corrective action.
Initiation Notification
Project Authorization Notification | Managing Product Delivery (3)
Project Board Request for Advice
Corporate Advice and Decisions | Event/Decision (PM & TM)
Closure Notification | Completed work package
Authority to deliver work package
Event/Decision (PM & Board)
Request to Initiate a Project (SU) | Processes
Authority to Initiate a Project (IP) | 1. Accept a Work Package
Request to Deliver a Project (IP) | 2. Execute a Work Package
Stage Authorization (CS) | 3. Deliver a Work Package.
Exception Plan Approved (CS)
Request to approve exception plan (MSB) | Managing a Stage Boundary (5)
Request to approve stage plan (MSB) | Event/Decision (PM & Board)
Exception plan request (MSB) | Request to approve a project plan
Project Manager Request for Advice (CS) | Request to approve next stage
Exception Raised (CS) | Exception plan request
New Issue (CS)
Project Board Advice & Decisions (CS) | Stage Project Boundary Approaching (IP, CS)
Premature Closure (CP)
Closure Recommendation (CP) | Processes
1. Plan the next stage
Processes | 2. Update the Project Plan
1. Authorize initiation | 3. Update the Business Case
2. Authorize the project | 4. Report stage end
3. Authorize a Stage or Exception Plan | 5. Produce an Exception Plan.
4. Give ad hoc direction
5. Authorize project closure.
Initiating a Project (8) | Closing a Project (5)
Event/Decision (PM & Board) | Event/Decision (PM & Board)
Authority to initiate project | Premature Closure
Request to deliver a project | Closure Recommendation
Stage boundary approaching (MSB) | Project End Approaching (CS)
Processes | Processes
1. Prepare the Risk Management Strategy | 1. Prepare planned closure
2. Prepare the Configuration Management Strategy | 2. Prepare premature closure
3. Prepare the Quality Management Strategy | 3. Hand over products
4. Prepare the Communication Management Strategy | 4. Evaluate the project
5. Set up the project controls | 5. Recommend project closure
6. Create the Project Plan
7. Refine the Business Case
8. Assemble the Project Initiation Documentation.