## TitleSheet
FPA Estimation Sheet
Document ID: |  |  | Version | DD-mmm-YY
Client |  | Intellinet | Country | USA
Project Name |  |  | Project ID
A/C Manager / SDH |  | Hari P. Thapliyal | PSM
Technology |  | .NET/ C#/ Biztalk Server/ SQL 2008 | Date
Total Adjusted Function Points |  | 111.39
Total Effort in Person Days |  | 81.9
Assumptions made during Estimation
1 | Working days in a month 20
2 | No buffer placed for unknown technology
3 | Human Resource team will be in place whenever requested
4 | Hardware/Software resources will be timely available
5 | No performance/network latency due to TFS
6 | System to support the process are working and well in place
7 | Escalated issues/risk managed within time
8 | Learning of agile development methodology will take time
9 | Learning of new technology will take time
10 | Newly hired senior people coming from various org culture backgrounds will bring good/bad to the projects
11
12
13
14
15

## Scope
S.No. | Req# | Category | SubCategory | In Scope | Req Type | Requirement | Date Added | User Role | Status | Notes / Assumptions

## Input
Requirement/Scope | [6 empty] | Function Point Counting
[7 empty] | Transactional Functions | [7 empty] | 91 | Data Functions | [8 empty] | 50
[10 empty] | Do not write anything in these columns. After you finish estimation follow 2 steps. 1- Copy Row#5 info into all the rows below. 2- Copy Col N into notepad and then copy notepad text into Col O. | [9 empty] | Do not write anything in these columns. After you finish estimation follow 2 steps. 1- Copy Row#5 info into all the rows below. 2- Copy Col Y into notepad and then copy notepad text into Col Z.
Category | SubCategory | SubSubCategory | Sub-SubSubcategory | In Scope | Req Type | Items | Trans.Type | DET | FTR | COL | ROW | CELL | Weight | Calcs | UAFPC | File Name | File Type | DET | RET | COL | ROW | CELL | Weight | Cals | UAFPC
[6 empty] | PROTECTED ROW | EO | 5 | 1 | D | 10 | =Tables!D10 | L | EOL | 4 | PROTECTED ROW | ILF | 1 | 2 | D | 23 | =Tables!D23 | L | ILFL | 7
[6 empty] | Add carline details | EI | 6 | 1 | F | 4 | =Tables!F4 | L | EIL | 3 | Carline | ILF | 5 | 1 | D | 22 | =Tables!D22 | L | ILFL | 7
[6 empty] | Edit Carline details | EI | 5 | 1 | F | 4 | =Tables!F4 | L | EIL | 3 | User | ILF | 10 | 1 | D | 22 | =Tables!D22 | L | ILFL | 7
[6 empty] | Show Carline details | EQ | 7 | 1 | F | 16 | =Tables!F16 | L | EQL | 3 | Roles | ILF | 2 | 1 | D | 22 | =Tables!D22 | L | ILFL | 7
[6 empty] | Add users | EI | 10 | 1 | F | 4 | =Tables!F4 | L | EIL | 3 | Permissions | ILF | 5 | 1 | D | 22 | =Tables!D22 | L | ILFL | 7
[6 empty] | Edit users | EI | 9 | 1 | F | 4 | =Tables!F4 | L | EIL | 3 | Organizational Unit | ILF | 10 | 1 | D | 22 | =Tables!D22 | L | ILFL | 7
[6 empty] | Show users | EQ | 15 | 1 | F | 16 | =Tables!F16 | L | EQL | 3 | Carline External file | EIF | 5 | 1 | D | 28 | =Tables!D28 | L | EIFL | 5
[6 empty] | Delete users | EI | 12 | 1 | F | 4 | =Tables!F4 | L | EIL | 3 | Role external file | EIF | 2 | 1 | D | 28 | =Tables!D28 | L | EIFL | 5
[6 empty] | Add Roles | EI | 4 | 1 | D | 4 | =Tables!D4 | L | EIL | 3 | Users external file | EIF | 10 | 1 | D | 28 | =Tables!D28 | L | EIFL | 5
[6 empty] | Edit Roles | EI | 3 | 1 | D | 4 | =Tables!D4 | L | EIL | 3
[6 empty] | Show Roles | EQ | 4 | 1 | D | 16 | =Tables!D16 | L | EQL | 3
[6 empty] | Show Permissions | EQ | 2 | 1 | D | 16 | =Tables!D16 | L | EQL | 3
[6 empty] | Permission assign & unassign | EI | 5 | 2 | F | 5 | =Tables!F5 | A | EIA | 4
[6 empty] | User Role mapping Add | EI | 3 | 1 | D | 4 | =Tables!D4 | L | EIL | 3
[6 empty] | User Role mapping Edit | EI | 3 | 1 | D | 4 | =Tables!D4 | L | EIL | 3
[6 empty] | Show user role mapping | EQ | 4 | 1 | D | 16 | =Tables!D16 | L | EQL | 3
[6 empty] | User Role mapping Delete | EI | 3 | 1 | D | 4 | =Tables!D4 | L | EIL | 3
[6 empty] | User Permission mapping Add | EI | 3 | 1 | D | 4 | =Tables!D4 | L | EIL | 3
[6 empty] | User Permission mapping Edit | EI | 3 | 1 | D | 4 | =Tables!D4 | L | EIL | 3
[6 empty] | Show user permission mapping | EQ | 4 | 1 | D | 16 | =Tables!D16 | L | EQL | 3
[6 empty] | User Permission mapping Delete | EI | 4 | 1 | D | 4 | =Tables!D4 | L | EIL | 3
[6 empty] | Manual Import master data of carline | EI | 5 | 1 | F | 4 | =Tables!F4 | L | EIL | 3
[6 empty] | Manual Import master data of users | EI | 5 | 1 | F | 4 | =Tables!F4 | L | EIL | 3
[6 empty] | Manual Import master data of roles | EI | 12 | 1 | F | 4 | =Tables!F4 | L | EIL | 3
[6 empty] | Interface import for carline | EI | 2 | 2 | D | 5 | =Tables!D5 | L | EIL | 3
[6 empty] | Inetrface import for roles | EI | 2 | 2 | D | 5 | =Tables!D5 | L | EIL | 3
[6 empty] | Interface import of users | EI | 2 | 2 | D | 5 | =Tables!D5 | L | EIL | 3
[6 empty] | Add Organizational unit | EI | 10 | 1 | F | 4 | =Tables!F4 | L | EIL | 3
[6 empty] | Edit Organizational unit | EI | 9 | 1 | F | 4 | =Tables!F4 | L | EIL | 3
[6 empty] | Show Org. Unit | EQ | 14 | 1 | F | 16 | =Tables!F16 | L | EQL | 3
[6 empty] | Delete Organizational unit | EI | 9 | 1 | F | 4 | =Tables!F4 | L | EIL | 3

## Tables
EI |  |  | 1 | 4 | 5 | 15 | 16 | 100 |  | TYPE | WTG. | COUNT | VALUE | General System Characterstics
|  |  | D | D | F | F | H | H | [5 empty] | GSC | DI
0 | 1 | 4 | L |  | L |  | A |  | EIL | L | 3 | 22 | 66 | Data Communications | 1
2 | 2 | 5 | L |  | A |  | H |  | EIA | A | 4 | 1 | 4 | Distributed Functions | 1
3 | 100 | 6 | A |  | H |  | H |  | EIH | H | 6 | 0 | 0 | Performance | 1
[14 empty] | Heavily Used Configuration | 1
EO |  |  | 1 | 5 | 6 | 19 | 20 | 100 | [5 empty] | Transaction Rate | 1
|  |  | D | D | F | F | H | H | [5 empty] | Online Data Entry | 1
0 | 1 | 10 | L |  | L |  | A |  | EOL | L | 4 | 0 | 0 | End User Efficiency | 1
2 | 3 | 11 | L |  | A |  | H |  | EOA | A | 5 | 0 | 0 | Online Update | 1
4 | 100 | 12 | A |  | H |  | H |  | EOH | H | 7 | 0 | 0 | Complex Processing | 1
[14 empty] | Reusability | 1
EQ |  |  | 1 | 5 | 6 | 19 | 20 | 100 | [5 empty] | Installation Ease | 1
|  |  | D | D | F | F | H | H | [5 empty] | Operational Ease | 1
0 | 1 | 16 | L |  | L |  | A |  | EQL | L | 3 | 7 | 21 | Multiple Sites | 1
2 | 3 | 17 | L |  | A |  | H |  | EQA | A | 4 | 0 | 0 | Facilitate Change | 1
4 | 100 | 18 | A |  | H |  | H |  | EQH | H | 6 | 0 | 0 | Total DIs | 14
ILF |  |  | 1 | 19 | 20 | 50 | 51 | 100 | [5 empty] | Value Adjustment Factor | 0.79
|  |  | D | D | F | F | H | H
0 | 1 | 22 | L |  | L |  | A |  | ILFL | L | 7 | 5 | 35
2 | 5 | 23 | L |  | A |  | H |  | ILFA | A | 10 | 0 | 0 | Total Function Point Count | 111.39
6 | 100 | 24 | A |  | H |  | H |  | ILFH | H | 15 | 0 | 0
EIF |  |  | 1 | 19 | 20 | 50 | 51 | 100
|  |  | D | D | F | F | H | H
0 | 1 | 28 | L |  | L |  | A |  | EIFL | L | 5 | 3 | 15
2 | 5 | 29 | L |  | A |  | H |  | EIFL | A | 7 | 0 | 0
6 | 100 | 30 | A |  | H |  | H |  | EIFH | H | 10 | 0 | 0
[10 empty] | Total UFPC for All Modules |  |  | 141
Note on T3: MM: Degree of Influence: rating between 0 (lowest) to 5 (highest)

## Efforts
Effort Estimation
Productivity in Hours per FP |  | 7 | Rationale for taking this Productivity
Working Hours in Day |  | 8
Avg. Working Days in Month |  | 20
Hours Per Month |  | 160
Project Mgmt.Effort (%age) |  | 5
Team Confidence Factor |  | H
Team Confidence Level
Factor Applicable for this Application |  |  | Project Size in FPs | L | A | H
Team Confidence Factor Correction for this System | <500 FP | 0.8 | < 500 | 8 | 9 | 10
| 500-1000 | 0.88889 | 500-1000 | 7 | 8 | 9
| >1000 FP | 1 | >1000 | 6 | 7 | 8
SDLC Efforts |  |  | Technologies/ Tools/ Languages
Adjusted Function Points |  | 111.39 | Ansi COBOL-85 |  | 16
Efforts in Person Hours |  | 624 | C++ |  | 10.6
Efforts for Project Mgmt. (Hrs) |  | 31.2 | CRYSTAL REPORTS |  | 8
Total SDLC Effort (Man-Hours) |  | 655.2 | FORTRAN |  | 16
Total SDLC Effort (Man-Days) |  | 81.9 | FOCUS |  | 8
|  |  | INFORMIX |  | 8
Efforts of Non-SDLC Phases |  |  | JAVA |  | 10.6
Data Conversion |  | 0 | ORACLE |  | 8
Documentation |  | 0 | DEVELOPER 2000 |  | 7.3
Translation |  | 0 | PERL |  | 8
Implementation |  | 0 | POWERBUILDER |  | 6.6
Training |  | 0 | PRO C |  | 8
Warranty |  | 0 | SQL |  | 5
Other |  | 0 | SYBASE |  | 8
HTML Static Pages |  | 0 | VISUAL BASIC |  | 8.5
Total Non-SDLC Effort (Man-Days) |  | 0 | VISUAL C++ |  | 9.5
|  |  | INGRESS |  | 8
Effort Distribution Phasewise
SDLC Phases | % | Per.Days.
Project Training | 5 | 4.1
Project Management | 8 | 6.55
Define | 8 | 6.55
Design | 14 | 11.47
Construction+UT | 38 | 31.12
Configuration Management | 3 | 2.46
Documentation | 5 | 4.1
Test Planning | 4 | 3.28
Test Execution | 15 | 12.29
Total Effort | 100 | 81.92
Total Effort (Mandays) |  | 81.9
Total Efforts (Man-Month) |  | 4.095
Work Already Done (Man-Days) |  | 0
Remaining Work (Man-Days) |  | 81.9
Remaining Work (Man-Months) |  | 4.095
Note on A10: hari.prasad: The values below depend upon a combination of two factors: project size and team confidence level and is computed using the adjacent table
Note on A17: MM-ACI: Effort is calculated (corrected) based on team confidence factor (TCF) and project size. TCF is taken from the table above
Note on A46: Hari Prasad: This is total SDLC effort plus total non-SDLC effort.