## TitleSheet
FPA Estimation Sheet
Document ID: |  |  | Version | DD-mmm-YY
Client |  | Intellinet | Country | USA
Project Name |  |  | Project ID
A/C Manager / SDH |  | Hari P. Thapliyal | PSM
Technology |  | .NET/ C#/ Biztalk Server/ SQL 2008 | Date
Total Adjusted Function Points |  | 2131.44
Total Effort in Person Days |  | 2735.2875
Assumptions made during Estimation
1 | Working days in a month 20
2 | No buffer placed for unknown technology
3 | Human Resource team will be in place whenever requested
4 | Hardware/Software resources will be timely available
5 | No performance/network latency due to TFS
6 | System to support the process are working and well in place
7 | Escalated issues/risk managed within time
8 | Learning of agile development methodology will take time
9 | Learning of new technology will take time
10 | Newly hired senior people coming from various org culture backgrounds will bring good/bad to the projects
11
12
13
14
15

## Scope
S.No. | Category | SubCategory | Sub-Subcategory | Sub-SubSubCategory | In Scope | Req Type | FPA | Requirement | Est. Catg. | Date Added | Req# | Role | Notes / Assumptions
1 | Administration | Branch Contractors |  |  | Y | BR | EQ | Prevent the user from saving a Branch Contractor with an Employee Number that is already used by an Employee or by another Branch Contractor.
2 | Administration | Branch Contractors |  |  | Y | LIST | EO | List Branch Contractors, including First Name, Last Name, Unique Employee Number, and Employment Service.
3 | Administration | Branch Contractors |  |  | Y | BR |  | Sort the Branch Contractors by Last Name, First Name
4 | Administration | Branch Contractors |  |  | Y | UA | EQ | Allow a user to Filter the Branch Contractors by All or Active Only. Default to Active Only.
5 | Administration | Branch Contractors |  |  | Y | UA | EQ | Allow a user to access a Branch Contractor from the list.
6 | Administration | Branch Contractors |  |  | Y | UA | EI | Allow a user to create a new Branch Contractor.
7 | Administration | Branch Contractors |  |  | Y | UA | EI | Allow a user to edit a new Branch Contractor.
8 | Administration | Branch Contractors |  |  | Y | BR | EQ | Prevent the user from saving a Branch Contractor without a First Name, Last Name, Employee Number, or specified Employment Service.
9 | Administration | Branch Contractors |  |  | Y | UA | EI | Allow a user to terminate/un‐terminate a Branch Contractor.
10 | Administration | Customer Gate Log Reconciliations |  |  | Y | LIST | EQ | List Labor records for a selected day for a selected Customer Site, displaying the Badge Number, First Name, Last Name, Employee Number (if it exists)and Start/Stop date/time (according to the Shift Summary), total hours/minutes worked, the Employee's Home Branch, Customer Area, Shift Summary Number, and Job Number.
11 | Administration | Customer Gate Log Reconciliations |  |  | N | LIST |  | List Primary Equipment records for a Shift, displaying the Customer's Equipment Number, and Start/Stop date/time (according to the Shift Summary) sorted by Equipment Number.
12 | Administration | Customer Gate Log Reconciliations |  |  | Y | UA | EQ | Allow a user to accept the default calculated Labor time (per the Shift Summary), or enter the Gate Log Labor time (in minutes, hours), per line.
13 | Administration | Customer Gate Log Reconciliations |  |  | N | UA |  | Allow a user to enter or change the Gate Log data for that Equipment for that shift.
14 | Administration | Customer Gate Log Reconciliations |  |  | Y | UA | EI | Allow a user to save the Gate Log data for a shift.
15 | Administration | Customer Gate Log Reconciliations |  |  | Y | BR | EQ | Sort the Gate Log Reconciliation records by Last Name (ascending), and First Name (ascending).
16 | Administration | Customer Gate Log Reconciliations |  |  | Y | BR | EQ | Filter the Gate Log Reconciliation records by the selected Customer Site, by all Shift Labor records that begin on the selected date.
17 | Administration | Customer Gate Log Reconciliations |  |  | Y | BR | EQ | Display summary duration values for each person (i.e., Badge Number).
18 | Administration | Customer Gate Log Reconciliations |  |  | Y | BR | EQ | Prevent a user from editing a Gate Log record if the corresponding item exists on an Invoice (unless the Invoice has been credited and the item has not been reinvoiced).
19 | Administration | Customer Gate Log Reconciliations |  |  | Y | BR | EQ | Warn the user, when reopening a Shift Summary with Gate Log Reconciliations, that the Gate Log Reconciliations will be deleted.
20 | Administration | Customer Gate Log Reconciliations |  |  | Y | BR | EI | When a user reopens a Shift Summary with Gate Log Reconciliations, delete the Gate Log Reconciliations associated with the Shift Summary.
21 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Calculate and display the difference between the original amount of the Purchase Order or Purchase Order Line, and the amount of the Invoices posted against it.
22 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Sort the Purchase Orders by Purchase Order Number (ascending).
23 | Administration | Customer Purchase Orders |  |  | Y | UA | EQ | Allow a user to filter the Purchase Orders (Open vs. Closed). Initialize the filter to display Open only.
24 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Filter the Purchase Orders by Customer Filter the Purchase Orders by Customer Site.
25 | Administration | Customer Purchase Orders |  |  | N | UA |  | Allow a user to deactivate a Purchase Order.
26 | Administration | Customer Purchase Orders |  |  | Y | LIST | EQ | List Purchase Orders.
27 | Administration | Customer Purchase Orders |  |  | N | BR |  | Prevent the user from deactivating a Purchase Order if it exists on a Job Header or Invoice.
28 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Prevent the user from closing a Purchase Order if one of its Purchase Order Lines exists on an unposted Invoice.
29 | Administration | Customer Purchase Orders |  |  | Y | UA | EI | Allow a user to close a Purchase Order.
30 | Administration | Customer Purchase Orders |  |  | Y | UA | EQ | Allow a user to select a Purchase Order
31 | Administration | Customer Purchase Orders |  |  | Y | UA | EI | Allow a user to create a Purchase Order
32 | Administration | Customer Purchase Orders |  |  | Y | UA | EI | Allow a user to order a Purchase Order
33 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Prevent the user from saving a Purchase Order with a Purchase Order Number that already exists for the Customer Site.
34 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Warn the user when saving the Purchase Order with a Purchase Order Number that does not pass the Purchase Order regular expression mask for the Customer Site, if one exists.
35 | Administration | Customer Purchase Orders |  |  | Y | UA | EI | Allow a user to reopen a Purchase Order.
36 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Calculate and display the difference between the original amount of the Purchase Order or Purchase Order Line, and the amount of the unposted and posted Invoices against it.
37 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Prevent the user from editing a closed Purchase Order, or a Purchase Order Line of a closed Purchase Order.
38 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Prevent the user from saving a Purchase Order Line that already exists for the Customer Site.
39 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Sort the Purchase Order Lines by Purchase Order Line Number (ascending).
40 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | Prevent the user from editing anything other than the Dollar Amount of a Purchase Order, if the Purchase Order has been used on a Posted Invoice.
41 | Administration | Customer Purchase Orders |  |  | Y | BR | EQ | If the user changes the Dollar Amount of a Purchase Order, recalculate the remaining values on the Purchase Order.
42 | Administration | Customer Purchase Orders | Customer‐ Defined Attributes |  | Y | UA |  | For each Purchase Order, Allow a user to enter the values for the Customer‐Defined Attributes.
43 | Administration | Customer Purchase Orders | Customer‐ Defined Attributes |  | Y | BR | EQ | For each Purchase Order, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue.
44 | Administration | Customer Purchase Orders | Customer‐ Defined Attributes |  | Y | BR | EQ | Warn the user when saving a Purchase Order with invalid Customer‐Defined Attribute values.
45 | Administration | Customer Purchase Orders | Purchase Order Lines |  | Y | LIST | EQ | List Purchase Order Lines per Purchase Order.
46 | Administration | Customer Purchase Orders | Purchase Order Lines |  | Y | UA | EI | Allow a user to create a new Purchase Order Line for a Purchase Order.
47 | Administration | Customer Purchase Orders | Purchase Order Lines |  | Y | UA | EI | Allow a user to edit a Purchase Order Line for a Purchase Order.
48 | Administration | Customer Purchase Orders | Purchase Order Lines |  | Y | BR | EQ | Prevent the user from creating a Purchase Order Line for a Purchase Order, if the Purchase Order is closed.
49 | Administration | Customer Purchase Orders | Purchase Order Lines |  | Y | BR | EQ | Prevent the user from creating a Purchase Order Line for a Purchase Order, if the Customer Site does not require Purchase Order Lines.
50 | Administration | Customer Purchase Orders | Purchase Order Lines |  | Y | BR | EQ | Prevent the user from editing anything other than the Dollar Amount of a Purchase Order Line, if the Purchase Order Line has been used on a Posted Invoice.
51 | Administration | Customer Purchase Orders | Purchase Order Lines |  | Y | BR | EQ | Prevent the user from deleting a Purchase Order Line if the Purchase Order is closed.
52 | Administration | Customer Purchase Orders | Purchase Order Lines |  | Y | BR | EQ | If the user changes the Dollar Amount of a Purchase Order Line, recalculate the remaining values on the Purchase Order Line.
53 | Administration | Customer Purchase Orders | Purchase Order Lines | Customer‐Defined Attributes | Y | UA | EI | Allow a user to delete a Purchase Order Line.
54 | Administration | Customer Purchase Orders | Purchase Order Lines | Customer‐Defined Attributes | Y | UA |  | For each Purchase Order Line, allow a user to enter the values for the Customer‐Defined Attributes.
55 | Administration | Customer Purchase Orders | Purchase Order Lines | Customer‐Defined Attributes | Y | BR | EQ | For each Purchase Order Line, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue.
56 | Administration | Customer Purchase Orders | Purchase Order Lines | Customer‐Defined Attributes | Y | BR | EQ | Warn the user when saving the Purchase Order Line with invalid Customer‐Defined Attribute values.
57 | Administration | Customer Purchase Orders | Purchase Order Lines | Customer‐Defined Attributes | Y | BR | EQ | Prevent the user from deleting a Purchase Order Line if it exists on an Invoice.
58 | Administration | Employees |  |  | Y | LIST | EQ | List Employees, including First Name, Last Name, Employee Number, Employee Type (i.e., Regular or Part‐Time Professional).@$
59 | Administration | Employees |  |  | Y | UA | EQ | Allow a user to sort Employees by Employee ID (ascending), or by Last Name (ascending)/First Name (ascending), default by Last Name/First Name.
60 | Administration | Employees |  |  | Y | UA | EQ | Allow a user to filter Employees by Branch, default to the Home Branch.@#
61 | Administration | Employees |  |  | Y | UA | EQ | Allow a user to select an Employee.@$
62 | Administration | Field Service Settings |  |  | Y | BR | EQ | Notify the user if a clock reset has been detected, and prevent the application from starting until the clock has been set.
63 | Administration | Month End Close |  |  | Y | BR | EQ | Provide real and estimated revenue values for all Shift Items within a month, for all items added in that month, and for all items whose real or estimated revenue has changed within the month; and for a place‐holder for a Corporate System to associate a month/year to the value.
64 | Administration | Month End Close |  |  | N | BR |  | Prevent a user from closing Month End prior to Month End.
65 | Administration | Pending Customers |  |  | N | UA |  | Allow a user to match a Pending Customer Site to an Oracle Customer.
66 | Administration | Pending Employees |  |  | Y | UA | EQ | Allow a user to match a Pending Employee to an Oracle Employee.
67 | Administration | Synchronization |  |  | Y | BR | EQ | Display a confirmation message at the end of a successful manual synchronization.
68 | Administration | Synchronization |  |  | Y | BR | EQ | Warn the user to synchronize when the Remote System 2.0 is opened and closed in branch.
69 | Administration | Synchronization |  |  | Y | BR | EQ | Display the synchronization status.
70 | Administration | Terms & Conditions Contract |  |  | Y | BR | EQ | Display Customer Terms & Conditions Contract Details (T&C Contract Number, Activation Date, Expiration Date)
71 | Administration | Terms & Conditions Contract |  |  | Y | BR | EQ | Warn the user when creating a new Job when the Terms & Conditions Contract has past its expiration date.
72 | Administration | Terms & Conditions Contract |  |  | Y | BR | EQ | Warn the user when creating a Shift for an existing Job when the Terms & Conditions Contract has past its expiration date.
73 | Invoicing | Contract Selection |  |  | N | LIST |  | List all Contracts for a Customer.
74 | Invoicing | Contract Selection |  |  | N | UA |  | Allow a user to select a Contract.
75 | Invoicing | Contract Selection |  |  | N | UA |  | Allow a user to view Contract header details (e.g., Contract Number, expiration date, etc.)
76 | Invoicing | Contract Selection |  |  | N | BR |  | Prevent a user from seeing Contract Pricing for a Contract, if the user's Branch is not authorized to view that Contract's Pricing.
77 | Invoicing | Contract Selection |  |  | Y | LIST | EQ | List all Contracts, Contract Levels, and Contract Level Version for a Customer, displaying the Contract Number, the Contract Level Description, the Contract Version Activation Date, and the Contract Expiration Date.
78 | Invoicing | Contract Selection |  |  | Y | UA | EQ | Allow a user to select a Contract / Contract Level / Contract Version.
79 | Invoicing | Contract Selection |  |  | Y | BR | EQ | Sort the Contract / Contract Level / Contract Versions by Active Date of the Contract (descending), then by Contract Level Priority (ascending), then by Contract Version Active Date (descending).
80 | Invoicing | Contract Selection |  |  | Y | BR | EQ | Filter the Contract / Contract Level / Contract Versions to only show records: (a) for the currently selected Customer Site (i.e., those where the Contract Level applies to no Customer Site or to the current Customer Site) (b) where the Active Date of the Contract and Contract Version are for today or older (c) where the Contract Revision are for currently active Contract Revisions (d) where the active date range of the Contract Version overlaps with at least one of the Jobs/Shifts within the Customer Site / Purchase Authorization method selected in the Inbox Queue.
81 | Invoicing | Contract Selection |  |  | Y | UA | EQ | Allow a user to revise the filtered view, to show older Contracts / Contract Levels / Contract Versions by date range, between today and the specified date.
82 | Invoicing | Credit Invoices |  |  | Y | UA | EI | Allow a user to create a Credit Invoice from an Invoice, including an indication of whether the Invoice Line Data: (a) will be returned to the Staging Area, (b) will be deleted, and marked as Lost Revenue, or (c) will be associated with a Re‐Invoice.
83 | Invoicing | Credit Invoices |  |  | Y | BR | EQ | If a Credit Invoice is created from an Invoice with a Custom View, automatically create a Custom View Line Items for the Credit Invoice, and set the Description of each to the Description of each Custom View Line Item of the source Invoice, and the Dollar Amount of each to the negative of the Dollar Amount of each Custom View Line Item of the source Invoice.
84 | Invoicing | Credit Invoices |  |  | Y | BR | EQ | Prevent the user from creating a Credit Invoice from an Invoice, or one or more of the Items on that Invoice, if the source Invoice is a Credit Invoice.
85 | Invoicing | Credit Invoices |  |  | Y | BR | EQ | Prevent the user from creating a Credit Invoice from an Invoice, or one or more of the Items on that Invoice, if the source Invoice is not in Posted Mode.
86 | Invoicing | Credit Invoices |  |  | Y | UA | EI | Allow a user to create a Credit Request associated with the Credit Invoice or Credit/Re‐Invoice.
87 | Invoicing | Custom Invoice Views |  |  | Y | UA | EI | Allow a user to create a Custom View for an Invoice.
88 | Invoicing | Custom Invoice Views |  |  | Y | UA | EI | Allow a user to delete the Custom View of an Invoice.
89 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent the user from creating a Custom View for an Invoice, when the Invoice already has a Custom View.
90 | Invoicing | Custom Invoice Views |  |  | N | BR |  | Prevent the user from creating a Custom View for an Invoice, when the Invoice is not in Open Mode.
91 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | When the user creates a Custom View of an Invoice, calculate the Custom View Variance Percentage.
92 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent the user from deleting a Custom View for an Invoice, when the Invoice does not have a Custom View.
93 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent the user from deleting the Custom View, when the Invoice is not in Open Mode.
94 | Invoicing | Custom Invoice Views |  |  | N | BR |  | When the user deletes a Custom View of an Invoice, remove the Variance Line from the Invoice.
95 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent the user from creating a Custom View for an Invoice, when the Invoice is a Credit Invoice.
96 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent the user from editing the Custom View text, when the Invoice is a Credit Invoice.
97 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent the user from editing the Invoice Total Amount of the Custom View, when the Invoice is a Credit Invoice.
98 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent the user from deleting the Custom View, when the Invoice is a Credit Invoice with a Custom View.
99 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, if the Invoice does not have a Custom View.
100 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode.
101 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice.
102 | Invoicing | Custom Invoice Views |  |  | N | BR |  | When the user adds a Custom View Line Item to a Custom View for an Invoice, automatically recalculate the Invoice Total Amount, the underlying Invoice Variance, and the Re‐Invoice Difference.
103 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent a user from editing a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode.
104 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent a user from editing a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice.
105 | Invoicing | Custom Invoice Views |  |  | N | BR |  | When the user edits a Custom View Line Item on a Custom View for an Invoice, automatically recalculate the Invoice Total Amount, the underlying Invoice Variance, and the Re‐Invoice Difference.
106 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent a user from deleting a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode.
107 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Prevent a user from deleting a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice.
108 | Invoicing | Custom Invoice Views |  |  | N | BR |  | When the user deletes a Custom View Line Item from a Custom View for an Invoice, automatically recalculate the Invoice Total Amount, the underlying Invoice Variance, and the Re‐Invoice Difference.
109 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | Calculate the Custom View Variance Percentage as: (A) The sum of all Custom View Invoice Lines, divided by (B) the price of all items on the Reference Invoice, according to the highest priority current Contract Pricing Level with specified pricing (i.e., not Branch Standard Pricing)
110 | Invoicing | Custom Invoice Views |  |  | Y | BR | EQ | When an Invoice with a Custom View is opened or saved, automatically recalculate the Reference Invoice Total Amount and the Custom View Total Amount, and recalculate and reallocate the Custom Variance across the Reference Invoice Items.
111 | Invoicing | Custom Invoice Views |  |  | Y | BR | EI | When the user creates a Custom View of an Invoice, save the Invoice.
112 | Invoicing | Custom Invoice Views |  |  | Y | BR | EI | When the user deletes a Custom View of an Invoice, save the Invoice.
113 | Invoicing | Custom Invoice Views |  |  | Y | BR | EI | When the user adds a Custom View Line Item to a Custom View for an Invoice, save the Invoice.
114 | Invoicing | Custom Invoice Views |  |  | Y | BR | EI | When the user edits a Custom View Line Item to a Custom View for an Invoice, save the Invoice.
115 | Invoicing | Custom Invoice Views |  |  | Y | BR | EI | When the user deletes a Custom View Line Item from a Custom View for an Invoice, save the Invoice.
116 | Invoicing | Custom Invoice Views | Line Items |  | Y | BR | EI | Allow a user to add a Custom View Line Item.
117 | Invoicing | Custom Invoice Views | Line Items |  | Y | BR | EI | Allow a user to edit a Custom View Line Item.
118 | Invoicing | Custom Invoice Views | Line Items |  | Y | UA | EI | Allow a user to delete a Custom View Line Item.
119 | Invoicing | Inbox Queue |  |  | Y | UA | EQ | List all Jobs which have uninvoiced items [Inbox Queue]. Display each Customer Site by Payment Authorization.
120 | Invoicing | Inbox Queue |  |  | Y | UA | EQ | Sort the Jobs in the Inbox Queue in ascending order by Customer Number, then by ascending chronological order according to the Job Start Date.
121 | Invoicing | Inbox Queue |  |  | Y | LIST | EQ | Allow a user to filter the Jobs in the Inbox Queue by Keyword search (on Customer Site), Job Start Date (within a specified date range), or Customer Site Number.
122 | Invoicing | Inbox Queue |  |  | Y | BR | EQ | Allow a user to open an Invoice Staging Area for a Customer Site/Purchase Order in the Inbox Queue.
123 | Invoicing | Invoice Formatting and Printing |  |  | Y | UA | EQ | Allow a user to print the Invoice.
124 | Invoicing | Invoice Formatting and Printing |  |  | Y | UA | EO | Allow a user to save the Invoice as a PDF.
125 | Invoicing | Invoice Formatting and Printing |  |  | Y | UA | EQ | Apply a watermark (e.g., "NOT AN INVOICE ‐‐ DO NOT PAY") to an Invoice when it is not in Posted Mode.
126 | Invoicing | Invoice Formatting and Printing |  |  | Y | UA | EQ | Allow a user to preview an Invoice prior to printing.
127 | Invoicing | Invoice Formatting and Printing | Invoice Print Preferences |  | Y | BR | EQ | Allow a user to select the Invoice Template for an Invoice.
128 | Invoicing | Invoice Formatting and Printing | Invoice Print Preferences |  | N | UA |  | Retain the last used Invoice Template selection for an Invoice.
129 | Invoicing | Invoice Lines |  |  | Y | UA | EQ | For each new (Open) Regular Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Branch location where it is created).
130 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | For each new (Open) Credit Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Source Invoice for which it is created).
131 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | For each new (Open) Re‐Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Credit Invoice for which it is created). Placing Letter at end plus number.
132 | Invoicing | Invoice Lines |  |  | Y | BR | EI | Allow a user to create a new Invoice
133 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | Display the Invoice header
134 | Invoicing | Invoice Lines |  |  | Y | UA | EQ | Allow a user to Edit the Invoice Header (i.e., Payment Authorization, Customer‐Defined Attributes, and Notes).
135 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | Prevent the user from editing the Invoice Header if the Invoice is a Credit Invoice.
136 | Invoicing | Invoice Lines |  |  | Y | UA | EQ | Prevent the user from editing the Invoice Header unless the Invoice is in Open Mode.
137 | Invoicing | Invoice Lines | Contract Level |  | Y | BR | EQ | Upon creation of each new Invoice, allow a user to select the Contract Level, selecting from a list of Contract Levels for the Customer.
138 | Invoicing | Invoice Lines | Customer‐Defined Attributes |  | Y | BR | EQ | Display a list of the Customer‐Defined Attributes for the Invoice, and their values.
139 | Invoicing | Invoice Lines | Customer‐Defined Attributes |  | Y | UA | EI | For each Open Invoice, allow a user to enter the values for the Customer‐Defined Attributes.
140 | Invoicing | Invoice Lines | Customer‐Defined Attributes |  | Y | BR | EQ | For each Open Invoice, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue.
141 | Invoicing | Invoice Lines | Payment Authorization |  | Y | UA | EQ | Prevent the user from selecting a Payment Authorization Method that is not available to the Customer.
142 | Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | EQ | Upon creation of each new Credit Invoice and Re‐Invoice, set the Contract Level to the Contract Level of the Source Invoice.
143 | Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | EQ | For each new (Open) Invoice, automatically set the Payment Authorization to that of the Job containing the Staging Area items being added.
144 | Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | EQ | Allow a user to change the Payment Authorization for an Open Invoice, selecting from the list of Payment Authorization Methods that are available to the Customer (e.g., Purchase Order or Pending Purchase Order, Credit Card Authorization, and/or No Authorization Required).
145 | Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | EQ | If a Payment Authorization Method of Purchase Order is selected, require that the user selects one and only one of the following: (a) an existing Purchase Order (one without Purchase Order Line detail), (b) an existing Purchase Order Line, or (c) a Pending Purchase Order. However, Post Status will not be available for Pending POs.
146 | Invoicing | Invoice Lines | Payment Authorization |  | Y | UA | EQ | Prevent the user from editing the Payment Authorization unless the Invoice is in Open or Submitted Mode.
147 | Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | EQ | Warn the user if the amount remaining on the Purchase Order ‐‐ minus the amount of the Invoice ‐‐ is less than 15% of the original value of the Purchase Order.
148 | Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | EQ | Warn the user if the amount remaining on the Purchase Order ‐‐ minus the amount of the Invoice ‐‐ is less than zero.
149 | Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | EI | When a user changes a Payment Authorization Method when invoicing one or more Jobs, update all future created Invoices for that Job to use the selected Payment Authorization Method.
150 | Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | EQ | Prevent the user from selecting a Payment Authorization Method of Purchase Order, when the Customer Site requires Purchase Order Lines.
151 | Invoicing | Invoice Lines | Taxation |  | Y | BR | EQ | For each Open Invoice, determine whether the products and/or services are taxable (by Customer Site).
152 | Invoicing | Invoice Lines | Taxation |  | Y | BR | EI | Allow a user to flag a taxable invoice as tax exempt.
153 | Invoicing | Invoice Lines | Taxation |  | Y | BR | EI | Allow a user to "un‐flag" a taxable invoice as tax exempt.
154 | Invoicing | Invoice Lines | User‐ Entered Invoice Discount |  | Y | UA | EI | Allow a user to specify a User‐Entered Invoice Discount.
155 | Invoicing | Invoice Lines | User‐ Entered Invoice Discount |  | Y | UA | EI | When a User‐Entered Invoice Discount is specified, changed, or removed, save the Invoice.
156 | Invoicing | Invoice Lines | User‐ Entered Invoice Discount |  | Y | UA | EQ | Prevent the user from specifying a User‐Entered Invoice Discount of less than 0%, or more than 100%.
157 | Invoicing | Invoice Lines | User‐ Entered Invoice Discount |  | Y | BR | EQ | Prevent the user from specifying a User‐Entered Invoice Discount unless the Invoice is in Open Mode.
158 | Invoicing | Invoice Lines | User‐ Entered Invoice Discount |  | Y | BR | EQ | Prevent the user from specifying a User‐Entered Invoice Discount when the Invoice is a Credit Invoice.
159 | Invoicing | Invoice Lines | User‐ Entered Invoice Discount |  | Y | BR | EQ | Prevent the user from specifying a User‐Entered Invoice Discount when the Contract of the Invoice indicates anything other than Branch Standard Pricing.
160 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | Calculate the Tax for each Item, based upon whether the Item is a Product or Service, whether the Customer Site prescribes a Product or Service Tax Rate, and whether the user has opted to make the Invoice non‐taxable.
161 | Invoicing | Invoice Lines |  |  | Y | BR | EI | Allow a user to remove one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from the Invoice.
162 | Invoicing | Invoice Lines |  |  | Y | BR | EI | When one or more Line Items are removed from an Invoice, if one or more of the Items are components of a Package, flag the Package components as unfulfilled.
163 | Invoicing | Invoice Lines |  |  | Y | UA | EQ | List Invoice Lines, including Item Code, Description, Quantity, Unit of Measure, Price per Unit, Amount, Discount Percentage, and Net Amount.
164 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | Allow a user to select one or more Invoice Lines.
165 | Invoicing | Invoice Lines |  |  | Y | LIST | EQ | Prevent the user from removing one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from the Invoice, if the Invoice is not in Open Mode.
166 | Invoicing | Invoice Lines |  |  | N | UA |  | Prevent the user from removing a Variance Line from the Invoice.
167 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | Prevent the user from removing partial quantity of a Package Item from an Invoice.
168 | Invoicing | Invoice Lines |  |  | Y | BR | EI | When a quantity of a non‐Package item is removed from a regular Invoice, move the quantity back to the Staging Area, and mark the quantity as available for Invoicing.
169 | Invoicing | Invoice Lines |  |  | Y | BR | EI | When a Package item is removed from a regular Invoice, the quantity of its Component Items are moved individually back to the Staging Area and marked as available for Invoicing.
170 | Invoicing | Invoice Lines |  |  | N | BR |  | When one or more Line Items are removed from an Invoice, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
171 | Invoicing | Invoice Lines |  |  | N | BR |  | When one or more Line Items are removed from an Invoice, if the Invoice has a Custom View, reallocate the Variance.
172 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | Prevent the user from removing one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from a Re‐Invoice.
173 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | Calculate the price of each Invoice Line as: (A) The Item Quantity, which is defined as: (A1) The Default Quantity minus (A2) the Contract‐Specified No‐Charge Quantity minus (A3) the User‐Entered No‐Charge Quantity; times (B) the Per Unit Price; times one minus (C) The Contract Discount, which is defined as: (C1) The Contract Line Item Discount, if one is specified for the Item Code; otherwise (C2) The Contract Discount; times one minus (D) the User‐Entered Invoice Discount; times one minus (E) the User‐Entered Line Item Discount; times (F) the Custom View Variance Percentage
174 | Invoicing | Invoice Lines |  |  | Y | BR | EQ | Calculate the displayed Discount Percentage as: One minus (A) The Contract Discount, which is defined as: (A1) The Contract Line Item Discount, if one is specified for the Item Code; otherwise (A2) The Contract Discount; times one minus (B) the User‐Entered Invoice Discount; times one minus (C) the User‐Entered Line Item Discount; times (D) the Custom View Variance Percentage
175 | Invoicing | Invoice Lines |  |  | Y | BR | EI | When one or more Line Items are removed from an Invoice, save the Invoice.
176 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | Y | BR | EI | Allow a user to allocate a Third Party Charge Line‐‐ partially or totally ‐‐ to a different Service Line.
177 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | Y | BR | EI | Allow a user to combine two or more Third‐Party Charge items into one invoice line item.
178 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | Y | UA | EQ | Prevent the user from combining Third‐Party Charge items if the Invoice is not in Open Mode.
179 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | N | UA |  | When one or more Third‐Party Charge Items are combined, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
180 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | N | BR |  | When one or more Third‐Party Charge Items are combined, if the Invoice has a Custom View, recalculate the Variance.
181 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | N | BR |  | When a combined Third‐Party Charge Item is un‐combined, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
182 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | N | BR |  | When a combined Third‐Party Charge Item is un‐combined, if the Invoice has a Custom View, reallocate the Variance.
183 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | Y | BR | EQ | Prevent the user from allocating Third‐Party Charge revenue to a different Service Line, if the Invoice is not in Open Mode.
184 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | Y | BR | EI | When one or more Third‐Party Charge Items are combined, save the Invoice.
185 | Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | Y | BR | EI | When one or more Third‐Party Charge Items are un‐combined, save the Invoice.
186 | Invoicing | Invoice Lines | Combining Items Whose Units of Measure Span Shifts |  | Y | BR | EI | Allow a user to combine two or more Invoice line items that refer to units of measure that span shifts.
187 | Invoicing | Invoice Lines | Combining Items Whose Units of Measure Span Shifts |  | Y | BR | EQ | Prevent the user from combining Items with units of measure that span shifts, if the Invoice is not in Open Mode.
188 | Invoicing | Invoice Lines | Combining Items Whose Units of Measure Span Shifts |  | Y | UA | EQ | Prevent the user from combining Items with units of measure that span shifts, if the Item Codes of the source Item Codes are different.
189 | Invoicing | Invoice Lines | Combining Items Whose Units of Measure Span Shifts |  | Y | BR | EI | Allow a user to undo a combined item for the units of measure that span shifts.
190 | Invoicing | Invoice Lines | Combining Items Whose Units of Measure Span Shifts |  | Y | BR | EQ | Prevent the user from un‐combining Items with units of measure that span shifts, if the Invoice is not in Open Mode.
191 | Invoicing | Invoice Lines | Combining Items Whose Units of Measure Span Shifts |  | Y | UA | EQ | Determine the Unit Cost for each Item, based upon the selected Contract Level, and whether it indicates Branch Standard Pricing (in which case Branch Standard Pricing is used), or Contract Specific Pricing or Fixed Fee (in which case the Contract Item's Price is used).
192 | Invoicing | Invoice Lines | Contract‐Defined Item Properties |  | Y | BR | EQ | Determine the Unit of Measure for each Item, based upon the selected Contract Level, and whether it indicates Branch Standard Pricing (in which case the Item Master's default Unit of Measure is used), or Contract Specific Pricing or Fixed Fee (in which case the Contract Item Unit of Measure is used).
193 | Invoicing | Invoice Lines | Contract‐Defined Item Properties |  | Y | BR | EQ | Determine the Item Code and Description for each Item, based upon the selected Contract Level, and whether it indicates Contract Specific Pricing, and specifies an Item Code and/or Description override; otherwise, the Item Master's default Item Code and/or Description are used.
194 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | BR | EQ | Allow a user to specify a Contract‐Defined No‐Charge Quantity.
195 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | BR | EQ | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is not in Open Mode.
196 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | UA | EQ | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is a Credit Invoice.
197 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | BR | EQ | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is not under a Contract Level that indicates Contract‐Defined Pricing.
198 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | BR | EQ | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is under a Contract Level that indicates Contract‐Defined Pricing, but the Contract Item does not indicate a Contract‐Defined No‐Charge Quantity.
199 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | BR | EQ | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is Priced on Request.
200 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | BR | EQ | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is marked as Destroyed.
201 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | BR | EQ | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is a Third‐Party Charge Item.
202 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | N | BR |  | When the Contract‐Defined No‐Charge Quantity is changed for an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
203 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | N | BR |  | When the Contract‐Defined No‐Charge Quantity is changed for an Item, if the Invoice has a Custom View, recalculate the Invoice Variance.
204 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | N | BR |  | When the Contract‐Defined No‐Charge Quantity is changed for an Item, if the Item is a component of a Package, recalculate the Package Variance.
205 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | BR | EQ | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity that makes the total invoiceable Item Quantity less than zero.
206 | Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | Y | BR | EI | When the Contract‐Defined No‐Charge Quantity is changed for an Item, save the Invoice.
207 | Invoicing | Invoice Lines | Invoice Line Editing | Default Quantity | Y | BR | EQ | Allow a user to specify a Default Quantity if at least one of the following is true: (a) A Contract‐Specified Unit of Measure is used, and the Unit of Measure in the Item Master is different than the Contract‐ Specified Unit of Measure. (b) The Contract refers to a Contract‐Specified Minimum Daily Billable Labor Duration. (c) The Contract refers to a Contract‐Specified Maximum Daily Billable Labor Duration.
208 | Invoicing | Invoice Lines | Invoice Line Editing | Default Quantity | Y | BR | EQ | Prevent the user from specifying a Default Quantity, when the Invoice is not in Open Mode.
209 | Invoicing | Invoice Lines | Invoice Line Editing | Default Quantity | Y | UA | EQ | Prevent the user from specifying a Default Quantity, when the Invoice is a Credit Invoice.
210 | Invoicing | Invoice Lines | Invoice Line Editing | Default Quantity | Y | BR | EQ | Prevent the user from specifying a Default Quantity that makes the total invoiceable Item Quantity less than zero.
211 | Invoicing | Invoice Lines | Invoice Line Editing | Default Quantity | Y | BR | EQ | When the selected Contract refers to a Contract‐Specified Maximum Daily Billable Labor Duration, prevent the user from specifying a Default Quantity that is greater than Contract‐ Specified Maximum Daily Billable Labor Duration.
212 | Invoicing | Invoice Lines | Invoice Line Editing | Default Quantity | Y | BR | EQ | Allow a user to enter or change a description for a Third‐Party Charge Item.
213 | Invoicing | Invoice Lines | Invoice Line Editing | Default Quantity | Y | BR | EQ | Prevent the user from changing a description for a Third‐Party Charge, when the Invoice is not in Open Mode.
214 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | Y | UA | EI | Allow a user to enter or change the Price per Unit for an Item.
215 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | Y | BR | EQ | Prevent the user from changing the Price per Unit of an Item, when the Invoice is not in Open Mode.
216 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | Y | UA | EQ | Prevent the user from changing the Price per Unit of an Item, when the Invoice is a Credit Invoice.
217 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | Y | BR | EQ | Only allow for a user to enter or change a Price per Unit for an item if the item is one of the following: (a) An Item (or Package Item) on a Invoice with a Contract Level that indicates Branch Standard Pricing (b) A Third‐Party Charge Item (c) Priced on Request Items
218 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | N | BR |  | When a Price per Unit is entered or changed for an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
219 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | N | BR |  | When a Price per Unit is entered or changed for an Item, if the Invoice has a Custom View, recalculate the Invoice Variance.
220 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | N | BR |  | When a Price per Unit is entered or changed for an Item, if the Item is a component of a Package, recalculate the Package Variance.
221 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | N | BR |  | When a Price per Unit is entered or changed for a Package Item, recalculate the Package Variance.
222 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | Y | BR | EQ | Prevent the user from specifying a Price per Unit that is less than zero.
223 | Invoicing | Invoice Lines | Invoice Line Editing | Price per Unit | Y | BR | EI | When a Price per Unit is entered or changed for an Item or Package Item, save the Invoice.
224 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | N | BR |  | Prevent the user from specifying a User‐Specified Discount, when the Item is marked as Destroyed.
225 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | Y | BR | EQ | Allow a user to specify a User‐Specified Discount a Line Item price.
226 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | Y | BR | EQ | Prevent the user from specifying a User‐Specified Discount, when the Invoice is not in Open Mode.
227 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | Y | UA | EQ | Prevent the user from specifying a User‐Specified Discount, when the Invoice is a Credit Invoice.
228 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | Y | BR | EQ | Prevent the user from specifying a User‐Specified Discount, when the Item is on an Invoice that has a Contract Level that does not indicate Branch Standard Pricing.
229 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | N | BR |  | Prevent the user from specifying a User‐Specified Discount, when the Item is a Third‐Party Charge Item.
230 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | N | BR |  | When a User‐Specified Discount is applied to an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
231 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | N | BR |  | When a User‐Specified Discount is applied to an Item, if the Invoice has a Custom View, recalculate the Invoice Variance.
232 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | N | BR |  | When a User‐Specified Discount is applied to an Item, if the Item is a component of a Package, recalculate the Package Variance.
233 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified Discount | Y | BR | EI | When a User‐Specified Discount is applied to an Item, save the Invoice.@$
234 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | BR | EQ | Allow a user to specify a User‐Specified No‐Charge Quantity.
235 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | BR | EQ | When a User‐Specified No‐Charge Quantity is entered, allow a user to enter the User‐Specified No Charge Reason, as one of the following: (a) By HydroChem's choice, (b) By Customer insistence, or (c) Because of a Gate Log Discrepancy
236 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | UA | EQ | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Invoice is not in Open Mode.
237 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | UA | EQ | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Invoice is a Credit Invoice.
238 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | BR | EQ | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is Priced on Request.
239 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | BR | EQ | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is marked as Destroyed.
240 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | BR | EQ | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is a Third‐Party Charge Item.
241 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | BR | EQ | Prevent the user from specifying a User‐Specified No‐Charge Quantity, without supplying the User‐Specified No Charge Reason.
242 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | N | BR |  | When the User‐Specified No‐Charge Quantity is changed for an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
243 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | N | BR |  | When the User‐Specified No‐Charge Quantity is changed for an Item, if the Invoice has a Custom View, recalculate the Invoice Variance.
244 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | N | BR |  | When the User‐Specified No‐Charge Quantity is changed for an Item, if the Item is a component of a Package, recalculate the Package Variance.
245 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | BR | EQ | Prevent the user from specifying a User‐Specified No‐Charge Quantity that makes the total invoiceable Item Quantity less than zero.
246 | Invoicing | Invoice Lines | Invoice Line Editing | User‐Specified No‐ Charge Quantity | Y | BR | EI | When a User‐Specified Discount is applied to an Item, save the Invoice.
247 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from setting the quantity of a Package component to a quantity greater than the Package Item's Maximum Quantity Allowed (if it exists).
248 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from setting the quantity of a Package component to a quantity less than the Package Item's Minimum Quantity Allowed (if it exists).
249 | Invoicing | Invoice Lines | Packages |  | Y | BR | EI | Allow a user to specify the quantity of the Package.
250 | Invoicing | Invoice Lines | Packages |  | Y | BR | EI | Allow a user to delete the Package.
251 | Invoicing | Invoice Lines | Packages |  | Y | UA | EQ | When an Invoice is opened or saved, recalculate and reallocate all Package Variances across each Package's Component Items.
252 | Invoicing | Invoice Lines | Packages |  | Y | UA | EI | Allow a user to add a Package to an Invoice.
253 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | List Packages.
254 | Invoicing | Invoice Lines | Packages |  | Y | UA | EQ | When the user adds a Package to an Invoice, create a Package Variance Line within the Package.
255 | Invoicing | Invoice Lines | Packages |  | Y | LIST | EI | Allow a user to add a partial quantity of a selected Line Item to a Package.
256 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from adding a a Package to an Invoice, when the Invoice is not in Open Mode.
257 | Invoicing | Invoice Lines | Packages |  | Y | UA | EQ | Prevent the user from adding a a Package to an Invoice, when the Invoice is a Credit Invoice.
258 | Invoicing | Invoice Lines | Packages |  | Y | BR | EI | Allow a user to select a Package.
259 | Invoicing | Invoice Lines | Packages |  | Y | BR | EI | Allow a user to add a selected Line Item to a Package.
260 | Invoicing | Invoice Lines | Packages |  | Y | UA | EQ | Prevent the user from adding a Line Item to a Package, when the Invoice is not in Open Mode.
261 | Invoicing | Invoice Lines | Packages |  | Y | UA | EQ | Prevent the user from adding a Line Item to a Package, when the Invoice is a Credit Invoice.
262 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from adding a Line Item to a Package, when that Item is not defined as a Package Component.
263 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from adding a Line Item to a Package, when the required quantity of that Item has already been added to the Package.
264 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from adding a Line Item to a Package, when the Package already contains a Component Item from a different Shift.
265 | Invoicing | Invoice Lines | Packages |  | N | BR |  | Prevent the user from adding a Variance Line Item to a Package.
266 | Invoicing | Invoice Lines | Packages |  | N | BR |  | Determine which Equipment Line Items are components of a Package, according to the Contract Level used on the Invoice.
267 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Provide a visual cue to the user if the Contract Level indicates Contract‐Specific Pricing ‐‐ one that contains one or more Packages ‐‐ and a Primary Equipment line item could be converted into one of those Packages.
268 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | When an Item or partial quantity of an Item is added to a Package, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
269 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | When an Item or partial quantity of an Item is added to a Package, if the Invoice has a Custom View, recalculate and reallocate the Variance.
270 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | When an Item or partial quantity of an Item is added to a Package, recalculate and reallocate the Variance.
271 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from adding a partial quantity of a Line Item to a Package, when the Invoice is not in Open Mode.
272 | Invoicing | Invoice Lines | Packages |  | N | BR |  | When a Component Item is removed from a Package, if the Invoice has a Custom View, recalculate and reallocate the Invoice Variance.
273 | Invoicing | Invoice Lines | Packages |  | N | BR |  | When a Component Item is removed from a Package, recalculate and reallocate the Package Variance.
274 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from specifying the quantity of a Package, when the Invoice is not in Open Mode.
275 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from modifying the quantity of a Package, when the Invoice is a Credit Invoice.
276 | Invoicing | Invoice Lines | Packages |  | N | BR |  | When a Package quantity is entered or modified, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
277 | Invoicing | Invoice Lines | Packages |  | N | BR |  | When a Package quantity is entered or modified, if the Invoice has a Custom View, recalculate and reallocate the Variance.
278 | Invoicing | Invoice Lines | Packages |  | N | BR |  | When a Package quantity is entered or modified, recalculate and reallocate the Variance.
279 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from deleting a Package, when the Invoice is not in Open Mode.
280 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Prevent the user from deleting a Package, when the Invoice is a Credit Invoice.
281 | Invoicing | Invoice Lines | Packages |  | N | BR |  | When the user deletes a Package from an Invoice, remove the Package Variance Line with the Package.
282 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Calculate the price of each Package Component Item as: (A) The item quantity, which is defined as: (A1) The Default Quantity minus (A2) the Contract‐Specified No‐Charge Quantity minus (A3) the User‐Entered No‐Charge Quantity; times (B) the Per Unit Price; times one minus (C) The Contract Discount, which is defined as: (C1) The Contract Line Item Discount, if one is specified for the Item Code; otherwise (C2) The Contract Discount; times one minus (D) the User‐Entered Invoice Discount; times one minus (E) the User‐Entered Line Item Discount; times one minus (F) the Package Variance Percentage
283 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | Calculate the Package Variance Percentage as: (A) The price of the Package Item, divided by (B) the price of all the Package Component Items, according to the highest priority current Contract Pricing Level
284 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | If the Invoice's Contract Level indicates Branch Standard Pricing, only allow the user to select one of the Packages covered by Branch Standard Pricing.
285 | Invoicing | Invoice Lines | Packages |  | Y | BR | EQ | If the Invoice's Contract Level does not indicate Branch Standard Pricing, only allow the user to select one of the Packages specified in the Contract Level.
286 | Invoicing | Invoice Lines | Packages |  | Y | BR | EI | When the user adds a Package to an Invoice, save the Invoice.
287 | Invoicing | Invoice Lines | Packages |  | Y | BR | EI | When an Item or partial quantity of an Item is added to a Package, save the Invoice.
288 | Invoicing | Invoice Lines | Packages |  | Y | BR | EI | When a Component Item is removed from a Package, save the Invoice.
289 | Invoicing | Invoice Lines | Packages |  | Y | BR | EI | When a Package quantity is entered or modified, save the Invoice.
290 | Invoicing | Invoice Lines | Packages |  | Y | BR | EI | When the user deletes a Package from an Invoice, save the Invoice
291 | Invoicing | Invoice Lines | Packages | Components | Y | BR | EQ | List fulfilled and unfulfilled Package Component Items of a selected Package on the Invoice.
292 | Invoicing | Invoice Lines | Packages | Components | Y | BR | EQ | Prevent the user from adding a partial quantity of a Line Item to a Package, when the Package already contains a Component Item from a different Shift.
293 | Invoicing | Invoice Lines | Packages | Components | Y | LIST | EI | Allow a user to remove a selected Component Item from a Package.
294 | Invoicing | Invoice Lines | Packages | Components | Y | BR | EQ | Prevent the user from removing a Component Item from a Package, when the Invoice is not in Open Mode.
295 | Invoicing | Invoice Lines | Packages | Components | Y | UA | EQ | Prevent the user from removing a Component Item from a Package, when the Invoice is a Credit Invoice.
296 | Invoicing | Invoice Lines | Packages | Components | N | BR |  | When a Component Item is removed from a Package, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
297 | Invoicing | Invoice Lines | Purchase Order/Line Variance |  | Y | BR | EQ | When an invoice is opened or saved, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
298 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | Y | BR | EI | Allow a user to split a Labor Line item into two or more Labor Line Items.
299 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | Y | BR | EQ | Prevent the user from splitting a Labor Item, if the Invoice is not in Open Mode.
300 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | Y | UA | EQ | Prevent the user from splitting a Labor Item into an additional Labor Item from a different Service Line.
301 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | Y | BR | EQ | Prevent the user from splitting a Labor Item if the Labor Item is a component of a Package.
302 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | N | BR |  | When a Labor Line Item is split, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
303 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | N | BR |  | When a Labor Line Item is split, if the Invoice has a Custom View, recalculate the Variance.
304 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | Y | BR | EI | Allow a user to recombine the split Labor Lines items back to their original single‐line entry.
305 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | Y | BR | EQ | Prevent the user from recombining a split Labor Item, if the Invoice is not in Open Mode.
306 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | N | UA |  | When split Labor Line Items are recombined, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
307 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | N | BR |  | When split Labor Line Items are recombined, if the Invoice has a Custom View, recalculate the Variance.
308 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | Y | BR | EI | When a Labor Line Item is split, save the Invoice.
309 | Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | Y | BR | EI | When split Labor Line Items are recombined, save the Invoice.
310 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EI | When an invoice is Posted, Determine the GL accounts for the revenue for each Item on the Invoice and calculate and allocate the dollar amount associated with
311 | Invoicing | Invoice Management and Workflow |  |  | N | BR |  | Allow a user to mark a Re‐Invoice as Disapproved. Move the Invoice to Disapproved Mode.
312 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EI | Determine if an Invoice in Pending Approval Mode, with one or more Approvals, can be fully Approved. If so, move the Invoice to Approved Mode.
313 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | When a Credit Invoice is Posted, if the Credit Invoice is not marked as Lost Revenue, re‐add the quantities of the Credited Items back to the Staging Area.
314 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EI | Mark all quantities of Items on a deleted Invoice as invoicable, and refresh the Staging Area to reflect the new Items and quantities.
315 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent a user from moving a Credit Invoice out of Open Mode without providing the required Credit Request data (i.e., Credit Reason, Description, and ‐‐ if the Credit Invoice will return the data to the Staging Area ‐‐ the expected Re‐Invoice amount.
316 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EI | When an Invoice is Posted, log the Invoice Number as "Posted" with the date/time the Posting occurred and the person who posted it.
317 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains an Item whose General Ledger code does not exist in the General Ledger table.
318 | Invoicing | Invoice Management and Workflow |  |  | N | BR |  | Allow a user to mark an Approved Credit Invoice as Lost Revenue.
319 | Invoicing | Invoice Management and Workflow |  |  | N | BR |  | Allow a user to mark an Invoice variance as Approved.
320 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | Allow a user to change an Invoice from Open to Posted Mode.
321 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | Allow a user to delete an Open Invoice.
322 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | When an Invoice is deleted, log the Invoice Number as "No Longer Needed".
323 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EQ | Prevent the user from moving the Invoice out of Open Mode, if doing so would exceed the amount remaining on the Purchase Order or Purchase Order Line for that Invoice.
324 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if the Payment Authorization is a Pending Purchase Order.
325 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if the Purchase Order or Purchase Order Line amount is unspecified.
326 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Third‐Party Charge Item with an unspecified price.
327 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Third‐Party Charge Item with an unspecified description.
328 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Contract Item with a variable item price (i.e., Priced on Request), with an unspecified price.
329 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if one or more Customer‐Defined Attributes' values have not been specified. Expected Regular esxpression rule need to validate.
330 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if the Invoice has a Custom View, and no Custom View Line Items with dollar amounts have been specified.
331 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if one or more Packages do not have quantities specified.
332 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode, if one or more required components of a Package have not yet been fulfilled.
333 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving an Invoice directly to Posted Mode if the Customer Site requires the Submitted Invoice Mode (for electronic invoicing).
334 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EI | Allow a user to change the selected invoice from Open to Submitted Mode.
335 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving an Invoice to Submitted Mode if the Customer Site does not require the Submitted Invoice Mode (for electronic invoicing).
336 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EQ | Prevent an Invoice from going to Submitted or Posted Mode, total Invoice variance is greater than n% off the original value the Invoice, and the Invoice total amount is greater than Instead move the Invoice to Pending Approval Mode.
337 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Calculate total invoice variance as the difference between all items' default price and the final dollar amount of the invoice.
338 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EI | When a Credit Invoice or Credit/Re‐Invoice is moved out of Open Mode, move the Invoice to Pending Approval Mode.
339 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent an Invoice from going to Submitted or Posted Mode, if the invoice has been overridden to be non‐taxable. Instead move the Invoice to Pending Approval Mode.
340 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EI | Allow a user to change the selected Invoice from Submitted to Posted Mode.
341 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EI | Allow a user to change the selected Invoice from Submitted to Open Mode.
342 | Invoicing | Invoice Management and Workflow |  |  | N | UA |  | Allow a user to mark an Invoice variance as Disapproved. Move the Invoice to Disapproved Mode.
343 | Invoicing | Invoice Management and Workflow |  |  | N | UA |  | Allow a user to mark a Credit Invoice as Approved.
344 | Invoicing | Invoice Management and Workflow |  |  | N | UA |  | Allow a user to mark a Credit Invoice as Disapproved. Move the Invoice to Disapproved Mode.
345 | Invoicing | Invoice Management and Workflow |  |  | N | UA |  | Allow a user to mark an Invoice as with a Taxability Override as Approved.
346 | Invoicing | Invoice Management and Workflow |  |  | N | UA |  | Allow a user to mark an Invoice with a Taxability override as Disapproved. Move the Invoice to Disapproved Mode.
347 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | Allow a user to change the selected Invoice from Pending Approval to Open Mode.
348 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | Allow a user to change the selected Invoice from Disapproved Mode to Open Mode.
349 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | Allow a user to change the selected Invoice from Approved Mode to Open Mode.
350 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | Allow a user to change the selected Invoice from Approved Mode to Submitted Mode.
351 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | Allow a user to change the selected Invoice from Approved Mode to Posted Mode.
352 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EQ | Prevent the user from moving the Invoice to Posted Mode, if the Invoice contains one or more Packages without a specified Price per Unit.
353 | Invoicing | Invoice Management and Workflow |  |  | N | UA |  | Allow a user to mark a Re‐Invoice as Approved.
354 | Invoicing | Invoice Management and Workflow |  |  | N | BR |  | Prevent a user from marking a Re‐Invoice as Approved without providing the required Credit Request data.
355 | Invoicing | Invoice Management and Workflow |  |  | Y | UA | EI | When a Credit Invoice is Posted, if the Credit Invoice is marked as Lost Revenue, do not re‐add the quantities of the Credited Items back to the Staging Area. Instead, mark the quantities of the items as uninvoiceable.
356 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode if the Invoice contains a Package with component items that are all zero priced.
357 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode if the Invoice has a Custom View, and the Custom View has no Custom View Line with a dollar value.
358 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice out of Open Mode if the Invoice has a Custom View, and the Reference Invoice has a zero dollar value.
359 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving the Invoice to Posted Mode, if doing so would exceed the amount remaining on the Purchase Order or Purchase Order Line for that Invoice.
360 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Display the Current Invoice Mode.
361 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving an Invoice out of Open Mode, if the Invoice is under Contract‐Specified Pricing, and contains one or more Items where the Unit of Measure in the Item Master is different from the Contract‐Specified Unit of Measure, for which no Item Quantity exists.
362 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from moving an Invoice out of Open Mode, if a Labor Item on the Invoice refers to a Shift Summary Labor Line whose start/stop date/time overlaps with another Shift Summary Labor Line within the system.
363 | Invoicing | Invoice Management and Workflow |  |  | Y | BR | EQ | Prevent the user from Posting an Invoice, if a Labor Item on the Invoice refers to a Shift Summary Labor Line whose start/stop date/time overlaps with another Shift Summary Labor Line within the system and both refer to the same employee ID.
364 | Invoicing | Invoice Management and Workflow | Custom Exports |  | Y | BR | EQ | Allow a user to generate a Customer‐Specific Invoice Export.
365 | Invoicing | Invoice Management and Workflow | Custom Exports |  | Y | BR | EQ | Prevent the user from generating a Customer‐Specific Invoice Export if the Customer does not accept Customer‐Specific Invoice Exports.
366 | Invoicing | Invoice Management and Workflow | Custom Exports |  | Y | UA | EQ | Prevent the user from generating a Customer‐Specific Invoice Export, if the Invoice is not in Posted Mode, and the Customer requires Customer‐Specific Invoice Exports from Posted Mode.
367 | Invoicing | Invoice Management and Workflow | Custom Exports |  | Y | BR | EQ | Prevent the user from generating a Customer‐Specific Invoice Export, if the Invoice is not in Submitted Mode, and the Customer requires Customer‐Specific Invoice Exports from Submitted Mode.
368 | Invoicing | Invoice Queue |  |  | Y | BR | EQ | List all Invoices [Invoice Queue]
369 | Invoicing | Invoice Queue |  |  | Y | BR | EQ | Allow a user to filter the Invoices in the Invoice Queue by Customer Site Keyword search (on Customer Site), Customer Number, Payment Authorization, Creation Date Range, Posted Data Range, Invoice Number, Branch Oracle Code, Invoice Mode (e.g., Open, Posted, etc.), and/or Invoice Type (Invoice, Credit Invoice, Re‐ Invoice)
370 | Invoicing | Invoice Queue |  |  | N | LIST |  | Allow a user to filter the Invoices in the Invoice Queue by Status (e.g., Open, Pending Approval, Approved, Disapproved, Submitted, Posted).
371 | Invoicing | Invoice Queue |  |  | N | UA |  | Allow a user to filter the Invoices in the Invoice Queue by Type (e.g., Invoice, Prepayment Invoice, Credit Invoice, Credit Reinvoice)
372 | Invoicing | Invoice Queue |  |  | N | UA |  | Allow a user to filter the Invoices in the Invoice Queue by Date.
373 | Invoicing | Invoice Queue |  |  | Y | UA | EQ | Sort the Invoices in the Invoice Queue by Invoice Number (descending)
374 | Invoicing | Invoice Queue |  |  | Y | UA | EI | Allow a user to open an Invoice from the Invoice Queue.
375 | Invoicing | Re‐Invoices |  |  | N | BR |  | Allow a user to create a Re‐Invoice from from a Credit Invoice.
376 | Invoicing | Re‐Invoices |  |  | Y | UA | EQ | When a Re‐Invoice mode changes, automatically change the mode of its corresponding Credit Invoice.
377 | Invoicing | Re‐Invoices |  |  | Y | UA | EQ | When a Re‐Invoice is authorized by the same Purchase Order or Purchase Order Line of the source Invoice, when recalculating the Remaining Value of the Purchase Order or Purchase Order Line, also calculate the value of Credit of the source Invoice.
378 | Invoicing | Re‐Invoices |  |  | Y | BR | EQ | If a user creates a Re‐Invoice from an Invoice with a Custom View, automatically create a Custom View Line Items for the Re‐Invoice, and set the Description of each to the Description of each Custom View Line Item of the source Invoice, and the Dollar Amount of each to the Dollar Amount of each Custom View Line Item of the source Invoice.
379 | Invoicing | Re‐Invoices |  |  | Y | BR | EI | When a Credit Invoice mode changes, if the Credit Invoice has a corresponding Re‐Invoice, automatically change the mode of its corresponding Re‐Invoice.
380 | Invoicing | Staging Area |  |  | Y | BR | EQ | List all the uninvoiced items for that Customer Site, by the Item Description.
381 | Invoicing | Staging Area |  |  | Y | BR | EQ | Organize the Staging Area items by Job (chronologically, from oldest to most recent), by Shift within the Job (chronologically, from oldest to most recent), by Item Type within the Shift, and by Description within the Item Type.
382 | Invoicing | Staging Area |  |  | Y | LIST | EQ | Allow a user to search for a Job by entering a Job Number, and navigate the user to that Job in the Staging Area.
383 | Invoicing | Staging Area |  |  | Y | BR | EQ | Allow a user to view a Staging Area Item's Item Code, Quantity available for invoicing, and Unit of Measure.
384 | Invoicing | Staging Area |  |  | Y | UA | EQ | Allow a user to filter the Staging Area by Payment Authorization, initializing the Payment Authorization to that of the Customer Site/Payment Authorization selected in the Inbox Queue, or of the current Payment Authorization of the Invoice selected in the Invoice Queue. Limit the selectable Payment Authorizations to those of Jobs for the selected Customer Site with Items remaining to be invoiced.
385 | Invoicing | Staging Area |  |  | Y | UA | EQ | Allow a user to filter the Staging Area to show either: (a) All Items (b) Only Labor Items
386 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | UA | EI | Allow a user to move the selected Items in the Staging Area (or those within the selected Shifts or Jobs) to an Open invoice.
387 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | N | UA |  | If the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value when an Item is added from the Staging
388 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | N | UA |  | If the Invoice has a Custom View, recalculate the Variance when an Item is added from the Staging Area.
389 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | BR | EQ | Allow a user to select one or multiple Staging Area lines.
390 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | BR | EQ | Allow a user to select one or multiple Shifts in the Staging Area.
391 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | UA | EQ | Allow a user to select one or multiple Jobs in the Staging Area.
392 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | UA | EQ | Prevent a user from moving Staging Area Items to a Credit Invoice.
393 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | UA | EQ | Prevent a user from moving Staging Area Items to a Re‐Invoice.
394 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | BR | EI | When Items are moved from the Staging Area to an Invoice, reduce the invoicable quantities of the Items, and refresh the Staging Area to reflect the remaining Items and quantities.
395 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | BR | EQ | Prevent the user from moving a Labor item to an Invoice if the Labor item refers to a Pending Employee.
396 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | N | BR |  | Allow a user to create a new Invoice from the selected Staging Area Line(s).
397 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | BR | EQ | Warn the user when moving a Labor or Equipment item to an Invoice if the Customer Site requires Labor / Equipment Time Reconciliations that have not been completed.
398 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | UA | EI | When an Item is added from the Staging Area, save the Invoice.
399 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | BR | EQ | Provide a visual cue to the user if a Labor Item in the Staging Area refers to a Pending Employee.
400 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | BR | EQ | If a user moves one or more selected Shifts or Jobs to an Invoice, and the Staging Area filter is set to show "Only Labor Items", only move the Labor items within the selected Shifts or Jobs to the Invoice.
401 | Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | Y | BR | EQ | Automatically adjust Labor and Equipment time entries to their saved Gate Log Reconciliation values, if applicable.
402 | Invoicing | Staging Area | Warnings and Adjustments |  | N | BR |  | Warn the user if the Staging Area contains two or more Labor or Equipment time entries that overlap.
403 | Invoicing | Staging Area | Warnings and Adjustments |  | Y | BR | EI | If a material item has a quantity that has been marked as destroyed, automatically split the item into Used Item and Destroyed Item staging area items, as needed.
404 | Invoicing | Staging Area | Warnings and Adjustments |  | Y | BR | EI | Automatically adjust Labor and Equipment time entries up to a contract‐specified minimum quantity, if one exists.
405 | Invoicing | Staging Area | Warnings and Adjustments |  | Y | BR | EI | Automatically adjust Labor and Equipment time entries down to a contract‐specified maximum quantity, if one exists.
406 | Payroll | Employee Payroll Lines |  |  | N | BR |  | Calculate special payment cases (e.g., overtime, double‐time, holiday time, etc.).
407 | Payroll | Employee Payroll Lines |  |  | N | BR |  | Prevent a user from editing an Employee Payroll Line in a closed Payroll Period.
408 | Payroll | Employee Payroll Lines |  |  | N | BR |  | Allow a user to delete an Employee Payroll Line.
409 | Payroll | Employee Payroll Lines |  |  | N | BR |  | List Employee Payroll Lines
410 | Payroll | Employee Payroll Lines |  |  | N | UA |  | Sort Employee Payroll Lines
411 | Payroll | Employee Payroll Lines |  |  | N | LIST |  | Allow a user to create a new Employee Payroll Line.
412 | Payroll | Employee Payroll Lines |  |  | N | BR |  | Prevent a user from creating a new Employee Payroll Line for a billable category.
413 | Payroll | Employee Payroll Lines |  |  | N | UA |  | Allow a user to edit an Employee Payroll Line.
414 | Payroll | Employee Payroll Lines |  |  | N | BR |  | Prevent a user from increasing the payable time for a billable Payroll record above the calculated value.
415 | Payroll | Employee Payroll Lines |  |  | N | UA |  | Prevent a user from changing a non‐billable category to a billable category.
416 | Payroll | Employee Payroll Lines |  |  | N | BR |  | Prevent a user from changing a billable category to a non‐billable category.
418 | Payroll | Employee Payroll Lines |  |  | N | BR |  | Prevent a user from specifying a date beyond the end of the Payroll Period.
419 | Payroll | Employee Payroll Lines |  |  | N | BR |  | Prevent a user from deleting an Employee Payroll Line for billable time.
420 | Payroll | Employee Payroll Lines |  |  | N | BR |  | Prevent a user from deleting an Employee Payroll Line in a closed Payroll Period.
421 | Payroll | Employee Payroll Periods |  |  | N | BR |  | Automatically populate Employee Payroll Periods list.
422 | Payroll | Employee Payroll Periods |  |  | N | BR |  | Automatically calculate differences between prior period Payroll data imported from Shift Summaries, and current period Payroll data imported from Shift Summaries, and generate offsetting records.
423 | Payroll | Employee Payroll Periods |  |  | N | BR |  | Allow a user to delete an Employee Payroll Period.
424 | Payroll | Employee Payroll Periods |  |  | N | UA |  | Allow a user to match a Pending Employee from a Pending Employee Payroll Period to an Oracle Employee.
425 | Payroll | Employee Payroll Periods |  |  | N | UA |  | Allow a user to see Payroll data for one of its Employees from Payroll data entered at another Branch.
426 | Payroll | Employee Payroll Periods |  |  | N | UA |  | Prevent a user from editing Payroll data for one of its Branch's Employees, if the Payroll data was entered at another Branch.
427 | Payroll | Employee Payroll Periods |  |  | N | BR |  | List Employee Payroll Periods.
428 | Payroll | Employee Payroll Periods |  |  | N | LIST |  | Sort Employee Payroll Periods.
429 | Payroll | Employee Payroll Periods |  |  | N | BR |  | Allow a user to create a new Employee Payroll Period.
430 | Payroll | Employee Payroll Periods |  |  | N | UA |  | Prevent a user from creating an Employee Payroll Period for an Employee that already has an Employee Payroll Period.
431 | Payroll | Employee Payroll Periods |  |  | N | BR |  | List Pending Employee Payroll Periods
432 | Payroll | Employee Payroll Periods |  |  | N | LIST |  | Allow a user to select an Employee Payroll Period.
433 | Payroll | Employee Payroll Periods |  |  | N | UA |  | Allow a user to access an Employee Payroll Period.
434 | Payroll | Employee Payroll Periods |  |  | N | UA |  | Prevent a user from deleting an Employee Payroll Period that contains billable time imported from a Shift Summary.
435 | Payroll | Employee Payroll Periods | Listing |  | Y | BR | EQ | List the Employee Payroll Records within the Employee Payroll Week, displaying date, Pay Type, Job (if applicable), and Shift (if applicable), Entered‐By Branch, and Duration (in hours:minutes).
436 | Payroll | Employee Payroll Periods | Listing |  | Y | LIST | EQ | Sort the Employee Payroll Records by date (ascending), then by Pay Type (ascending by Pay Type Code).
437 | Payroll | Employee Payroll Periods | Listing |  | Y | BR | EQ | Filter the Employee Payroll Records by selected Employee and selected Employee Payroll Week, for all Employee Payroll Records manually entered by the Branch, plus all Employee Payroll Records for an Employee of the Branch.
438 | Payroll | Employee Payroll Periods | Listing |  | Y | BR | EQ | Aggregate the Employee Payroll Records by date, Pay Type, Home Branch, Entered Branch, Job (if applicable), and Shift (if applicable), summing the Duration.
439 | Payroll | Employee Payroll Periods | Listing |  | Y | BR | EI | Allow a user to add a new Employee Payroll Record.
441 | Payroll | Employee Payroll Periods | Listing | Special Payment Calculations | Y | BR | EQ | Automatically calculate special payment cases (e.g., overtime, double‐time, etc.) for added, edited, and deleted records.
442 | Payroll | Employee Payroll Periods | Listing | Special Payment Calculations | Y | BR | EQ | Display the calculated straight time, overtime, double‐time and total hours durations for the the Employee Payroll Week.
443 | Payroll | Employee Payroll Periods | Listing | Special Payment Calculations | Y | BR | EQ | If an Employee with an Employee Type of "Part‐Time Professional" has one or more Employee Payroll Records for a day, and the total duration of all Employee Payroll records is greater than 0:00, automatically calculate that Employee's Duration at 8:00 hours per day.
444 | Payroll | Employee Payroll Periods | Listing | Special Payment Calculations | Y | UA | EQ | Alow a user to access an existing Employee Payroll Record.
445 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | UA | EI | Allow a user to edit an existing Employee Payroll Record, including the Employee, the date worked, the Pay Type, the Duration in hours:minutes, and the Shift Summary Number.
446 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | UA | EI | Allow a user to delete an existing Employee Payroll Record.
447 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR | EQ | Prevent a user from editing a Manual Employee Payroll Record not created at the user's Branch.
448 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR | EQ | Prevent a user from editing an Automatic Employee Payroll Record.
449 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR | EQ | Prevent a user from deleting a Manual Employee Payroll Record not created at the user's Branch.
450 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR | EQ | Prevent a user from deleting an Automatic Employee Payroll Record.
451 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR | EQ | When a Shift Summary Labor Line is recorded by the system as added, create one (or two, if the Shift Summary Labor Line spans midnight of Sunday night of the time zone of the Employee's Home Branch) Automatic Employee Payroll Records, including all time for the Employee Payroll Record within the Payroll Week for the Branch of the Shift Summary's Job, starting Monday morning midnight of the time zone of the RS/FS device, ending Sunday night midnight of the time zone of the RS/FS device.
452 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR | EQ | When a Shift Summary Labor Line is recorded by the system as edited, create two Automatic Employee Payroll Records for every existing, current, related Automatic Employee Payroll Record, one with a negative‐Duration of the existing Automatic Employee Payroll Record(s) for the Shift Summary Labor Line, and one with a positive‐Duration of the new Automatic Employee Payroll Record(s) for the Shift Summary Line.
453 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR | EQ | When a Shift Summary Labor Line is recorded by the system as deleted, create an Automatic Employee Payroll Record for every existing, current, related Automatic Employee Payroll Record, with a negative‐Duration of the existing Automatic Employee Payroll Record for the Shift Summary Labor Line.
454 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR | EI | When a Manual Employee Payroll Record is edited, automatically create a Manual Employee Payroll Records with a negative‐ Duration of the existing Manual Employee Payroll Record, and one with a positive‐Duration of the new Manual Employee Payroll Record.
455 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR | EI | When a Manual Employee Payroll Record is deleted, create a Manual Employee Payroll Records with a negative‐Duration of the existing Manual Employee Payroll Record.
456 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR |  | Prevent a user from saving an Employee Payroll Record without a specified Employee.
457 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR |  | Prevent a user from saving an Employee Payroll Record without a specified Pay Type.
458 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR |  | Prevent a user from saving an Employee Payroll Record without a specified Duration.
459 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR |  | Prevent a user from saving an Employee Payroll Record without a specified Date.
460 | Payroll | Employee Payroll Periods | Viewing/Editing |  | Y | BR |  | Prevent a user from saving an Employee Payroll Record without a specified Shift Summary, if the Pay Type is "Manual Billable".
461 | Payroll | Employee Payroll Periods | Viewing/Editing | Duration | N | BR |  | Prevent the user from specifying the Duration of an Automatic Employee Payroll Record to less than zero, or more than the value recorded on the Shift Summary.
462 | Payroll | Employee Payroll Periods | Viewing/Editing | Duration | Y | BR | EQ | Prevent the user from specifying the Duration of an Employee Payroll Record to any value that would make the sum of all Employee Payroll Records of the specified Pay Type on the specified Date for the Branch who created the Employee Payroll Record be less than zero, unless the Pay Type is "Manual Billable".
463 | Payroll | Employee Payroll Periods | Viewing/Editing | Pay Type | Y | BR | EQ | Prevent the user from specifying a Pay Type that is an Automatic Employee Pay Type.
464 | Payroll | Employee Payroll Periods | Viewing/Editing | Pay Type | Y | BR | EQ | Prevent the user from changing the Pay Type of an Automatic Employee Payroll Record.
465 | Payroll | Employee Payroll Periods | Viewing/Editing | Pay Type | Y | BR | EQ | Prevent the user from changing the Pay Type of a Manual Employee Payroll Record to an Automatic Pay Type.
466 | Payroll | Employee Payroll Periods | Viewing/Editing | Shift Summary Number | Y | BR | EQ | Prevent the user from entering a Shift Summary Number for an Employee Payroll Record if the Pay Type is not "Manual Billable" type.
467 | Payroll | Employee Payroll Weeks |  |  | Y | BR | EQ | Prepopulate the Employee Payroll Weeks to automatically appear within a Payroll Week, which is a combination of Employees with Automatic Employee Payroll Records for the Payroll Week (i.e., those Employees with billable hours for the current Branch), and Employees with Manual Employee Payroll Records for the current and one prior Payroll Weeks.
468 | Payroll | Employee Payroll Weeks |  |  | Y | LIST | EQ | List the Employee Payroll Weeks within a Payroll Week, including First Name, Last Name, Employee Number, Home Branch Code, Employee Type (i.e., Regular or Part‐Time Professional), Straight Time Hours, Overtime Hours, Double‐Time Hours, Input Branch and Total Hours.
469 | Payroll | Employee Payroll Weeks |  |  | Y | BR | EQ | Sort the Employee Payroll Weeks by Last Name (ascending), then by First Name (ascending)
470 | Payroll | Employee Payroll Weeks |  |  | Y | UA | EQ | Allow a user to access an Employee Payroll Week.
471 | Payroll | Employee Selection |  |  | Y | BR | EQ | Filter the Employees by those who were Active (according to Oracle) on or after Monday of the previous week.
472 | Payroll | Employee Selection |  |  | Y | LIST | EQ | List Employees, including First Name, Last Name, Employee Number, Employee Type (i.e., Regular or Part‐Time Professional).
473 | Payroll | Employee Selection |  |  | Y | UA | EQ | Allow a user to sort Employees by Employee ID (ascending), or by Last Name (ascending)/First Name (ascending), default by Last Name/First Name.@$
474 | Payroll | Employee Selection |  |  | Y | UA | EQ | Allow a user to filter Employees by Branch, default to the Home Branch.
475 | Payroll | Employee Selection |  |  | Y | UA | EQ | Allow a user to select an Employee.
476 | Payroll | Payroll Periods |  |  | N | LIST |  | List Payroll Periods.
477 | Payroll | Payroll Periods |  |  | N | BR |  | Sort Payroll Periods in descending order by date.
478 | Payroll | Payroll Periods |  |  | N | UA |  | Allow a user to select a Payroll Period.
479 | Payroll | Payroll Periods |  |  | N | UA |  | Allow a user to access an existing Payroll Period.
480 | Payroll | Payroll Periods |  |  | Y | UA | EQ | Allow a user to access the current Payroll Week.
481 | Payroll | Payroll Weeks |  |  | Y | UA | EQ | Allow a user to select a Payroll Week by specifying a date within the Payroll Week (Monday to Sunday).
482 | Payroll | Posting |  |  | Y | BR | EQ | Allow for an external system/process to flag each Employee Payroll Record as having been imported into Oracle as of a provided date.
x | Invoicing | A/C Transaction File |  |  | Y |  | ILF
x | Administration | Branch Contractor |  |  | Y |  | ILF
x | Invoicing | Contract Master |  |  | Y |  | ILF
x | Invoicing | Custom Invoice |  |  | Y |  | ILF
x | Invoicing | Customer Master |  |  | Y |  | ILF
x | Invoicing | Customer-Invoice Master |  |  | Y |  | ILF
x | Invoicing | Discount Master |  |  | Y |  | ILF
x | Payroll | Employee Master |  |  | Y |  | ILF
x | Administration | GateLog |  |  | Y |  | ILF
x | Invoicing | General Leader Master |  |  | Y |  | ILF
x | Invoicing | Inventory Trans File |  |  | Y |  | ILF
x | Invoicing | Invoice |  |  | Y |  | ILF
x | Invoicing | Invoice Queue |  |  | Y |  | ILF
x | Invoicing | Labour Invoice |  |  | Y |  | ILF
x | Invoicing | Package |  |  | Y |  | ILF
x | Invoicing | Party Ledger Master |  |  | Y |  | ILF
x | Invoicing | Payment AuthMaster |  |  | Y |  | ILF
x | Payroll | Payroll Details |  |  | Y |  | ILF
x | Payroll | Payroll Transaction |  |  | Y |  | ILF
x | Invoicing | Product Master |  |  | Y |  | ILF
x | Invoicing | PurchaseOrder |  |  | Y |  | ILF
x | Invoicing | Staged-Invoice |  |  | Y |  | ILF
x | Administration | Tax Master |  |  | Y |  | ILF
x | Invoicing | Unit Master |  |  | Y |  | ILF

## ScopeGrid
In Scope | Category | SubCategory | Sub-Subcategory | Sub-SubSubCategory | Req Type | Requirement
Y | Administration | Branch Contractors | (blank) | (blank) | BR | Prevent the user from saving a Branch Contractor with an Employee Number that is already used by an Employee or by another Branch Contractor.
Prevent the user from saving a Branch Contractor without a First Name, Last Name, Employee Number, or specified Employment Service.
Sort the Branch Contractors by Last Name, First Name
[5 empty] | LIST | List Branch Contractors, including First Name, Last Name, Unique Employee Number, and Employment Service.
[5 empty] | UA | Allow a user to access a Branch Contractor from the list.
Allow a user to create a new Branch Contractor.
Allow a user to edit a new Branch Contractor.
Allow a user to Filter the Branch Contractors by All or Active Only. Default to Active Only.
Allow a user to terminate/un‐terminate a Branch Contractor.
|  | Customer Gate Log Reconciliations | (blank) | (blank) | BR | Display summary duration values for each person (i.e., Badge Number).
Filter the Gate Log Reconciliation records by the selected Customer Site, by all Shift Labor records that begin on the selected date.
Prevent a user from editing a Gate Log record if the corresponding item exists on an Invoice (unless the Invoice has been credited and the item has not been reinvoiced).
Sort the Gate Log Reconciliation records by Last Name (ascending), and First Name (ascending).
Warn the user, when reopening a Shift Summary with Gate Log Reconciliations, that the Gate Log Reconciliations will be deleted.
When a user reopens a Shift Summary with Gate Log Reconciliations, delete the Gate Log Reconciliations associated with the Shift Summary.
[5 empty] | LIST | List Labor records for a selected day for a selected Customer Site, displaying the Badge Number, First Name, Last Name, Employee Number (if it exists)and Start/Stop date/time (according to the Shift Summary), total hours/minutes worked, the Employee's Hom
[5 empty] | UA | Allow a user to accept the default calculated Labor time (per the Shift Summary), or enter the Gate Log Labor time (in minutes, hours), per line.
Allow a user to save the Gate Log data for a shift.
|  | Customer Purchase Orders | Customer‐ Defined Attributes | (blank) | BR | For each Purchase Order, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue.
Warn the user when saving a Purchase Order with invalid Customer‐Defined Attribute values.
[5 empty] | UA | For each Purchase Order, Allow a user to enter the values for the Customer‐Defined Attributes.
|  |  | Purchase Order Lines | Customer‐Defined Attributes | BR | For each Purchase Order Line, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue.
Prevent the user from deleting a Purchase Order Line if it exists on an Invoice.
Warn the user when saving the Purchase Order Line with invalid Customer‐Defined Attribute values.
[5 empty] | UA | Allow a user to delete a Purchase Order Line.
For each Purchase Order Line, allow a user to enter the values for the Customer‐Defined Attributes.
|  |  |  | (blank) | BR | If the user changes the Dollar Amount of a Purchase Order Line, recalculate the remaining values on the Purchase Order Line.
Prevent the user from creating a Purchase Order Line for a Purchase Order, if the Customer Site does not require Purchase Order Lines.
Prevent the user from creating a Purchase Order Line for a Purchase Order, if the Purchase Order is closed.
Prevent the user from deleting a Purchase Order Line if the Purchase Order is closed.
Prevent the user from editing anything other than the Dollar Amount of a Purchase Order Line, if the Purchase Order Line has been used on a Posted Invoice.
[5 empty] | LIST | List Purchase Order Lines per Purchase Order.
[5 empty] | UA | Allow a user to create a new Purchase Order Line for a Purchase Order.
Allow a user to edit a Purchase Order Line for a Purchase Order.
|  |  | (blank) | (blank) | BR | Calculate and display the difference between the original amount of the Purchase Order or Purchase Order Line, and the amount of the Invoices posted against it.
Calculate and display the difference between the original amount of the Purchase Order or Purchase Order Line, and the amount of the unposted and posted Invoices against it.
Filter the Purchase Orders by Customer Filter the Purchase Orders by Customer Site.
If the user changes the Dollar Amount of a Purchase Order, recalculate the remaining values on the Purchase Order.
Prevent the user from closing a Purchase Order if one of its Purchase Order Lines exists on an unposted Invoice.
Prevent the user from editing a closed Purchase Order, or a Purchase Order Line of a closed Purchase Order.
Prevent the user from editing anything other than the Dollar Amount of a Purchase Order, if the Purchase Order has been used on a Posted Invoice.
Prevent the user from saving a Purchase Order Line that already exists for the Customer Site.
Prevent the user from saving a Purchase Order with a Purchase Order Number that already exists for the Customer Site.
Sort the Purchase Order Lines by Purchase Order Line Number (ascending).
Sort the Purchase Orders by Purchase Order Number (ascending).
Warn the user when saving the Purchase Order with a Purchase Order Number that does not pass the Purchase Order regular expression mask for the Customer Site, if one exists.
[5 empty] | LIST | List Purchase Orders.
[5 empty] | UA | Allow a user to close a Purchase Order.
Allow a user to create a Purchase Order
Allow a user to filter the Purchase Orders (Open vs. Closed). Initialize the filter to display Open only.
Allow a user to order a Purchase Order
Allow a user to reopen a Purchase Order.
Allow a user to select a Purchase Order
|  | Employees | (blank) | (blank) | LIST | List Employees, including First Name, Last Name, Employee Number, Employee Type (i.e., Regular or Part‐Time Professional).@$
[5 empty] | UA | Allow a user to sort Employees by Employee ID (ascending), or by Last Name (ascending)/First Name (ascending), default by Last Name/First Name.
Allow a user to filter Employees by Branch, default to the Home Branch.@#
Allow a user to select an Employee.@$
|  | Field Service Settings | (blank) | (blank) | BR | Notify the user if a clock reset has been detected, and prevent the application from starting until the clock has been set.
|  | Month End Close | (blank) | (blank) | BR | Provide real and estimated revenue values for all Shift Items within a month, for all items added in that month, and for all items whose real or estimated revenue has changed within the month; and for a place‐holder for a Corporate System to associate a m
|  | Pending Employees | (blank) | (blank) | UA | Allow a user to match a Pending Employee to an Oracle Employee.
|  | Synchronization | (blank) | (blank) | BR | Display a confirmation message at the end of a successful manual synchronization.
Display the synchronization status.
Warn the user to synchronize when the Remote System 2.0 is opened and closed in branch.
|  | Terms & Conditions Contract | (blank) | (blank) | BR | Display Customer Terms & Conditions Contract Details (T&C Contract Number, Activation Date, Expiration Date)
Warn the user when creating a new Job when the Terms & Conditions Contract has past its expiration date.
Warn the user when creating a Shift for an existing Job when the Terms & Conditions Contract has past its expiration date.
| Invoicing | Contract Selection | (blank) | (blank) | BR | Filter the Contract / Contract Level / Contract Versions to only show records: (a) for the currently selected Customer Site (i.e., those where the Contract Level applies to no Customer Site or to the current Customer Site) (b) where the Active Date of the
Sort the Contract / Contract Level / Contract Versions by Active Date of the Contract (descending), then by Contract Level Priority (ascending), then by Contract Version Active Date (descending).
[5 empty] | LIST | List all Contracts, Contract Levels, and Contract Level Version for a Customer, displaying the Contract Number, the Contract Level Description, the Contract Version Activation Date, and the Contract Expiration Date.
[5 empty] | UA | Allow a user to revise the filtered view, to show older Contracts / Contract Levels / Contract Versions by date range, between today and the specified date.
Allow a user to select a Contract / Contract Level / Contract Version.
|  | Credit Invoices | (blank) | (blank) | BR | If a Credit Invoice is created from an Invoice with a Custom View, automatically create a Custom View Line Items for the Credit Invoice, and set the Description of each to the Description of each Custom View Line Item of the source Invoice, and the Dollar
Prevent the user from creating a Credit Invoice from an Invoice, or one or more of the Items on that Invoice, if the source Invoice is a Credit Invoice.
Prevent the user from creating a Credit Invoice from an Invoice, or one or more of the Items on that Invoice, if the source Invoice is not in Posted Mode.
[5 empty] | UA | Allow a user to create a Credit Invoice from an Invoice, including an indication of whether the Invoice Line Data: (a) will be returned to the Staging Area, (b) will be deleted, and marked as Lost Revenue, or (c) will be associated with a Re‐Invoice.
Allow a user to create a Credit Request associated with the Credit Invoice or Credit/Re‐Invoice.
|  | Custom Invoice Views | Line Items | (blank) | BR | Allow a user to add a Custom View Line Item.
Allow a user to edit a Custom View Line Item.
[5 empty] | UA | Allow a user to delete a Custom View Line Item.
|  |  | (blank) | (blank) | BR | Calculate the Custom View Variance Percentage as: (A) The sum of all Custom View Invoice Lines, divided by (B) the price of all items on the Reference Invoice, according to the highest priority current Contract Pricing Level with specified pricing (i.e.,
Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, if the Invoice does not have a Custom View.
Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice.
Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode.
Prevent a user from deleting a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice.
Prevent a user from deleting a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode.
Prevent a user from editing a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice.
Prevent a user from editing a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode.
Prevent the user from creating a Custom View for an Invoice, when the Invoice already has a Custom View.
Prevent the user from creating a Custom View for an Invoice, when the Invoice is a Credit Invoice.
Prevent the user from deleting a Custom View for an Invoice, when the Invoice does not have a Custom View.
Prevent the user from deleting the Custom View, when the Invoice is a Credit Invoice with a Custom View.
Prevent the user from deleting the Custom View, when the Invoice is not in Open Mode.
Prevent the user from editing the Custom View text, when the Invoice is a Credit Invoice.
Prevent the user from editing the Invoice Total Amount of the Custom View, when the Invoice is a Credit Invoice.
When an Invoice with a Custom View is opened or saved, automatically recalculate the Reference Invoice Total Amount and the Custom View Total Amount, and recalculate and reallocate the Custom Variance across the Reference Invoice Items.
When the user adds a Custom View Line Item to a Custom View for an Invoice, save the Invoice.
When the user creates a Custom View of an Invoice, calculate the Custom View Variance Percentage.
When the user creates a Custom View of an Invoice, save the Invoice.
When the user deletes a Custom View Line Item from a Custom View for an Invoice, save the Invoice.
When the user deletes a Custom View of an Invoice, save the Invoice.
When the user edits a Custom View Line Item to a Custom View for an Invoice, save the Invoice.
[5 empty] | UA | Allow a user to create a Custom View for an Invoice.
Allow a user to delete the Custom View of an Invoice.
|  | Inbox Queue | (blank) | (blank) | BR | Allow a user to open an Invoice Staging Area for a Customer Site/Purchase Order in the Inbox Queue.
[5 empty] | LIST | Allow a user to filter the Jobs in the Inbox Queue by Keyword search (on Customer Site), Job Start Date (within a specified date range), or Customer Site Number.
[5 empty] | UA | List all Jobs which have uninvoiced items [Inbox Queue]. Display each Customer Site by Payment Authorization.
Sort the Jobs in the Inbox Queue in ascending order by Customer Number, then by ascending chronological order according to the Job Start Date.
|  | Invoice Formatting and Printing | Invoice Print Preferences | (blank) | BR | Allow a user to select the Invoice Template for an Invoice.
|  |  | (blank) | (blank) | UA | Allow a user to preview an Invoice prior to printing.
Allow a user to print the Invoice.
Allow a user to save the Invoice as a PDF.
Apply a watermark (e.g., "NOT AN INVOICE ‐‐ DO NOT PAY") to an Invoice when it is not in Posted Mode.
|  | Invoice Lines | Combining and Allocating Third‐ Party Charge Items | (blank) | BR | Allow a user to allocate a Third Party Charge Line‐‐ partially or totally ‐‐ to a different Service Line.
Allow a user to combine two or more Third‐Party Charge items into one invoice line item.
Prevent the user from allocating Third‐Party Charge revenue to a different Service Line, if the Invoice is not in Open Mode.
When one or more Third‐Party Charge Items are combined, save the Invoice.
When one or more Third‐Party Charge Items are un‐combined, save the Invoice.
[5 empty] | UA | Prevent the user from combining Third‐Party Charge items if the Invoice is not in Open Mode.
|  |  | Combining Items Whose Units of Measure Span Shifts | (blank) | BR | Allow a user to combine two or more Invoice line items that refer to units of measure that span shifts.
Allow a user to undo a combined item for the units of measure that span shifts.
Prevent the user from combining Items with units of measure that span shifts, if the Invoice is not in Open Mode.
Prevent the user from un‐combining Items with units of measure that span shifts, if the Invoice is not in Open Mode.
[5 empty] | UA | Determine the Unit Cost for each Item, based upon the selected Contract Level, and whether it indicates Branch Standard Pricing (in which case Branch Standard Pricing is used), or Contract Specific Pricing or Fixed Fee (in which case the Contract Item's P
Prevent the user from combining Items with units of measure that span shifts, if the Item Codes of the source Item Codes are different.
|  |  | Contract Level | (blank) | BR | Upon creation of each new Invoice, allow a user to select the Contract Level, selecting from a list of Contract Levels for the Customer.
|  |  | Contract‐Defined Item Properties | (blank) | BR | Determine the Item Code and Description for each Item, based upon the selected Contract Level, and whether it indicates Contract Specific Pricing, and specifies an Item Code and/or Description override; otherwise, the Item Master's default Item Code and/o
Determine the Unit of Measure for each Item, based upon the selected Contract Level, and whether it indicates Branch Standard Pricing (in which case the Item Master's default Unit of Measure is used), or Contract Specific Pricing or Fixed Fee (in which ca
|  |  | Customer‐Defined Attributes | (blank) | BR | Display a list of the Customer‐Defined Attributes for the Invoice, and their values.
For each Open Invoice, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue.
[5 empty] | UA | For each Open Invoice, allow a user to enter the values for the Customer‐Defined Attributes.
|  |  | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | BR | Allow a user to specify a Contract‐Defined No‐Charge Quantity.
Prevent the user from specifying a Contract‐Defined No‐Charge Quantity that makes the total invoiceable Item Quantity less than zero.
Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is not in Open Mode.
Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is not under a Contract Level that indicates Contract‐Defined Pricing.
Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is under a Contract Level that indicates Contract‐Defined Pricing, but the Contract Item does not indicate a Contract‐Defined No‐Charge Quantity.
Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is a Third‐Party Charge Item.
Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is marked as Destroyed.
Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is Priced on Request.
When the Contract‐Defined No‐Charge Quantity is changed for an Item, save the Invoice.
[5 empty] | UA | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is a Credit Invoice.
|  |  |  | Default Quantity | BR | Allow a user to enter or change a description for a Third‐Party Charge Item.
Allow a user to specify a Default Quantity if at least one of the following is true: (a) A Contract‐Specified Unit of Measure is used, and the Unit of Measure in the Item Master is different than the Contract‐ Specified Unit of Measure. (b) The Contract r
Prevent the user from changing a description for a Third‐Party Charge, when the Invoice is not in Open Mode.
Prevent the user from specifying a Default Quantity that makes the total invoiceable Item Quantity less than zero.
Prevent the user from specifying a Default Quantity, when the Invoice is not in Open Mode.
When the selected Contract refers to a Contract‐Specified Maximum Daily Billable Labor Duration, prevent the user from specifying a Default Quantity that is greater than Contract‐ Specified Maximum Daily Billable Labor Duration.
[5 empty] | UA | Prevent the user from specifying a Default Quantity, when the Invoice is a Credit Invoice.
|  |  |  | Price per Unit | BR | Only allow for a user to enter or change a Price per Unit for an item if the item is one of the following: (a) An Item (or Package Item) on a Invoice with a Contract Level that indicates Branch Standard Pricing (b) A Third‐Party Charge Item (c) Priced on
Prevent the user from changing the Price per Unit of an Item, when the Invoice is not in Open Mode.
Prevent the user from specifying a Price per Unit that is less than zero.
When a Price per Unit is entered or changed for an Item or Package Item, save the Invoice.
[5 empty] | UA | Allow a user to enter or change the Price per Unit for an Item.
Prevent the user from changing the Price per Unit of an Item, when the Invoice is a Credit Invoice.
|  |  |  | User‐Specified Discount | BR | Allow a user to specify a User‐Specified Discount a Line Item price.
Prevent the user from specifying a User‐Specified Discount, when the Invoice is not in Open Mode.
Prevent the user from specifying a User‐Specified Discount, when the Item is on an Invoice that has a Contract Level that does not indicate Branch Standard Pricing.
When a User‐Specified Discount is applied to an Item, save the Invoice.@$
[5 empty] | UA | Prevent the user from specifying a User‐Specified Discount, when the Invoice is a Credit Invoice.
|  |  |  | User‐Specified No‐ Charge Quantity | BR | Allow a user to specify a User‐Specified No‐Charge Quantity.
Prevent the user from specifying a User‐Specified No‐Charge Quantity that makes the total invoiceable Item Quantity less than zero.
Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is a Third‐Party Charge Item.
Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is marked as Destroyed.
Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is Priced on Request.
Prevent the user from specifying a User‐Specified No‐Charge Quantity, without supplying the User‐Specified No Charge Reason.
When a User‐Specified Discount is applied to an Item, save the Invoice.
When a User‐Specified No‐Charge Quantity is entered, allow a user to enter the User‐Specified No Charge Reason, as one of the following: (a) By HydroChem's choice, (b) By Customer insistence, or (c) Because of a Gate Log Discrepancy
[5 empty] | UA | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Invoice is a Credit Invoice.
Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Invoice is not in Open Mode.
|  |  | Packages | Components | BR | List fulfilled and unfulfilled Package Component Items of a selected Package on the Invoice.
Prevent the user from adding a partial quantity of a Line Item to a Package, when the Package already contains a Component Item from a different Shift.
Prevent the user from removing a Component Item from a Package, when the Invoice is not in Open Mode.
[5 empty] | LIST | Allow a user to remove a selected Component Item from a Package.
[5 empty] | UA | Prevent the user from removing a Component Item from a Package, when the Invoice is a Credit Invoice.
|  |  |  | (blank) | BR | Allow a user to add a selected Line Item to a Package.
Allow a user to delete the Package.
Allow a user to select a Package.
Allow a user to specify the quantity of the Package.
Calculate the Package Variance Percentage as: (A) The price of the Package Item, divided by (B) the price of all the Package Component Items, according to the highest priority current Contract Pricing Level
Calculate the price of each Package Component Item as: (A) The item quantity, which is defined as: (A1) The Default Quantity minus (A2) the Contract‐Specified No‐Charge Quantity minus (A3) the User‐Entered No‐Charge Quantity; times (B) the Per Unit Price;
If the Invoice's Contract Level does not indicate Branch Standard Pricing, only allow the user to select one of the Packages specified in the Contract Level.
If the Invoice's Contract Level indicates Branch Standard Pricing, only allow the user to select one of the Packages covered by Branch Standard Pricing.
List Packages.
Prevent the user from adding a a Package to an Invoice, when the Invoice is not in Open Mode.
Prevent the user from adding a Line Item to a Package, when that Item is not defined as a Package Component.
Prevent the user from adding a Line Item to a Package, when the Package already contains a Component Item from a different Shift.
Prevent the user from adding a Line Item to a Package, when the required quantity of that Item has already been added to the Package.
Prevent the user from adding a partial quantity of a Line Item to a Package, when the Invoice is not in Open Mode.
Prevent the user from deleting a Package, when the Invoice is a Credit Invoice.
Prevent the user from deleting a Package, when the Invoice is not in Open Mode.
Prevent the user from modifying the quantity of a Package, when the Invoice is a Credit Invoice.
Prevent the user from setting the quantity of a Package component to a quantity greater than the Package Item's Maximum Quantity Allowed (if it exists).
Prevent the user from setting the quantity of a Package component to a quantity less than the Package Item's Minimum Quantity Allowed (if it exists).
Prevent the user from specifying the quantity of a Package, when the Invoice is not in Open Mode.
Provide a visual cue to the user if the Contract Level indicates Contract‐Specific Pricing ‐‐ one that contains one or more Packages ‐‐ and a Primary Equipment line item could be converted into one of those Packages.
When a Component Item is removed from a Package, save the Invoice.
When a Package quantity is entered or modified, save the Invoice.
When an Item or partial quantity of an Item is added to a Package, if the Invoice has a Custom View, recalculate and reallocate the Variance.
When an Item or partial quantity of an Item is added to a Package, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
When an Item or partial quantity of an Item is added to a Package, recalculate and reallocate the Variance.
When an Item or partial quantity of an Item is added to a Package, save the Invoice.
When the user adds a Package to an Invoice, save the Invoice.
When the user deletes a Package from an Invoice, save the Invoice
[5 empty] | LIST | Allow a user to add a partial quantity of a selected Line Item to a Package.
[5 empty] | UA | Allow a user to add a Package to an Invoice.
Prevent the user from adding a a Package to an Invoice, when the Invoice is a Credit Invoice.
Prevent the user from adding a Line Item to a Package, when the Invoice is a Credit Invoice.
Prevent the user from adding a Line Item to a Package, when the Invoice is not in Open Mode.
When an Invoice is opened or saved, recalculate and reallocate all Package Variances across each Package's Component Items.
When the user adds a Package to an Invoice, create a Package Variance Line within the Package.
|  |  | Payment Authorization | (blank) | BR | Allow a user to change the Payment Authorization for an Open Invoice, selecting from the list of Payment Authorization Methods that are available to the Customer (e.g., Purchase Order or Pending Purchase Order, Credit Card Authorization, and/or No Authori
For each new (Open) Invoice, automatically set the Payment Authorization to that of the Job containing the Staging Area items being added.
If a Payment Authorization Method of Purchase Order is selected, require that the user selects one and only one of the following: (a) an existing Purchase Order (one without Purchase Order Line detail), (b) an existing Purchase Order Line, or (c) a Pendin
Prevent the user from selecting a Payment Authorization Method of Purchase Order, when the Customer Site requires Purchase Order Lines.
Upon creation of each new Credit Invoice and Re‐Invoice, set the Contract Level to the Contract Level of the Source Invoice.
Warn the user if the amount remaining on the Purchase Order ‐‐ minus the amount of the Invoice ‐‐ is less than 15% of the original value of the Purchase Order.
Warn the user if the amount remaining on the Purchase Order ‐‐ minus the amount of the Invoice ‐‐ is less than zero.
When a user changes a Payment Authorization Method when invoicing one or more Jobs, update all future created Invoices for that Job to use the selected Payment Authorization Method.
[5 empty] | UA | Prevent the user from editing the Payment Authorization unless the Invoice is in Open or Submitted Mode.
Prevent the user from selecting a Payment Authorization Method that is not available to the Customer.
|  |  | Purchase Order/Line Variance | (blank) | BR | When an invoice is opened or saved, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
|  |  | Splitting Labor Time into Other Categories | (blank) | BR | Allow a user to recombine the split Labor Lines items back to their original single‐line entry.
Allow a user to split a Labor Line item into two or more Labor Line Items.
Prevent the user from recombining a split Labor Item, if the Invoice is not in Open Mode.
Prevent the user from splitting a Labor Item if the Labor Item is a component of a Package.
Prevent the user from splitting a Labor Item, if the Invoice is not in Open Mode.
When a Labor Line Item is split, save the Invoice.
When split Labor Line Items are recombined, save the Invoice.
[5 empty] | UA | Prevent the user from splitting a Labor Item into an additional Labor Item from a different Service Line.
|  |  | Taxation | (blank) | BR | Allow a user to "un‐flag" a taxable invoice as tax exempt.
Allow a user to flag a taxable invoice as tax exempt.
For each Open Invoice, determine whether the products and/or services are taxable (by Customer Site).
|  |  | User‐ Entered Invoice Discount | (blank) | BR | Prevent the user from specifying a User‐Entered Invoice Discount unless the Invoice is in Open Mode.
Prevent the user from specifying a User‐Entered Invoice Discount when the Contract of the Invoice indicates anything other than Branch Standard Pricing.
Prevent the user from specifying a User‐Entered Invoice Discount when the Invoice is a Credit Invoice.
[5 empty] | UA | Allow a user to specify a User‐Entered Invoice Discount.
Prevent the user from specifying a User‐Entered Invoice Discount of less than 0%, or more than 100%.
When a User‐Entered Invoice Discount is specified, changed, or removed, save the Invoice.
|  |  | (blank) | (blank) | BR | Allow a user to create a new Invoice
Allow a user to remove one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from the Invoice.
Allow a user to select one or more Invoice Lines.
Calculate the displayed Discount Percentage as: One minus (A) The Contract Discount, which is defined as: (A1) The Contract Line Item Discount, if one is specified for the Item Code; otherwise (A2) The Contract Discount; times one minus (B) the User‐Enter
Calculate the price of each Invoice Line as: (A) The Item Quantity, which is defined as: (A1) The Default Quantity minus (A2) the Contract‐Specified No‐Charge Quantity minus (A3) the User‐Entered No‐Charge Quantity; times (B) the Per Unit Price; times one
Calculate the Tax for each Item, based upon whether the Item is a Product or Service, whether the Customer Site prescribes a Product or Service Tax Rate, and whether the user has opted to make the Invoice non‐taxable.
Display the Invoice header
For each new (Open) Credit Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Source Invoice for which it is created).
For each new (Open) Re‐Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Credit Invoice for which it is created). Placing Letter at end plus number.
Prevent the user from editing the Invoice Header if the Invoice is a Credit Invoice.
Prevent the user from removing one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from a Re‐Invoice.
Prevent the user from removing partial quantity of a Package Item from an Invoice.
When a Package item is removed from a regular Invoice, the quantity of its Component Items are moved individually back to the Staging Area and marked as available for Invoicing.
When a quantity of a non‐Package item is removed from a regular Invoice, move the quantity back to the Staging Area, and mark the quantity as available for Invoicing.
When one or more Line Items are removed from an Invoice, if one or more of the Items are components of a Package, flag the Package components as unfulfilled.
When one or more Line Items are removed from an Invoice, save the Invoice.
[5 empty] | LIST | Prevent the user from removing one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from the Invoice, if the Invoice is not in Open Mode.
[5 empty] | UA | Allow a user to Edit the Invoice Header (i.e., Payment Authorization, Customer‐Defined Attributes, and Notes).
For each new (Open) Regular Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Branch location where it is created).
List Invoice Lines, including Item Code, Description, Quantity, Unit of Measure, Price per Unit, Amount, Discount Percentage, and Net Amount.
Prevent the user from editing the Invoice Header unless the Invoice is in Open Mode.
|  | Invoice Management and Workflow | Custom Exports | (blank) | BR | Allow a user to generate a Customer‐Specific Invoice Export.
Prevent the user from generating a Customer‐Specific Invoice Export if the Customer does not accept Customer‐Specific Invoice Exports.
Prevent the user from generating a Customer‐Specific Invoice Export, if the Invoice is not in Submitted Mode, and the Customer requires Customer‐Specific Invoice Exports from Submitted Mode.
[5 empty] | UA | Prevent the user from generating a Customer‐Specific Invoice Export, if the Invoice is not in Posted Mode, and the Customer requires Customer‐Specific Invoice Exports from Posted Mode.
|  |  | (blank) | (blank) | BR | Allow a user to change the selected invoice from Open to Submitted Mode.
Allow a user to change the selected Invoice from Submitted to Open Mode.
Allow a user to change the selected Invoice from Submitted to Posted Mode.
Calculate total invoice variance as the difference between all items' default price and the final dollar amount of the invoice.
Determine if an Invoice in Pending Approval Mode, with one or more Approvals, can be fully Approved. If so, move the Invoice to Approved Mode.
Display the Current Invoice Mode.
Mark all quantities of Items on a deleted Invoice as invoicable, and refresh the Staging Area to reflect the new Items and quantities.
Prevent a user from moving a Credit Invoice out of Open Mode without providing the required Credit Request data (i.e., Credit Reason, Description, and ‐‐ if the Credit Invoice will return the data to the Staging Area ‐‐ the expected Re‐Invoice amount.
Prevent an Invoice from going to Submitted or Posted Mode, if the invoice has been overridden to be non‐taxable. Instead move the Invoice to Pending Approval Mode.
Prevent the user from moving an Invoice directly to Posted Mode if the Customer Site requires the Submitted Invoice Mode (for electronic invoicing).
Prevent the user from moving an Invoice out of Open Mode, if a Labor Item on the Invoice refers to a Shift Summary Labor Line whose start/stop date/time overlaps with another Shift Summary Labor Line within the system.
Prevent the user from moving an Invoice out of Open Mode, if the Invoice is under Contract‐Specified Pricing, and contains one or more Items where the Unit of Measure in the Item Master is different from the Contract‐Specified Unit of Measure, for which n
Prevent the user from moving an Invoice to Submitted Mode if the Customer Site does not require the Submitted Invoice Mode (for electronic invoicing).
Prevent the user from moving the Invoice out of Open Mode if the Invoice contains a Package with component items that are all zero priced.
Prevent the user from moving the Invoice out of Open Mode if the Invoice has a Custom View, and the Custom View has no Custom View Line with a dollar value.
Prevent the user from moving the Invoice out of Open Mode if the Invoice has a Custom View, and the Reference Invoice has a zero dollar value.
Prevent the user from moving the Invoice out of Open Mode, if one or more Customer‐Defined Attributes' values have not been specified. Expected Regular esxpression rule need to validate.
Prevent the user from moving the Invoice out of Open Mode, if one or more Packages do not have quantities specified.
Prevent the user from moving the Invoice out of Open Mode, if one or more required components of a Package have not yet been fulfilled.
Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Contract Item with a variable item price (i.e., Priced on Request), with an unspecified price.
Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Third‐Party Charge Item with an unspecified description.
Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Third‐Party Charge Item with an unspecified price.
Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains an Item whose General Ledger code does not exist in the General Ledger table.
Prevent the user from moving the Invoice out of Open Mode, if the Invoice has a Custom View, and no Custom View Line Items with dollar amounts have been specified.
Prevent the user from moving the Invoice out of Open Mode, if the Payment Authorization is a Pending Purchase Order.
Prevent the user from moving the Invoice out of Open Mode, if the Purchase Order or Purchase Order Line amount is unspecified.
Prevent the user from moving the Invoice to Posted Mode, if doing so would exceed the amount remaining on the Purchase Order or Purchase Order Line for that Invoice.
Prevent the user from Posting an Invoice, if a Labor Item on the Invoice refers to a Shift Summary Labor Line whose start/stop date/time overlaps with another Shift Summary Labor Line within the system and both refer to the same employee ID.
When a Credit Invoice or Credit/Re‐Invoice is moved out of Open Mode, move the Invoice to Pending Approval Mode.
When an invoice is Posted, Determine the GL accounts for the revenue for each Item on the Invoice and calculate and allocate the dollar amount associated with
When an Invoice is Posted, log the Invoice Number as "Posted" with the date/time the Posting occurred and the person who posted it.
[5 empty] | UA | Allow a user to change an Invoice from Open to Posted Mode.
Allow a user to change the selected Invoice from Approved Mode to Open Mode.
Allow a user to change the selected Invoice from Approved Mode to Posted Mode.
Allow a user to change the selected Invoice from Approved Mode to Submitted Mode.
Allow a user to change the selected Invoice from Disapproved Mode to Open Mode.
Allow a user to change the selected Invoice from Pending Approval to Open Mode.
Allow a user to delete an Open Invoice.
Prevent an Invoice from going to Submitted or Posted Mode, total Invoice variance is greater than n% off the original value the Invoice, and the Invoice total amount is greater than Instead move the Invoice to Pending Approval Mode.
Prevent the user from moving the Invoice out of Open Mode, if doing so would exceed the amount remaining on the Purchase Order or Purchase Order Line for that Invoice.
Prevent the user from moving the Invoice to Posted Mode, if the Invoice contains one or more Packages without a specified Price per Unit.
When a Credit Invoice is Posted, if the Credit Invoice is marked as Lost Revenue, do not re‐add the quantities of the Credited Items back to the Staging Area. Instead, mark the quantities of the items as uninvoiceable.
When a Credit Invoice is Posted, if the Credit Invoice is not marked as Lost Revenue, re‐add the quantities of the Credited Items back to the Staging Area.
When an Invoice is deleted, log the Invoice Number as "No Longer Needed".
|  | Invoice Queue | (blank) | (blank) | BR | Allow a user to filter the Invoices in the Invoice Queue by Customer Site Keyword search (on Customer Site), Customer Number, Payment Authorization, Creation Date Range, Posted Data Range, Invoice Number, Branch Oracle Code, Invoice Mode (e.g., Open, Post
List all Invoices [Invoice Queue]
[5 empty] | UA | Allow a user to open an Invoice from the Invoice Queue.
Sort the Invoices in the Invoice Queue by Invoice Number (descending)
|  | Re‐Invoices | (blank) | (blank) | BR | If a user creates a Re‐Invoice from an Invoice with a Custom View, automatically create a Custom View Line Items for the Re‐Invoice, and set the Description of each to the Description of each Custom View Line Item of the source Invoice, and the Dollar Amo
When a Credit Invoice mode changes, if the Credit Invoice has a corresponding Re‐Invoice, automatically change the mode of its corresponding Re‐Invoice.
[5 empty] | UA | When a Re‐Invoice is authorized by the same Purchase Order or Purchase Order Line of the source Invoice, when recalculating the Remaining Value of the Purchase Order or Purchase Order Line, also calculate the value of Credit of the source Invoice.
When a Re‐Invoice mode changes, automatically change the mode of its corresponding Credit Invoice.
|  | Staging Area | Adding Staging Area Lines to Invoice | (blank) | BR | Allow a user to select one or multiple Shifts in the Staging Area.
Allow a user to select one or multiple Staging Area lines.
Automatically adjust Labor and Equipment time entries to their saved Gate Log Reconciliation values, if applicable.
If a user moves one or more selected Shifts or Jobs to an Invoice, and the Staging Area filter is set to show "Only Labor Items", only move the Labor items within the selected Shifts or Jobs to the Invoice.
Prevent the user from moving a Labor item to an Invoice if the Labor item refers to a Pending Employee.
Provide a visual cue to the user if a Labor Item in the Staging Area refers to a Pending Employee.
Warn the user when moving a Labor or Equipment item to an Invoice if the Customer Site requires Labor / Equipment Time Reconciliations that have not been completed.
When Items are moved from the Staging Area to an Invoice, reduce the invoicable quantities of the Items, and refresh the Staging Area to reflect the remaining Items and quantities.
[5 empty] | UA | Allow a user to move the selected Items in the Staging Area (or those within the selected Shifts or Jobs) to an Open invoice.
Allow a user to select one or multiple Jobs in the Staging Area.
Prevent a user from moving Staging Area Items to a Credit Invoice.
Prevent a user from moving Staging Area Items to a Re‐Invoice.
When an Item is added from the Staging Area, save the Invoice.
|  |  | Warnings and Adjustments | (blank) | BR | Automatically adjust Labor and Equipment time entries down to a contract‐specified maximum quantity, if one exists.
Automatically adjust Labor and Equipment time entries up to a contract‐specified minimum quantity, if one exists.
If a material item has a quantity that has been marked as destroyed, automatically split the item into Used Item and Destroyed Item staging area items, as needed.
|  |  | (blank) | (blank) | BR | Allow a user to view a Staging Area Item's Item Code, Quantity available for invoicing, and Unit of Measure.
List all the uninvoiced items for that Customer Site, by the Item Description.
Organize the Staging Area items by Job (chronologically, from oldest to most recent), by Shift within the Job (chronologically, from oldest to most recent), by Item Type within the Shift, and by Description within the Item Type.
[5 empty] | LIST | Allow a user to search for a Job by entering a Job Number, and navigate the user to that Job in the Staging Area.
[5 empty] | UA | Allow a user to filter the Staging Area by Payment Authorization, initializing the Payment Authorization to that of the Customer Site/Payment Authorization selected in the Inbox Queue, or of the current Payment Authorization of the Invoice selected in the
Allow a user to filter the Staging Area to show either: (a) All Items (b) Only Labor Items
| Payroll | Employee Payroll Periods | Listing | Special Payment Calculations | BR | Automatically calculate special payment cases (e.g., overtime, double‐time, etc.) for added, edited, and deleted records.
Display the calculated straight time, overtime, double‐time and total hours durations for the the Employee Payroll Week.
If an Employee with an Employee Type of "Part‐Time Professional" has one or more Employee Payroll Records for a day, and the total duration of all Employee Payroll records is greater than 0:00, automatically calculate that Employee's Duration at 8:00 hour
[5 empty] | UA | Alow a user to access an existing Employee Payroll Record.
|  |  |  | (blank) | BR | Aggregate the Employee Payroll Records by date, Pay Type, Home Branch, Entered Branch, Job (if applicable), and Shift (if applicable), summing the Duration.
Allow a user to add a new Employee Payroll Record.
Filter the Employee Payroll Records by selected Employee and selected Employee Payroll Week, for all Employee Payroll Records manually entered by the Branch, plus all Employee Payroll Records for an Employee of the Branch.
List the Employee Payroll Records within the Employee Payroll Week, displaying date, Pay Type, Job (if applicable), and Shift (if applicable), Entered‐By Branch, and Duration (in hours:minutes).
[5 empty] | LIST | Sort the Employee Payroll Records by date (ascending), then by Pay Type (ascending by Pay Type Code).
|  |  | Viewing/Editing | Duration | BR | Prevent the user from specifying the Duration of an Employee Payroll Record to any value that would make the sum of all Employee Payroll Records of the specified Pay Type on the specified Date for the Branch who created the Employee Payroll Record be less
|  |  |  | Pay Type | BR | Prevent the user from changing the Pay Type of a Manual Employee Payroll Record to an Automatic Pay Type.
Prevent the user from changing the Pay Type of an Automatic Employee Payroll Record.
Prevent the user from specifying a Pay Type that is an Automatic Employee Pay Type.
|  |  |  | Shift Summary Number | BR | Prevent the user from entering a Shift Summary Number for an Employee Payroll Record if the Pay Type is not "Manual Billable" type.
|  |  |  | (blank) | BR | Prevent a user from deleting a Manual Employee Payroll Record not created at the user's Branch.
Prevent a user from deleting an Automatic Employee Payroll Record.
Prevent a user from editing a Manual Employee Payroll Record not created at the user's Branch.
Prevent a user from editing an Automatic Employee Payroll Record.
Prevent a user from saving an Employee Payroll Record without a specified Date.
Prevent a user from saving an Employee Payroll Record without a specified Duration.
Prevent a user from saving an Employee Payroll Record without a specified Employee.
Prevent a user from saving an Employee Payroll Record without a specified Pay Type.
Prevent a user from saving an Employee Payroll Record without a specified Shift Summary, if the Pay Type is "Manual Billable".
When a Manual Employee Payroll Record is deleted, create a Manual Employee Payroll Records with a negative‐Duration of the existing Manual Employee Payroll Record.
When a Manual Employee Payroll Record is edited, automatically create a Manual Employee Payroll Records with a negative‐ Duration of the existing Manual Employee Payroll Record, and one with a positive‐Duration of the new Manual Employee Payroll Record.
When a Shift Summary Labor Line is recorded by the system as added, create one (or two, if the Shift Summary Labor Line spans midnight of Sunday night of the time zone of the Employee's Home Branch) Automatic Employee Payroll Records, including all time f
When a Shift Summary Labor Line is recorded by the system as deleted, create an Automatic Employee Payroll Record for every existing, current, related Automatic Employee Payroll Record, with a negative‐Duration of the existing Automatic Employee Payroll R
When a Shift Summary Labor Line is recorded by the system as edited, create two Automatic Employee Payroll Records for every existing, current, related Automatic Employee Payroll Record, one with a negative‐Duration of the existing Automatic Employee Payr
[5 empty] | UA | Allow a user to delete an existing Employee Payroll Record.
Allow a user to edit an existing Employee Payroll Record, including the Employee, the date worked, the Pay Type, the Duration in hours:minutes, and the Shift Summary Number.
|  | Employee Payroll Weeks | (blank) | (blank) | BR | Prepopulate the Employee Payroll Weeks to automatically appear within a Payroll Week, which is a combination of Employees with Automatic Employee Payroll Records for the Payroll Week (i.e., those Employees with billable hours for the current Branch), and
Sort the Employee Payroll Weeks by Last Name (ascending), then by First Name (ascending)
[5 empty] | LIST | List the Employee Payroll Weeks within a Payroll Week, including First Name, Last Name, Employee Number, Home Branch Code, Employee Type (i.e., Regular or Part‐Time Professional), Straight Time Hours, Overtime Hours, Double‐Time Hours, Input Branch and To
[5 empty] | UA | Allow a user to access an Employee Payroll Week.
|  | Employee Selection | (blank) | (blank) | BR | Filter the Employees by those who were Active (according to Oracle) on or after Monday of the previous week.
[5 empty] | LIST | List Employees, including First Name, Last Name, Employee Number, Employee Type (i.e., Regular or Part‐Time Professional).
[5 empty] | UA | Allow a user to filter Employees by Branch, default to the Home Branch.
Allow a user to select an Employee.
Allow a user to sort Employees by Employee ID (ascending), or by Last Name (ascending)/First Name (ascending), default by Last Name/First Name.@$
|  | Payroll Periods | (blank) | (blank) | UA | Allow a user to access the current Payroll Week.
|  | Payroll Weeks | (blank) | (blank) | UA | Allow a user to select a Payroll Week by specifying a date within the Payroll Week (Monday to Sunday).
|  | Posting | (blank) | (blank) | BR | Allow for an external system/process to flag each Employee Payroll Record as having been imported into Oracle as of a provided date.
Grand Total

## Tables
EI |  |  | 1 | 4 | 5 | 15 | 16 | 100 | TYPE | WTG. | COUNT | VALUE | General System Characterstics
|  |  | D | D | F | F | H | H |  |  |  |  | GSC | DI
0 | 1 | 4 | L |  | L |  | A |  | L | 3 | 5 | 15 | Data Communications | 3
2 | 2 | 5 | L |  | A |  | H |  | A | 4 | 38 | 152 | Distributed Functions | 3
3 | 100 | 6 | A |  | H |  | H |  | H | 6 | 54 | 324 | Performance | 3
[13 empty] | Heavily Used Configuration | 3
EO |  |  | 1 | 5 | 6 | 19 | 20 | 100 |  |  |  |  | Transaction Rate | 3
|  |  | D | D | F | F | H | H |  |  |  |  | Online Data Entry | 3
0 | 1 | 10 | L |  | L |  | A |  | L | 4 | 0 | 0 | End User Efficiency | 3
2 | 3 | 11 | L |  | A |  | H |  | A | 5 | 1 | 5 | Online Update | 3
4 | 100 | 12 | A |  | H |  | H |  | H | 7 | 1 | 7 | Complex Processing | 3
[13 empty] | Reusability | 3
EQ |  |  | 1 | 5 | 6 | 19 | 20 | 100 |  |  |  |  | Installation Ease | 3
|  |  | D | D | F | F | H | H |  |  |  |  | Operational Ease | 3
0 | 1 | 16 | L |  | L |  | A |  | L | 3 | 24 | 72 | Multiple Sites | 3
2 | 3 | 17 | L |  | A |  | H |  | A | 4 | 92 | 368 | Facilitate Change | 3
4 | 100 | 18 | A |  | H |  | H |  | H | 6 | 145 | 870 | Total DIs | 42
ILF |  |  | 1 | 19 | 20 | 50 | 51 | 100 |  |  |  |  | Value Adjustment Factor | 1.07
|  |  | D | D | F | F | H | H
0 | 1 | 22 | L |  | L |  | A |  | L | 7 | 22 | 154
2 | 5 | 23 | L |  | A |  | H |  | A | 10 | 1 | 10 | Total Function Point Count | 2131.44
6 | 100 | 24 | A |  | H |  | H |  | H | 15 | 1 | 15
EIF |  |  | 1 | 19 | 20 | 50 | 51 | 100
|  |  | D | D | F | F | H | H
0 | 1 | 28 | L |  | L |  | A |  | L | 5 | 0 | 0
2 | 5 | 29 | L |  | A |  | H |  | A | 7 | 0 | 0
6 | 100 | 30 | A |  | H |  | H |  | H | 10 | 0 | 0
[9 empty] | Total UFPC for All Modules |  |  | 1992
Note on S3: MM: Degree of Influence: rating between 0 (lowest) to 5 (highest)

## Input
Requirement/Scope | [6 empty] | Function Point Counting
[8 empty] | Transactional | [7 empty] | Static
Category | SubCategory | SubSubCategory | Sub-SubSubcategory | In Scope | Req Type | Items |  | Trans.Type | DET | FTR | COL | ROW | CELL | Weight | Calcs | File Name | File Type | DET | RET | COL | ROW | CELL | Trans Type | Weight | Cals
[6 empty] | PROTECTED ROW |  | EO | 5 | 1 | D | 10 | =Tables!D10 | L | EOL | [7 empty] | EI
Administration | Branch Contractors |  |  | Y | BR | Prevent the user from saving a Branch Contractor with an Employee Number that is already used by an Employee or by another Branch Contractor. |  | EQ | 3 | 2 | D | 17 | =Tables!D17 | L | EQL | A/C Transaction File | ILF |  |  | #N/A | 22 | #N/A | EO | L | ILFL
Administration | Branch Contractors |  |  | Y | BR | Prevent the user from saving a Branch Contractor without a First Name, Last Name, Employee Number, or specified Employment Service. |  | EQ | 5 | 1 | D | 16 | =Tables!D16 | L | EQL | Branch Contractor | ILF |  |  | #N/A | 22 | #N/A | EQ | L | ILFL
Administration | Branch Contractors |  |  | Y | BR | Sort the Branch Contractors by Last Name, First Name | [9 empty] | Contract Master | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Branch Contractors |  |  | Y | LIST | List Branch Contractors, including First Name, Last Name, Unique Employee Number, and Employment Service. |  | EO | 15 | 2 | F | 11 | =Tables!F11 | A | EOA | Custom Invoice | ILF |  |  | #N/A | 22 | #N/A | File Type | L | ILFL
Administration | Branch Contractors |  |  | Y | UA | Allow a user to access a Branch Contractor from the list. |  | EQ | 12 | 2 | F | 17 | =Tables!F17 | A | EQA | Customer Master | ILF |  |  | #N/A | 22 | #N/A | ILF | L | ILFL
Administration | Branch Contractors |  |  | Y | UA | Allow a user to create a new Branch Contractor. |  | EI | 8 | 3 | F | 6 | =Tables!F6 | H | EIH | Customer-Invoice Master | ILF |  |  | #N/A | 22 | #N/A | EIF | L | ILFL
Administration | Branch Contractors |  |  | Y | UA | Allow a user to edit a new Branch Contractor. |  | EI | 6 | 2 | F | 5 | =Tables!F5 | A | EIA | Discount Master | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Branch Contractors |  |  | Y | UA | Allow a user to Filter the Branch Contractors by All or Active Only. Default to Active Only. |  | EQ | 9 | 2 | F | 17 | =Tables!F17 | A | EQA | Employee Master | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Branch Contractors |  |  | Y | UA | Allow a user to terminate/un‐terminate a Branch Contractor. |  | EI | 12 | 1 | F | 4 | =Tables!F4 | L | EIL | GateLog | ILF |  |  | #N/A | 22 | #N/A |  | A | ILFA
Administration | Customer Gate Log Reconciliations |  |  | N | LIST | List Primary Equipment records for a Shift, displaying the Customer's Equipment Number, and Start/Stop date/time (according to the Shift Summary) sorted by Equipment Number. | [8 empty] | EQ
Administration | Customer Gate Log Reconciliations |  |  | N | UA | Allow a user to enter or change the Gate Log data for that Equipment for that shift. | [8 empty] | EQ
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Display summary duration values for each person (i.e., Badge Number). |  | EQ | 15 | 2 | F | 17 | =Tables!F17 | A | EQA | General Leader Master | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Filter the Gate Log Reconciliation records by the selected Customer Site, by all Shift Labor records that begin on the selected date. |  | EQ | 18 | 2 | F | 17 | =Tables!F17 | A | EQA | Inventory Trans File | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Prevent a user from editing a Gate Log record if the corresponding item exists on an Invoice (unless the Invoice has been credited and the item has not been reinvoiced). |  | EQ | 25 | 2 | H | 17 | =Tables!H17 | H | EQH | Invoice | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Sort the Gate Log Reconciliation records by Last Name (ascending), and First Name (ascending). |  | EQ | 27 | 3 | H | 17 | =Tables!H17 | H | EIH | Invoice Queue | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Warn the user, when reopening a Shift Summary with Gate Log Reconciliations, that the Gate Log Reconciliations will be deleted. |  | EQ | 25 | 2 | H | 17 | =Tables!H17 | H | EQH | Labour Invoice | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | When a user reopens a Shift Summary with Gate Log Reconciliations, delete the Gate Log Reconciliations associated with the Shift Summary. |  | EI | 28 | 3 | H | 6 | =Tables!H6 | H | EQH | Package | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Gate Log Reconciliations |  |  | Y | LIST | List Labor records for a selected day for a selected Customer Site, displaying the Badge Number, First Name, Last Name, Employee Number (if it exists)and Start/Stop date/time (according to the Shift Summary), total hours/minutes worked, the Employee's Hom |  | EQ | 29 | 3 | H | 17 | =Tables!H17 | H | EIH | Party Ledger Master | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Gate Log Reconciliations |  |  | Y | UA | Allow a user to accept the default calculated Labor time (per the Shift Summary), or enter the Gate Log Labor time (in minutes, hours), per line. |  | EQ | 32 | 3 | H | 17 | =Tables!H17 | H | EQH | Payment AuthMaster | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Gate Log Reconciliations |  |  | Y | UA | Allow a user to save the Gate Log data for a shift. |  | EI | 34 | 2 | H | 5 | =Tables!H5 | H | EQH | Payroll Details | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Purchase Orders | Customer‐ Defined Attributes |  | Y | BR | For each Purchase Order, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue. |  | EQ | 24 | 5 | H | 18 | =Tables!H18 | H | H | Payroll Transaction | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Purchase Orders |  |  | Y | BR | Warn the user when saving a Purchase Order with invalid Customer‐Defined Attribute values. |  | EQ | 24 | 3 | H | 17 | =Tables!H17 | H | EQH | Product Master | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Purchase Orders |  |  | Y | UA | For each Purchase Order, Allow a user to enter the values for the Customer‐Defined Attributes. | [8 empty] | EQ | PurchaseOrder | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Purchase Orders | Purchase Order Lines | Customer‐Defined Attributes | Y | BR | For each Purchase Order Line, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue. |  | EQ | 69 | 2 | H | 17 | =Tables!H17 | H | EQH | Staged-Invoice | ILF |  |  | #N/A | 22 | #N/A |  | H | ILFH
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from deleting a Purchase Order Line if it exists on an Invoice. |  | EQ | 20 | 1 | H | 16 | =Tables!H16 | A | EIA | Tax Master | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Purchase Orders |  |  | Y | BR | Warn the user when saving the Purchase Order Line with invalid Customer‐Defined Attribute values. |  | EQ | 22 | 2 | H | 17 | =Tables!H17 | H | H | Unit Master | ILF |  |  | #N/A | 22 | #N/A |  | L | ILFL
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to delete a Purchase Order Line. |  | EI | 60 | 1 | H | 4 | =Tables!H4 | A | EQA
Administration | Customer Purchase Orders |  |  | Y | UA | For each Purchase Order Line, allow a user to enter the values for the Customer‐Defined Attributes. | [8 empty] | EQ
Administration | Customer Purchase Orders |  |  | Y | BR | If the user changes the Dollar Amount of a Purchase Order Line, recalculate the remaining values on the Purchase Order Line. |  | EQ | 57 | 3 | H | 17 | =Tables!H17 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from creating a Purchase Order Line for a Purchase Order, if the Customer Site does not require Purchase Order Lines. |  | EQ | 25 | 4 | H | 18 | =Tables!H18 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from creating a Purchase Order Line for a Purchase Order, if the Purchase Order is closed. |  | EQ | 50 | 3 | H | 17 | =Tables!H17 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from deleting a Purchase Order Line if the Purchase Order is closed. |  | EQ | 23 | 3 | H | 17 | =Tables!H17 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from editing anything other than the Dollar Amount of a Purchase Order Line, if the Purchase Order Line has been used on a Posted Invoice. |  | EQ | 38 | 3 | H | 17 | =Tables!H17 | H | EIH
Administration | Customer Purchase Orders |  |  | Y | LIST | List Purchase Order Lines per Purchase Order. |  | EQ | 33 | 1 | H | 16 | =Tables!H16 | A | EIA
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to create a new Purchase Order Line for a Purchase Order. |  | EI | 66 | 2 | H | 5 | =Tables!H5 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to edit a Purchase Order Line for a Purchase Order. |  | EI | 24 | 1 | H | 4 | =Tables!H4 | A | EQA
Administration | Customer Purchase Orders |  |  | N | BR | Prevent the user from deactivating a Purchase Order if it exists on a Job Header or Invoice. | [8 empty] | EQ
Administration | Customer Purchase Orders |  |  | N | UA | Allow a user to deactivate a Purchase Order. | [8 empty] | EQ
Administration | Customer Purchase Orders |  |  | Y | BR | Calculate and display the difference between the original amount of the Purchase Order or Purchase Order Line, and the amount of the Invoices posted against it. |  | EQ | 29 | 3 | H | 17 | =Tables!H17 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | BR | Calculate and display the difference between the original amount of the Purchase Order or Purchase Order Line, and the amount of the unposted and posted Invoices against it. |  | EQ | 62 | 1 | H | 16 | =Tables!H16 | A | EQA
Administration | Customer Purchase Orders |  |  | Y | BR | Filter the Purchase Orders by Customer Filter the Purchase Orders by Customer Site. |  | EQ | 26 | 2 | H | 17 | =Tables!H17 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | BR | If the user changes the Dollar Amount of a Purchase Order, recalculate the remaining values on the Purchase Order. |  | EQ | 19 | 1 | F | 16 | =Tables!F16 | L | EQL
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from closing a Purchase Order if one of its Purchase Order Lines exists on an unposted Invoice. |  | EQ | 17 | 2 | F | 17 | =Tables!F17 | A | EQA
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from editing a closed Purchase Order, or a Purchase Order Line of a closed Purchase Order. |  | EQ | 72 | 1 | H | 16 | =Tables!H16 | A | EQA
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from editing anything other than the Dollar Amount of a Purchase Order, if the Purchase Order has been used on a Posted Invoice. |  | EQ | 25 | 1 | H | 16 | =Tables!H16 | A | EQA
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from saving a Purchase Order Line that already exists for the Customer Site. |  | EQ | 25 | 1 | H | 16 | =Tables!H16 | A | EQA
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from saving a Purchase Order with a Purchase Order Number that already exists for the Customer Site. |  | EQ | 29 | 2 | H | 17 | =Tables!H17 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | BR | Sort the Purchase Order Lines by Purchase Order Line Number (ascending). |  | EQ | 64 | 4 | H | 18 | =Tables!H18 | H | EIH
Administration | Customer Purchase Orders |  |  | Y | BR | Sort the Purchase Orders by Purchase Order Number (ascending). |  | EQ | 58 | 1 | H | 16 | =Tables!H16 | A | EIA
Administration | Customer Purchase Orders |  |  | Y | BR | Warn the user when saving the Purchase Order with a Purchase Order Number that does not pass the Purchase Order regular expression mask for the Customer Site, if one exists. |  | EQ | 32 | 2 | H | 17 | =Tables!H17 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | LIST | List Purchase Orders. |  | EQ | 29 | 4 | H | 18 | =Tables!H18 | H | EIH
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to close a Purchase Order. |  | EI | 25 | 2 | H | 5 | =Tables!H5 | H | EIH
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to create a Purchase Order |  | EI | 33 | 4 | H | 6 | =Tables!H6 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to filter the Purchase Orders (Open vs. Closed). Initialize the filter to display Open only. |  | EQ | 4 | 1 | D | 16 | =Tables!D16 | L | EQL
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to order a Purchase Order |  | EI | 45 | 1 | H | 4 | =Tables!H4 | A | EQA
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to reopen a Purchase Order. |  | EI | 35 | 2 | H | 5 | =Tables!H5 | H | EQH
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to select a Purchase Order |  | EQ | 54 | 3 | H | 17 | =Tables!H17 | H | EQH
Administration | Employees |  |  | Y | LIST | List Employees, including First Name, Last Name, Employee Number, Employee Type (i.e., Regular or Part‐Time Professional).@$ |  | EQ | 20 | 3 | H | 17 | =Tables!H17 | H | EQH
Administration | Employees |  |  | Y | UA | Allow a user to sort Employees by Employee ID (ascending), or by Last Name (ascending)/First Name (ascending), default by Last Name/First Name. |  | EQ | 73 | 2 | H | 17 | =Tables!H17 | H | EQH
Administration | Employees |  |  | Y | UA | Allow a user to filter Employees by Branch, default to the Home Branch.@# |  | EQ | 61 | 4 | H | 18 | =Tables!H18 | H | EQH
Administration | Employees |  |  | Y | UA | Allow a user to select an Employee.@$ |  | EQ | 68 | 1 | H | 16 | =Tables!H16 | A | EQA
Administration | Field Service Settings |  |  | Y | BR | Notify the user if a clock reset has been detected, and prevent the application from starting until the clock has been set. |  | EQ | 29 | 3 | H | 17 | =Tables!H17 | H | EQH
Administration | Month End Close |  |  | N | BR | Prevent a user from closing Month End prior to Month End. | [8 empty] | EQ
Administration | Month End Close |  |  | Y | BR | Provide real and estimated revenue values for all Shift Items within a month, for all items added in that month, and for all items whose real or estimated revenue has changed within the month; and for a place‐holder for a Corporate System to associate a m |  | EQ | 26 | 1 | H | 16 | =Tables!H16 | A | EQA
Administration | Pending Customers |  |  | N | UA | Allow a user to match a Pending Customer Site to an Oracle Customer. | [8 empty] | EQ
Administration | Pending Employees |  |  | Y | UA | Allow a user to match a Pending Employee to an Oracle Employee. |  | EQ | 27 | 2 | H | 17 | =Tables!H17 | H | EQH
Administration | Synchronization |  |  | Y | BR | Display a confirmation message at the end of a successful manual synchronization. |  | EQ | 49 | 3 | H | 17 | =Tables!H17 | H | EQH
Administration | Synchronization |  |  | Y | BR | Display the synchronization status. |  | EQ | 28 | 1 | H | 16 | =Tables!H16 | A | EQA
Administration | Synchronization |  |  | Y | BR | Warn the user to synchronize when the Remote System 2.0 is opened and closed in branch. |  | EQ | 59 | 2 | H | 17 | =Tables!H17 | H | EQH
Administration | Terms & Conditions Contract |  |  | Y | BR | Display Customer Terms & Conditions Contract Details (T&C Contract Number, Activation Date, Expiration Date) |  | EQ | 41 | 2 | H | 17 | =Tables!H17 | H | EQH
Administration | Terms & Conditions Contract |  |  | Y | BR | Warn the user when creating a new Job when the Terms & Conditions Contract has past its expiration date. |  | EQ | 62 | 1 | H | 16 | =Tables!H16 | A | EQA
Administration | Terms & Conditions Contract |  |  | Y | BR | Warn the user when creating a Shift for an existing Job when the Terms & Conditions Contract has past its expiration date. |  | EQ | 29 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Contract Selection |  |  | N | BR | Prevent a user from seeing Contract Pricing for a Contract, if the user's Branch is not authorized to view that Contract's Pricing. | [8 empty] | EQ
Invoicing | Contract Selection |  |  | N | LIST | List all Contracts for a Customer. | [8 empty] | EQ
Invoicing | Contract Selection |  |  | N | UA | Allow a user to select a Contract. | [8 empty] | #REF!
Invoicing | Contract Selection |  |  | N | UA | Allow a user to view Contract header details (e.g., Contract Number, expiration date, etc.) | [8 empty] | #REF!
Invoicing | Contract Selection |  |  | Y | BR | Filter the Contract / Contract Level / Contract Versions to only show records: (a) for the currently selected Customer Site (i.e., those where the Contract Level applies to no Customer Site or to the current Customer Site) (b) where the Active Date of the |  | EQ | 29 | 1 | H | 16 | =Tables!H16 | A | #REF!
Invoicing | Contract Selection |  |  | Y | BR | Sort the Contract / Contract Level / Contract Versions by Active Date of the Contract (descending), then by Contract Level Priority (ascending), then by Contract Version Active Date (descending). |  | EQ | 24 | 3 | H | 17 | =Tables!H17 | H | #REF!
Invoicing | Contract Selection |  |  | Y | LIST | List all Contracts, Contract Levels, and Contract Level Version for a Customer, displaying the Contract Number, the Contract Level Description, the Contract Version Activation Date, and the Contract Expiration Date. |  | EQ | 30 | 3 | H | 17 | =Tables!H17 | H | #REF!
Invoicing | Contract Selection |  |  | Y | UA | Allow a user to revise the filtered view, to show older Contracts / Contract Levels / Contract Versions by date range, between today and the specified date. |  | EQ | 43 | 2 | H | 17 | =Tables!H17 | H | #REF!
Invoicing | Contract Selection |  |  | Y | UA | Allow a user to select a Contract / Contract Level / Contract Version. |  | EQ | 22 | 2 | H | 17 | =Tables!H17 | H | #REF!
Invoicing | Credit Invoices |  |  | Y | BR | If a Credit Invoice is created from an Invoice with a Custom View, automatically create a Custom View Line Items for the Credit Invoice, and set the Description of each to the Description of each Custom View Line Item of the source Invoice, and the Dollar |  | EQ | 23 | 3 | H | 17 | =Tables!H17 | H | #REF!
Invoicing | Credit Invoices |  |  | Y | BR | Prevent the user from creating a Credit Invoice from an Invoice, or one or more of the Items on that Invoice, if the source Invoice is a Credit Invoice. |  | EQ | 57 | 1 | H | 16 | =Tables!H16 | A | #REF!
Invoicing | Credit Invoices |  |  | Y | BR | Prevent the user from creating a Credit Invoice from an Invoice, or one or more of the Items on that Invoice, if the source Invoice is not in Posted Mode. |  | EQ | 63 | 2 | H | 17 | =Tables!H17 | H | #REF!
Invoicing | Credit Invoices |  |  | Y | UA | Allow a user to create a Credit Invoice from an Invoice, including an indication of whether the Invoice Line Data: (a) will be returned to the Staging Area, (b) will be deleted, and marked as Lost Revenue, or (c) will be associated with a Re‐Invoice. |  | EI | 24 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Credit Invoices |  |  | Y | UA | Allow a user to create a Credit Request associated with the Credit Invoice or Credit/Re‐Invoice. |  | EI | 8 | 2 | F | 5 | =Tables!F5 | A | EIA
Invoicing | Custom Invoice Views | Line Items |  | Y | BR | Allow a user to add a Custom View Line Item. |  | EI | 64 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Custom Invoice Views |  |  | Y | BR | Allow a user to edit a Custom View Line Item. |  | EI | 8 | 1 | F | 4 | =Tables!F4 | L | EIL
Invoicing | Custom Invoice Views |  |  | Y | UA | Allow a user to delete a Custom View Line Item. |  | EI | 1 | 3 | D | 6 | =Tables!D6 | A | EIA
Invoicing | Custom Invoice Views |  |  | N | BR | Prevent the user from creating a Custom View for an Invoice, when the Invoice is not in Open Mode.
Invoicing | Custom Invoice Views |  |  | N | BR | When the user adds a Custom View Line Item to a Custom View for an Invoice, automatically recalculate the Invoice Total Amount, the underlying Invoice Variance, and the Re‐Invoice Difference.
Invoicing | Custom Invoice Views |  |  | N | BR | When the user deletes a Custom View Line Item from a Custom View for an Invoice, automatically recalculate the Invoice Total Amount, the underlying Invoice Variance, and the Re‐Invoice Difference.
Invoicing | Custom Invoice Views |  |  | N | BR | When the user deletes a Custom View of an Invoice, remove the Variance Line from the Invoice.
Invoicing | Custom Invoice Views |  |  | N | BR | When the user edits a Custom View Line Item on a Custom View for an Invoice, automatically recalculate the Invoice Total Amount, the underlying Invoice Variance, and the Re‐Invoice Difference.
Invoicing | Custom Invoice Views |  |  | Y | BR | Calculate the Custom View Variance Percentage as: (A) The sum of all Custom View Invoice Lines, divided by (B) the price of all items on the Reference Invoice, according to the highest priority current Contract Pricing Level with specified pricing (i.e., |  | EQ | 25 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, if the Invoice does not have a Custom View. |  | EQ | 31 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice. |  | EQ | 28 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode. |  | EQ | 29 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from deleting a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice. |  | EQ | 20 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from deleting a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode. |  | EQ | 21 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from editing a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice. |  | EQ | 15 | 1 | F | 16 | =Tables!F16 | L | EQL
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from editing a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode. |  | EQ | 22 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from creating a Custom View for an Invoice, when the Invoice already has a Custom View. |  | EQ | 38 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from creating a Custom View for an Invoice, when the Invoice is a Credit Invoice. |  | EQ | 6 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from deleting a Custom View for an Invoice, when the Invoice does not have a Custom View. |  | EQ | 34 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from deleting the Custom View, when the Invoice is a Credit Invoice with a Custom View. |  | EQ | 8 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from deleting the Custom View, when the Invoice is not in Open Mode. |  | EQ | 20 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from editing the Custom View text, when the Invoice is a Credit Invoice. |  | EQ | 57 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from editing the Invoice Total Amount of the Custom View, when the Invoice is a Credit Invoice. |  | EQ | 10 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Custom Invoice Views |  |  | Y | BR | When an Invoice with a Custom View is opened or saved, automatically recalculate the Reference Invoice Total Amount and the Custom View Total Amount, and recalculate and reallocate the Custom Variance across the Reference Invoice Items. |  | EQ | 23 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user adds a Custom View Line Item to a Custom View for an Invoice, save the Invoice. |  | EI | 69 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user creates a Custom View of an Invoice, calculate the Custom View Variance Percentage. |  | EQ | 23 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user creates a Custom View of an Invoice, save the Invoice. |  | EI | 53 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user deletes a Custom View Line Item from a Custom View for an Invoice, save the Invoice. |  | EI | 47 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user deletes a Custom View of an Invoice, save the Invoice. |  | EI | 71 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user edits a Custom View Line Item to a Custom View for an Invoice, save the Invoice. |  | EI | 24 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Custom Invoice Views |  |  | Y | UA | Allow a user to create a Custom View for an Invoice. |  | EI | 58 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Custom Invoice Views |  |  | Y | UA | Allow a user to delete the Custom View of an Invoice. |  | EI | 1 | 3 | D | 6 | =Tables!D6 | A | EIA
Invoicing | Inbox Queue |  |  | Y | BR | Allow a user to open an Invoice Staging Area for a Customer Site/Purchase Order in the Inbox Queue. |  | EQ | 58 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Inbox Queue |  |  | Y | LIST | Allow a user to filter the Jobs in the Inbox Queue by Keyword search (on Customer Site), Job Start Date (within a specified date range), or Customer Site Number. |  | EQ | 2 | 1 | D | 16 | =Tables!D16 | L | EQL
Invoicing | Inbox Queue |  |  | Y | UA | List all Jobs which have uninvoiced items [Inbox Queue]. Display each Customer Site by Payment Authorization. | 2 | EQ | 46 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Inbox Queue |  |  | Y | UA | Sort the Jobs in the Inbox Queue in ascending order by Customer Number, then by ascending chronological order according to the Job Start Date. |  | EQ | 30 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Formatting and Printing | Invoice Print Preferences |  | N | UA | Retain the last used Invoice Template selection for an Invoice.
Invoicing | Invoice Formatting and Printing |  |  | Y | BR | Allow a user to select the Invoice Template for an Invoice. |  | EQ | 25 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Formatting and Printing |  |  | Y | UA | Allow a user to preview an Invoice prior to printing. | 2 | EQ | 43 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Formatting and Printing |  |  | Y | UA | Allow a user to print the Invoice. |  | EQ | 44 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Formatting and Printing |  |  | Y | UA | Allow a user to save the Invoice as a PDF. |  | EO | 38 | 2 | H | 11 | =Tables!H11 | H | EOH
Invoicing | Invoice Formatting and Printing |  |  | Y | UA | Apply a watermark (e.g., "NOT AN INVOICE ‐‐ DO NOT PAY") to an Invoice when it is not in Posted Mode. |  | EQ | 28 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | N | BR | When a combined Third‐Party Charge Item is un‐combined, if the Invoice has a Custom View, reallocate the Variance.
Invoicing | Invoice Lines |  |  | N | BR | When a combined Third‐Party Charge Item is un‐combined, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | N | BR | When one or more Third‐Party Charge Items are combined, if the Invoice has a Custom View, recalculate the Variance.
Invoicing | Invoice Lines |  |  | N | UA | When one or more Third‐Party Charge Items are combined, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to allocate a Third Party Charge Line‐‐ partially or totally ‐‐ to a different Service Line. |  | EI | 73 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to combine two or more Third‐Party Charge items into one invoice line item. |  | EI | 75 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from allocating Third‐Party Charge revenue to a different Service Line, if the Invoice is not in Open Mode. |  | EQ | 31 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | When one or more Third‐Party Charge Items are combined, save the Invoice. |  | EI | 69 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | When one or more Third‐Party Charge Items are un‐combined, save the Invoice. |  | EI | 42 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from combining Third‐Party Charge items if the Invoice is not in Open Mode. |  | EQ | 11 | 1 | F | 16 | =Tables!F16 | L | EQL
Invoicing | Invoice Lines | Combining Items Whose Units of Measure Span Shifts |  | Y | BR | Allow a user to combine two or more Invoice line items that refer to units of measure that span shifts. |  | EI | 17 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to undo a combined item for the units of measure that span shifts. |  | EI | 20 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from combining Items with units of measure that span shifts, if the Invoice is not in Open Mode. |  | EQ | 12 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from un‐combining Items with units of measure that span shifts, if the Invoice is not in Open Mode. |  | EQ | 27 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | Determine the Unit Cost for each Item, based upon the selected Contract Level, and whether it indicates Branch Standard Pricing (in which case Branch Standard Pricing is used), or Contract Specific Pricing or Fixed Fee (in which case the Contract Item's P |  | EQ | 29 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from combining Items with units of measure that span shifts, if the Item Codes of the source Item Codes are different. |  | EQ | 30 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines | Contract Level |  | Y | BR | Upon creation of each new Invoice, allow a user to select the Contract Level, selecting from a list of Contract Levels for the Customer. | 2 | EQ | 36 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines | Contract‐Defined Item Properties |  | Y | BR | Determine the Item Code and Description for each Item, based upon the selected Contract Level, and whether it indicates Contract Specific Pricing, and specifies an Item Code and/or Description override; otherwise, the Item Master's default Item Code and/o | 2 | EQ | 44 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Determine the Unit of Measure for each Item, based upon the selected Contract Level, and whether it indicates Branch Standard Pricing (in which case the Item Master's default Unit of Measure is used), or Contract Specific Pricing or Fixed Fee (in which ca | 2 | EQ | 65 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines | Customer‐Defined Attributes |  | Y | BR | Display a list of the Customer‐Defined Attributes for the Invoice, and their values. |  | EQ | 32 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | For each Open Invoice, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue. |  | EQ | 7 | 1 | F | 16 | =Tables!F16 | L | EQL
Invoicing | Invoice Lines |  |  | Y | UA | For each Open Invoice, allow a user to enter the values for the Customer‐Defined Attributes. |  | EI | 23 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | N | BR | When the Contract‐Defined No‐Charge Quantity is changed for an Item, if the Invoice has a Custom View, recalculate the Invoice Variance.
Invoicing | Invoice Lines |  |  | N | BR | When the Contract‐Defined No‐Charge Quantity is changed for an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | N | BR | When the Contract‐Defined No‐Charge Quantity is changed for an Item, if the Item is a component of a Package, recalculate the Package Variance.
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify a Contract‐Defined No‐Charge Quantity. |  | EQ | 22 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity that makes the total invoiceable Item Quantity less than zero. |  | EQ | 14 | 1 | F | 16 | =Tables!F16 | L | EQL
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is not in Open Mode. |  | EQ | 51 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is not under a Contract Level that indicates Contract‐Defined Pricing. |  | EQ | 58 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is under a Contract Level that indicates Contract‐Defined Pricing, but the Contract Item does not indicate a Contract‐Defined No‐Charge Quantity. |  | EQ | 70 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is a Third‐Party Charge Item. |  | EQ | 45 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is marked as Destroyed. |  | EQ | 20 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is Priced on Request. |  | EQ | 70 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | When the Contract‐Defined No‐Charge Quantity is changed for an Item, save the Invoice. |  | EI | 13 | 2 | F | 5 | =Tables!F5 | A | EIA
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is a Credit Invoice. |  | EQ | 6 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  | Default Quantity | Y | BR | Allow a user to enter or change a description for a Third‐Party Charge Item. |  | EQ | 24 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify a Default Quantity if at least one of the following is true: (a) A Contract‐Specified Unit of Measure is used, and the Unit of Measure in the Item Master is different than the Contract‐ Specified Unit of Measure. (b) The Contract r | 2 | EQ | 28 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from changing a description for a Third‐Party Charge, when the Invoice is not in Open Mode. |  | EQ | 59 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Default Quantity that makes the total invoiceable Item Quantity less than zero. |  | EQ | 5 | 3 | D | 17 | =Tables!D17 | L | EQL
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Default Quantity, when the Invoice is not in Open Mode. |  | EQ | 27 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | When the selected Contract refers to a Contract‐Specified Maximum Daily Billable Labor Duration, prevent the user from specifying a Default Quantity that is greater than Contract‐ Specified Maximum Daily Billable Labor Duration. |  | EQ | 10 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a Default Quantity, when the Invoice is a Credit Invoice. |  | EQ | 13 | 4 | F | 18 | =Tables!F18 | H | EQH
Invoicing | Invoice Lines |  | Price per Unit | N | BR | When a Price per Unit is entered or changed for a Package Item, recalculate the Package Variance.
Invoicing | Invoice Lines |  |  | N | BR | When a Price per Unit is entered or changed for an Item, if the Invoice has a Custom View, recalculate the Invoice Variance.
Invoicing | Invoice Lines |  |  | N | BR | When a Price per Unit is entered or changed for an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | N | BR | When a Price per Unit is entered or changed for an Item, if the Item is a component of a Package, recalculate the Package Variance.
Invoicing | Invoice Lines |  |  | Y | BR | Only allow for a user to enter or change a Price per Unit for an item if the item is one of the following: (a) An Item (or Package Item) on a Invoice with a Contract Level that indicates Branch Standard Pricing (b) A Third‐Party Charge Item (c) Priced on | 2 | EQ | 45 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from changing the Price per Unit of an Item, when the Invoice is not in Open Mode. |  | EQ | 69 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Price per Unit that is less than zero. |  | EQ | 73 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | When a Price per Unit is entered or changed for an Item or Package Item, save the Invoice. |  | EI | 55 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | UA | Allow a user to enter or change the Price per Unit for an Item. |  | EI | 43 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from changing the Price per Unit of an Item, when the Invoice is a Credit Invoice. |  | EQ | 55 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  | User‐Specified Discount | N | BR | Prevent the user from specifying a User‐Specified Discount, when the Item is a Third‐Party Charge Item.
Invoicing | Invoice Lines |  |  | N | BR | Prevent the user from specifying a User‐Specified Discount, when the Item is marked as Destroyed.
Invoicing | Invoice Lines |  |  | N | BR | When a User‐Specified Discount is applied to an Item, if the Invoice has a Custom View, recalculate the Invoice Variance.
Invoicing | Invoice Lines |  |  | N | BR | When a User‐Specified Discount is applied to an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | N | BR | When a User‐Specified Discount is applied to an Item, if the Item is a component of a Package, recalculate the Package Variance.
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify a User‐Specified Discount a Line Item price. |  | EQ | 50 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified Discount, when the Invoice is not in Open Mode. |  | EQ | 40 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified Discount, when the Item is on an Invoice that has a Contract Level that does not indicate Branch Standard Pricing. |  | EQ | 34 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | When a User‐Specified Discount is applied to an Item, save the Invoice.@$ |  | EI | 38 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a User‐Specified Discount, when the Invoice is a Credit Invoice. |  | EQ | 35 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  | User‐Specified No‐ Charge Quantity | N | BR | When the User‐Specified No‐Charge Quantity is changed for an Item, if the Invoice has a Custom View, recalculate the Invoice Variance.
Invoicing | Invoice Lines |  |  | N | BR | When the User‐Specified No‐Charge Quantity is changed for an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | N | BR | When the User‐Specified No‐Charge Quantity is changed for an Item, if the Item is a component of a Package, recalculate the Package Variance.
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify a User‐Specified No‐Charge Quantity. |  | EQ | 32 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity that makes the total invoiceable Item Quantity less than zero. |  | EQ | 56 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is a Third‐Party Charge Item. |  | EQ | 15 | 4 | F | 18 | =Tables!F18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is marked as Destroyed. |  | EQ | 52 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is Priced on Request. |  | EQ | 30 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity, without supplying the User‐Specified No Charge Reason. |  | EQ | 62 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | When a User‐Specified Discount is applied to an Item, save the Invoice. |  | EI | 14 | 2 | F | 5 | =Tables!F5 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | When a User‐Specified No‐Charge Quantity is entered, allow a user to enter the User‐Specified No Charge Reason, as one of the following: (a) By HydroChem's choice, (b) By Customer insistence, or (c) Because of a Gate Log Discrepancy |  | EQ | 26 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Invoice is a Credit Invoice. |  | EQ | 11 | 1 | F | 16 | =Tables!F16 | L | EQL
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Invoice is not in Open Mode. |  | EQ | 3 | 1 | D | 16 | =Tables!D16 | L | EQL
Invoicing | Invoice Lines | Packages | Components | N | BR | When a Component Item is removed from a Package, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | Y | BR | List fulfilled and unfulfilled Package Component Items of a selected Package on the Invoice. |  | EQ | 32 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a partial quantity of a Line Item to a Package, when the Package already contains a Component Item from a different Shift. |  | EQ | 33 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from removing a Component Item from a Package, when the Invoice is not in Open Mode. |  | EQ | 70 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | LIST | Allow a user to remove a selected Component Item from a Package. |  | EI | 72 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from removing a Component Item from a Package, when the Invoice is a Credit Invoice. |  | EQ | 74 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | N | BR | Determine which Equipment Line Items are components of a Package, according to the Contract Level used on the Invoice.
Invoicing | Invoice Lines |  |  | N | BR | Prevent the user from adding a Variance Line Item to a Package.
Invoicing | Invoice Lines |  |  | N | BR | When a Component Item is removed from a Package, if the Invoice has a Custom View, recalculate and reallocate the Invoice Variance.
Invoicing | Invoice Lines |  |  | N | BR | When a Component Item is removed from a Package, recalculate and reallocate the Package Variance.
Invoicing | Invoice Lines |  |  | N | BR | When a Package quantity is entered or modified, if the Invoice has a Custom View, recalculate and reallocate the Variance.
Invoicing | Invoice Lines |  |  | N | BR | When a Package quantity is entered or modified, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | N | BR | When a Package quantity is entered or modified, recalculate and reallocate the Variance.
Invoicing | Invoice Lines |  |  | N | BR | When the user deletes a Package from an Invoice, remove the Package Variance Line with the Package.
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to add a selected Line Item to a Package. |  | EI | 62 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to delete the Package. |  | EI | 30 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to select a Package. |  | EI | 67 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify the quantity of the Package. |  | EI | 13 | 2 | F | 5 | =Tables!F5 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the Package Variance Percentage as: (A) The price of the Package Item, divided by (B) the price of all the Package Component Items, according to the highest priority current Contract Pricing Level |  | EQ | 68 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the price of each Package Component Item as: (A) The item quantity, which is defined as: (A1) The Default Quantity minus (A2) the Contract‐Specified No‐Charge Quantity minus (A3) the User‐Entered No‐Charge Quantity; times (B) the Per Unit Price; |  | EQ | 28 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | If the Invoice's Contract Level does not indicate Branch Standard Pricing, only allow the user to select one of the Packages specified in the Contract Level. |  | EQ | 62 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | If the Invoice's Contract Level indicates Branch Standard Pricing, only allow the user to select one of the Packages covered by Branch Standard Pricing. |  | EQ | 23 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | List Packages. |  | EQ | 11 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a a Package to an Invoice, when the Invoice is not in Open Mode. |  | EQ | 52 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a Line Item to a Package, when that Item is not defined as a Package Component. |  | EQ | 43 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a Line Item to a Package, when the Package already contains a Component Item from a different Shift. |  | EQ | 32 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a Line Item to a Package, when the required quantity of that Item has already been added to the Package. |  | EQ | 6 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a partial quantity of a Line Item to a Package, when the Invoice is not in Open Mode. |  | EQ | 7 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from deleting a Package, when the Invoice is a Credit Invoice. |  | EQ | 68 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from deleting a Package, when the Invoice is not in Open Mode. |  | EQ | 24 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from modifying the quantity of a Package, when the Invoice is a Credit Invoice. |  | EQ | 23 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from setting the quantity of a Package component to a quantity greater than the Package Item's Maximum Quantity Allowed (if it exists). |  | EQ | 15 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from setting the quantity of a Package component to a quantity less than the Package Item's Minimum Quantity Allowed (if it exists). |  | EQ | 33 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying the quantity of a Package, when the Invoice is not in Open Mode. |  | EQ | 5 | 2 | D | 17 | =Tables!D17 | L | EQL
Invoicing | Invoice Lines |  |  | Y | BR | Provide a visual cue to the user if the Contract Level indicates Contract‐Specific Pricing ‐‐ one that contains one or more Packages ‐‐ and a Primary Equipment line item could be converted into one of those Packages. |  | EQ | 18 | 1 | F | 16 | =Tables!F16 | L | EQL
Invoicing | Invoice Lines |  |  | Y | BR | When a Component Item is removed from a Package, save the Invoice. |  | EI | 71 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | When a Package quantity is entered or modified, save the Invoice. |  | EI | 34 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | When an Item or partial quantity of an Item is added to a Package, if the Invoice has a Custom View, recalculate and reallocate the Variance. |  | EQ | 29 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | When an Item or partial quantity of an Item is added to a Package, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | EQ | 52 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | When an Item or partial quantity of an Item is added to a Package, recalculate and reallocate the Variance. |  | EQ | 43 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | When an Item or partial quantity of an Item is added to a Package, save the Invoice. |  | EI | 40 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | When the user adds a Package to an Invoice, save the Invoice. |  | EI | 23 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | When the user deletes a Package from an Invoice, save the Invoice |  | EI | 10 | 1 | F | 4 | =Tables!F4 | L | EIL
Invoicing | Invoice Lines |  |  | Y | LIST | Allow a user to add a partial quantity of a selected Line Item to a Package. |  | EI | 43 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | UA | Allow a user to add a Package to an Invoice. |  | EI | 26 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from adding a a Package to an Invoice, when the Invoice is a Credit Invoice. |  | EQ | 44 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from adding a Line Item to a Package, when the Invoice is a Credit Invoice. |  | EQ | 30 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from adding a Line Item to a Package, when the Invoice is not in Open Mode. |  | EQ | 32 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | When an Invoice is opened or saved, recalculate and reallocate all Package Variances across each Package's Component Items. |  | EQ | 15 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | UA | When the user adds a Package to an Invoice, create a Package Variance Line within the Package. |  | EQ | 35 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | Allow a user to change the Payment Authorization for an Open Invoice, selecting from the list of Payment Authorization Methods that are available to the Customer (e.g., Purchase Order or Pending Purchase Order, Credit Card Authorization, and/or No Authori |  | EQ | 19 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | For each new (Open) Invoice, automatically set the Payment Authorization to that of the Job containing the Staging Area items being added. |  | EQ | 38 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | If a Payment Authorization Method of Purchase Order is selected, require that the user selects one and only one of the following: (a) an existing Purchase Order (one without Purchase Order Line detail), (b) an existing Purchase Order Line, or (c) a Pendin |  | EQ | 33 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from selecting a Payment Authorization Method of Purchase Order, when the Customer Site requires Purchase Order Lines. |  | EQ | 36 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Upon creation of each new Credit Invoice and Re‐Invoice, set the Contract Level to the Contract Level of the Source Invoice. |  | EQ | 47 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Warn the user if the amount remaining on the Purchase Order ‐‐ minus the amount of the Invoice ‐‐ is less than 15% of the original value of the Purchase Order. |  | EQ | 71 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Warn the user if the amount remaining on the Purchase Order ‐‐ minus the amount of the Invoice ‐‐ is less than zero. |  | EQ | 27 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | When a user changes a Payment Authorization Method when invoicing one or more Jobs, update all future created Invoices for that Job to use the selected Payment Authorization Method. |  | EI | 31 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from editing the Payment Authorization unless the Invoice is in Open or Submitted Mode. |  | EQ | 48 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from selecting a Payment Authorization Method that is not available to the Customer. |  | EQ | 6 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines | Purchase Order/Line Variance |  | Y | BR | When an invoice is opened or saved, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | EQ | 40 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | N | BR | When a Labor Line Item is split, if the Invoice has a Custom View, recalculate the Variance.
Invoicing | Invoice Lines |  |  | N | BR | When a Labor Line Item is split, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | N | BR | When split Labor Line Items are recombined, if the Invoice has a Custom View, recalculate the Variance.
Invoicing | Invoice Lines |  |  | N | UA | When split Labor Line Items are recombined, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to recombine the split Labor Lines items back to their original single‐line entry. |  | EI | 44 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to split a Labor Line item into two or more Labor Line Items. |  | EI | 74 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from recombining a split Labor Item, if the Invoice is not in Open Mode. |  | EQ | 59 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from splitting a Labor Item if the Labor Item is a component of a Package. |  | EQ | 67 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from splitting a Labor Item, if the Invoice is not in Open Mode. |  | EQ | 36 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | When a Labor Line Item is split, save the Invoice. |  | EI | 32 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | When split Labor Line Items are recombined, save the Invoice. |  | EI | 26 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from splitting a Labor Item into an additional Labor Item from a different Service Line. |  | EQ | 21 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines | Taxation |  | Y | BR | Allow a user to "un‐flag" a taxable invoice as tax exempt. |  | EI | 11 | 1 | F | 4 | =Tables!F4 | L | EIL
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to flag a taxable invoice as tax exempt. |  | EI | 29 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | For each Open Invoice, determine whether the products and/or services are taxable (by Customer Site). |  | EQ | 22 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines | User‐ Entered Invoice Discount |  | Y | BR | Prevent the user from specifying a User‐Entered Invoice Discount unless the Invoice is in Open Mode. |  | EQ | 23 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Entered Invoice Discount when the Contract of the Invoice indicates anything other than Branch Standard Pricing. |  | EQ | 70 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Entered Invoice Discount when the Invoice is a Credit Invoice. |  | EQ | 43 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | Allow a user to specify a User‐Entered Invoice Discount. |  | EI | 63 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a User‐Entered Invoice Discount of less than 0%, or more than 100%. |  | EQ | 40 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | When a User‐Entered Invoice Discount is specified, changed, or removed, save the Invoice. |  | EI | 23 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | N | BR | When one or more Line Items are removed from an Invoice, if the Invoice has a Custom View, reallocate the Variance.
Invoicing | Invoice Lines |  |  | N | BR | When one or more Line Items are removed from an Invoice, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value.
Invoicing | Invoice Lines |  |  | N | UA | Prevent the user from removing a Variance Line from the Invoice.
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to create a new Invoice |  | EI | 28 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to remove one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from the Invoice. |  | EI | 53 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to select one or more Invoice Lines. |  | EQ | 16 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the displayed Discount Percentage as: One minus (A) The Contract Discount, which is defined as: (A1) The Contract Line Item Discount, if one is specified for the Item Code; otherwise (A2) The Contract Discount; times one minus (B) the User‐Enter |  | EQ | 9 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the price of each Invoice Line as: (A) The Item Quantity, which is defined as: (A1) The Default Quantity minus (A2) the Contract‐Specified No‐Charge Quantity minus (A3) the User‐Entered No‐Charge Quantity; times (B) the Per Unit Price; times one |  | EQ | 2 | 4 | D | 18 | =Tables!D18 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the Tax for each Item, based upon whether the Item is a Product or Service, whether the Customer Site prescribes a Product or Service Tax Rate, and whether the user has opted to make the Invoice non‐taxable. |  | EQ | 51 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Display the Invoice header |  | EQ | 56 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | For each new (Open) Credit Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Source Invoice for which it is created). |  | EQ | 64 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | For each new (Open) Re‐Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Credit Invoice for which it is created). Placing Letter at end plus number. |  | EQ | 38 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from editing the Invoice Header if the Invoice is a Credit Invoice. |  | EQ | 66 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from removing one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from a Re‐Invoice. |  | EQ | 76 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from removing partial quantity of a Package Item from an Invoice. |  | EQ | 38 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | BR | When a Package item is removed from a regular Invoice, the quantity of its Component Items are moved individually back to the Staging Area and marked as available for Invoicing. |  | EI | 72 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | When a quantity of a non‐Package item is removed from a regular Invoice, move the quantity back to the Staging Area, and mark the quantity as available for Invoicing. |  | EI | 8 | 1 | F | 4 | =Tables!F4 | L | EIL
Invoicing | Invoice Lines |  |  | Y | BR | When one or more Line Items are removed from an Invoice, if one or more of the Items are components of a Package, flag the Package components as unfulfilled. |  | EI | 32 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Lines |  |  | Y | BR | When one or more Line Items are removed from an Invoice, save the Invoice. |  | EI | 32 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Lines |  |  | Y | LIST | Prevent the user from removing one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from the Invoice, if the Invoice is not in Open Mode. |  | EQ | 29 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Lines |  |  | Y | UA | Allow a user to Edit the Invoice Header (i.e., Payment Authorization, Customer‐Defined Attributes, and Notes). |  | EQ | 20 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | For each new (Open) Regular Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Branch location where it is created). |  | EQ | 58 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | List Invoice Lines, including Item Code, Description, Quantity, Unit of Measure, Price per Unit, Amount, Discount Percentage, and Net Amount. |  | EQ | 67 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from editing the Invoice Header unless the Invoice is in Open Mode. |  | EQ | 24 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow | Custom Exports |  | Y | BR | Allow a user to generate a Customer‐Specific Invoice Export. |  | EQ | 17 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from generating a Customer‐Specific Invoice Export if the Customer does not accept Customer‐Specific Invoice Exports. |  | EQ | 39 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from generating a Customer‐Specific Invoice Export, if the Invoice is not in Submitted Mode, and the Customer requires Customer‐Specific Invoice Exports from Submitted Mode. |  | EQ | 39 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Prevent the user from generating a Customer‐Specific Invoice Export, if the Invoice is not in Posted Mode, and the Customer requires Customer‐Specific Invoice Exports from Posted Mode. |  | EQ | 74 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | N | BR | Allow a user to mark a Re‐Invoice as Disapproved. Move the Invoice to Disapproved Mode.
Invoicing | Invoice Management and Workflow |  |  | N | BR | Allow a user to mark an Approved Credit Invoice as Lost Revenue.
Invoicing | Invoice Management and Workflow |  |  | N | BR | Allow a user to mark an Invoice variance as Approved.
Invoicing | Invoice Management and Workflow |  |  | N | BR | Prevent a user from marking a Re‐Invoice as Approved without providing the required Credit Request data.
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark a Credit Invoice as Approved.
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark a Credit Invoice as Disapproved. Move the Invoice to Disapproved Mode.
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark a Re‐Invoice as Approved.
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark an Invoice as with a Taxability Override as Approved.
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark an Invoice variance as Disapproved. Move the Invoice to Disapproved Mode.
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark an Invoice with a Taxability override as Disapproved. Move the Invoice to Disapproved Mode.
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Allow a user to change the selected invoice from Open to Submitted Mode. |  | EI | 61 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Allow a user to change the selected Invoice from Submitted to Open Mode. |  | EI | 67 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Allow a user to change the selected Invoice from Submitted to Posted Mode. |  | EI | 3 | 3 | D | 6 | =Tables!D6 | A | EIA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Calculate total invoice variance as the difference between all items' default price and the final dollar amount of the invoice. |  | EQ | 32 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Determine if an Invoice in Pending Approval Mode, with one or more Approvals, can be fully Approved. If so, move the Invoice to Approved Mode. |  | EI | 39 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Display the Current Invoice Mode. |  | EQ | 31 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Mark all quantities of Items on a deleted Invoice as invoicable, and refresh the Staging Area to reflect the new Items and quantities. |  | EI | 73 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent a user from moving a Credit Invoice out of Open Mode without providing the required Credit Request data (i.e., Credit Reason, Description, and ‐‐ if the Credit Invoice will return the data to the Staging Area ‐‐ the expected Re‐Invoice amount. |  | EQ | 44 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent an Invoice from going to Submitted or Posted Mode, if the invoice has been overridden to be non‐taxable. Instead move the Invoice to Pending Approval Mode. |  | EQ | 62 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving an Invoice directly to Posted Mode if the Customer Site requires the Submitted Invoice Mode (for electronic invoicing). |  | EQ | 43 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving an Invoice out of Open Mode, if a Labor Item on the Invoice refers to a Shift Summary Labor Line whose start/stop date/time overlaps with another Shift Summary Labor Line within the system. |  | EQ | 67 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving an Invoice out of Open Mode, if the Invoice is under Contract‐Specified Pricing, and contains one or more Items where the Unit of Measure in the Item Master is different from the Contract‐Specified Unit of Measure, for which n |  | EQ | 29 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving an Invoice to Submitted Mode if the Customer Site does not require the Submitted Invoice Mode (for electronic invoicing). |  | EQ | 68 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode if the Invoice contains a Package with component items that are all zero priced. |  | EQ | 1 | 1 | D | 16 | =Tables!D16 | L | EQL
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode if the Invoice has a Custom View, and the Custom View has no Custom View Line with a dollar value. |  | EQ | 2 | 2 | D | 17 | =Tables!D17 | L | EQL
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode if the Invoice has a Custom View, and the Reference Invoice has a zero dollar value. |  | EQ | 52 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if one or more Customer‐Defined Attributes' values have not been specified. Expected Regular esxpression rule need to validate. |  | EQ | 23 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if one or more Packages do not have quantities specified. |  | EQ | 56 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if one or more required components of a Package have not yet been fulfilled. |  | EQ | 73 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Contract Item with a variable item price (i.e., Priced on Request), with an unspecified price. |  | EQ | 69 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Third‐Party Charge Item with an unspecified description. |  | EQ | 53 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Third‐Party Charge Item with an unspecified price. |  | EQ | 50 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains an Item whose General Ledger code does not exist in the General Ledger table. |  | EQ | 53 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice has a Custom View, and no Custom View Line Items with dollar amounts have been specified. |  | EQ | 15 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Payment Authorization is a Pending Purchase Order. |  | EQ | 21 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Purchase Order or Purchase Order Line amount is unspecified. |  | EQ | 14 | 2 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice to Posted Mode, if doing so would exceed the amount remaining on the Purchase Order or Purchase Order Line for that Invoice. |  | EQ | 24 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from Posting an Invoice, if a Labor Item on the Invoice refers to a Shift Summary Labor Line whose start/stop date/time overlaps with another Shift Summary Labor Line within the system and both refer to the same employee ID. |  | EQ | 4 | 2 | D | 17 | =Tables!D17 | L | EQL
Invoicing | Invoice Management and Workflow |  |  | Y | BR | When a Credit Invoice or Credit/Re‐Invoice is moved out of Open Mode, move the Invoice to Pending Approval Mode. |  | EI | 59 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | When an invoice is Posted, Determine the GL accounts for the revenue for each Item on the Invoice and calculate and allocate the dollar amount associated with |  | EI | 19 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | BR | When an Invoice is Posted, log the Invoice Number as "Posted" with the date/time the Posting occurred and the person who posted it. |  | EI | 61 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change an Invoice from Open to Posted Mode. |  | EI | 7 | 2 | F | 5 | =Tables!F5 | A | EIA
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Approved Mode to Open Mode. |  | EI | 20 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Approved Mode to Posted Mode. |  | EI | 32 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Approved Mode to Submitted Mode. |  | EI | 70 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Disapproved Mode to Open Mode. |  | EI | 13 | 2 | F | 5 | =Tables!F5 | A | EIA
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Pending Approval to Open Mode. |  | EI | 48 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to delete an Open Invoice. |  | EI | 55 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Prevent an Invoice from going to Submitted or Posted Mode, total Invoice variance is greater than n% off the original value the Invoice, and the Invoice total amount is greater than Instead move the Invoice to Pending Approval Mode. |  | EQ | 38 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Prevent the user from moving the Invoice out of Open Mode, if doing so would exceed the amount remaining on the Purchase Order or Purchase Order Line for that Invoice. |  | EQ | 11 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Prevent the user from moving the Invoice to Posted Mode, if the Invoice contains one or more Packages without a specified Price per Unit. |  | EQ | 33 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Invoice Management and Workflow |  |  | Y | UA | When a Credit Invoice is Posted, if the Credit Invoice is marked as Lost Revenue, do not re‐add the quantities of the Credited Items back to the Staging Area. Instead, mark the quantities of the items as uninvoiceable. |  | EI | 40 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Management and Workflow |  |  | Y | UA | When a Credit Invoice is Posted, if the Credit Invoice is not marked as Lost Revenue, re‐add the quantities of the Credited Items back to the Staging Area. |  | EI | 71 | 1 | H | 4 | =Tables!H4 | A | EIA
Invoicing | Invoice Management and Workflow |  |  | Y | UA | When an Invoice is deleted, log the Invoice Number as "No Longer Needed". |  | EI | 53 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Queue |  |  | N | LIST | Allow a user to filter the Invoices in the Invoice Queue by Status (e.g., Open, Pending Approval, Approved, Disapproved, Submitted, Posted).
Invoicing | Invoice Queue |  |  | N | UA | Allow a user to filter the Invoices in the Invoice Queue by Date.
Invoicing | Invoice Queue |  |  | N | UA | Allow a user to filter the Invoices in the Invoice Queue by Type (e.g., Invoice, Prepayment Invoice, Credit Invoice, Credit Reinvoice)
Invoicing | Invoice Queue |  |  | Y | BR | Allow a user to filter the Invoices in the Invoice Queue by Customer Site Keyword search (on Customer Site), Customer Number, Payment Authorization, Creation Date Range, Posted Data Range, Invoice Number, Branch Oracle Code, Invoice Mode (e.g., Open, Post |  | EQ | 32 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Queue |  |  | Y | BR | List all Invoices [Invoice Queue] |  | EQ | 43 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Invoice Queue |  |  | Y | UA | Allow a user to open an Invoice from the Invoice Queue. |  | EI | 49 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Invoice Queue |  |  | Y | UA | Sort the Invoices in the Invoice Queue by Invoice Number (descending) |  | EQ | 3 | 2 | D | 17 | =Tables!D17 | L | EQL
Invoicing | Re‐Invoices |  |  | N | BR | Allow a user to create a Re‐Invoice from from a Credit Invoice.
Invoicing | Re‐Invoices |  |  | Y | BR | If a user creates a Re‐Invoice from an Invoice with a Custom View, automatically create a Custom View Line Items for the Re‐Invoice, and set the Description of each to the Description of each Custom View Line Item of the source Invoice, and the Dollar Amo |  | EQ | 42 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Re‐Invoices |  |  | Y | BR | When a Credit Invoice mode changes, if the Credit Invoice has a corresponding Re‐Invoice, automatically change the mode of its corresponding Re‐Invoice. |  | EI | 27 | 2 | H | 5 | =Tables!H5 | H | EIH
Invoicing | Re‐Invoices |  |  | Y | UA | When a Re‐Invoice is authorized by the same Purchase Order or Purchase Order Line of the source Invoice, when recalculating the Remaining Value of the Purchase Order or Purchase Order Line, also calculate the value of Credit of the source Invoice. |  | EQ | 69 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Re‐Invoices |  |  | Y | UA | When a Re‐Invoice mode changes, automatically change the mode of its corresponding Credit Invoice. |  | EQ | 32 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | N | BR | Allow a user to create a new Invoice from the selected Staging Area Line(s).
Invoicing | Staging Area |  |  | N | UA | If the Invoice has a Custom View, recalculate the Variance when an Item is added from the Staging Area.
Invoicing | Staging Area |  |  | N | UA | If the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value when an Item is added from the Staging
Invoicing | Staging Area |  |  | Y | BR | Allow a user to select one or multiple Shifts in the Staging Area. |  | EQ | 9 | 1 | F | 16 | =Tables!F16 | L | EQL
Invoicing | Staging Area |  |  | Y | BR | Allow a user to select one or multiple Staging Area lines. |  | EQ | 36 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Staging Area |  |  | Y | BR | Automatically adjust Labor and Equipment time entries to their saved Gate Log Reconciliation values, if applicable. |  | EQ | 33 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Staging Area |  |  | Y | BR | If a user moves one or more selected Shifts or Jobs to an Invoice, and the Staging Area filter is set to show "Only Labor Items", only move the Labor items within the selected Shifts or Jobs to the Invoice. |  | EQ | 46 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Staging Area |  |  | Y | BR | Prevent the user from moving a Labor item to an Invoice if the Labor item refers to a Pending Employee. |  | EQ | 22 | 3 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Staging Area |  |  | Y | BR | Provide a visual cue to the user if a Labor Item in the Staging Area refers to a Pending Employee. |  | EQ | 15 | 3 | F | 17 | =Tables!F17 | A | EQA
Invoicing | Staging Area |  |  | Y | BR | Warn the user when moving a Labor or Equipment item to an Invoice if the Customer Site requires Labor / Equipment Time Reconciliations that have not been completed. |  | EQ | 51 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Staging Area |  |  | Y | BR | When Items are moved from the Staging Area to an Invoice, reduce the invoicable quantities of the Items, and refresh the Staging Area to reflect the remaining Items and quantities. |  | EI | 22 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Staging Area |  |  | Y | UA | Allow a user to move the selected Items in the Staging Area (or those within the selected Shifts or Jobs) to an Open invoice. |  | EI | 30 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Staging Area |  |  | Y | UA | Allow a user to select one or multiple Jobs in the Staging Area. |  | EQ | 67 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Staging Area |  |  | Y | UA | Prevent a user from moving Staging Area Items to a Credit Invoice. |  | EQ | 52 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Staging Area |  |  | Y | UA | Prevent a user from moving Staging Area Items to a Re‐Invoice. |  | EQ | 71 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Staging Area |  |  | Y | UA | When an Item is added from the Staging Area, save the Invoice. |  | EI | 22 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Staging Area | Warnings and Adjustments |  | N | BR | Warn the user if the Staging Area contains two or more Labor or Equipment time entries that overlap.
Invoicing | Staging Area |  |  | Y | BR | Automatically adjust Labor and Equipment time entries down to a contract‐specified maximum quantity, if one exists. |  | EI | 20 | 3 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Staging Area |  |  | Y | BR | Automatically adjust Labor and Equipment time entries up to a contract‐specified minimum quantity, if one exists. |  | EI | 14 | 3 | F | 6 | =Tables!F6 | H | EIH
Invoicing | Staging Area |  |  | Y | BR | If a material item has a quantity that has been marked as destroyed, automatically split the item into Used Item and Destroyed Item staging area items, as needed. |  | EI | 22 | 4 | H | 6 | =Tables!H6 | H | EIH
Invoicing | Staging Area |  |  | Y | BR | Allow a user to view a Staging Area Item's Item Code, Quantity available for invoicing, and Unit of Measure. |  | EQ | 5 | 3 | D | 17 | =Tables!D17 | L | EQL
Invoicing | Staging Area |  |  | Y | BR | List all the uninvoiced items for that Customer Site, by the Item Description. |  | EQ | 22 | 2 | H | 17 | =Tables!H17 | H | EQH
Invoicing | Staging Area |  |  | Y | BR | Organize the Staging Area items by Job (chronologically, from oldest to most recent), by Shift within the Job (chronologically, from oldest to most recent), by Item Type within the Shift, and by Description within the Item Type. |  | EQ | 68 | 1 | H | 16 | =Tables!H16 | A | EQA
Invoicing | Staging Area |  |  | Y | LIST | Allow a user to search for a Job by entering a Job Number, and navigate the user to that Job in the Staging Area. |  | EQ | 5 | 3 | D | 17 | =Tables!D17 | L | EQL
Invoicing | Staging Area |  |  | Y | UA | Allow a user to filter the Staging Area by Payment Authorization, initializing the Payment Authorization to that of the Customer Site/Payment Authorization selected in the Inbox Queue, or of the current Payment Authorization of the Invoice selected in the |  | EQ | 44 | 4 | H | 18 | =Tables!H18 | H | EQH
Invoicing | Staging Area |  |  | Y | UA | Allow a user to filter the Staging Area to show either: (a) All Items (b) Only Labor Items |  | EQ | 68 | 1 | H | 16 | =Tables!H16 | A | EQA
Payroll | Employee Payroll Lines |  |  | N | BR | Allow a user to delete an Employee Payroll Line.
Payroll | Employee Payroll Lines |  |  | N | BR | Calculate special payment cases (e.g., overtime, double‐time, holiday time, etc.).
Payroll | Employee Payroll Lines |  |  | N | BR | List Employee Payroll Lines
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from changing a billable category to a non‐billable category.
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from creating a new Employee Payroll Line for a billable category.
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from deleting an Employee Payroll Line for billable time.
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from deleting an Employee Payroll Line in a closed Payroll Period.
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from editing an Employee Payroll Line in a closed Payroll Period.
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from increasing the payable time for a billable Payroll record above the calculated value.
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from specifying a date beyond the end of the Payroll Period.
Payroll | Employee Payroll Lines |  |  | N | LIST | Allow a user to create a new Employee Payroll Line.
Payroll | Employee Payroll Lines |  |  | N | UA | Allow a user to edit an Employee Payroll Line.
Payroll | Employee Payroll Lines |  |  | N | UA | Prevent a user from changing a non‐billable category to a billable category.
Payroll | Employee Payroll Lines |  |  | N | UA | Sort Employee Payroll Lines
Payroll | Employee Payroll Periods | Listing | Special Payment Calculations | Y | BR | Automatically calculate special payment cases (e.g., overtime, double‐time, etc.) for added, edited, and deleted records. |  | EQ | 69 | 3 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Payroll Periods |  |  | Y | BR | Display the calculated straight time, overtime, double‐time and total hours durations for the the Employee Payroll Week. |  | EQ | 64 | 2 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Payroll Periods |  |  | Y | BR | If an Employee with an Employee Type of "Part‐Time Professional" has one or more Employee Payroll Records for a day, and the total duration of all Employee Payroll records is greater than 0:00, automatically calculate that Employee's Duration at 8:00 hour |  | EQ | 25 | 3 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Payroll Periods |  |  | Y | UA | Alow a user to access an existing Employee Payroll Record. |  | EQ | 17 | 3 | F | 17 | =Tables!F17 | A | EQA
Payroll | Employee Payroll Periods |  |  | Y | BR | Aggregate the Employee Payroll Records by date, Pay Type, Home Branch, Entered Branch, Job (if applicable), and Shift (if applicable), summing the Duration. |  | EQ | 34 | 1 | H | 16 | =Tables!H16 | A | EQA
Payroll | Employee Payroll Periods |  |  | Y | BR | Allow a user to add a new Employee Payroll Record. |  | EI | 32 | 4 | H | 6 | =Tables!H6 | H | EIH
Payroll | Employee Payroll Periods |  |  | Y | BR | Filter the Employee Payroll Records by selected Employee and selected Employee Payroll Week, for all Employee Payroll Records manually entered by the Branch, plus all Employee Payroll Records for an Employee of the Branch. |  | EQ | 63 | 4 | H | 18 | =Tables!H18 | H | EQH
Payroll | Employee Payroll Periods |  |  | Y | BR | List the Employee Payroll Records within the Employee Payroll Week, displaying date, Pay Type, Job (if applicable), and Shift (if applicable), Entered‐By Branch, and Duration (in hours:minutes). |  | EQ | 62 | 2 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Payroll Periods |  |  | Y | LIST | Sort the Employee Payroll Records by date (ascending), then by Pay Type (ascending by Pay Type Code). |  | EQ | 33 | 2 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Payroll Periods | Viewing/Editing | Duration | N | BR | Prevent the user from specifying the Duration of an Automatic Employee Payroll Record to less than zero, or more than the value recorded on the Shift Summary.
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent the user from specifying the Duration of an Employee Payroll Record to any value that would make the sum of all Employee Payroll Records of the specified Pay Type on the specified Date for the Branch who created the Employee Payroll Record be less |  | EQ | 43 | 1 | H | 16 | =Tables!H16 | A | EQA
Payroll | Employee Payroll Periods |  | Pay Type | Y | BR | Prevent the user from changing the Pay Type of a Manual Employee Payroll Record to an Automatic Pay Type. |  | EQ | 51 | 2 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent the user from changing the Pay Type of an Automatic Employee Payroll Record. |  | EQ | 76 | 1 | H | 16 | =Tables!H16 | A | EQA
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent the user from specifying a Pay Type that is an Automatic Employee Pay Type. |  | EQ | 6 | 3 | F | 17 | =Tables!F17 | A | EQA
Payroll | Employee Payroll Periods |  | Shift Summary Number | Y | BR | Prevent the user from entering a Shift Summary Number for an Employee Payroll Record if the Pay Type is not "Manual Billable" type. |  | EQ | 69 | 3 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from deleting a Manual Employee Payroll Record not created at the user's Branch. |  | EQ | 69 | 1 | H | 16 | =Tables!H16 | A | EQA
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from deleting an Automatic Employee Payroll Record. |  | EQ | 4 | 2 | D | 17 | =Tables!D17 | L | EQL
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from editing a Manual Employee Payroll Record not created at the user's Branch. |  | EQ | 10 | 2 | F | 17 | =Tables!F17 | A | EQA
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from editing an Automatic Employee Payroll Record. |  | EQ | 6 | 1 | F | 16 | =Tables!F16 | L | EQL
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Date.
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Duration.
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Employee.
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Pay Type.
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Shift Summary, if the Pay Type is "Manual Billable".
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Manual Employee Payroll Record is deleted, create a Manual Employee Payroll Records with a negative‐Duration of the existing Manual Employee Payroll Record. |  | EI | 22 | 4 | H | 6 | =Tables!H6 | H | EIH
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Manual Employee Payroll Record is edited, automatically create a Manual Employee Payroll Records with a negative‐ Duration of the existing Manual Employee Payroll Record, and one with a positive‐Duration of the new Manual Employee Payroll Record. |  | EI | 57 | 1 | H | 4 | =Tables!H4 | A | EIA
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Shift Summary Labor Line is recorded by the system as added, create one (or two, if the Shift Summary Labor Line spans midnight of Sunday night of the time zone of the Employee's Home Branch) Automatic Employee Payroll Records, including all time f |  | EI | 41 | 1 | H | 4 | =Tables!H4 | A | EIA
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Shift Summary Labor Line is recorded by the system as deleted, create an Automatic Employee Payroll Record for every existing, current, related Automatic Employee Payroll Record, with a negative‐Duration of the existing Automatic Employee Payroll R |  | EI | 60 | 4 | H | 6 | =Tables!H6 | H | EIH
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Shift Summary Labor Line is recorded by the system as edited, create two Automatic Employee Payroll Records for every existing, current, related Automatic Employee Payroll Record, one with a negative‐Duration of the existing Automatic Employee Payr |  | EI | 43 | 3 | H | 6 | =Tables!H6 | H | EIH
Payroll | Employee Payroll Periods |  |  | Y | UA | Allow a user to delete an existing Employee Payroll Record. |  | EI | 42 | 3 | H | 6 | =Tables!H6 | H | EIH
Payroll | Employee Payroll Periods |  |  | Y | UA | Allow a user to edit an existing Employee Payroll Record, including the Employee, the date worked, the Pay Type, the Duration in hours:minutes, and the Shift Summary Number. |  | EI | 73 | 2 | H | 5 | =Tables!H5 | H | EIH
Payroll | Employee Payroll Periods |  |  | N | BR | Allow a user to create a new Employee Payroll Period.
Payroll | Employee Payroll Periods |  |  | N | BR | Allow a user to delete an Employee Payroll Period.
Payroll | Employee Payroll Periods |  |  | N | BR | Automatically calculate differences between prior period Payroll data imported from Shift Summaries, and current period Payroll data imported from Shift Summaries, and generate offsetting records.
Payroll | Employee Payroll Periods |  |  | N | BR | Automatically populate Employee Payroll Periods list.
Payroll | Employee Payroll Periods |  |  | N | BR | List Employee Payroll Periods.
Payroll | Employee Payroll Periods |  |  | N | BR | List Pending Employee Payroll Periods
Payroll | Employee Payroll Periods |  |  | N | LIST | Allow a user to select an Employee Payroll Period.
Payroll | Employee Payroll Periods |  |  | N | LIST | Sort Employee Payroll Periods.
Payroll | Employee Payroll Periods |  |  | N | UA | Allow a user to access an Employee Payroll Period.
Payroll | Employee Payroll Periods |  |  | N | UA | Allow a user to match a Pending Employee from a Pending Employee Payroll Period to an Oracle Employee.
Payroll | Employee Payroll Periods |  |  | N | UA | Allow a user to see Payroll data for one of its Employees from Payroll data entered at another Branch.
Payroll | Employee Payroll Periods |  |  | N | UA | Prevent a user from creating an Employee Payroll Period for an Employee that already has an Employee Payroll Period.
Payroll | Employee Payroll Periods |  |  | N | UA | Prevent a user from deleting an Employee Payroll Period that contains billable time imported from a Shift Summary.
Payroll | Employee Payroll Periods |  |  | N | UA | Prevent a user from editing Payroll data for one of its Branch's Employees, if the Payroll data was entered at another Branch.
Payroll | Employee Payroll Weeks |  |  | Y | BR | Prepopulate the Employee Payroll Weeks to automatically appear within a Payroll Week, which is a combination of Employees with Automatic Employee Payroll Records for the Payroll Week (i.e., those Employees with billable hours for the current Branch), and |  | EQ | 64 | 1 | H | 16 | =Tables!H16 | A | EQA
Payroll | Employee Payroll Weeks |  |  | Y | BR | Sort the Employee Payroll Weeks by Last Name (ascending), then by First Name (ascending) |  | EQ | 9 | 4 | F | 18 | =Tables!F18 | H | EQH
Payroll | Employee Payroll Weeks |  |  | Y | LIST | List the Employee Payroll Weeks within a Payroll Week, including First Name, Last Name, Employee Number, Home Branch Code, Employee Type (i.e., Regular or Part‐Time Professional), Straight Time Hours, Overtime Hours, Double‐Time Hours, Input Branch and To |  | EQ | 1 | 2 | D | 17 | =Tables!D17 | L | EQL
Payroll | Employee Payroll Weeks |  |  | Y | UA | Allow a user to access an Employee Payroll Week. |  | EQ | 22 | 1 | H | 16 | =Tables!H16 | A | EQA
Payroll | Employee Selection |  |  | Y | BR | Filter the Employees by those who were Active (according to Oracle) on or after Monday of the previous week. |  | EQ | 39 | 3 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Selection |  |  | Y | LIST | List Employees, including First Name, Last Name, Employee Number, Employee Type (i.e., Regular or Part‐Time Professional). |  | EQ | 58 | 2 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Selection |  |  | Y | UA | Allow a user to filter Employees by Branch, default to the Home Branch. |  | EQ | 41 | 2 | H | 17 | =Tables!H17 | H | EQH
Payroll | Employee Selection |  |  | Y | UA | Allow a user to select an Employee. |  | EQ | 63 | 4 | H | 18 | =Tables!H18 | H | EQH
Payroll | Employee Selection |  |  | Y | UA | Allow a user to sort Employees by Employee ID (ascending), or by Last Name (ascending)/First Name (ascending), default by Last Name/First Name.@$ |  | EQ | 33 | 3 | H | 17 | =Tables!H17 | H | EQH
Payroll | Payroll Periods |  |  | N | BR | Sort Payroll Periods in descending order by date.
Payroll | Payroll Periods |  |  | N | LIST | List Payroll Periods.
Payroll | Payroll Periods |  |  | N | UA | Allow a user to access an existing Payroll Period.
Payroll | Payroll Periods |  |  | N | UA | Allow a user to select a Payroll Period.
Payroll | Payroll Periods |  |  | Y | UA | Allow a user to access the current Payroll Week. |  | EQ | 67 | 2 | H | 17 | =Tables!H17 | H | EQH
Payroll | Payroll Weeks |  |  | Y | UA | Allow a user to select a Payroll Week by specifying a date within the Payroll Week (Monday to Sunday). |  | EQ | 43 | 3 | H | 17 | =Tables!H17 | H | EQH
Payroll | Posting |  |  | Y | BR | Allow for an external system/process to flag each Employee Payroll Record as having been imported into Oracle as of a provided date. |  | EQ | 65 | 1 | H | 16 | =Tables!H16 | A | EQA

## NonSDLC (hidden)
Effort Estimation (Non-SDLC)
Other Parameters |  | Role | Duration | No. of persons | Effort
Data Conversion | On-site | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
| Off-shore | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
Documentation | On-site | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
| Off-shore | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
Translation | On-site | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
| Off-shore | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
Implementation | On-site | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
| Off-shore | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
Training | On-site | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
| Off-shore | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
Warranty | On-site | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
| Off-shore | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
Others | No of Page | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
| Off-shore | PM |  |  | 0
|  | TL |  |  | 0
|  | TM |  |  | 0
HTML Static Pages | No of Page |  |  |  | 0

## Efforts
Effort Estimation
Productivity in Hours per FP |  | 7 | Rationale for taking this Productivity
Working Hours in Day |  | 8
Avg. Working Days in Month |  | 20
Hours Per Month |  | 160
Project Mgmt.Effort (%age) |  | 10
Team Confidence Factor |  | L
Team Confidence Level
Factor Applicable for this Application |  |  | Project Size in FPs | L | A | H
Team Confidence Factor Correction for this System | <500 FP | 1 | < 500 | 8 | 9 | 10
| 500-1000 | 1.1429 | 500-1000 | 7 | 8 | 9
| >1000 FP | 1.3333 | >1000 | 6 | 7 | 8
SDLC Efforts |  |  | Technologies/ Tools/ Languages
Adjusted Function Points |  | 2131.44 | Ansi COBOL-85 |  | 16
Efforts in Person Hours |  | 19893 | C++ |  | 10.6
Efforts for Project Mgmt. (Hrs) |  | 1989.3 | CRYSTAL REPORTS |  | 8
Total SDLC Effort (Man-Hours) |  | 21882.3 | FORTRAN |  | 16
Total SDLC Effort (Man-Days) |  | 2735.2875 | FOCUS |  | 8
|  |  | INFORMIX |  | 8
Efforts of Non-SDLC Phases |  |  | JAVA |  | 10.6
Data Conversion |  | 0 | ORACLE |  | 8
Documentation |  | 0 | DEVELOPER 2000 |  | 7.3
Translation |  | 0 | PERL |  | 8
Implementation |  | 0 | POWERBUILDER |  | 6.6
Training |  | 0 | PRO C |  | 8
Warranty |  | 0 | SQL |  | 5
Other |  | 0 | SYBASE |  | 8
HTML Static Pages |  | 0 | VISUAL BASIC |  | 8.5
Total Non-SDLC Effort (Man-Days) |  | 0 | VISUAL C++ |  | 9.5
|  |  | INGRESS |  | 8
Effort Distribution Phasewise
SDLC Phases | % | Per.Days.
Project Training | 5 | 136.76
Project Management | 8 | 218.82
Define | 8 | 218.82
Design | 14 | 382.94
Construction+UT | 38 | 1039.41
Configuration Management | 3 | 82.06
Documentation | 5 | 136.76
Test Planning | 4 | 109.41
Test Execution | 15 | 410.29
Total Effort | 100 | 2735.27
Total Effort (Mandays) |  | 2735.2875
Total Efforts (Man-Month) |  | 136.7644
Work Already Done (Man-Days) |  | 0
Remaining Work (Man-Days) |  | 2735.2875
Remaining Work (Man-Months) |  | 136.7644
Note on A10: hari.prasad: The values below depend upon a combination of two factors: project size and team confidence level and is computed using the adjacent table
Note on A17: MM-ACI: Effort is calculated (corrected) based on team confidence factor (TCF) and project size. TCF is taken from the table above
Note on A46: Hari Prasad: This is total SDLC effort plus total non-SDLC effort.

## ResourceDistribution (hidden)
Resource Distribution Schedule
Client |  | Intellinet |  |  |  |  | Country |  | India
Project Name |  | Remote System 2.0 |  |  |  |  | Project ID |  | INRS20
A/C Manager / SDH |  | Arunabha |  |  |  |  | PSM |  | Hari Thapliyal
|  |  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Weeks==> |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | Sept. | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug
By Role | Name
|  | Total | 3.8 | 12 | 13.6 | 13.1 | 13.9 | 13.9 | 13.9 | 11.4 | 0 | 0 | 0 | 0
Development Project Manager | Hari Thapliyal | 3.5 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | Development Project Manager | 0 | 84 | 84 | 84 | 84 | 84 | 84 | 84
.NET Tech Manager | TBD | 6.5 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0
Senior Configuration Manager |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | Senior Configuration Manager | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84
Senior .NET Architect | Ajay Mishra | 5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | Senior Architect\Dev. Lead | 84 | 168 | 168 | 84 | 84 | 84 | 84 | 84
Senior Data Architect | Randeep | 5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | Senior Data Architect \ DB Dev. | 84 | 168 | 168 | 84 | 84 | 84 | 84 | 84
Senior Database Developer | TBD | 4 | 0 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | Senior Database Developer | 0 | 84 | 168 | 168 | 168 | 168 | 168 | 168
.NET Tech Lead | TBD | 7 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Senior Architect\Developer | 0 | 168 | 168 | 168 | 168 | 168 | 168 | 168
Senior .Net Developer (3+2) 2 Dedicated Shadow Resources for peer programming | Amit Gupta Nikhil Gupta Ritesh TBD TBD | 34 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | Senior .Net Developer | 336 | 504 | 504 | 504 | 504 | 504 | 504 | 504
Web Designer (Web-expression exp) | Satyajit Roy | 4.2 | 0 | 1 | 1 | 1 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | Web Designer (Web-expression exp) |  | 84 | 84 | 84 | 42 | 42 | 42 | 42
Senior Biztalk Developer | TBD (reqd from Jan) | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Senior Biztalk Developer | 0 | 0 | 0 | 0 | 168 | 168 | 168 | 168
Senior QA Lead | Vikas Shukla | 6.5 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Senior QA Lead | 0 | 84 | 84 | 84 | 84 | 84 | 84 | 84
Tester-1 | TBD (reqd from Dec) | 5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Senior QA Analysts | 0 | 0 | 0 | 168 | 168 | 168 | 168 | 168
Tester-2 (Automation) | Ajay Singh | 5.8 | 0.3 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Senior QA Automation | 42 | 84 | 84 | 84 | 168 | 168 | 168 | 168
Senior System (IT) Enginer | TBD (clarification - what is the need) | 1.1 | 0 | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | Senior System (IT) Enginer | 0 | 168 | 40 | 20 | 20 | 20 | 20 | 20
| Man-months | 95.6
By Phase
Project Management |  | 0
SRS |  | 0
Design |  | 0
Construction & Unit Testing |  | 0
Integration & System Testing |  | 0
Data Entry |  | 0
Training |  | 0
POC |  | 0
R&D |  | 0
Deployment |  | 0
Total Efforts (Mandays) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
By Resource
Resource 1 |  | 0
Resource 2 |  | 0
Resource 3 |  | 0
Resource 4 |  | 0
Resource 5 |  | 0
Resource 6 |  | 0
Resource 7 |  | 0
Resource 8 |  | 0
Resource 9 |  | 0
Resource 10 |  | 0
Total Efforts (Mandays) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A5: Implies Onsite deployment

## MergedInput (hidden)
Category | SubCategory | SubSubCategory | Sub-SubSubcategory | In Scope | Req Type | Items | Trans.Type | No
Administration | Branch Contractors |  |  | Y | BR | Prevent the user from saving a Branch Contractor with an Employee Number that is already used by an Employee or by another Branch Contractor. | EQ | 1
Administration | Branch Contractors |  |  | Y | BR | Prevent the user from saving a Branch Contractor without a First Name, Last Name, Employee Number, or specified Employment Service. | EQ | 1
Administration | Branch Contractors |  |  | Y | BR | Sort the Branch Contractors by Last Name, First Name
Administration | Branch Contractors |  |  | Y | LIST | List Branch Contractors, including First Name, Last Name, Unique Employee Number, and Employment Service. | EO | 1
Administration | Branch Contractors |  |  | Y | UA | Allow a user to access a Branch Contractor from the list. | EQ | 1
Administration | Branch Contractors |  |  | Y | UA | Allow a user to create a new Branch Contractor. | EI | 1
Administration | Branch Contractors |  |  | Y | UA | Allow a user to edit a new Branch Contractor. | EI | 1
Administration | Branch Contractors |  |  | Y | UA | Allow a user to Filter the Branch Contractors by All or Active Only. Default to Active Only. | EQ | 1
Administration | Branch Contractors |  |  | Y | UA | Allow a user to terminate/un‐terminate a Branch Contractor. | EI | 1
Administration | Customer Gate Log Reconciliations |  |  | N | LIST | List Primary Equipment records for a Shift, displaying the Customer's Equipment Number, and Start/Stop date/time (according to the Shift Summary) sorted by Equipment Number. |  | 1
Administration | Customer Gate Log Reconciliations |  |  | N | UA | Allow a user to enter or change the Gate Log data for that Equipment for that shift. |  | 1
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Display summary duration values for each person (i.e., Badge Number). | EQ | 1
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Filter the Gate Log Reconciliation records by the selected Customer Site, by all Shift Labor records that begin on the selected date. | EQ | 1
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Prevent a user from editing a Gate Log record if the corresponding item exists on an Invoice (unless the Invoice has been credited and the item has not been reinvoiced). | EQ | 1
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Sort the Gate Log Reconciliation records by Last Name (ascending), and First Name (ascending). | EQ | 1
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | Warn the user, when reopening a Shift Summary with Gate Log Reconciliations, that the Gate Log Reconciliations will be deleted. | EQ | 1
Administration | Customer Gate Log Reconciliations |  |  | Y | BR | When a user reopens a Shift Summary with Gate Log Reconciliations, delete the Gate Log Reconciliations associated with the Shift Summary. | EI | 1
Administration | Customer Gate Log Reconciliations |  |  | Y | LIST | List Labor records for a selected day for a selected Customer Site, displaying the Badge Number, First Name, Last Name, Employee Number (if it exists)and Start/Stop date/time (according to the Shift Summary), total hours/minutes worked, the Employee's Hom | EQ | 1
Administration | Customer Gate Log Reconciliations |  |  | Y | UA | Allow a user to accept the default calculated Labor time (per the Shift Summary), or enter the Gate Log Labor time (in minutes, hours), per line. | EQ | 1
Administration | Customer Gate Log Reconciliations |  |  | Y | UA | Allow a user to save the Gate Log data for a shift. | EI | 1
Administration | Customer Purchase Orders | Customer‐ Defined Attributes |  | Y | BR | For each Purchase Order, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Warn the user when saving a Purchase Order with invalid Customer‐Defined Attribute values. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | UA | For each Purchase Order, Allow a user to enter the values for the Customer‐Defined Attributes.
Administration | Customer Purchase Orders | Purchase Order Lines | Customer‐Defined Attributes | Y | BR | For each Purchase Order Line, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from deleting a Purchase Order Line if it exists on an Invoice. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Warn the user when saving the Purchase Order Line with invalid Customer‐Defined Attribute values. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to delete a Purchase Order Line. | EI | 1
Administration | Customer Purchase Orders |  |  | Y | UA | For each Purchase Order Line, allow a user to enter the values for the Customer‐Defined Attributes.
Administration | Customer Purchase Orders |  |  | Y | BR | If the user changes the Dollar Amount of a Purchase Order Line, recalculate the remaining values on the Purchase Order Line. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from creating a Purchase Order Line for a Purchase Order, if the Customer Site does not require Purchase Order Lines. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from creating a Purchase Order Line for a Purchase Order, if the Purchase Order is closed. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from deleting a Purchase Order Line if the Purchase Order is closed. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from editing anything other than the Dollar Amount of a Purchase Order Line, if the Purchase Order Line has been used on a Posted Invoice. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | LIST | List Purchase Order Lines per Purchase Order. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to create a new Purchase Order Line for a Purchase Order. | EI | 1
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to edit a Purchase Order Line for a Purchase Order. | EI | 1
Administration | Customer Purchase Orders |  |  | N | BR | Prevent the user from deactivating a Purchase Order if it exists on a Job Header or Invoice. |  | 1
Administration | Customer Purchase Orders |  |  | N | UA | Allow a user to deactivate a Purchase Order. |  | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Calculate and display the difference between the original amount of the Purchase Order or Purchase Order Line, and the amount of the Invoices posted against it. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Calculate and display the difference between the original amount of the Purchase Order or Purchase Order Line, and the amount of the unposted and posted Invoices against it. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Filter the Purchase Orders by Customer Filter the Purchase Orders by Customer Site. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | If the user changes the Dollar Amount of a Purchase Order, recalculate the remaining values on the Purchase Order. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from closing a Purchase Order if one of its Purchase Order Lines exists on an unposted Invoice. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from editing a closed Purchase Order, or a Purchase Order Line of a closed Purchase Order. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from editing anything other than the Dollar Amount of a Purchase Order, if the Purchase Order has been used on a Posted Invoice. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from saving a Purchase Order Line that already exists for the Customer Site. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Prevent the user from saving a Purchase Order with a Purchase Order Number that already exists for the Customer Site. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Sort the Purchase Order Lines by Purchase Order Line Number (ascending). | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Sort the Purchase Orders by Purchase Order Number (ascending). | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | BR | Warn the user when saving the Purchase Order with a Purchase Order Number that does not pass the Purchase Order regular expression mask for the Customer Site, if one exists. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | LIST | List Purchase Orders. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to close a Purchase Order. | EI | 1
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to create a Purchase Order | EI | 1
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to filter the Purchase Orders (Open vs. Closed). Initialize the filter to display Open only. | EQ | 1
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to order a Purchase Order | EI | 1
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to reopen a Purchase Order. | EI | 1
Administration | Customer Purchase Orders |  |  | Y | UA | Allow a user to select a Purchase Order | EQ | 1
Administration | Employees |  |  | Y | LIST | List Employees, including First Name, Last Name, Employee Number, Employee Type (i.e., Regular or Part‐Time Professional).@$ | EQ | 1
Administration | Employees |  |  | Y | UA | Allow a user to sort Employees by Employee ID (ascending), or by Last Name (ascending)/First Name (ascending), default by Last Name/First Name. | EQ | 1
Administration | Employees |  |  | Y | UA | Allow a user to filter Employees by Branch, default to the Home Branch.@# | EQ | 1
Administration | Employees |  |  | Y | UA | Allow a user to select an Employee.@$ | EQ | 1
Administration | Field Service Settings |  |  | Y | BR | Notify the user if a clock reset has been detected, and prevent the application from starting until the clock has been set. | EQ | 1
Administration | Month End Close |  |  | N | BR | Prevent a user from closing Month End prior to Month End. |  | 1
Administration | Month End Close |  |  | Y | BR | Provide real and estimated revenue values for all Shift Items within a month, for all items added in that month, and for all items whose real or estimated revenue has changed within the month; and for a place‐holder for a Corporate System to associate a m | EQ | 1
Administration | Pending Customers |  |  | N | UA | Allow a user to match a Pending Customer Site to an Oracle Customer. |  | 1
Administration | Pending Employees |  |  | Y | UA | Allow a user to match a Pending Employee to an Oracle Employee. | EQ | 1
Administration | Synchronization |  |  | Y | BR | Display a confirmation message at the end of a successful manual synchronization. | EQ | 1
Administration | Synchronization |  |  | Y | BR | Display the synchronization status. | EQ | 1
Administration | Synchronization |  |  | Y | BR | Warn the user to synchronize when the Remote System 2.0 is opened and closed in branch. | EQ | 1
Administration | Terms & Conditions Contract |  |  | Y | BR | Display Customer Terms & Conditions Contract Details (T&C Contract Number, Activation Date, Expiration Date) | EQ | 1
Administration | Terms & Conditions Contract |  |  | Y | BR | Warn the user when creating a new Job when the Terms & Conditions Contract has past its expiration date. | EQ | 1
Administration | Terms & Conditions Contract |  |  | Y | BR | Warn the user when creating a Shift for an existing Job when the Terms & Conditions Contract has past its expiration date. | EQ | 1
Invoicing | Contract Selection |  |  | N | BR | Prevent a user from seeing Contract Pricing for a Contract, if the user's Branch is not authorized to view that Contract's Pricing. |  | 1
Invoicing | Contract Selection |  |  | N | LIST | List all Contracts for a Customer. |  | 1
Invoicing | Contract Selection |  |  | N | UA | Allow a user to select a Contract. |  | 1
Invoicing | Contract Selection |  |  | N | UA | Allow a user to view Contract header details (e.g., Contract Number, expiration date, etc.) |  | 1
Invoicing | Contract Selection |  |  | Y | BR | Filter the Contract / Contract Level / Contract Versions to only show records: (a) for the currently selected Customer Site (i.e., those where the Contract Level applies to no Customer Site or to the current Customer Site) (b) where the Active Date of the | EQ | 1
Invoicing | Contract Selection |  |  | Y | BR | Sort the Contract / Contract Level / Contract Versions by Active Date of the Contract (descending), then by Contract Level Priority (ascending), then by Contract Version Active Date (descending). | EQ | 1
Invoicing | Contract Selection |  |  | Y | LIST | List all Contracts, Contract Levels, and Contract Level Version for a Customer, displaying the Contract Number, the Contract Level Description, the Contract Version Activation Date, and the Contract Expiration Date. | EQ | 1
Invoicing | Contract Selection |  |  | Y | UA | Allow a user to revise the filtered view, to show older Contracts / Contract Levels / Contract Versions by date range, between today and the specified date. | EQ | 1
Invoicing | Contract Selection |  |  | Y | UA | Allow a user to select a Contract / Contract Level / Contract Version. | EQ | 1
Invoicing | Credit Invoices |  |  | Y | BR | If a Credit Invoice is created from an Invoice with a Custom View, automatically create a Custom View Line Items for the Credit Invoice, and set the Description of each to the Description of each Custom View Line Item of the source Invoice, and the Dollar | EQ | 1
Invoicing | Credit Invoices |  |  | Y | BR | Prevent the user from creating a Credit Invoice from an Invoice, or one or more of the Items on that Invoice, if the source Invoice is a Credit Invoice. | EQ | 1
Invoicing | Credit Invoices |  |  | Y | BR | Prevent the user from creating a Credit Invoice from an Invoice, or one or more of the Items on that Invoice, if the source Invoice is not in Posted Mode. | EQ | 1
Invoicing | Credit Invoices |  |  | Y | UA | Allow a user to create a Credit Invoice from an Invoice, including an indication of whether the Invoice Line Data: (a) will be returned to the Staging Area, (b) will be deleted, and marked as Lost Revenue, or (c) will be associated with a Re‐Invoice. | EI | 1
Invoicing | Credit Invoices |  |  | Y | UA | Allow a user to create a Credit Request associated with the Credit Invoice or Credit/Re‐Invoice. | EI | 1
Invoicing | Custom Invoice Views | Line Items |  | Y | BR | Allow a user to add a Custom View Line Item. | EI | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Allow a user to edit a Custom View Line Item. | EI | 1
Invoicing | Custom Invoice Views |  |  | Y | UA | Allow a user to delete a Custom View Line Item. | EI | 1
Invoicing | Custom Invoice Views |  |  | N | BR | Prevent the user from creating a Custom View for an Invoice, when the Invoice is not in Open Mode. |  | 1
Invoicing | Custom Invoice Views |  |  | N | BR | When the user adds a Custom View Line Item to a Custom View for an Invoice, automatically recalculate the Invoice Total Amount, the underlying Invoice Variance, and the Re‐Invoice Difference. |  | 1
Invoicing | Custom Invoice Views |  |  | N | BR | When the user deletes a Custom View Line Item from a Custom View for an Invoice, automatically recalculate the Invoice Total Amount, the underlying Invoice Variance, and the Re‐Invoice Difference. |  | 1
Invoicing | Custom Invoice Views |  |  | N | BR | When the user deletes a Custom View of an Invoice, remove the Variance Line from the Invoice. |  | 1
Invoicing | Custom Invoice Views |  |  | N | BR | When the user edits a Custom View Line Item on a Custom View for an Invoice, automatically recalculate the Invoice Total Amount, the underlying Invoice Variance, and the Re‐Invoice Difference. |  | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Calculate the Custom View Variance Percentage as: (A) The sum of all Custom View Invoice Lines, divided by (B) the price of all items on the Reference Invoice, according to the highest priority current Contract Pricing Level with specified pricing (i.e., | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, if the Invoice does not have a Custom View. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from adding a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from deleting a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from deleting a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from editing a Custom View Line Item to a Custom View for an Invoice, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent a user from editing a Custom View Line Item to a Custom View for an Invoice, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from creating a Custom View for an Invoice, when the Invoice already has a Custom View. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from creating a Custom View for an Invoice, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from deleting a Custom View for an Invoice, when the Invoice does not have a Custom View. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from deleting the Custom View, when the Invoice is a Credit Invoice with a Custom View. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from deleting the Custom View, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from editing the Custom View text, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | Prevent the user from editing the Invoice Total Amount of the Custom View, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | When an Invoice with a Custom View is opened or saved, automatically recalculate the Reference Invoice Total Amount and the Custom View Total Amount, and recalculate and reallocate the Custom Variance across the Reference Invoice Items. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user adds a Custom View Line Item to a Custom View for an Invoice, save the Invoice. | EI | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user creates a Custom View of an Invoice, calculate the Custom View Variance Percentage. | EQ | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user creates a Custom View of an Invoice, save the Invoice. | EI | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user deletes a Custom View Line Item from a Custom View for an Invoice, save the Invoice. | EI | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user deletes a Custom View of an Invoice, save the Invoice. | EI | 1
Invoicing | Custom Invoice Views |  |  | Y | BR | When the user edits a Custom View Line Item to a Custom View for an Invoice, save the Invoice. | EI | 1
Invoicing | Custom Invoice Views |  |  | Y | UA | Allow a user to create a Custom View for an Invoice. | EI | 1
Invoicing | Custom Invoice Views |  |  | Y | UA | Allow a user to delete the Custom View of an Invoice. | EI | 1
Invoicing | Inbox Queue |  |  | Y | BR | Allow a user to open an Invoice Staging Area for a Customer Site/Purchase Order in the Inbox Queue. | EQ | 1
Invoicing | Inbox Queue |  |  | Y | LIST | Allow a user to filter the Jobs in the Inbox Queue by Keyword search (on Customer Site), Job Start Date (within a specified date range), or Customer Site Number. | EQ | 1
Invoicing | Inbox Queue |  |  | Y | UA | List all Jobs which have uninvoiced items [Inbox Queue]. Display each Customer Site by Payment Authorization. | EQ | 2
Invoicing | Inbox Queue |  |  | Y | UA | Sort the Jobs in the Inbox Queue in ascending order by Customer Number, then by ascending chronological order according to the Job Start Date. | EQ | 1
Invoicing | Invoice Formatting and Printing | Invoice Print Preferences |  | N | UA | Retain the last used Invoice Template selection for an Invoice. |  | 1
Invoicing | Invoice Formatting and Printing |  |  | Y | BR | Allow a user to select the Invoice Template for an Invoice. | EQ | 1
Invoicing | Invoice Formatting and Printing |  |  | Y | UA | Allow a user to preview an Invoice prior to printing. | EQ | 2
Invoicing | Invoice Formatting and Printing |  |  | Y | UA | Allow a user to print the Invoice. | EQ | 1
Invoicing | Invoice Formatting and Printing |  |  | Y | UA | Allow a user to save the Invoice as a PDF. | EO | 1
Invoicing | Invoice Formatting and Printing |  |  | Y | UA | Apply a watermark (e.g., "NOT AN INVOICE ‐‐ DO NOT PAY") to an Invoice when it is not in Posted Mode. | EQ | 1
Invoicing | Invoice Lines | Combining and Allocating Third‐ Party Charge Items |  | N | BR | When a combined Third‐Party Charge Item is un‐combined, if the Invoice has a Custom View, reallocate the Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a combined Third‐Party Charge Item is un‐combined, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When one or more Third‐Party Charge Items are combined, if the Invoice has a Custom View, recalculate the Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | UA | When one or more Third‐Party Charge Items are combined, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to allocate a Third Party Charge Line‐‐ partially or totally ‐‐ to a different Service Line. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to combine two or more Third‐Party Charge items into one invoice line item. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from allocating Third‐Party Charge revenue to a different Service Line, if the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When one or more Third‐Party Charge Items are combined, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When one or more Third‐Party Charge Items are un‐combined, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from combining Third‐Party Charge items if the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines | Combining Items Whose Units of Measure Span Shifts |  | Y | BR | Allow a user to combine two or more Invoice line items that refer to units of measure that span shifts. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to undo a combined item for the units of measure that span shifts. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from combining Items with units of measure that span shifts, if the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from un‐combining Items with units of measure that span shifts, if the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Determine the Unit Cost for each Item, based upon the selected Contract Level, and whether it indicates Branch Standard Pricing (in which case Branch Standard Pricing is used), or Contract Specific Pricing or Fixed Fee (in which case the Contract Item's P | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from combining Items with units of measure that span shifts, if the Item Codes of the source Item Codes are different. | EQ | 1
Invoicing | Invoice Lines | Contract Level |  | Y | BR | Upon creation of each new Invoice, allow a user to select the Contract Level, selecting from a list of Contract Levels for the Customer. | EQ | 2
Invoicing | Invoice Lines | Contract‐Defined Item Properties |  | Y | BR | Determine the Item Code and Description for each Item, based upon the selected Contract Level, and whether it indicates Contract Specific Pricing, and specifies an Item Code and/or Description override; otherwise, the Item Master's default Item Code and/o | EQ | 2
Invoicing | Invoice Lines |  |  | Y | BR | Determine the Unit of Measure for each Item, based upon the selected Contract Level, and whether it indicates Branch Standard Pricing (in which case the Item Master's default Unit of Measure is used), or Contract Specific Pricing or Fixed Fee (in which ca | EQ | 2
Invoicing | Invoice Lines | Customer‐Defined Attributes |  | Y | BR | Display a list of the Customer‐Defined Attributes for the Invoice, and their values. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | For each Open Invoice, validate each entered or modified Customer‐Defined Attribute against the Customer‐Defined Attribute's regular expression mask, if one exists. If the validation fails, warn the user with a visual cue. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | For each Open Invoice, allow a user to enter the values for the Customer‐Defined Attributes. | EI | 1
Invoicing | Invoice Lines | Invoice Line Editing | Contract‐Defined No‐Charge Quantity | N | BR | When the Contract‐Defined No‐Charge Quantity is changed for an Item, if the Invoice has a Custom View, recalculate the Invoice Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When the Contract‐Defined No‐Charge Quantity is changed for an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When the Contract‐Defined No‐Charge Quantity is changed for an Item, if the Item is a component of a Package, recalculate the Package Variance. |  | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify a Contract‐Defined No‐Charge Quantity. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity that makes the total invoiceable Item Quantity less than zero. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is not under a Contract Level that indicates Contract‐Defined Pricing. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is under a Contract Level that indicates Contract‐Defined Pricing, but the Contract Item does not indicate a Contract‐Defined No‐Charge Quantity. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is a Third‐Party Charge Item. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is marked as Destroyed. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Item is Priced on Request. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When the Contract‐Defined No‐Charge Quantity is changed for an Item, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a Contract‐Defined No‐Charge Quantity, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  | Default Quantity | Y | BR | Allow a user to enter or change a description for a Third‐Party Charge Item. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify a Default Quantity if at least one of the following is true: (a) A Contract‐Specified Unit of Measure is used, and the Unit of Measure in the Item Master is different than the Contract‐ Specified Unit of Measure. (b) The Contract r | EQ | 2
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from changing a description for a Third‐Party Charge, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Default Quantity that makes the total invoiceable Item Quantity less than zero. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Default Quantity, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When the selected Contract refers to a Contract‐Specified Maximum Daily Billable Labor Duration, prevent the user from specifying a Default Quantity that is greater than Contract‐ Specified Maximum Daily Billable Labor Duration. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a Default Quantity, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  | Price per Unit | N | BR | When a Price per Unit is entered or changed for a Package Item, recalculate the Package Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a Price per Unit is entered or changed for an Item, if the Invoice has a Custom View, recalculate the Invoice Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a Price per Unit is entered or changed for an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a Price per Unit is entered or changed for an Item, if the Item is a component of a Package, recalculate the Package Variance. |  | 1
Invoicing | Invoice Lines |  |  | Y | BR | Only allow for a user to enter or change a Price per Unit for an item if the item is one of the following: (a) An Item (or Package Item) on a Invoice with a Contract Level that indicates Branch Standard Pricing (b) A Third‐Party Charge Item (c) Priced on | EQ | 2
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from changing the Price per Unit of an Item, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a Price per Unit that is less than zero. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a Price per Unit is entered or changed for an Item or Package Item, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Allow a user to enter or change the Price per Unit for an Item. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from changing the Price per Unit of an Item, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  | User‐Specified Discount | N | BR | Prevent the user from specifying a User‐Specified Discount, when the Item is a Third‐Party Charge Item. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | Prevent the user from specifying a User‐Specified Discount, when the Item is marked as Destroyed. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a User‐Specified Discount is applied to an Item, if the Invoice has a Custom View, recalculate the Invoice Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a User‐Specified Discount is applied to an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a User‐Specified Discount is applied to an Item, if the Item is a component of a Package, recalculate the Package Variance. |  | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify a User‐Specified Discount a Line Item price. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified Discount, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified Discount, when the Item is on an Invoice that has a Contract Level that does not indicate Branch Standard Pricing. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a User‐Specified Discount is applied to an Item, save the Invoice.@$ | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a User‐Specified Discount, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  | User‐Specified No‐ Charge Quantity | N | BR | When the User‐Specified No‐Charge Quantity is changed for an Item, if the Invoice has a Custom View, recalculate the Invoice Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When the User‐Specified No‐Charge Quantity is changed for an Item, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When the User‐Specified No‐Charge Quantity is changed for an Item, if the Item is a component of a Package, recalculate the Package Variance. |  | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify a User‐Specified No‐Charge Quantity. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity that makes the total invoiceable Item Quantity less than zero. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is a Third‐Party Charge Item. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is marked as Destroyed. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Item is Priced on Request. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Specified No‐Charge Quantity, without supplying the User‐Specified No Charge Reason. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a User‐Specified Discount is applied to an Item, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a User‐Specified No‐Charge Quantity is entered, allow a user to enter the User‐Specified No Charge Reason, as one of the following: (a) By HydroChem's choice, (b) By Customer insistence, or (c) Because of a Gate Log Discrepancy | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a User‐Specified No‐Charge Quantity, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines | Packages | Components | N | BR | When a Component Item is removed from a Package, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | Y | BR | List fulfilled and unfulfilled Package Component Items of a selected Package on the Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a partial quantity of a Line Item to a Package, when the Package already contains a Component Item from a different Shift. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from removing a Component Item from a Package, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | LIST | Allow a user to remove a selected Component Item from a Package. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from removing a Component Item from a Package, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | N | BR | Determine which Equipment Line Items are components of a Package, according to the Contract Level used on the Invoice. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | Prevent the user from adding a Variance Line Item to a Package. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a Component Item is removed from a Package, if the Invoice has a Custom View, recalculate and reallocate the Invoice Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a Component Item is removed from a Package, recalculate and reallocate the Package Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a Package quantity is entered or modified, if the Invoice has a Custom View, recalculate and reallocate the Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a Package quantity is entered or modified, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a Package quantity is entered or modified, recalculate and reallocate the Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When the user deletes a Package from an Invoice, remove the Package Variance Line with the Package. |  | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to add a selected Line Item to a Package. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to delete the Package. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to select a Package. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to specify the quantity of the Package. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the Package Variance Percentage as: (A) The price of the Package Item, divided by (B) the price of all the Package Component Items, according to the highest priority current Contract Pricing Level | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the price of each Package Component Item as: (A) The item quantity, which is defined as: (A1) The Default Quantity minus (A2) the Contract‐Specified No‐Charge Quantity minus (A3) the User‐Entered No‐Charge Quantity; times (B) the Per Unit Price; | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | If the Invoice's Contract Level does not indicate Branch Standard Pricing, only allow the user to select one of the Packages specified in the Contract Level. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | If the Invoice's Contract Level indicates Branch Standard Pricing, only allow the user to select one of the Packages covered by Branch Standard Pricing. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | List Packages. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a a Package to an Invoice, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a Line Item to a Package, when that Item is not defined as a Package Component. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a Line Item to a Package, when the Package already contains a Component Item from a different Shift. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a Line Item to a Package, when the required quantity of that Item has already been added to the Package. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from adding a partial quantity of a Line Item to a Package, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from deleting a Package, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from deleting a Package, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from modifying the quantity of a Package, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from setting the quantity of a Package component to a quantity greater than the Package Item's Maximum Quantity Allowed (if it exists). | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from setting the quantity of a Package component to a quantity less than the Package Item's Minimum Quantity Allowed (if it exists). | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying the quantity of a Package, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Provide a visual cue to the user if the Contract Level indicates Contract‐Specific Pricing ‐‐ one that contains one or more Packages ‐‐ and a Primary Equipment line item could be converted into one of those Packages. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a Component Item is removed from a Package, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a Package quantity is entered or modified, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When an Item or partial quantity of an Item is added to a Package, if the Invoice has a Custom View, recalculate and reallocate the Variance. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When an Item or partial quantity of an Item is added to a Package, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When an Item or partial quantity of an Item is added to a Package, recalculate and reallocate the Variance. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When an Item or partial quantity of an Item is added to a Package, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When the user adds a Package to an Invoice, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When the user deletes a Package from an Invoice, save the Invoice | EI | 1
Invoicing | Invoice Lines |  |  | Y | LIST | Allow a user to add a partial quantity of a selected Line Item to a Package. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Allow a user to add a Package to an Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from adding a a Package to an Invoice, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from adding a Line Item to a Package, when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from adding a Line Item to a Package, when the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | When an Invoice is opened or saved, recalculate and reallocate all Package Variances across each Package's Component Items. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | When the user adds a Package to an Invoice, create a Package Variance Line within the Package. | EQ | 1
Invoicing | Invoice Lines | Payment Authorization |  | Y | BR | Allow a user to change the Payment Authorization for an Open Invoice, selecting from the list of Payment Authorization Methods that are available to the Customer (e.g., Purchase Order or Pending Purchase Order, Credit Card Authorization, and/or No Authori | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | For each new (Open) Invoice, automatically set the Payment Authorization to that of the Job containing the Staging Area items being added. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | If a Payment Authorization Method of Purchase Order is selected, require that the user selects one and only one of the following: (a) an existing Purchase Order (one without Purchase Order Line detail), (b) an existing Purchase Order Line, or (c) a Pendin | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from selecting a Payment Authorization Method of Purchase Order, when the Customer Site requires Purchase Order Lines. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Upon creation of each new Credit Invoice and Re‐Invoice, set the Contract Level to the Contract Level of the Source Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Warn the user if the amount remaining on the Purchase Order ‐‐ minus the amount of the Invoice ‐‐ is less than 15% of the original value of the Purchase Order. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Warn the user if the amount remaining on the Purchase Order ‐‐ minus the amount of the Invoice ‐‐ is less than zero. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a user changes a Payment Authorization Method when invoicing one or more Jobs, update all future created Invoices for that Job to use the selected Payment Authorization Method. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from editing the Payment Authorization unless the Invoice is in Open or Submitted Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from selecting a Payment Authorization Method that is not available to the Customer. | EQ | 1
Invoicing | Invoice Lines | Purchase Order/Line Variance |  | Y | BR | When an invoice is opened or saved, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. | EQ | 1
Invoicing | Invoice Lines | Splitting Labor Time into Other Categories |  | N | BR | When a Labor Line Item is split, if the Invoice has a Custom View, recalculate the Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When a Labor Line Item is split, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When split Labor Line Items are recombined, if the Invoice has a Custom View, recalculate the Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | UA | When split Labor Line Items are recombined, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to recombine the split Labor Lines items back to their original single‐line entry. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to split a Labor Line item into two or more Labor Line Items. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from recombining a split Labor Item, if the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from splitting a Labor Item if the Labor Item is a component of a Package. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from splitting a Labor Item, if the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a Labor Line Item is split, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When split Labor Line Items are recombined, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from splitting a Labor Item into an additional Labor Item from a different Service Line. | EQ | 1
Invoicing | Invoice Lines | Taxation |  | Y | BR | Allow a user to "un‐flag" a taxable invoice as tax exempt. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to flag a taxable invoice as tax exempt. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | For each Open Invoice, determine whether the products and/or services are taxable (by Customer Site). | EQ | 1
Invoicing | Invoice Lines | User‐ Entered Invoice Discount |  | Y | BR | Prevent the user from specifying a User‐Entered Invoice Discount unless the Invoice is in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Entered Invoice Discount when the Contract of the Invoice indicates anything other than Branch Standard Pricing. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from specifying a User‐Entered Invoice Discount when the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Allow a user to specify a User‐Entered Invoice Discount. | EI | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from specifying a User‐Entered Invoice Discount of less than 0%, or more than 100%. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | When a User‐Entered Invoice Discount is specified, changed, or removed, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | N | BR | When one or more Line Items are removed from an Invoice, if the Invoice has a Custom View, reallocate the Variance. |  | 1
Invoicing | Invoice Lines |  |  | N | BR | When one or more Line Items are removed from an Invoice, if the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value. |  | 1
Invoicing | Invoice Lines |  |  | N | UA | Prevent the user from removing a Variance Line from the Invoice. |  | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to create a new Invoice | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to remove one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | Allow a user to select one or more Invoice Lines. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the displayed Discount Percentage as: One minus (A) The Contract Discount, which is defined as: (A1) The Contract Line Item Discount, if one is specified for the Item Code; otherwise (A2) The Contract Discount; times one minus (B) the User‐Enter | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the price of each Invoice Line as: (A) The Item Quantity, which is defined as: (A1) The Default Quantity minus (A2) the Contract‐Specified No‐Charge Quantity minus (A3) the User‐Entered No‐Charge Quantity; times (B) the Per Unit Price; times one | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Calculate the Tax for each Item, based upon whether the Item is a Product or Service, whether the Customer Site prescribes a Product or Service Tax Rate, and whether the user has opted to make the Invoice non‐taxable. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Display the Invoice header | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | For each new (Open) Credit Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Source Invoice for which it is created). | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | For each new (Open) Re‐Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Credit Invoice for which it is created). Placing Letter at end plus number. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from editing the Invoice Header if the Invoice is a Credit Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from removing one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from a Re‐Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | Prevent the user from removing partial quantity of a Package Item from an Invoice. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a Package item is removed from a regular Invoice, the quantity of its Component Items are moved individually back to the Staging Area and marked as available for Invoicing. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When a quantity of a non‐Package item is removed from a regular Invoice, move the quantity back to the Staging Area, and mark the quantity as available for Invoicing. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When one or more Line Items are removed from an Invoice, if one or more of the Items are components of a Package, flag the Package components as unfulfilled. | EI | 1
Invoicing | Invoice Lines |  |  | Y | BR | When one or more Line Items are removed from an Invoice, save the Invoice. | EI | 1
Invoicing | Invoice Lines |  |  | Y | LIST | Prevent the user from removing one or more selected Invoice Lines ‐‐ or a partial quantity of a single Invoice Line ‐‐ from the Invoice, if the Invoice is not in Open Mode. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Allow a user to Edit the Invoice Header (i.e., Payment Authorization, Customer‐Defined Attributes, and Notes). | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | For each new (Open) Regular Invoice, generate a unique, unbrokensequential Invoice Number (i.e., unique to the Branch location where it is created). | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | List Invoice Lines, including Item Code, Description, Quantity, Unit of Measure, Price per Unit, Amount, Discount Percentage, and Net Amount. | EQ | 1
Invoicing | Invoice Lines |  |  | Y | UA | Prevent the user from editing the Invoice Header unless the Invoice is in Open Mode. | EQ | 1
Invoicing | Invoice Management and Workflow | Custom Exports |  | Y | BR | Allow a user to generate a Customer‐Specific Invoice Export. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from generating a Customer‐Specific Invoice Export if the Customer does not accept Customer‐Specific Invoice Exports. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from generating a Customer‐Specific Invoice Export, if the Invoice is not in Submitted Mode, and the Customer requires Customer‐Specific Invoice Exports from Submitted Mode. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Prevent the user from generating a Customer‐Specific Invoice Export, if the Invoice is not in Posted Mode, and the Customer requires Customer‐Specific Invoice Exports from Posted Mode. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | N | BR | Allow a user to mark a Re‐Invoice as Disapproved. Move the Invoice to Disapproved Mode. |  | 1
Invoicing | Invoice Management and Workflow |  |  | N | BR | Allow a user to mark an Approved Credit Invoice as Lost Revenue. |  | 1
Invoicing | Invoice Management and Workflow |  |  | N | BR | Allow a user to mark an Invoice variance as Approved. |  | 1
Invoicing | Invoice Management and Workflow |  |  | N | BR | Prevent a user from marking a Re‐Invoice as Approved without providing the required Credit Request data. |  | 1
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark a Credit Invoice as Approved. |  | 1
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark a Credit Invoice as Disapproved. Move the Invoice to Disapproved Mode. |  | 1
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark a Re‐Invoice as Approved. |  | 1
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark an Invoice as with a Taxability Override as Approved. |  | 1
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark an Invoice variance as Disapproved. Move the Invoice to Disapproved Mode. |  | 1
Invoicing | Invoice Management and Workflow |  |  | N | UA | Allow a user to mark an Invoice with a Taxability override as Disapproved. Move the Invoice to Disapproved Mode. |  | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Allow a user to change the selected invoice from Open to Submitted Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Allow a user to change the selected Invoice from Submitted to Open Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Allow a user to change the selected Invoice from Submitted to Posted Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Calculate total invoice variance as the difference between all items' default price and the final dollar amount of the invoice. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Determine if an Invoice in Pending Approval Mode, with one or more Approvals, can be fully Approved. If so, move the Invoice to Approved Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Display the Current Invoice Mode. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Mark all quantities of Items on a deleted Invoice as invoicable, and refresh the Staging Area to reflect the new Items and quantities. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent a user from moving a Credit Invoice out of Open Mode without providing the required Credit Request data (i.e., Credit Reason, Description, and ‐‐ if the Credit Invoice will return the data to the Staging Area ‐‐ the expected Re‐Invoice amount. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent an Invoice from going to Submitted or Posted Mode, if the invoice has been overridden to be non‐taxable. Instead move the Invoice to Pending Approval Mode. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving an Invoice directly to Posted Mode if the Customer Site requires the Submitted Invoice Mode (for electronic invoicing). | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving an Invoice out of Open Mode, if a Labor Item on the Invoice refers to a Shift Summary Labor Line whose start/stop date/time overlaps with another Shift Summary Labor Line within the system. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving an Invoice out of Open Mode, if the Invoice is under Contract‐Specified Pricing, and contains one or more Items where the Unit of Measure in the Item Master is different from the Contract‐Specified Unit of Measure, for which n | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving an Invoice to Submitted Mode if the Customer Site does not require the Submitted Invoice Mode (for electronic invoicing). | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode if the Invoice contains a Package with component items that are all zero priced. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode if the Invoice has a Custom View, and the Custom View has no Custom View Line with a dollar value. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode if the Invoice has a Custom View, and the Reference Invoice has a zero dollar value. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if one or more Customer‐Defined Attributes' values have not been specified. Expected Regular esxpression rule need to validate. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if one or more Packages do not have quantities specified. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if one or more required components of a Package have not yet been fulfilled. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Contract Item with a variable item price (i.e., Priced on Request), with an unspecified price. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Third‐Party Charge Item with an unspecified description. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains a Third‐Party Charge Item with an unspecified price. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice contains an Item whose General Ledger code does not exist in the General Ledger table. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Invoice has a Custom View, and no Custom View Line Items with dollar amounts have been specified. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Payment Authorization is a Pending Purchase Order. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice out of Open Mode, if the Purchase Order or Purchase Order Line amount is unspecified. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from moving the Invoice to Posted Mode, if doing so would exceed the amount remaining on the Purchase Order or Purchase Order Line for that Invoice. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | Prevent the user from Posting an Invoice, if a Labor Item on the Invoice refers to a Shift Summary Labor Line whose start/stop date/time overlaps with another Shift Summary Labor Line within the system and both refer to the same employee ID. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | When a Credit Invoice or Credit/Re‐Invoice is moved out of Open Mode, move the Invoice to Pending Approval Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | When an invoice is Posted, Determine the GL accounts for the revenue for each Item on the Invoice and calculate and allocate the dollar amount associated with | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | BR | When an Invoice is Posted, log the Invoice Number as "Posted" with the date/time the Posting occurred and the person who posted it. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change an Invoice from Open to Posted Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Approved Mode to Open Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Approved Mode to Posted Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Approved Mode to Submitted Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Disapproved Mode to Open Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to change the selected Invoice from Pending Approval to Open Mode. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Allow a user to delete an Open Invoice. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Prevent an Invoice from going to Submitted or Posted Mode, total Invoice variance is greater than n% off the original value the Invoice, and the Invoice total amount is greater than Instead move the Invoice to Pending Approval Mode. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Prevent the user from moving the Invoice out of Open Mode, if doing so would exceed the amount remaining on the Purchase Order or Purchase Order Line for that Invoice. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | Prevent the user from moving the Invoice to Posted Mode, if the Invoice contains one or more Packages without a specified Price per Unit. | EQ | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | When a Credit Invoice is Posted, if the Credit Invoice is marked as Lost Revenue, do not re‐add the quantities of the Credited Items back to the Staging Area. Instead, mark the quantities of the items as uninvoiceable. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | When a Credit Invoice is Posted, if the Credit Invoice is not marked as Lost Revenue, re‐add the quantities of the Credited Items back to the Staging Area. | EI | 1
Invoicing | Invoice Management and Workflow |  |  | Y | UA | When an Invoice is deleted, log the Invoice Number as "No Longer Needed". | EI | 1
Invoicing | Invoice Queue |  |  | N | LIST | Allow a user to filter the Invoices in the Invoice Queue by Status (e.g., Open, Pending Approval, Approved, Disapproved, Submitted, Posted). |  | 1
Invoicing | Invoice Queue |  |  | N | UA | Allow a user to filter the Invoices in the Invoice Queue by Date. |  | 1
Invoicing | Invoice Queue |  |  | N | UA | Allow a user to filter the Invoices in the Invoice Queue by Type (e.g., Invoice, Prepayment Invoice, Credit Invoice, Credit Reinvoice) |  | 1
Invoicing | Invoice Queue |  |  | Y | BR | Allow a user to filter the Invoices in the Invoice Queue by Customer Site Keyword search (on Customer Site), Customer Number, Payment Authorization, Creation Date Range, Posted Data Range, Invoice Number, Branch Oracle Code, Invoice Mode (e.g., Open, Post | EQ | 1
Invoicing | Invoice Queue |  |  | Y | BR | List all Invoices [Invoice Queue] | EQ | 1
Invoicing | Invoice Queue |  |  | Y | UA | Allow a user to open an Invoice from the Invoice Queue. | EI | 1
Invoicing | Invoice Queue |  |  | Y | UA | Sort the Invoices in the Invoice Queue by Invoice Number (descending) | EQ | 1
Invoicing | Re‐Invoices |  |  | N | BR | Allow a user to create a Re‐Invoice from from a Credit Invoice. |  | 1
Invoicing | Re‐Invoices |  |  | Y | BR | If a user creates a Re‐Invoice from an Invoice with a Custom View, automatically create a Custom View Line Items for the Re‐Invoice, and set the Description of each to the Description of each Custom View Line Item of the source Invoice, and the Dollar Amo | EQ | 1
Invoicing | Re‐Invoices |  |  | Y | BR | When a Credit Invoice mode changes, if the Credit Invoice has a corresponding Re‐Invoice, automatically change the mode of its corresponding Re‐Invoice. | EI | 1
Invoicing | Re‐Invoices |  |  | Y | UA | When a Re‐Invoice is authorized by the same Purchase Order or Purchase Order Line of the source Invoice, when recalculating the Remaining Value of the Purchase Order or Purchase Order Line, also calculate the value of Credit of the source Invoice. | EQ | 1
Invoicing | Re‐Invoices |  |  | Y | UA | When a Re‐Invoice mode changes, automatically change the mode of its corresponding Credit Invoice. | EQ | 1
Invoicing | Staging Area | Adding Staging Area Lines to Invoice |  | N | BR | Allow a user to create a new Invoice from the selected Staging Area Line(s). |  | 1
Invoicing | Staging Area |  |  | N | UA | If the Invoice has a Custom View, recalculate the Variance when an Item is added from the Staging Area. |  | 1
Invoicing | Staging Area |  |  | N | UA | If the Invoice is authorized by a Purchase Order or Purchase Order Line, recalculate the Remaining Value when an Item is added from the Staging |  | 1
Invoicing | Staging Area |  |  | Y | BR | Allow a user to select one or multiple Shifts in the Staging Area. | EQ | 1
Invoicing | Staging Area |  |  | Y | BR | Allow a user to select one or multiple Staging Area lines. | EQ | 1
Invoicing | Staging Area |  |  | Y | BR | Automatically adjust Labor and Equipment time entries to their saved Gate Log Reconciliation values, if applicable. | EQ | 1
Invoicing | Staging Area |  |  | Y | BR | If a user moves one or more selected Shifts or Jobs to an Invoice, and the Staging Area filter is set to show "Only Labor Items", only move the Labor items within the selected Shifts or Jobs to the Invoice. | EQ | 1
Invoicing | Staging Area |  |  | Y | BR | Prevent the user from moving a Labor item to an Invoice if the Labor item refers to a Pending Employee. | EQ | 1
Invoicing | Staging Area |  |  | Y | BR | Provide a visual cue to the user if a Labor Item in the Staging Area refers to a Pending Employee. | EQ | 1
Invoicing | Staging Area |  |  | Y | BR | Warn the user when moving a Labor or Equipment item to an Invoice if the Customer Site requires Labor / Equipment Time Reconciliations that have not been completed. | EQ | 1
Invoicing | Staging Area |  |  | Y | BR | When Items are moved from the Staging Area to an Invoice, reduce the invoicable quantities of the Items, and refresh the Staging Area to reflect the remaining Items and quantities. | EI | 1
Invoicing | Staging Area |  |  | Y | UA | Allow a user to move the selected Items in the Staging Area (or those within the selected Shifts or Jobs) to an Open invoice. | EI | 1
Invoicing | Staging Area |  |  | Y | UA | Allow a user to select one or multiple Jobs in the Staging Area. | EQ | 1
Invoicing | Staging Area |  |  | Y | UA | Prevent a user from moving Staging Area Items to a Credit Invoice. | EQ | 1
Invoicing | Staging Area |  |  | Y | UA | Prevent a user from moving Staging Area Items to a Re‐Invoice. | EQ | 1
Invoicing | Staging Area |  |  | Y | UA | When an Item is added from the Staging Area, save the Invoice. | EI | 1
Invoicing | Staging Area | Warnings and Adjustments |  | N | BR | Warn the user if the Staging Area contains two or more Labor or Equipment time entries that overlap. |  | 1
Invoicing | Staging Area |  |  | Y | BR | Automatically adjust Labor and Equipment time entries down to a contract‐specified maximum quantity, if one exists. | EI | 1
Invoicing | Staging Area |  |  | Y | BR | Automatically adjust Labor and Equipment time entries up to a contract‐specified minimum quantity, if one exists. | EI | 1
Invoicing | Staging Area |  |  | Y | BR | If a material item has a quantity that has been marked as destroyed, automatically split the item into Used Item and Destroyed Item staging area items, as needed. | EI | 1
Invoicing | Staging Area |  |  | Y | BR | Allow a user to view a Staging Area Item's Item Code, Quantity available for invoicing, and Unit of Measure. | EQ | 1
Invoicing | Staging Area |  |  | Y | BR | List all the uninvoiced items for that Customer Site, by the Item Description. | EQ | 1
Invoicing | Staging Area |  |  | Y | BR | Organize the Staging Area items by Job (chronologically, from oldest to most recent), by Shift within the Job (chronologically, from oldest to most recent), by Item Type within the Shift, and by Description within the Item Type. | EQ | 1
Invoicing | Staging Area |  |  | Y | LIST | Allow a user to search for a Job by entering a Job Number, and navigate the user to that Job in the Staging Area. | EQ | 1
Invoicing | Staging Area |  |  | Y | UA | Allow a user to filter the Staging Area by Payment Authorization, initializing the Payment Authorization to that of the Customer Site/Payment Authorization selected in the Inbox Queue, or of the current Payment Authorization of the Invoice selected in the | EQ | 1
Invoicing | Staging Area |  |  | Y | UA | Allow a user to filter the Staging Area to show either: (a) All Items (b) Only Labor Items | EQ | 1
Payroll | Employee Payroll Lines |  |  | N | BR | Allow a user to delete an Employee Payroll Line. |  | 1
Payroll | Employee Payroll Lines |  |  | N | BR | Calculate special payment cases (e.g., overtime, double‐time, holiday time, etc.). |  | 1
Payroll | Employee Payroll Lines |  |  | N | BR | List Employee Payroll Lines |  | 1
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from changing a billable category to a non‐billable category. |  | 1
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from creating a new Employee Payroll Line for a billable category. |  | 1
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from deleting an Employee Payroll Line for billable time. |  | 1
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from deleting an Employee Payroll Line in a closed Payroll Period. |  | 1
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from editing an Employee Payroll Line in a closed Payroll Period. |  | 1
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from increasing the payable time for a billable Payroll record above the calculated value. |  | 1
Payroll | Employee Payroll Lines |  |  | N | BR | Prevent a user from specifying a date beyond the end of the Payroll Period. |  | 1
Payroll | Employee Payroll Lines |  |  | N | LIST | Allow a user to create a new Employee Payroll Line. |  | 1
Payroll | Employee Payroll Lines |  |  | N | UA | Allow a user to edit an Employee Payroll Line. |  | 1
Payroll | Employee Payroll Lines |  |  | N | UA | Prevent a user from changing a non‐billable category to a billable category. |  | 1
Payroll | Employee Payroll Lines |  |  | N | UA | Sort Employee Payroll Lines |  | 1
Payroll | Employee Payroll Periods | Listing | Special Payment Calculations | Y | BR | Automatically calculate special payment cases (e.g., overtime, double‐time, etc.) for added, edited, and deleted records. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Display the calculated straight time, overtime, double‐time and total hours durations for the the Employee Payroll Week. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | If an Employee with an Employee Type of "Part‐Time Professional" has one or more Employee Payroll Records for a day, and the total duration of all Employee Payroll records is greater than 0:00, automatically calculate that Employee's Duration at 8:00 hour | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | UA | Alow a user to access an existing Employee Payroll Record. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Aggregate the Employee Payroll Records by date, Pay Type, Home Branch, Entered Branch, Job (if applicable), and Shift (if applicable), summing the Duration. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Allow a user to add a new Employee Payroll Record. | EI | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Filter the Employee Payroll Records by selected Employee and selected Employee Payroll Week, for all Employee Payroll Records manually entered by the Branch, plus all Employee Payroll Records for an Employee of the Branch. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | List the Employee Payroll Records within the Employee Payroll Week, displaying date, Pay Type, Job (if applicable), and Shift (if applicable), Entered‐By Branch, and Duration (in hours:minutes). | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | LIST | Sort the Employee Payroll Records by date (ascending), then by Pay Type (ascending by Pay Type Code). | EQ | 1
Payroll | Employee Payroll Periods | Viewing/Editing | Duration | N | BR | Prevent the user from specifying the Duration of an Automatic Employee Payroll Record to less than zero, or more than the value recorded on the Shift Summary. |  | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent the user from specifying the Duration of an Employee Payroll Record to any value that would make the sum of all Employee Payroll Records of the specified Pay Type on the specified Date for the Branch who created the Employee Payroll Record be less | EQ | 1
Payroll | Employee Payroll Periods |  | Pay Type | Y | BR | Prevent the user from changing the Pay Type of a Manual Employee Payroll Record to an Automatic Pay Type. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent the user from changing the Pay Type of an Automatic Employee Payroll Record. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent the user from specifying a Pay Type that is an Automatic Employee Pay Type. | EQ | 1
Payroll | Employee Payroll Periods |  | Shift Summary Number | Y | BR | Prevent the user from entering a Shift Summary Number for an Employee Payroll Record if the Pay Type is not "Manual Billable" type. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from deleting a Manual Employee Payroll Record not created at the user's Branch. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from deleting an Automatic Employee Payroll Record. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from editing a Manual Employee Payroll Record not created at the user's Branch. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from editing an Automatic Employee Payroll Record. | EQ | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Date.
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Duration.
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Employee.
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Pay Type.
Payroll | Employee Payroll Periods |  |  | Y | BR | Prevent a user from saving an Employee Payroll Record without a specified Shift Summary, if the Pay Type is "Manual Billable".
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Manual Employee Payroll Record is deleted, create a Manual Employee Payroll Records with a negative‐Duration of the existing Manual Employee Payroll Record. | EI | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Manual Employee Payroll Record is edited, automatically create a Manual Employee Payroll Records with a negative‐ Duration of the existing Manual Employee Payroll Record, and one with a positive‐Duration of the new Manual Employee Payroll Record. | EI | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Shift Summary Labor Line is recorded by the system as added, create one (or two, if the Shift Summary Labor Line spans midnight of Sunday night of the time zone of the Employee's Home Branch) Automatic Employee Payroll Records, including all time f | EI | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Shift Summary Labor Line is recorded by the system as deleted, create an Automatic Employee Payroll Record for every existing, current, related Automatic Employee Payroll Record, with a negative‐Duration of the existing Automatic Employee Payroll R | EI | 1
Payroll | Employee Payroll Periods |  |  | Y | BR | When a Shift Summary Labor Line is recorded by the system as edited, create two Automatic Employee Payroll Records for every existing, current, related Automatic Employee Payroll Record, one with a negative‐Duration of the existing Automatic Employee Payr | EI | 1
Payroll | Employee Payroll Periods |  |  | Y | UA | Allow a user to delete an existing Employee Payroll Record. | EI | 1
Payroll | Employee Payroll Periods |  |  | Y | UA | Allow a user to edit an existing Employee Payroll Record, including the Employee, the date worked, the Pay Type, the Duration in hours:minutes, and the Shift Summary Number. | EI | 1
Payroll | Employee Payroll Periods |  |  | N | BR | Allow a user to create a new Employee Payroll Period. |  | 1
Payroll | Employee Payroll Periods |  |  | N | BR | Allow a user to delete an Employee Payroll Period. |  | 1
Payroll | Employee Payroll Periods |  |  | N | BR | Automatically calculate differences between prior period Payroll data imported from Shift Summaries, and current period Payroll data imported from Shift Summaries, and generate offsetting records. |  | 1
Payroll | Employee Payroll Periods |  |  | N | BR | Automatically populate Employee Payroll Periods list. |  | 1
Payroll | Employee Payroll Periods |  |  | N | BR | List Employee Payroll Periods. |  | 1
Payroll | Employee Payroll Periods |  |  | N | BR | List Pending Employee Payroll Periods |  | 1
Payroll | Employee Payroll Periods |  |  | N | LIST | Allow a user to select an Employee Payroll Period. |  | 1
Payroll | Employee Payroll Periods |  |  | N | LIST | Sort Employee Payroll Periods. |  | 1
Payroll | Employee Payroll Periods |  |  | N | UA | Allow a user to access an Employee Payroll Period. |  | 1
Payroll | Employee Payroll Periods |  |  | N | UA | Allow a user to match a Pending Employee from a Pending Employee Payroll Period to an Oracle Employee. |  | 1
Payroll | Employee Payroll Periods |  |  | N | UA | Allow a user to see Payroll data for one of its Employees from Payroll data entered at another Branch. |  | 1
Payroll | Employee Payroll Periods |  |  | N | UA | Prevent a user from creating an Employee Payroll Period for an Employee that already has an Employee Payroll Period. |  | 1
Payroll | Employee Payroll Periods |  |  | N | UA | Prevent a user from deleting an Employee Payroll Period that contains billable time imported from a Shift Summary. |  | 1
Payroll | Employee Payroll Periods |  |  | N | UA | Prevent a user from editing Payroll data for one of its Branch's Employees, if the Payroll data was entered at another Branch. |  | 1
Payroll | Employee Payroll Weeks |  |  | Y | BR | Prepopulate the Employee Payroll Weeks to automatically appear within a Payroll Week, which is a combination of Employees with Automatic Employee Payroll Records for the Payroll Week (i.e., those Employees with billable hours for the current Branch), and | EQ | 1
Payroll | Employee Payroll Weeks |  |  | Y | BR | Sort the Employee Payroll Weeks by Last Name (ascending), then by First Name (ascending) | EQ | 1
Payroll | Employee Payroll Weeks |  |  | Y | LIST | List the Employee Payroll Weeks within a Payroll Week, including First Name, Last Name, Employee Number, Home Branch Code, Employee Type (i.e., Regular or Part‐Time Professional), Straight Time Hours, Overtime Hours, Double‐Time Hours, Input Branch and To | EQ | 1
Payroll | Employee Payroll Weeks |  |  | Y | UA | Allow a user to access an Employee Payroll Week. | EQ | 1
Payroll | Employee Selection |  |  | Y | BR | Filter the Employees by those who were Active (according to Oracle) on or after Monday of the previous week. | EQ | 1
Payroll | Employee Selection |  |  | Y | LIST | List Employees, including First Name, Last Name, Employee Number, Employee Type (i.e., Regular or Part‐Time Professional). | EQ | 1
Payroll | Employee Selection |  |  | Y | UA | Allow a user to filter Employees by Branch, default to the Home Branch. | EQ | 1
Payroll | Employee Selection |  |  | Y | UA | Allow a user to select an Employee. | EQ | 1
Payroll | Employee Selection |  |  | Y | UA | Allow a user to sort Employees by Employee ID (ascending), or by Last Name (ascending)/First Name (ascending), default by Last Name/First Name.@$ | EQ | 1
Payroll | Payroll Periods |  |  | N | BR | Sort Payroll Periods in descending order by date. |  | 1
Payroll | Payroll Periods |  |  | N | LIST | List Payroll Periods. |  | 1
Payroll | Payroll Periods |  |  | N | UA | Allow a user to access an existing Payroll Period. |  | 1
Payroll | Payroll Periods |  |  | N | UA | Allow a user to select a Payroll Period. |  | 1
Payroll | Payroll Periods |  |  | Y | UA | Allow a user to access the current Payroll Week. | EQ | 1
Payroll | Payroll Weeks |  |  | Y | UA | Allow a user to select a Payroll Week by specifying a date within the Payroll Week (Monday to Sunday). | EQ | 1
Payroll | Posting |  |  | Y | BR | Allow for an external system/process to flag each Employee Payroll Record as having been imported into Oracle as of a provided date. | EQ | 1
Administration | A/C Transaction File |  |  | Y |  |  | ILF | 1
Administration | Branch Contractor |  |  | Y |  |  | ILF | 1
Administration | Contract Master |  |  | Y |  |  | ILF | 1
Administration | Custom Invoice |  |  | Y |  |  | ILF | 1
Administration | Customer Master |  |  | Y |  |  | ILF | 1
Administration | Customer-Invoice Master |  |  | Y |  |  | ILF | 1
Administration | Discount Master |  |  | Y |  |  | ILF | 1
Administration | Employee Master |  |  | Y |  |  | ILF | 1
Administration | GateLog |  |  | Y |  |  | ILF | 1
Administration | General Leader Master |  |  | Y |  |  | ILF | 1
Invoicing | Inventory Trans File |  |  | Y |  |  | ILF | 1
Invoicing | Invoice |  |  | Y |  |  | ILF | 1
Invoicing | Invoice Queue |  |  | Y |  |  | ILF | 1
Invoicing | Labour Invoice |  |  | Y |  |  | ILF | 1
Invoicing | Package |  |  | Y |  |  | ILF | 1
Invoicing | Party Ledger Master |  |  | Y |  |  | ILF | 1
Invoicing | Payment AuthMaster |  |  | Y |  |  | ILF | 1
Payroll | Payroll Details |  |  | Y |  |  | ILF | 1
Payroll | Payroll Transaction |  |  | Y |  |  | ILF | 1
Invoicing | Product Master |  |  | Y |  |  | ILF | 1
Invoicing | PurchaseOrder |  |  | Y |  |  | ILF | 1

## Eff-Modulewise
[8 empty] | Factor | 5.5
Sum of No |  | Trans.Type
Category | SubCategory | EI | EO | EQ | ILF | (blank) | Grand Total | Total Points | Days
Administration | A/C Transaction File |  |  |  | 1 |  | 1
| Branch Contractor |  |  |  | 1 |  | 1
| Branch Contractors | 3 | 1 | 4 |  |  | 8
| Contract Master |  |  |  | 1 |  | 1
| Custom Invoice |  |  |  | 1 |  | 1
| Customer Gate Log Reconciliations | 2 |  | 7 |  | 2 | 11
| Customer Master |  |  |  | 1 |  | 1
| Customer Purchase Orders | 7 |  | 26 |  | 2 | 35
| Customer-Invoice Master |  |  |  | 1 |  | 1
| Discount Master |  |  |  | 1 |  | 1
| Employee Master |  |  |  | 1 |  | 1
| Employees |  |  | 4 |  |  | 4
| Field Service Settings |  |  | 1 |  |  | 1
| GateLog |  |  |  | 1 |  | 1
| General Leader Master |  |  |  | 1 |  | 1
| Month End Close |  |  | 1 |  | 1 | 2 | 1 | 5.5
| Pending Customers |  |  |  |  | 1 | 1 | 1 | 5.5
| Pending Employees |  |  | 1 |  |  | 1 | 8 | 44
| Synchronization |  |  | 3 |  |  | 3 | 1 | 5.5
| Terms & Conditions Contract |  |  | 3 |  |  | 3 | 1 | 5.5
Invoicing | Contract Selection |  |  | 5 |  | 4 | 9 | 9 | 49.5
| Credit Invoices | 2 |  | 3 |  |  | 5 | 1 | 5.5
| Custom Invoice Views | 10 |  | 17 |  | 5 | 32 | 33 | 181.5
| Inbox Queue |  |  | 5 |  |  | 5 | 1 | 5.5
| Inventory Trans File |  |  |  | 1 |  | 1 | 1 | 5.5
| Invoice |  |  |  | 1 |  | 1 | 1 | 5.5
| Invoice Formatting and Printing |  | 1 | 5 |  | 1 | 7 | 4 | 22
| Invoice Lines | 39 |  | 112 |  | 35 | 186 | 1 | 5.5
| Invoice Management and Workflow | 18 |  | 30 |  | 10 | 58 | 1 | 5.5
| Invoice Queue | 1 |  | 3 | 1 | 3 | 8 | 1 | 5.5
| Labour Invoice |  |  |  | 1 |  | 1 | 1 | 5.5
| Package |  |  |  | 1 |  | 1 | 1 | 5.5
| Party Ledger Master |  |  |  | 1 |  | 1 | 3 | 16.5
| Payment AuthMaster |  |  |  | 1 |  | 1 | 3 | 16.5
| Product Master |  |  |  | 1 |  | 1 | 5 | 27.5
| PurchaseOrder |  |  |  | 1 |  | 1 | 5 | 27.5
| Re‐Invoices | 1 |  | 3 |  | 1 | 5 | 27 | 148.5
| Staging Area | 6 |  | 16 |  | 4 | 26 | 5 | 27.5
Payroll | Employee Payroll Lines |  |  |  |  | 14 | 14 | 1 | 5.5
| Employee Payroll Periods | 8 |  | 17 |  | 15 | 40 | 1 | 5.5
| Employee Payroll Weeks |  |  | 4 |  |  | 4 | 6 | 33
| Employee Selection |  |  | 5 |  |  | 5 | 151 | 830.5
| Payroll Details |  |  |  | 1 |  | 1 | 48 | 264
| Payroll Periods |  |  | 1 |  | 4 | 5 | 5 | 27.5
| Payroll Transaction |  |  |  | 1 |  | 1 | 1 | 5.5
| Payroll Weeks |  |  | 1 |  |  | 1 | 1 | 5.5
| Posting |  |  | 1 |  |  | 1 | 1 | 5.5
Grand Total |  | 97 | 2 | 278 | 21 | 102 | 500 | 1 | 5.5
[8 empty] | 1 | 5.5
[8 empty] | 1 | 5.5
[8 empty] | 4 | 22
[8 empty] | 22 | 121
[8 empty] | 25 | 137.5
[8 empty] | 4 | 22
[8 empty] | 5 | 27.5
[8 empty] | 1 | 5.5
[8 empty] | 1 | 5.5
[8 empty] | 1 | 5.5
[8 empty] | 1 | 5.5
[8 empty] | 1 | 5.5
[8 empty] | 500 | 2750
Note on L4: Hari Prasad: This is rough estimate. Transaction and static points are treated equal

## Eff-ModuleReqTypewise (hidden)
Count of FPA |  |  | Req Type
In Scope | Category | SubCategory | BR | LIST | UA | (blank) | Grand Total
N | Administration | Customer Gate Log Reconciliations
Customer Purchase Orders
Month End Close
Pending Customers
| Invoicing | Contract Selection
Custom Invoice Views
Invoice Formatting and Printing
Invoice Lines
Invoice Management and Workflow
Invoice Queue
Re‐Invoices
Staging Area
| Payroll | Employee Payroll Lines
Employee Payroll Periods
Payroll Periods
Y | Administration | Branch Contractor |  |  |  | 1 | 1
|  | Branch Contractors | 2 | 1 | 5 |  | 8
|  | Customer Gate Log Reconciliations | 6 | 1 | 2 |  | 9
|  | Customer Purchase Orders | 22 | 2 | 9 |  | 33
|  | Employees |  | 1 | 3 |  | 4
|  | Field Service Settings | 1 |  |  |  | 1
|  | GateLog |  |  |  | 1 | 1
|  | Month End Close | 1 |  |  |  | 1
|  | Pending Employees |  |  | 1 |  | 1
|  | Synchronization | 3 |  |  |  | 3
|  | Tax Master |  |  |  | 1 | 1
|  | Terms & Conditions Contract | 3 |  |  |  | 3
| Invoicing | A/C Transaction File |  |  |  | 1 | 1
|  | Contract Master |  |  |  | 1 | 1
|  | Contract Selection | 2 | 1 | 2 |  | 5
|  | Credit Invoices | 3 |  | 2 |  | 5
|  | Custom Invoice |  |  |  | 1 | 1
|  | Custom Invoice Views | 24 |  | 3 |  | 27
|  | Customer Master |  |  |  | 1 | 1
|  | Customer-Invoice Master |  |  |  | 1 | 1
|  | Discount Master |  |  |  | 1 | 1
|  | General Leader Master |  |  |  | 1 | 1
|  | Inbox Queue | 1 | 1 | 2 |  | 4
|  | Inventory Trans File |  |  |  | 1 | 1
|  | Invoice |  |  |  | 1 | 1
|  | Invoice Formatting and Printing | 1 |  | 4 |  | 5
|  | Invoice Lines | 115 | 3 | 28 |  | 146
|  | Invoice Management and Workflow | 34 |  | 14 |  | 48
|  | Invoice Queue | 2 |  | 2 | 1 | 5
|  | Labour Invoice |  |  |  | 1 | 1
|  | Package |  |  |  | 1 | 1
|  | Party Ledger Master |  |  |  | 1 | 1
|  | Payment AuthMaster |  |  |  | 1 | 1
|  | Product Master |  |  |  | 1 | 1
|  | PurchaseOrder |  |  |  | 1 | 1
|  | Re‐Invoices | 2 |  | 2 |  | 4
|  | Staged-Invoice |  |  |  | 1 | 1
|  | Staging Area | 14 | 1 | 7 |  | 22
|  | Unit Master |  |  |  | 1 | 1
| Payroll | Employee Master |  |  |  | 1 | 1
|  | Employee Payroll Periods | 21 | 1 | 3 |  | 25
|  | Employee Payroll Weeks | 2 | 1 | 1 |  | 4
|  | Employee Selection | 1 | 1 | 3 |  | 5
|  | Payroll Details |  |  |  | 1 | 1
|  | Payroll Periods |  |  | 1 |  | 1
|  | Payroll Transaction |  |  |  | 1 | 1
|  | Payroll Weeks |  |  | 1 |  | 1
|  | Posting | 1 |  |  |  | 1
Grand Total |  |  | 261 | 14 | 95 | 24 | 394