## Slide 1: Engineering to Scale Height
Project Management Backbone Processes

## Slide 2: Prelude
  BFL are India’s market leaders in designing, manufacturing and commissioning small hydro power plants.
  World class technology – Collaboration with Boving UK, Kvaerner and GE
BFL has ventured into global markets recently and is planning to expand its base significantly. To support its growth plans, capitalize opportunities and meet different demands, BFL is looking forward to create a benchmark back bone processes for its end to end operations, basis Project Management framework.

## Slide 3: Perceptive Learning Consultants

## Slide 4: Our Approach
Recommendations of PMO Framework is based on Industry Neutral Project Best Practices from
  PMBOK V5 (PMI),
  PRINCE2 2009 (The UK Cabinet) and
  Agile Project Management Practices
  ScrumAlliance.com
  OPM3 v3 of PMI

## Slide 5: Principle behind this approach
Why this framework can work for you?
  You are a project company. Your success depends on the success of your projects.
Why PMO?
  PMO is accountable for overall Delivery and success of the project (not just efforts / actions)
  Provides infrastructure to project managers to manage the project.
  Any other department within the organization is responsible mainly for related planning & its execution within its domain (seldom for the larger outcome)
Why management by exception?
  It saves time for Senior management and gives flexibility to junior management to deliver project results.
  Facilitates timely escalations and faster decision making
Why refer to 5 standards/frameworks?
  These standards have evolved over 5 decades and reflects project management solutions in the current context.
  It helps explore possibilities within the framework and then tuning it your organization’s needs

## Slide 6: Our Rationale:
Why I am referring to 5 standards?
Why PMO?
Why some specific roles?
Why this framework can work for you?
Why management by exception?
Why to differentiate between Commitment and Involvement of resources.

## Slide 7: A comparison of Sectors that Report Delivery on Time, Budget, Scope
Organization running on PMO had
85% of Project Running within budget
80% of Project Running within schedule.
Source: Project Management Survey Report July 2013 - Strategies to capture business value
PMI-KPMG Study on Drivers for Success in Infrastructure Projects 2010

## Slide 8: PMO Domain of Work
Standards, Methodologies and Processes
  Methodology definition; metrics definition; process development and improvement
Project/Program Delivery Management
  Define the business goals; resource management; schedule/cost/scope management; business realization management; risk management; stakeholder management; communications; project integration
Talent Management
  Talent Pool, Training, career paths, career development, capability/skills development and certifications/qualifications/credentials
Governance and Performance Management
  Performance reporting; issue escalation; information distribution; metrics/KPIs; compliance; financial management; PMO performance management
Organizational Change Management
  Customer/stakeholder satisfaction; managing resistance; readiness assessment; stakeholder management; communications
Administration and Support
  Tools (provisioning/implementation/support); consulting; IT/IS support
Knowledge Management
  Defining knowledge management policies, managing intellectual collateral/property, lessons learned, content management and collaboration
Strategic Planning
  Confirming strategic priorities; defining business goals and aligning to initiatives; environmental scanning; opportunity analysis
Portfolio Management
  Prioritization; strategic alignment; portfolio reporting; resource management allocation; opportunities and investment analysis; risk management; benefits realization tracking/reporting

## Slide 9: Few companies we have assisted

## Slide 10: Few companies we have assisted

## Slide 11: Agenda
PMO Roles & Responsibilities
PMO Skelton Processes
Management by Exceptions
Project Organization Chart
Next Steps

## Slide 12: PMO Responsibilities
PMO is a function within organization.
Like any other function this has a Head of Function.
PMO Responsibilities should be rendered by PMO Head and his team of project managers to the Assigned Project Manager or to the Organization.
Key Responsibilities:
Preparation
Planning
Execution
Governance

## Slide 13: PMO Responsibilities
Before Initiation of Phase / Project:
    Competency building of Project Managers
    Help organization in evaluating new business opportunities
    Creating knowledge infrastructure for Project Management
Initiation of Phase / Project:
    Internal Project Sponsoring (Project Charter)
    Allocating a dedicated and trained project manager
    Identify & evaluate project inherent risks
    Refer to lessons learned from previous projects
    Ensure business case and feasibility study has been done else feasibility study is the first Phase of the project

## Slide 14: PMO Responsibilities
Planning of Phase/Project
    Helping project manager in making a project plan of execution and governance.
    Approving and allocating resources for project
    Negotiate with functional heads for availability of required project resources
    Reviewing/approving project plan
    Prepare project management infrastructure (templates, checklist, forms, guidelines, reporting systems)
    Help project manager in selecting a project management approach
    Setup appraisal system

## Slide 15: PMO Responsibilities
Execution of Phase/Project
    Provide Infrastructure to Project Manager
    If required get resources from market for a project
    Mentoring and Coaching Project Manager
    Maintain Project Records and permission for all projects
    Maintain Organization Process Assets
    Human Resource management at organization level
    Inventory Management at organization level

## Slide 16: PMO Responsibilities
Governance of Phase/Project:
  Review phase/project status/progress with project manager
  Prepare project dashboard for entire organization
  Review the status with CEO and make go/no-go decision for future work
  Change Approval within threshold limits Or Seek approval from CEO.
  Perform Project Quality and Configuration Audit
  Perform Project Risk Audit
  Organizational Level Project Risk Profiling
  Coordination with account, supply-chain, quality team about payment, purchase quality, material availability

## Slide 17: PMO Head Responsibilities
Head of the PMO Ensure that PMO Responsibilities are taken care with the help of his team of Project Managers.
If PMO head is doing some project then
    Another person should sponsor his projects
    Another person should review and approve his project plans
    Another person should Audit his projects
    He can represent his projects before CEO
Ideally this person should have authority and respect within the organization. And he should be kept away from doing projects.

## Slide 18: Project Manager’s Responsibilities
  Conduct project Kickoff
  Prepare/Update project plan
  Get approval from project board and baseline project plan
  Manage project within allowed thresholds
  Brief project progress to project board on periodic basis
  Ensure vendors are delivering as per contract
  Team motivation
  Process compliance
  Deliver project product as per specification
  Assessment of Change Request within threshold limit OR Seek Approval from Project Board
  Maintain Project Documents
  Maintain project records
  Appraise human resources working on project
  Get Project Sign off
Ideally this person should be BFL senior employee trained on PM frameworks.

## Slide 19: Senior User Responsibilities
  Provide customer quality expectations and define acceptance criteria
  Ensure project’s outcome is useful
  Resolve user requirements and priority conflicts
  Ensure user experts required are available (if needed)
  Brief and advise users on requirement decisions
  Provide user view on follow-on action recommendations
  Project Assurance from user perspective.
Ideally this person should be a representative from BFL’s client side

## Slide 20: Senior Supplier Responsibilities
  Assess and confirm viability of the project approach
  Ensure design is realistic
  Advise on the selection of design, development and acceptance methods
  Ensure supplier resources are available
  Safeguarding complete solutions and make decision on escalated issues
  Resolve supplier requirements and priority conflicts
  Brief non-technical management on supplier aspects
  Ensure quality procedures are used correctly
  Project Assurance from supplier perspective
Ideally from BFL Design Team or major vendor side

## Slide 21: Project Planning
Scope
Time
Cost
Requirement
Understanding
Solutioning
Scope Baselining
Activity Identification & Sequencing
Estimate
Resource & Duration
Schedule Development
Activity Cost
Estimation
Budgeting with Consolidated Cost
Negotiate Scope, Time, Cost, Quality
Add all other cost
Baseline Scope, Schedule, Cost, Quality Expectations
Quality
Project & Product Quality Planning
Cost of Quality
P2
P5
P6
P7
P8
P9
P10
P11
P24
P3
P4
Configuration Management
Integration
P1

## Slide 22: Project Planning
Risk
Risk Identification
Risk Response Planning
Cost of Risk Management
Human Resource
HR & Staff Management Planning
Cost/Schedule of Training/Hiring/ Appraisal etc.
Procurement
Procurement Planning
Cost/Schedule of Contracting P/S/R
Communication
Communication Planning & Technology
Cost of Communication
Stakeholder
Stakeholder Management Planning
Cost of Stakeholder Engagement
Consolidate All Costs / Scheduled Activities
P12
P13
P14
P15
P16
P17
P18
P19
P20
P21
P22
P23
P24

## Slide 23: Project Execution
Human Resources
Procurement
Communication
Stakeholder
Contracting
Resource Acquisition
Team Capability Building
Team & Work Management
Project Planned/Ad-hoc Communications
Routine Stakeholder Engagements
Quality
Quality/Configuration Audits
Integration
Work Authorization
Work Tracking/Coordination/Communication
E1
E2
E3
E4
E5
E6
E7
E8

## Slide 24: Project Governance : Project Level
Risk
Procurement
Communication
Contract P/S/R Management
Risk Reassessment
Risk Audits
Reassess Communication/
Engagement Needs
Quality
Product Testing by QA Team
Integration
Integrated Change Control
Work Monitoring/Controlling/Coordination/Communication
Report Preparation
Product Testing by Customer
Scope, Time, Cost
CST Variance Management
Quality Variance Management
G1
G2
G3
G4
G5
G6
G7
G8
G9
G10

## Slide 25: Project Governance : PMO Level
PMO Review Project Progress/ Status with PM
Addressing Impediments & Taking Decisions
Authorize Next Phase/ Project
Approve (Revised) Baseline
Share Lessons Learned with/from Other Projects
Org Level Project Metrics
PMO Review Project Progress/ Status with CEO
Stakeholder Engagement
Risk
Procurement
Stakeholder / Communication
Quality
Integration
G1
Org Level Risk Management
Org Level Vendor & Inventory Control
G2
G3
G4
G5
G6
G7
G8
G9
G10

## Slide 26: Project Initiation
Prepare Project Charter
Identify Stakeholders
Risk
Integration
Stakeholders
I1
I2

## Slide 27: Project Closure
Each Vendor Contract Closing
Customer Sign Off
Phase or Project Closure
Procurement
Integration
C1
C2
C3

## Slide 28: Umbrella Processes
Communication & Stakeholder Engagement
Project Quality & Product Quality
Configuration Management

## Slide 29: Management by Exceptions
Project Board
CEO
Project Board
Project Manager
Team Leaders/ Vendors
Project Level Thresholds of S, T, C, Q
Phase Level Thresholds of S, T, C, Q
Workpackage Level Thresholds of S, T, C, Q
PMO Head
Senior User
Senior Supplier
S, T, C, Q: Scope, Time, Cost, Quality

## Slide 30: Project Organization Chart
CEO
PMO Head
Project Manager
Project Manager
Functional/ Operation Managers
Functional/ Technical Experts
Functional/ Technical Experts
Functional/ Operation Managers

## Slide 31: PMO & Departmental Services in P.L.C.
Directive-PMO
Contracting Experts
Design Experts
Supply Chain Experts
Manufacturing Experts
Erection & Commissioning Experts
Product Component Testing
Site Testing
1
2
3
4
6
5
7
Stage 1:
Contracts
Stage 2:
Design
Stage 3:
Supply Chain
Stage 4:
Manufacturing
Stage 5:
Erection & Commissioning
Project
Phases
Quality Experts

## Slide 32: Important Practices
Daily Standup
Sprint Planning
Retrospectives
Project Kanban Board

## Slide 33: Summary of Project Management Processes
Initiation (2)
Planning (24)
Execution (8)
Governance at Project Manager (10)
Governance at PMO Level (10)
Closing (3)
Scrum Best Practice (4)

## Slide 34: Optimizing Knowledge Inputs and Actions
Expert Judgment (EJ)
  Part time.
  Involved
  Provides Input/ share perspective
  Typical from outside of the organization or senior people
  Knowledge Driven
  Project Manager seeks EJ input based on the need
Project Team Member (PTM)
Full time
Committed
Chose options and Perform actions
Typical from within the organization.
5) Doers./ Action Driven
6) Project Manager expects PTM to produce project deliverables

## Slide 35: Define your PMO Metrics…
PMO Metrics can be like
Number of projects in organization vs managed by PMO
Increase in Utilization, Productivity,
Increased project Success rate,
Increased Customer satisfaction, Employee satisfaction,
Skills acquired by project staff,
Number of issues addressed
No of issues reduced by virtue of proper risk planning
% of project resources trained in PMO defined processes
Cost of setting up PMO and running the PMO vs value add of PMO
Average team size, average hourly rate, average training hours
Hours saved by PMO intervention,
Improved Staff Retention
Improved Project Planned/Forecasting vs Actual gaps
Change Management Efficiency
Risk Management Efficiency
………
......................

## Slide 36: Process- Relevancy Grid
Evaluate the relevancy of existing processes
Processes – Followed Low High | Luxury. Leave them aside. Let people do them at their on cost but show the team that these are not important | Strengthen them further
 | Leave them aside | Train the team Highlight importance Refine processes Develop systems around these processes
 | Low High Processes – Importance | 

## Slide 37: Process- Value Grid
Evaluate the value of existing processes
Processes - Followed Low High | Why people are following those if they are not important? Are they really useless or some value add is happening? | What data/information/ decision/ value add these processes are doing
 | Why do you think they are not important | What data/information/ decision/ value add is possible by these processes
 | Low High Processes - Importance | 

## Slide 38: Current status of Projects
Understand the current status & importance of projects
Current Status (Success) Low High | Do not touch resources unless they must be on some other important projects Keep doing them. Take the lessons | Do not touch resources Sit and discuss best practices from the PM
 | Cancel them | Identify what is required to make them successful
 | Low High Project - Importance | 

## Slide 39: PMO: Caution
PMO is NOT a silver bullet solution of your project management problems immediately.
PMO should not be just administrative function.
More it remains in the organization, more is the success rates of project.
Research Finding on PMO Failure
  21% perceived it as an overhead.
  17% Focus on processes.
  7% insufficient learning being transferred across programmes and projects.
  7% process inefficiencies due to different business units not being joined up.
Source: KPMG Project Management Survey Report July 2013 - Strategies to capture business value

## Slide 40: Next Steps
Project Management Workshops to all Managers/PM/ Departmental Heads
??
Procure/Install Automation Tools/ Automate processes as much possible
Processes Awareness/ Training
Training on Leadership / Interpersonal Skills
Map/Define PM processes to the implementation details
Phase 1
Defining Framework & fine tuning to BFL
Phase 2
Phase 3
Finalize a tool for Automation
Phase 4
Periodic Audit/Review of Implementation
Support

## Slide 41: Building BFL Internal Capability
We suggest PMO workshops for the PMO Head, Department Heads, Project Managers & Technical Staffs
This shall assist in …
Ensuring better buy in, facilitate constructive deliberations
Helping them understand the importance of this change initiative by BFL management
Helping BFL stake holders learn project management framework which will be the basis of PMO
Creating openness & share their processes and possible fine tuning in the light of new understanding

## Slide 42: Capability Building Roadmap
Project Management Framework
Project Risk Management
Scope Management
Project Scheduling
Project Cost Management
Project Quality Management
Project Resource Management
Project Communication & Stakeholder Management
Project Procurement Management
Integration Management

## Slide 43: Way Forward
PMO Objective Defined
PMO Champion/PMO Head identified
Training of all your relevant stakeholders
Ensuring buy in from the key stakeholders
Define Project Management Processes for BFL based on the Skelton agreed upon
Plugging BFL engineering processes and BFL Project management