## Projects-Sum
Project Details
# | Project_ID | Project Name | Description | Category | Project Type | Scrum Master | Accountable | Project Sponsor | Planned St Date | Planned End Date | Approx Duration | Revised Estimated End Date | Planned Efforts | Actual Efforts | Remarks
1 | KE.BBPE.1 | Benefit Bridge/Private Exchange |  | Development | Regular | Seshan | Veeren | Bharat
2 | KE.DWBI.1 | DWBI | BI Reporting & Dashboards for Keenan Insurance, Claim etc. | Dev & Support | Regular | Sampath | Seshan | Tanbeer
3 | KE.BBD.01 | Benefit Bridge Documentation |  | Documentation | Regular | Latha | Seshan | Bharat | 2015-11-19 | 2015-11-26
4 | KE.MP.001 | Market Place |  | Development | Regular | Seshan | Veeren | Bharat | 2015-07-15 | 2015-10-01 | 56 | 2015-10-30
5 | KE.BBCB.1 | Benefit Bridge/CBMS |  | Dev & Support | Regular | ?? | Seshan | Bharat |  | 2016-01-01
6 | KE.CEC.01 | Cadillac Excel Calculator |  | Dev & Support | Need Basis | Shreya | Seshan | Bharat
7 | KE.SERP.1 | SERP |  | Dev & Support | Need Basis | Seshan | Veeren | Sanjeev
8 | KE.PPCB.1 | Portal PCB Rel 6.0 |  | Full Testing | Regular | Sathish | Seshan | Sanjeev | 2015-05-15 | 2015-11-01
9 | KE.PQNR.1 | Portal QnR Revamp |  | Full Testing | Regular | Sathish | Seshan | Sanjeev | 2015-05-15 | 2015-11-01
10 | KE.PS.001 | Portal Sprint (#1) |  | Support/Ticket Based | Regular | Sathish | Seshan | Sanjeev | 2015-03-01 | 2015-11-06
11 | KE.IFP.01 | IFP Commission |  | Support | Need Basis | Shreya | Veeren | Bharat
12 | KE.DE.001 | Data Exchange |  | Dev & Support | Regular | Seshan | Veeren | Bharat | ?? | 2015-11-30
Note on A10: Hari Thapliyal: There is data here so think before removing

## Project-Dashboard
Project Dash Board
|  | Date | 2015-12-15
|  | Week# | 2015-51 |  |  |  | Overall |  |  |  | Current Sprint
ScrumBoard | # | Project_ID | Scrum Master | Sprint# | Sprint Dur (In Weeks) | # Resources | Planned Work | Actual Work | Remaining Work | % Complete | Planned Work | Actual Work | Remaining Work | % Complete
KE.DWBI.1-Online-ScrumBoard | 1 | KE.DWBI.1 | Sampath | Sprint04 | 2 | 9 | 740 | 510 | 52 | 92.97% |  |  |  | 0%
|  | DW-Support | Sampath | Sprint04 | 2 |  | 358 | 340 | 18 | 94.97% |  |  |  | 0%
KE.BBPE.1-Online-ScrumBoard | 2 | KE.BBPE.1 | Seshan |  |  |  | 313.7 | 143.2 | 0 | 100% |  |  |  | 0%
KE.MP.001-Online-ScrumBoard | 3 | KE.MP.001 | Seshan | Sprint07 | 1 | 0 | 174.5 | 76.5 | 98 | 43.84% |  |  |  | 0%
KE.BBD.01-Online-ScrumBoard | 4 | KE.BBD.01 | Nathan | Sprint03 | 1 | 4 | 293 | 261 | 54 | 81.57% | 72 | 16 | 56 | 22.22%
Note on D2: Enter Date Here to Refresh the Dashboard for different date

## PRA-Summary
Every Scrum Master Must Update this for his Projects Every Weekend or Retrospective from Online-ScrumBoard
Projet Resource Assignment
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role | Account
FFI | 2015-00 | Sprint00 | 0 | EMP#01 | 0 | Alexander | AX | QA | KE
FFI | 2015-00 | Sprint00 | 0 | EMP#02 | 0 | Andrew | AN | QA | KE
FFI | 2015-00 | Sprint00 | 0 | F0101 | 0 | Seshan T R | STR | SM | KE
FFI | 2015-00 | Sprint00 | 0 | F12175 | 0 | Thirupathi Kusa | TK | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F13676 | 0 | Ravindra Kumar Tiwary | RKT | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F14031 | 0 | Venkatasrinath Yelchuru | VY | Dev | SP
FFI | 2015-00 | Sprint00 | 0 | F14100 | 0 | Senthilvel C | SC | Dev | SP
FFI | 2015-00 | Sprint00 | 0 | F14101 | 0 | Nivedha C | NC | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F14177 | 0 | Vinoth M | VM | Dev | SP
FFI | 2015-00 | Sprint00 | 0 | F14279 | 0 | Sanjana S | SS | QA | KE
FFI | 2015-00 | Sprint00 | 0 | F14580 | 0 | Braj Mohan Goud | BM | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F14733 | 0 | Shaik Basha Murthuja Vali | SBM | Dev | SP
FFI | 2015-00 | Sprint00 | 0 | F15435 | 0 | Sathish V | SV | QA | KE
FFI | 2015-00 | Sprint00 | 0 | F15463 | 0 | Sai Prasanth | SP | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F15600 | 0 | Sanjana Babu | SB | QA | KE
FFI | 2015-00 | Sprint00 | 0 | F15658 | 0 | Roshan Ara A W | RAA | QA | KE
FFI | 2015-00 | Sprint00 | 0 | F15762 | 0 | Ramachandran Ganesan | RG | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F15856 | 0 | Deepika Ranganathan | DR | QA | KE
FFI | 2015-00 | Sprint00 | 0 | F16039 | 0 | Karthikeyan V | KV | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F16305 | 0 | Dilip Prasad J | DP | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F16453 | 0 | Ashok S | AS | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F16520 | 0 | Pramod Kumar Matam | PKM | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F16707 | 0 | Rajeshkanna P | RK | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F16839 | 0 | Nadem Manohar | NM | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F17018 | 0 | Murali Krishna J | KJ | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F17044 | 0 | Naresh Narava | NN | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F17107 | 0 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
FFI | 2015-00 | Sprint00 | 0 | F17170 | 0 | Krishna Avadhani Trv | KA | PC | KE
FFI | 2015-00 | Sprint00 | 0 | F5609 | 0 | Allwin A | AA | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F7303 | 0 | Senthil Nathan Sai | SNS | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F7422 | 0 | Asan Mohamed A | AM | QA | KE
FFI | 2015-00 | Sprint00 | 0 | F7423 | 0 | Sugumar | RS | QA | KE
FFI | 2015-00 | Sprint00 | 0 | F8614 | 0 | Suresh V | SUV | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | F8767 | 0 | Priya E | PE | Dev | SP
FFI | 2015-00 | Sprint00 | 0 | FT12358 | 0 | Shreya Gupta | SG | BA | KE
FFI | 2015-00 | Sprint00 | 0 | FT13554 | 0 | Aashiq Hameed | AH | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | FT14752 | 0 | Ramakrishnan | RKN | QA | KE
FFI | 2015-00 | Sprint00 | 0 | FT15989 | 0 | Kuzhal Malan S | KMS | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | FT16751 | 0 | Gowher John A S | GJ | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | FT16781 | 0 | Anusha B | AB | Dev | SP
FFI | 2015-00 | Sprint00 | 0 | CON#1 | 0 | Latha V | LV | SME | KE
FFI | 2015-00 | Sprint00 | 0 | CON#2 | 0 | Priya P | PP | DS | KE
FFI | 2015-00 | Sprint00 | 0 | CON#3 | 0 | Sudha M | SUM | DS | KE
FFI | 2015-00 | Sprint00 | 0 | CON#4 | 0 | Dileep | DIL | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | CON#5 | 0 | Rajesh | RJ | Dev | KE
FFI | 2015-00 | Sprint00 | 0 | Client03 | 0 | Tanbeer Ahmed | TA | PO | KE
FFI | 2015-00 | Sprint00 | 0 | F100 | 0 | NT Nathan | NTN | SM | KE
KE.BBD.01 | 2015-46 | Sprint01 | 2 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-46 | Sprint01 | 2 | CON#2 | 1 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-46 | Sprint01 | 2 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | CON#2 | 0.2 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | F7303 | 0.2 | Senthil Nathan Sai | SNS | Dev | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | CON#2 | 1 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | F7303 | 0.2 | Senthil Nathan Sai | SNS | Dev | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | CON#2 | 1 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | F7303 | 0.2 | Senthil Nathan Sai | SNS | Dev | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | CON#2 | 1 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | F7303 | 0.2 | Senthil Nathan Sai | SNS | Dev | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | FT13554 | 0.2 | Aashiq Hameed | AH | Dev | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | F100 | 0.2 | NT Nathan | NTN | SM | KE
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16039 | 1 | Karthikeyan V | KV | Dev | KE
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16305 | 1 | Dilip Prasad J | DP | Dev | KE
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16453 | 1 | Ashok S | AS | Dev | KE
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F15435 | 1 | Sathish V | SV | QA | KE
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F15600 | 1 | Sanjana Babu | SB | QA | KE
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | FT12358 | 1 | Shreya Gupta | SG | BA | KE
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16707 | 1 | Rajeshkanna P | RK | Dev | KE
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F0101 | 1 | Seshan T R | STR | SM | KE
KE.BBPE.1 | 2015-48 | Sprint02 | 2 | F16453 | 1 | Ashok S | AS | Dev | KE
KE.BBPE.1 | 2015-48 | Sprint02 | 2 | F16707 | 0.2 | Rajeshkanna P | RK | Dev | KE
KE.BBPE.1 | 2015-48 | Sprint02 | 2 | F15600 | 1 | Sanjana Babu | SB | QA | KE
KE.BBPE.1 | 2015-48 | Sprint02 | 2 | F0101 | 1 | Seshan T R | STR | SM | KE
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F16453 | 1 | Ashok S | AS | Dev | KE
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F15600 | 0.4 | Sanjana Babu | SB | QA | KE
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F14101 | 1 | Nivedha C | NC | Dev | KE
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F17044 | 1 | Naresh Narava | NN | Dev | KE
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F15762 | 1 | Ramachandran Ganesan | RG | Dev | KE
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F15658 | 1 | Roshan Ara A W | RAA | QA | KE
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F0101 | 1 | Seshan T R | STR | SM | KE
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F16453 | 1 | Ashok S | AS | Dev | KE
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F15600 | 0.4 | Sanjana Babu | SB | QA | KE
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F14101 | 1 | Nivedha C | NC | Dev | KE
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F17044 | 1 | Naresh Narava | NN | Dev | KE
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F15762 | 0.8 | Ramachandran Ganesan | RG | Dev | KE
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F15658 | 1 | Roshan Ara A W | RAA | QA | KE
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F0101 | 1 | Seshan T R | STR | SM | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | Client03 | 1 | Tanbeer Ahmed | TA | PO | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F15435 | 1 | Sathish V | SV | QA | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F15856 | 1 | Deepika Ranganathan | DR | QA | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16453 | 1 | Ashok S | AS | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16305 | 1 | Dilip Prasad J | DP | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16039 | 1 | Karthikeyan V | KV | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16707 | 1 | Rajeshkanna P | RK | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F13676 | 0.2 | Ravindra Kumar Tiwary | RKT | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F0101 | 1 | Seshan T R | STR | SM | KE
KE.MP.001 | 2015-48 | Sprint05 | 17 | F13676 | 1 | Ravindra Kumar Tiwary | RKT | Dev | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F13676 | 1 | Ravindra Kumar Tiwary | RKT | Dev | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F16707 | 1 | Rajeshkanna P | RK | Dev | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F15435 | 0.2 | Sathish V | SV | QA | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F15856 | 1 | Deepika Ranganathan | DR | QA | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | FT16751 | 1 | Gowher John A S | GJ | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | Client03 | 1 | Tanbeer Ahmed | TA | PO | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | F100 | 0.2 | NT Nathan | NTN | SM | KE
Note on F3: Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1

## PRA-Consolidated
Do Not Disturb this Pivot. It is used for Appraisal Purpose.
Sum of Present | Column Labels
Row Labels | KE.BBD.01 | KE.BBPE.1 | KE.DWBI.1 | KE.MP.001
CON#1 | 1
CON#2 | 4.2
CON#3 | 5
F0101 | 0.8 | 4 |  | 1.2
F100 | 0.2
F12175 |  |  | 6
F13676 |  |  |  | 2.2
F14101 |  | 2
F14580 |  |  | 6
F15435 |  | 1 |  | 1.2
F15463 |  |  | 6
F15600 |  | 2.8
F15658 |  | 2
F15762 |  | 1.8
F15856 |  |  |  | 2
F16039 |  | 1 |  | 1
F16305 |  | 1 |  | 1
F16453 |  | 4 |  | 1
F16520 |  |  | 6
F16707 |  | 1.2 |  | 2
F16839 |  |  | 6
F17018 |  |  | 6
F17044 |  | 2
F17107 |  |  | 6
F7303 | 0.8
F8614 |  |  | 5
FT12358 |  | 1
FT13554 | 0.2
FT14752 |  |  | 6
FT16751 |  |  |  | 1

## Weekly-Engagement
Account | (Multiple Items)
Scrum Role | (Multiple Items)
Project ID | (Multiple Items)
Sum of Present |  | Week of Year
Emp ID# | Emp Name | 2015-00 | 2015-51 | Grand Total
Client03 | Tanbeer Ahmed | 0 | 2 | 2
CON#1 | Latha V | 0 | 0.2 | 0.2
CON#2 | Priya P | 0 | 1 | 1
CON#3 | Sudha M | 0 | 1 | 1
CON#4 | Dileep | 0 |  | 0
CON#5 | Rajesh | 0 |  | 0
EMP#01 | Alexander | 0 |  | 0
EMP#02 | Andrew | 0 |  | 0
F0101 | Seshan T R | 0 | 0.2 | 0.2
F100 | NT Nathan | 0 | 0.4 | 0.4
F12175 | Thirupathi Kusa | 0 | 1 | 1
F13676 | Ravindra Kumar Tiwary | 0 |  | 0
F14101 | Nivedha C | 0 |  | 0
F14279 | Sanjana S | 0 |  | 0
F14580 | Braj Mohan Goud | 0 | 1 | 1
F15435 | Sathish V | 0 |  | 0
F15463 | Sai Prasanth | 0 | 1 | 1
F15600 | Sanjana Babu | 0 |  | 0
F15658 | Roshan Ara A W | 0 |  | 0
F15762 | Ramachandran Ganesan | 0 |  | 0
F15856 | Deepika Ranganathan | 0 |  | 0
F16039 | Karthikeyan V | 0 |  | 0
F16305 | Dilip Prasad J | 0 |  | 0
F16453 | Ashok S | 0 |  | 0
F16520 | Pramod Kumar Matam | 0 | 1 | 1
F16707 | Rajeshkanna P | 0 |  | 0
F16839 | Nadem Manohar | 0 | 1 | 1
F17018 | Murali Krishna J | 0 | 1 | 1
F17044 | Naresh Narava | 0 |  | 0
F17107 | Sampath Rao Tirumala Ratnagiri Raju | 0 | 1 | 1
F17170 | Krishna Avadhani Trv | 0 |  | 0
F5609 | Allwin A | 0 |  | 0
F7303 | Senthil Nathan Sai | 0 | 0.2 | 0.2
F7422 | Asan Mohamed A | 0 |  | 0
F7423 | Sugumar | 0 |  | 0
F8614 | Suresh V | 0 | 1 | 1
FT12358 | Shreya Gupta | 0 |  | 0
FT13554 | Aashiq Hameed | 0 | 0.2 | 0.2
FT14752 | Ramakrishnan | 0 | 1 | 1
FT15989 | Kuzhal Malan S | 0 |  | 0
FT16751 | Gowher John A S | 0 |  | 0
Grand Total |  | 0 | 14.2 | 14.2

## Impediments
Project Code | Impediments | Assigned To | Status | Due Date

## PM Practices
Owner | Who Should Do | Practice | Frequency | Remarks
Scrum Master | Scrum Master | Should maintain a daily log for all the project he is managing. | Daily Basis
Scrum Master | Scrum Master | Should maintain a log of requirement clearification at project level. | As and when requirement elicitation happens
Scrum Master | Development Team | Daily Stand Up Call | Daily same time, same location
Scrum Master | Development Team | Maintain Scrum Board | Daily Basis | Scrum Board= Kanban/ Burndown Charts/ Team Members/ Impediments
Scrum Master | Development Team | Sprint Planning at the start of every sprint | Once in a sprint
Scrum Master | Development Team | Test Driven Development | Daily Basis
Scrum Master | Product Owner | Product Demo | Once in a sprint
Scrum Master | Development Team | Continuous Functional & Integration Testing | As soon as code is checked in
Scrum Master | Product Owner | Product Backlog Grooming | During sprint after sprint planning and before Product demo.
Scrum Master | Scrum Master | Discuss issues which need management attention with possible proposed solutions | On Need Basis
Scrum Master | Development Team | Perform Retrospective at the end of every sprint | Once in a sprint
Scrum Master | Project Co-ordinator | Collect project data on regular basis | As and when needed
Scrum Master | Scrum Master | Update project dashboard on regular basis | Everyday morning (only if needed)
Scrum Master | Scrum Team | Keep risk register updated / plan risk response/ ensure action are taken | On Need Basis
Scrum Master | Scrum Team | Configuration Management System in Place | On Daily Basis | Document naming, version numbering, location, storage, archival, access permission, redundancy

## Challenges
Input from PM
Challenges from PM Angle
Requirment documents missing
Scope is not defined
Micro management
Communication gap/ Communication Management Strategy missing
Reporting structure is not planned
Change management not in place
Configuration management System is not being used
Adhoc work by customer
We are not estimating the work but timeline is given to us
PM is not coordinating all work/ PM bypassed
Issue management is not effective
No proper risk management
Challenges from Bharat Angle
Not getting right information at right time
Quality of project management
Planned vs Actual work progress report is not visible
Resource Loading Info is Missing
Ticket Status Information
Quality of Testing is not upto the mark
Coding quality is bad
General
Upto 12-Sep (before Bharat came to India) everything was good. He appreciated PM on 11-Sep.
18-19-Sep

## RISK
Risk-ID | Risk-Name | Risk-Description | Probablity | Impact-Schedule | Impact-Cost | Impact-Quality | Impact-Scope | Mitigation Plan | Contigency Plan | Risk Owner | Risk status | Risk Updated Date