## Projects
Status
# | Project_ID | Project Name | Category | Project Type | Scrum Master | Accountable | Dev Resources | QA Resources | Support Res | Project Sponsor | Planned Effort | Planned Dur. | Pending PBL Items | Pending Sprint Items | Burndown Efforts for Sprint | Planned St Date | Planned End Date | Replanned End Date | Overall | Schedule | Cost | Quality | Scope | Remarks
1 | CBM001 | Benefit Bridge/CBMS | Dev & Support | Regular | Senthil | Seshan | 6 | 2 |  | Bharat | [6 empty] | 2016-01-01
2 | DWB001 | DWBI | Dev & Support | Regular | Sampath | Seshan | 7 |  |  | Bharat
3 | CAD001 | Cadillac | Dev & Support | Need Basis | Shreya | Seshan |  |  |  | Bharat
4 | SER001 | SERP | Dev & Support | Need Basis | Seshan | Veeren | 1 |  |  | Sanjeev
5 | BEN001 | Benefit Bridge/Private Exchange | Development | Regular | Seshan | Veeren | 3 | 2 |  | Bharat
6 | MAR001 | Market Place | Development | Regular | Seshan | Veeren | 5 | 4 |  | Bharat | [5 empty] | 2015-07-15 | 2015-10-01 | 2015-10-30 |  | -29 | -180 | 70 |  | 70 Defects
7 | PCB001 | Portal PCB Rel 6.0 | Full Testing | Regular | Sathish | Seshan |  |  |  | Sanjeev | [5 empty] | 2015-05-15 | 2015-11-01
8 | QNR001 | Portal QnR Revamp | Full Testing | Regular | Sathish | Seshan |  |  |  | Sanjeev | [5 empty] | 2015-05-15 | 2015-11-01
9 | PSP001 | Portal Sprint (#1) | Support/Ticket Based | Regular | Sathish | Seshan |  |  |  | Sanjeev | [5 empty] | 2015-03-01 | 2015-11-06
10 | IFP001 | IFP Commission | Support | Need Basis | ?? | Veeren |  |  | 1 | Bharat
11 | DAT001 | Data Exchange | Dev & Support | Regular | Seshan | Veeren | 1 |  |  | Bharat | [5 empty] | ?? | 2015-11-30
12 | BEND01 | Benefit Management Documentation | Documentation | Regular | Seshan | Veeren |  |  | 3 | Bharat
[7 empty] | 23 | 8 | 4
Project Blocker
Formulas:
Cost = 5*(WEEKNUM([Planned End Date])-WEEKNUM([Replanned End Date]))*([Dev Resources]+[QA Resources])

## Appraisal-Parameters
[7 empty] | Scale | 1 | 2 | 3 | 4 | 5
23 |  | 50% | 50% | 98%
Weightage/Gross Total | Weightage | Teams's Rating | Customer's Rating | Total | Objective |  | Objective
Functional Point Written by a team every month | 4.348% | 5 | 5 | 4.348% |  | TB | Team Binding
Rating by customer every sprint | 4.348% | 5 | 5 | 4.348% |  | PF | Project Focussed
Moral of the team every sprint | 4.348% | 3 | 4 | 3.043% |  | RP | Retention of Performers
Meeting commitment | 3% | 5 | 5 | 3% |  | AEL | Auto Expulsion of Laggers
How agile is team? | 4.348% | 5 | 5 | 4.348% |  | NCCPQ | No competion at the cost of Product Quality
Champion of the Sprint | 5% | 5 | 5 | 5% |  | QD | Quality Delivery
No of defect leak to production | 4.348% | 5 | 5 | 4.348% |  | TD | Timely Delivery
No of UAT test cases passed | 4.348% | 5 | 5 | 4.348% |  | B4O | Binding for the Organization
Test Coverage | 4.348% | 5 | 5 | 4.348% |  | DUPL | Discourage unplanned off from wrok
Issues in the issue log | 4.348% | 5 | 5 | 4.348% |  | VCC | Value creation for Customer
Functional Point Test Coverage | 4.348% | 5 | 5 | 4.348% |  | VCO | Value creation for Organization
Project Resource Iteration | 4.348% | 5 | 5 | 4.348% |  | TP | Team Play
Value Delivered Per Sprint | 4.348% | 5 | 5 | 4.348% |  | AT | Agility in Team
Value of Contribution every sprint | 4.348% | 5 | 5 | 4.348% |  | TPR | Team Productivity
Team Proactiveness | 4.348% | 5 | 5 | 4.348%
Team's ability to deliver the commitments | 4.348% | 5 | 5 | 4.348%
Team's ability to live agile values | 4.348% | 5 | 5 | 4.348%
Team's ability to agile principles | 4.348% | 5 | 5 | 4.348%
Time spent on rework | 4.348% | 5 | 5 | 4.348%
Number of Product Demos | 4.348% | 5 | 5 | 4.348%
Team's unplanned leaves | 4.348% | 5 | 5 | 4.348%
Helpfulness of team to each other | 4.348% | 5 | 5 | 4.348%
Ability to solve impediments | 4.348% | 5 | 5 | 4.348%

## Project-Team
Sl. No | Resource |  | Project 1 | Project 2 | Project 3 | Project 4 | Project 5 | Project Role | Org Designation | Location | Total Exp | Technolgoies | Personal | Org Req | Gap
1 | Asan Mohamed | Old Emp | BEN001 | PCB001 | QNR001 | PSP001 |  |  | Tester Lead | Chennai | 8 Years | QTP Automation, Certified Performance Tester/Automation (KTE) , ISTQB Certified, Security Testing, OWASP (ZAP Tool), Load Runner, Open Star, Jmeter, WinRunner, QTP, | Good Communicator, Ready to adapt, | I do not know what tools required
2 | Sanjana Babu | Proper | [6 empty] | Tester | Chennai | 2 Years | Functional (Manual) Regression Testing, Mainframe Testing, compatility Testing, Domain (retail, healthcare). Tools: ALM, HP-QC | Flexitbity, Self confident, Possitive Attitude | I do not know
3 | Ramachandran | Proper | DAT001 | BEN001 |  |  |  |  | Sr. Developer | Chennai | 11.5 Years | WIN Form, WPF, SSIS, SSRS, VSTO, ASP.NET, WCF, SQL Server. | Organized & Systematic, Punctual, Family Driver, Short Story Writer | ASP.NET, MVC, REST WCF, Entity Framework, SQL Server | No Gap
4 | Roshan | Proper | [6 empty] | Tester | Chennai | 4 Years | Functional/Regression/Browser compatility (Manual) testing, DB Testing, TFS Test Management | Optimistic, Quick Learner, High Confidence | Security Testing is required, TFS for Test Management | Security Testing
5 | Sathish | Proper | [6 empty] | QA Manager | Chennai | 11.5 Years | Performance Testing, Mobile Testing (manual/automation), Browser Compatibility testing, Bigdata testing, Domain Banking, VOIP, Retail, Healthcare. Certified HP ALM, ISTQB. | Self learner & motivated, Quick leaner, Good team player, Adapt quickly, practical solution provider | Selenium Eclipse Automation Tool, Earlier we were using QTP but not now. Test cases need to be written from scratch because of new tool for testing. Performance Testing using Jmeter is required, Security testing is required, Browser compatility testing, | J Meter, ZAP (Security testing)
6 | Aashiq | Proper/Trainee | [6 empty] | Developer | Chennai
7 | Allwin | Old Emp | [6 empty] | Sr. Developer | Chennai
8 | Kuzhal | Experia ?? | [6 empty] | Jr. Developer | Chennai
9 | Senthil Sai | Old Emp | [6 empty] | Sr. Developer | Chennai
10 | Braj Mohan | BDI/Old Emp | [6 empty] | Sr. Developer | Chennai
11 | Nadem Manohar | Proper | [6 empty] | Developer | Chennai
12 | Pramod | Experia ?? | [6 empty] | Developer | Chennai
13 | Shreya | Proper/Trainee/ Sr. Inv Relative | [6 empty] | Developer | Chennai
14 | Suresh Vasantha | Old Emp | [6 empty] | Sr. Developer | Vijaywada
15 | Thirupati | BDI/Old Emp | [6 empty] | Developer | Chennai
16 | Krishna | Internal Ref | [6 empty] | Sr. Developer | Chennai
17 | Ashok S | Experia | [6 empty] | Developer | Chennai
18 | Dilip Prasad | Experia/ Interviewed | [6 empty] | Team Lead | Chennai
19 | KarthiKeyan V | Experia | [6 empty] | Sr. Developer | Chennai
20 | Nivedha | Proper | [6 empty] | Sr. Developer | Hydrabad
21 | Rajesh Kanna | Experia | [6 empty] | Developer | Chennai
22 | Ravindra Tiwari | Proper | [6 empty] | Sr. Developer | Chennai
23 | Gowher John | Internal Ref | [6 empty] | Trainee | Chennai
24 | Naresh Narava | No Idea | [6 empty] | Sr. Developer | Chennai
25 | Ahmed | Bharat | [6 empty] | PM | Chennai
26 | Abdul K | Proper | [6 empty] | PM Coordinator | Chennai
27 | Alexander Teeple | US Person | [6 empty] | QA | Onsite
28 | Andrew Springer | US Person | [6 empty] | Tester | Onsite
29 | Deepika | Proper | [6 empty] | Tester | Chennai
30 | Ramakrishnan | Trainee | [6 empty] | Trainee | Chennai
31 | Sai Prashant | Trainee | [6 empty] | Tester | Chennai
32 | Sanjana S | Internal Veeren | [6 empty] | Tester | Chennai
33 | Sugumar | Old Emp | [6 empty] | Sr. QA Testet | Chennai

## Blocker
Project Code | Blocker Name | Assigned To | Due Date
CBM001
DWB001
CAD001
SER001
BEN001
MAR001
PCB001
QNR001
PSP001
IFP001
DAT001

## Role-Resp
Developer
Sr. Developer
Jr. Developer
Team Lead
Trainee
PM
PM Coordinator
QA
Tester
QA Manager
Sr. QA Testet
Dev Team | Understand Requirments from user stories/defects
Analyse requirement
| Write unit test cases | Code has some security issue
Use TDD method for development

## Reporting
| Status | Audience
Daily Status Report | Yes | Sponsor (Bharat)
WSR | No | Sponsor (Bharat)
5 Point Status | No | Account Manager (Veeren)
?? | No | Project Manager (Ahmed)
Project wise milestone

## Challenges
Input from PM
Challenges from PM Angle
Requirment documents missing
Scope is not defined
Micro management
Communication gap/ Communication Management Strategy missing
Reporting structure is not planned
Change management not in place
Configuration management System is not being used
Adhoc work by customer
We are not estimating the work but timeline is given to us
PM is not coordinating all work/ PM bypassed
Issue management is not effective
No proper risk management
Challenges from Bharat Angle
Not getting right information at right time
Quality of project management
Planned vs Actual work progress report is not visible
Resource Loading Info is Missing
Ticket Status Information
Quality of Testing is not upto the mark
Coding quality is bad
General
Upto 12-Sep (before Bharat came to India) everything was good. He appreciated PM on 11-Sep.
18-19-Sep

## PM Practices
Note
Issue tracking | Google docs & excel
Project plan in MPP | But not updated
Peer Review
Unit Testing
Standup (morning)
Status Check (evening)

## RISK
Risk-ID | Risk-Name | Risk-Description | Probablity | Impact-Schedule | Impact-Cost | Impact-Quality | Impact-Scope | Mitigation Plan | Contigency Plan | Risk Owner | Risk status | Risk Updated Date