## KM - Plan
Section #
Section # | Section | Sub-Section | DEV Resource | QA Resource | BI Resource | Document Started? | Document Completed? | Document Reviewed? | Overall Status | Tentative Start Date | Tentative End Date | Actual Start Date | Actual End Date | Tentative Sessions Est. Hours Duration | Actual Sessions Hours Duration | Remarks
0 |  | Introduction | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/19/2015 | 10/19/2015 |  |  | 1 |  | Kick Off Meeting, Introductions to BB/CBMS, Configuration Management System for documents and process
1 | Set Up | Carrier Setup | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/20/2015 | 10/20/2015 |  |  | 0.5
2 | Set Up | Client Setup | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/20/2015 | 10/20/2015 |  |  | 0.5
3 | Set Up | Policy Setup / Carrier Group Setup | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/21/2015 | 10/21/2015 |  |  | 1
4 | Set Up | Employer Group Setup | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/22/2015 | 10/22/2015 |  |  | 0.25
5 | Set Up | Add Classification | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/22/2015 | 10/22/2015 |  |  | 0.25
6 | Set Up | Add Location | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/22/2015 | 10/22/2015 |  |  | 0.25
7 | Set Up | Add Occupation | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/22/2015 | 10/22/2015 |  |  | 0.25
8 | Set Up | Enrollment Rule | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/23/2015 | 10/23/2015 |  |  | 0.5
9 | Set Up | Rule Setup | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/23/2015 | 10/23/2015 |  |  | 0.5
10 | Set Up | Open Enrollment Setup | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/26/2015 | 10/26/2015 |  |  | 1
11 | Admin | Manage Subscribers | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/27/2015 | 10/27/2015 |  |  | 1
12 | Admin | Manage Dependents | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/28/2015 | 10/28/2015 |  |  | 1
13 | Admin | Manage Benefits | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/29/2015 | 10/29/2015 |  |  | 1
14 | Admin | Rate Updater | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 10/30/2015 | 10/30/2015 |  |  | 2
15 | Admin | Rate Updater for Type 2 plans | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 11/2/2015 | 11/2/2015 |  |  | 1
16 | Admin | Age Band Changes / Age Reduction | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 11/3/2015 | 11/3/2015 |  |  | 2
17 | Admin | Salary Update | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 11/4/2015 | 11/4/2015 |  |  | 1
18 | Interfaces | Transmittals | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 11/5/2015 | 11/9/2015 |  |  | 4
19 | Interfaces | Recurring Multi-Client Import (RMCI) | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 11/10/2015 | 11/13/2015 |  |  | 4
20 | Interfaces | Web Import | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 11/16/2015 | 11/19/2015 |  |  | 4
21 | Enrollment | Commit Process | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 11/20/2015 | 11/23/2015 |  |  | 2
22 | Enrollment | Open Enrollment (OE), Life Events (LE), New Hire (NH) | Gowher John, Naresh, Ramachandra | Sanjana B, Deepika, Roshan | Nadem Manohar, Pramod Kumar | No | No | No | To be done | 11/24/2015 | 11/26/2015 |  |  | 3
|  | Total | [11 empty] | 32