## Slide 1: ERP Implementation Road Map

## Slide 2: Total Cost of Ownership
 | Year 1 | Year 2 | Year 3 | Total
ERP License Cost | 52,00,000 | 12,00,000 |  | 64,00,000
Implementation Cost - vendor | 35,00,000 | 35,00,000 | 10,00,000 | 80,00,000
Implementation Cost – internal | 17,50,000 | 17,50,000 | 5,00,000 | 40,00,000
Microsoft Support (BREP) | 10,00,000 | 12,00,000 | 12,00,000 | 34,00,000
Partner Support Cost | 4,00,000 | 8,00,000 | 8,00,000 | 20,00,000
Product Upgrade / Migration |  |  | 20,00,000 | 20,00,000
ERP Manager / Team | 8,00,000 | 8,80,000 | 9,60,000 | 26,40,000
Server Hardware | 10,00,000 |  | 3,00,000 | 13,00,000
Total Cost |  |  |  | 2,97,40,000

## Slide 3: Methodology
Agile Methodology with Multiple Release Cycles
The duration of each sprint shall be 10 business days
Each release cycle may have multiple sprints (2 or 3 or 4)
Lead time of 5 business days at the end of each release cycle for bug fixing and stabilization.
Release cycle shall be planned entity-wise.
User Training and Go live at the end of each release cycle.

## Slide 4: Pre-Implementation
User Stories Documentation
Product Familiarization
Master Data Collection, Validation & Loading
  G/L Account (Chart of Accounts)
  Item Master, Vendor / Supplier Master, Customer Master
  Fixed Assets, Resources
  Non-stock Items
  Contacts

## Slide 5: Implementation Road Map
 | GST | ISKCON | TSF G | TSF P
Finance & Accounts | R1 S1 | R2 S2 | R2 S2 | R2 S2
Fixed Asset Management | R1 S2 | R4 S3 | R4 S3 | R4 S3
Procurement Planning | NA | NA | R2 S1 | NA
Purchase to Payment | R1 S1 | R3 S3 | R2 S1 | R3 S1
Inventory & Stores | R1 S1 | R3 S3 | R2 S1 | R3 S1
Quality Control | NA | R3 S3 | R2 S1 | R3 S1
Sales Forecasting | NA | NA | R2 S2 | R3 S2
Sales Management | R1 S2 | NA | R2 S2 | R3 S2
Production (MRP) | NA | NA | NA | R3 S2
Dhananjaya Integration | NA | R4 S1 | NA | NA
POS Solutions Integration | NA | NA | NA | NA
HRMS & Payroll (Add-on) | NA | NA | NA | NA
Plant Maintenance (Add-on) | NA | NA | NA | NA
Projects (Jobs) | NA | R4 S2 | NA | NA

## Slide 6: ERP Implementation
Team Structure
Roles and Responsibilities

## Slide 7: Boards
Board of Directors (Vice Presidents):
  Members: Amitasana Dasa, Radhakanta Dasa, Vasudev Keshav Dasa
  Involvement: Remove any hurdles in the implementation, which cannot be addressed at Division Head level.
  Reporting Frequency: Monthly / Fortnightly (to be decided)
  Progress Report by Product Owner / Major Risks and Issues
  RYG Report Indicator of time and cost

## Slide 8: Boards
Project Steering Committee
  Members: Project Sponsor, Product Owner,
  Involvement:

## Slide 9: Boards
Project Change Control Board
  Members: Project Sponsor, Product Owner,
  Involvement:

## Slide 10: Team Structure
President
Project Sponsor
Product Owner
Project Management Coach
Vice Presidents
Unit Heads
Division Heads
Users
Executive Sponsor
Account Manager
Scrum Master
Engagement Manager
Project Team
ISKCON
Implementation Partner

## Slide 11: Project Sponsor
Project Sponsor: Amitasana Dasa
Involvement:
  Resolving escalations, if any.
  Ensuring funding for the project.
  Continuous business justification meeting with product owner.
  Ensure support for the project success from the management and peers.
Reporting to Project Sponsor (by Product Owner)
  Business Value, Release Plan, Product Usability Report

## Slide 12: Product Owner
Product Owner:
Involvement
  Understand requirements from key users / unit heads
  Prioritize requirements with the help of unit heads / division heads
  Show product demo to user community
  Take feedback and sign off for the implemented product
  Justify business value continuously (can cancel the sprint, if required)
  Ensure project team is configuring as per the plan for the sprint
  Grooming the product backlog (user stories)
Reporting to Product Owner:
  Status of Completed User Stories by Scrum Master
Reporting by Product Owner:
  Progress Reporting to the board of directors (vice-presidents)
  Business Value Justification Report to Project Sponsor

## Slide 13: Project Management Coach
Project Management Coach: Mr. Hari Prasad Thapliyal
Involvement
  Help the project team, scrum master and product owner in understanding and imbibing the best practices in Agile Project Management
  Continuously evaluate the vendor / partner performance and provide inputs so that the project timeline and cost can be controlled.

## Slide 14: Division Head
Division Heads
  TSF Gift (Ravi K R) | TSF Food (KVPP) | GST (CRKP)
  ISKCON: Material Management (MPGP) | Accounts & Finance (SMVP) | Donations (KRSP) | Maintenance (PHLP) | HR (NANP)
Involvement
  Remove any hurdles that cannot be addressed by unit head
  Assign one person from their division to work with product owner to understand requirements and prioritize them
  Approve the prioritization of the requirements
  Attend the product demo at the end of each sprint
  Optionally can attend the daily stand-up meeting
Reporting to Division Head
  Based on the need – finalize with the division head before release cycle

## Slide 15: Unit Head / Key Users
The list of unit heads involved are presented in next slide.
Involvement
  Writing User Stories
  Clarifying the Requirements
  Writing Test Cases
  Attend Product Demo
  Provide Feedback
  Sign off Acceptance
  Attend Daily Stand-up Meeting
Reporting to Unit Head: Nil
Reporting by Unit Head: Nil

## Slide 16: Scrum Master
Scrum Master:
Involvement
  Ensure that the team is following Agile Practices
  Remove external impediments, if any
  Ensure that the required infrastructure is available for the team
  Ensure that the team is updating the information radiator on daily basis
  Participate in release and sprint planning
  Ensure that the team is motivated and self-organized
Reporting to Scrum Master: Impediments

## Slide 17: Project Team