## High Level Plan
Things to do
S. No. | Activity | Who | Team | Start Date | End Date | Status
1 | License Clarity on MS Dynamics NAV | JNVD |  |  |  | Completed
2.1 | MS Dynamics NAV Training Environment Setup | Ayyappa D |  |  |  | Completed
2.2 | MS Dynamics NAV Development Environment Setup | Ayyappa D |  |  |  | Not Started
2.3 | MS Dynamics NAV Testing Environment Setup | Ayyappa D |  |  |  | Not Started
2.4 | MS Dynamics NAV Production Environment Setup | Ayyappa D |  |  |  | Not Started
3 | Vendor Finalization for ERP Implementation | JNVD |  |  |  | Not Started
4 | Product Familiarization & Configuration Training for Core Team | Vendor |  | 2015-03-10 | 2015-03-24
5 | Identifying the Key Users | JNVD |  |  | 2015-03-07 | Completed
6.1 | Prepare User Stories & segmenting based on process / sub-process | JNVD
6.2 | Understand user stories, prioritize and make product road map | Hari Prasad | FC / TC / PO / SM / KU | 2015-03-30 | 2015-03-31
7 | Finalizing the Implementation Methodology | Hari Prasad
8 | Finalizing the Team Structure | Hari Prasad
9 | Finalizing the Chart of Accounts | SMVD
10 | Collection of Master Data | Ganesh M S
11 | Standardize the Printers Used and the Formats
Sprint Start
| Pickup User Stories and Processes from Backlog | PO
| Discuss User Stories and Processes with Key Users | FC / TC / PO / KU
| Break-up Key User Stories to Task Level | FC / TC
| Implement the User Stories | TC
| Move the configured product to Test Environment | TC
| System Testing | FC / PO / KU
| End User Training | KU
| Move the configured / tested product to Production Environment | TC
Upload Master Data and Opening Balances

## Action Register
S. No. | Meeting Date | Action Item | Who | Target Date | Status | Indicator
1 | 2015-03-06 | Documentation of license related information | Janaki Vallabha Dasa |  |  | RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED
RED