## HighLevel
Things to do
S. No. | Activity | Who | Team | Start Date | End Date | Status
1 | License Clarity on MS Dynamics NAV | JNVD |  |  |  | Completed
2.1 | MS Dynamics NAV Training Environment Setup | Ayyappa D |  |  |  | Completed
2.2 | MS Dynamics NAV Development Environment Setup | Ayyappa D |  |  |  | Not Started
2.3 | MS Dynamics NAV Testing Environment Setup | Ayyappa D |  |  |  | Not Started
2.4 | MS Dynamics NAV Production Environment Setup | Ayyappa D |  |  |  | Not Started
3 | Vendor Finalization for ERP Implementation | JNVD |  |  |  | Not Started
4 | Product Familiarization & Configuration Training for Core Team | Vendor |  | 2015-03-10 | 2015-03-24
5 | Identifying the Key Users | JNVD |  |  | 2015-03-07 | Completed
6.1 | Prepare User Stories & segmenting based on process / sub-process | JNVD
6.2 | Understand user stories, prioritize and make product road map | Hari Prasad | FC / TC / PO / SM / KU | 2015-03-30 | 2015-03-31
7 | Finalizing the Implementation Methodology | Hari Prasad
8 | Finalizing the Team Structure | Hari Prasad
9 | Finalizing the Chart of Accounts | SMVD
10 | Collection of Master Data | Ganesh M S
11 | Standardize the Printers Used and the Formats
Sprint Start
| Pickup User Stories and Processes from Backlog | PO
| Discuss User Stories and Processes with Key Users | FC / TC / PO / KU
| Break-up Key User Stories to Task Level | FC / TC
| Upload Master Data and Opening Balances in Dev DB | TC
| Implement the User Stories | TC
| Move the configured product to Test Environment | TC
| Upload Master Data and Opening Balances in Test DB | TC
| System Testing | FC / PO / KU
| End User Training | KU
| Move the configured / tested product to Production Environment | TC
| Upload Master Data and Opening Balances in Prod DB | TC