## Schedule (hidden)
Process | ISKCON | ABS | IB | TSF-G | TSF-P | GST | Status | Legend
Accounts & Finance | SMVD | Lakshmi A |  |  |  |  | Completed | Completed
Sales Forecasting | SMVD | Lakshmi A |  | 2015-01-08 | 2015-01-07 | 2014-12-25 | Completed | Scheduled
Procurement Planning | SMVD | Lakshmi A |  |  |  |  | Completed | In Progress
Procurement to Payment | SMVD | Lakshmi A | 2014-12-24 |  |  |  | Completed | Pending
Inventory & Stores Management | SMVD | Lakshmi A |  |  |  |  | Completed
Quality Control | SMVD | Lakshmi A |  |  |  |  | Completed
Production Planning | SMVD | Lakshmi A |  |  |  |  | Completed
Sales Management | SMVD | Lakshmi A |  |  |  |  | Completed
Consignment Sales | SMVD | Lakshmi A |  |  |  |  | Completed
Payroll & Human Resources Management | JNVD | Lakshmi A | 2014-12-24 |  |  |  | Completed
Donations Management | JNVD | Lakshmi A | 2014-12-25 |  |  |  | Completed
Guest House & Convention Halls | JNVD | Lakshmi A | 2015-01-07 |  |  |  | Completed
Magazine Printing - Job Automation | JNVD | Lakshmi A |  | 2015-01-02 |  |  | Completed
Subscription Management for Magazines | JNVD | Lakshmi A |  |  |  |  | Completed
Facility Maintenance | JNVD / SMVD | Lakshmi A | 2015-01-06 |  |  |  | Pending
Project Management | JNVD / SMVD | Lakshmi A | Parked. Need to discuss at later stage. |  |  |  | Parked
Customer Relationship Management | JNVD | Lakshmi A | 2015-01-07 |  |  |  | Completed
POS Requirements Study | SMVD | ABS Team | 2015-01-13 | 2015-01-05 |  | 2015-01-13 | In progress
Integration vs. Build Requirements | JNVD | Lakshmi A | 2015-01-13 | 2015-01-13 | 2015-01-13 | 2015-01-13 | In progress
Note on E3: 24/12/2014: Had discussion with Ganesh and Team (Nanjundaswamy , Raghavendra and Rashmi ) Introduction meeting with SMVD 2nd Session: Meeting with Ganesh and team with Sudhakar Reddy. 25/12/2014: (12 - 5 ) Meeting with Ganesh , Swamy, Raghavendra and Rashmi, Sudhakar Reddy On Current process flow / destiny and prism pain points / current manual and system process. 06/01/2015: Meeting with Shashi on BVD Requirements. S/w Needs Capture marketing data / incentive calculation 08/01/2015: (3.30 - 5.30) - Ravi K R, Madhu, Raghu , Ranganath, Rekha, Swheta , Subhashish, Nagaratna Mataji,Ganesh, Raghavendra, Nanjunda Swamy, Rashmi Points Discusses: pain points / Expectations / Process Flow explanation by each unit Head. 08/01/2014: BM Meeting " Wtih Shashi / Ravi Kumar. Events / Van sales / Event Exp tracknig / PoS billing/OT /Veh log and maintenance /
Note on F3: 07/01/2015 - (11-30 - 2 ) All user Meeting Discussed with (Ganesh, Lakshmi, Naveen Kumar, Vijay Rajesh, Murali, Siddarth Sinha, Umadevi Desai,Gopinath, Maqbool, Mandanna, Anand Devadiga Individual Team Meetting: FGA Meeting: 07/1/2015: 4 pm to 5 .45 pm : Beera Gowda / Chitra Mataji Current FGA pain points Sales Team: 07/1/2015: 5.45 8 pm : Vijay Rajesh /Santosh /Siddesh Retail Requiremetns / POS/ Stock management issuse / SM and FG stock management , Transport issues 08/1/15: QC Team: (2.15 - 3.30) Anand Devadiga : QC inspection data capturing/ Gate pass entry info to QC / QC planning for late inspection /Rejection note data capture
Note on G3: Discussed with Gowri and Charu Krishna Prabhu. Visited the packing section. Shared Stock Summary, BOM Sample, Finished Goods, Packing Materials.
Note on D5: Discussed with Uma S and Prabhu R.
Note on A7: raw materials / production plants / finished goods stores
Note on G9: Exports / Distributors / Retail / Online
Note on D11: Discussed with NAND and JNVD. NAND shared the department structure, payroll MSP, proposed C&B grade matrix and the sample data.
Note on D12: Discussed with JNVD. Shared the process document for donation management.
Note on D13: Discussed with JNVD and collected the inputs.
Note on E14: Met Ganesh MS and Shashikumar. Collected details of cost components for magazine printing and the tarrif for advertisements.
Note on E19: ABS Team (Ravindra Kini, Anand Murali, Lakshmi A) did a walk through of TSF Gift counters and will propose the solution options after Jan 8. Jan 12: Had a meeting with AAP. It is decided that a committee will be formed to finalize the solution. Ragu, Ganesh and Ravi KR will be part of the committee; JNVD and SMVD to give required inputs.

## Business Processes-1
Division | Department | Process | System
TSF G | Procurement to Payment | Procurement Planning | MANUAL
TSF G | Procurement to Payment | Purchase Indents | MANUAL
TSF G | Procurement to Payment | Supplier Quotation | DESTINY
TSF G | Procurement to Payment | Supplier Order | DESTINY
TSF G | Procurement to Payment | Gate Pass Entry | MANUAL
TSF G | Procurement to Payment | Goods Receipts | DESTINY
TSF G | Procurement to Payment | Supplier Returns | DESTINY
TSF G | Procurement to Payment | Purchase Inward Notes | DESTINY
TSF G | Procurement to Payment | Payment Advice | MANUAL
TSF G | Procurement to Payment | Payment Processing | TALLY
TSF G | Quality Control | Quality Inspection | DESTINY
TSF G | Quality Control | Quality Acceptance | DESTINY
TSF G | Quality Control | Quality Rejection | DESTINY
TSF G | Quality Control | Quality Rework | MANUAL
TSF G | Quality Control | Scrap / Waste Management | MANUAL
TSF G | Quality Control | Second Sales | MANUAL
TSF G | Cash Sales Management | Customer Order | DESTINY
TSF G | Cash Sales Management | Cash Invoice | DESTINY
TSF G | Cash Sales Management | Payment Collections | DESTINY
TSF G | Credit Sales Management | Sales Forecasting & Planning | MANUAL
TSF G | Credit Sales Management | Indents | DESTINY
TSF G | Credit Sales Management | Customer Order | DESTINY
TSF G | Credit Sales Management | Credit Invoice | DESTINY
TSF G | Credit Sales Management | Customer Returns | DESTINY
TSF G | Credit Sales Management | Payment Collections | DESTINY
TSF G | Inventory & Stores | Store Issues | DESTINY
TSF G | Inventory & Stores | Delivery Challan | DESTINY
TSF G | Inventory & Stores | Packing Slip | DESTINY
TSF G | Inventory & Stores | Store Receipts | DESTINY
TSF G | Inventory & Stores | Stock Transfers | DESTINY
TSF G | Inventory & Stores | Item Conversions | MANUAL
TSF G | Inventory & Stores | Counter Returns | DESTINY
TSF G | Inventory & Stores | Counter Issues | DESTINY
TSF G | Inventory & Stores | Job Work Issues | DESTINY
TSF G | Inventory & Stores | Job Work Returns | DESTINY
TSF G | Production | Production Planning | MANUAL
TSF G | Production | BOM Creation | MANUAL
TSF G | Production | Job Work Creation | DESTINY
TSF G | Production | Production Issues | DESTINY
TSF G | Production | Finished Goods Receipts | DESTINY
TSF G | Production | Sub contract work order | DESTINY
TSF F | Procurement to Payment | Procurement Planning | MANUAL
TSF F | Procurement to Payment | Purchase Indents | MANUAL
TSF F | Procurement to Payment | Supplier Quotation | MANUAL
TSF F | Procurement to Payment | Supplier Order | PRISM
TSF F | Procurement to Payment | Gate Pass Entry | MANUAL
TSF F | Procurement to Payment | Goods Receipts | PRISM
TSF F | Procurement to Payment | Supplier Returns | PRISM
TSF F | Procurement to Payment | Purchase Inward Notes | NA
TSF F | Procurement to Payment | Payment Advice | MANUAL
TSF F | Procurement to Payment | Payment Processing | TALLY
TSF F | Quality Control | Quality Inspection | MANUAL
TSF F | Quality Control | Quality Acceptance | MANUAL
TSF F | Quality Control | Quality Rejection | MANUAL
TSF F | Quality Control | Quality Rework | NA
TSF F | Quality Control | Scrap / Waste Management | MANUAL
TSF F | Quality Control | Second Sales | NA
TSF F | Cash Sales Management | Customer Order | MANUAL
TSF F | Cash Sales Management | Cash Invoice | MANUAL
TSF F | Cash Sales Management | Payment Collections | MANUAL
TSF F | Credit Sales Management | Sales Forecasting & Planning | MANUAL
TSF F | Credit Sales Management | Indents | PARTIAL
TSF F | Credit Sales Management | Customer Order | PARTIAL
TSF F | Credit Sales Management | Credit Invoice | MANUAL
TSF F | Credit Sales Management | Customer Returns | MANUAL
TSF F | Credit Sales Management | Payment Collections | MANUAL
TSF F | Inventory & Stores | Store Issues | PRISM
TSF F | Inventory & Stores | Delivery Challan | MANUAL
TSF F | Inventory & Stores | Packing Slip | MANUAL
TSF F | Inventory & Stores | Store Receipts | PRISM
TSF F | Inventory & Stores | Stock Transfers | PRISM
TSF F | Inventory & Stores | Item Conversions | MANUAL
TSF F | Inventory & Stores | Counter Returns | MANUAL
TSF F | Inventory & Stores | Counter Issues | MANUAL
TSF F | Inventory & Stores | Job Work Issues | NA
TSF F | Inventory & Stores | Job Work Returns | NA
TSF F | Production | Production Planning | MANUAL
TSF F | Production | BOM Creation | MANUAL
TSF F | Production | Job Work Creation | NA
TSF F | Production | Production Issues | PARTIAL
TSF F | Production | Finished Goods Receipts | PRISM
TSF F | Production | Sub contract work order | NA
SST | Procurement to Payment | Procurement Planning | NA
SST | Procurement to Payment | Purchase Indents | NA
SST | Procurement to Payment | Supplier Quotation | NA
SST | Procurement to Payment | Supplier Order | DESTINY
SST | Procurement to Payment | Gate Pass Entry | MANUAL
SST | Procurement to Payment | Goods Receipts | DESTINY
SST | Procurement to Payment | Supplier Returns | NA
SST | Procurement to Payment | Purchase Inward Notes | DESTINY
SST | Procurement to Payment | Payment Advice | MANUAL
SST | Procurement to Payment | Payment Processing | TALLY
SST | Quality Control | Quality Inspection | DESTINY
SST | Quality Control | Quality Acceptance | DESTINY
SST | Quality Control | Quality Rejection | DESTINY
SST | Quality Control | Quality Rework | MANUAL
SST | Quality Control | Scrap / Waste Management | MANUAL
SST | Quality Control | Second Sales | MANUAL
SST | Cash Sales Management | Customer Order | MANUAL
SST | Cash Sales Management | Cash Invoice | MANUAL
SST | Cash Sales Management | Payment Collections | MANUAL
SST | Credit Sales Management | Sales Forecasting & Planning | NA
SST | Credit Sales Management | Indents | NA
SST | Credit Sales Management | Customer Order | NA
SST | Credit Sales Management | Credit Invoice | NA
SST | Credit Sales Management | Customer Returns | NA
SST | Credit Sales Management | Payment Collections | NA
SST | Inventory & Stores | Store Issues | DESTINY
SST | Inventory & Stores | Delivery Challan | DESTINY
SST | Inventory & Stores | Packing Slip | DESTINY
SST | Inventory & Stores | Store Receipts | DESTINY
SST | Inventory & Stores | Stock Transfers | DESTINY
SST | Inventory & Stores | Item Conversions | MANUAL
SST | Inventory & Stores | Counter Returns | NA
SST | Inventory & Stores | Counter Issues | NA
SST | Inventory & Stores | Job Work Issues | NA
SST | Inventory & Stores | Job Work Returns | NA
SST | Production | Production Planning | NA
SST | Production | BOM Creation | NA
SST | Production | Job Work Creation | NA
SST | Production | Production Issues | NA
SST | Production | Finished Goods Receipts | NA
SST | Production | Sub contract work order | NA
BBT | Procurement to Payment | Procurement Planning | MANUAL
BBT | Procurement to Payment | Purchase Indents | MANUAL
BBT | Procurement to Payment | Supplier Quotation | DESTINY
BBT | Procurement to Payment | Supplier Order | DESTINY
BBT | Procurement to Payment | Gate Pass Entry | MANUAL
BBT | Procurement to Payment | Goods Receipts | DESTINY
BBT | Procurement to Payment | Supplier Returns | DESTINY
BBT | Procurement to Payment | Purchase Inward Notes | DESTINY
BBT | Procurement to Payment | Payment Advice | MANUAL
BBT | Procurement to Payment | Payment Processing | TALLY
BBT | Quality Control | Quality Inspection | DESTINY
BBT | Quality Control | Quality Acceptance | DESTINY
BBT | Quality Control | Quality Rejection | DESTINY
BBT | Quality Control | Quality Rework | MANUAL
BBT | Quality Control | Scrap / Waste Management | MANUAL
BBT | Quality Control | Second Sales | MANUAL
BBT | Cash Sales Management | Customer Order | NA
BBT | Cash Sales Management | Cash Invoice | NA
BBT | Cash Sales Management | Payment Collections | NA
BBT | Credit Sales Management | Sales Forecasting & Planning | MANUAL
BBT | Credit Sales Management | Indents | DESTINY
BBT | Credit Sales Management | Customer Order | DESTINY
BBT | Credit Sales Management | Credit Invoice | DESTINY
BBT | Credit Sales Management | Customer Returns | DESTINY
BBT | Credit Sales Management | Payment Collections | DESTINY
BBT | Inventory & Stores | Store Issues | DESTINY
BBT | Inventory & Stores | Delivery Challan | DESTINY
BBT | Inventory & Stores | Packing Slip | DESTINY
BBT | Inventory & Stores | Store Receipts | DESTINY
BBT | Inventory & Stores | Stock Transfers | DESTINY
BBT | Inventory & Stores | Item Conversions | NA
BBT | Inventory & Stores | Counter Returns | NA
BBT | Inventory & Stores | Counter Issues | NA
BBT | Inventory & Stores | Job Work Issues | NA
BBT | Inventory & Stores | Job Work Returns | NA
BBT | Production | Production Planning | MANUAL
BBT | Production | BOM Creation | NA
BBT | Production | Job Work Creation | DESTINY
BBT | Production | Production Issues | DESTINY
BBT | Production | Finished Goods Receipts | DESTINY
BBT | Production | Sub contract work order | DESTINY

## BP-Pivot
Count of Department | Column Labels
Row Labels | BBT | SST | TSF F | TSF G | Grand Total
DESTINY | 22 | 11 |  | 29 | 62
MANUAL | 9 | 9 | 23 | 11 | 52
NA | 9 | 20 | 7 |  | 36
PARTIAL |  |  | 3 |  | 3
PRISM |  |  | 7 |  | 7
TALLY | 1 | 1 | 1 | 1 | 4
Grand Total | 41 | 41 | 41 | 41 | 164

## Gap Fit Analysis
ISKCON BRASS ENGAGEMENT ( PROCESS WISE, SUB-PROCESS WISE FIT-GAP)
S.No. | Trust | Process | Sub Process |  | ERP Module | Direct Fit (Y/N) | Customization (Y/N) | Recommendation for process changes as per industry standards to make this a direct fit | Approximate Effort in man days | Approximate Customization Effort | Approx. Cost of Customization | Phase | Risk | Business Value
1 | ISKCON | Accounts & Finance | Donation Accounting |  | ?? | No | Yes | Integration with Donation Mgmt. system is recommended to pull the receipt data to finance | 120 | 15 |  | 1
2 | ISKCON | Accounts & Finance | Ticket and Other Incomes Accounting |  | Sales & Receivables | Yes | No |  |  |  |  | 1
3 | ISKCON | Accounts & Finance | Kalyana Mantapa Income Accounting |  | Sales & Receivables | Yes | No |  |  |  |  | 1
4 | ISKCON | Accounts & Finance | Fixed Assets Accounting |  | Fixed Asset | Yes | No |  |  |  |  | 1
5 | ISKCON | Accounts & Finance | General Ledger |  | General Ledger | Yes | No |  |  |  |  | 1
6 | ISKCON | Accounts & Finance | Accounts Payable |  | Purchase & Payables | Yes | No |  |  |  |  | 1
7 | ISKCON | Accounts & Finance | Budget and MIS |  | Financial Management | Yes | No |  |  |  |  | 1
8 | ISKCON | Accounts & Finance | Audit (Internal and External) |  | ?? | ?? | No |  |  |  |  | 1
9 | ISKCON | Accounts & Finance | Taxation |  | India Localization | Yes | No |  |  |  |  | 1
10 | ISKCON | Accounts & Finance | Chart of Accounts |  | Chart of Accounts | Yes | No |  |  |  |  | 1
11 | ISKCON | Accounts & Finance | Balance Score Card |  | ?? | No | Yes |  |  | 6 |  | 1
12 | ISKCON | Procurement to Payment | Purchase Requisition |  | Indent Mgmt | No | Yes | Consolidation of Indent, Purchase Request & Issue based on indent to be customised |  | 14 |  | 1
13 | ISKCON | Procurement to Payment | Material Indent |  | Indent Mgmt | No | Yes |  |  |  |  | 1
14 | ISKCON | Procurement to Payment | Quotation |  | Purchase & Payables | Yes | No |  |  |  |  | 1
15 | ISKCON | Procurement to Payment | Rate Contract |  | Purchase & Payables | Yes | No |  |  |  |  | 1
16 | ISKCON | Procurement to Payment | Purchase Order (Tolerance Limits) |  | Purchase & Payables | Yes | No | P.O Amedment to be used |  |  |  | 1
17 | ISKCON | Procurement to Payment | Purchase Voucher |  | Purchase & Payables | Yes | No |  |  |  |  | 1
18 | ISKCON | Procurement to Payment | Payments |  | Cash Management | Yes | No |  |  |  |  | 1
19 | ISKCON | Inventory & Stores Management | Main Store and Sub Store Management |  | Inventory | Yes | No | Locations to be used |  |  |  | 1
20 | ISKCON | Inventory & Stores Management | Receipt of Goods (GRN) |  | Inventory | Yes | No |  |  |  |  | 1
21 | ISKCON | Inventory & Stores Management | Material Issues |  | Indent Mgmt | No | Yes | Refer point #12 & 13 |  |  |  | 1
22 | ISKCON | Inventory & Stores Management | Quality Inspection & Control |  | QC Module | Yes | No |  |  |  |  | 1
23 | ISKCON | Inventory & Stores Management | Re-order Level, MOQ & UOM conversions |  | Inventory | Yes | No |  |  |  |  | 1
24 | ISKCON | Material Management | Balance Score Card |  | ?? | No | Yes |  |  | 3 |  | 1
25 | ISKCON | Payroll & Statutory Compliance | Payroll |  | Payroll | Yes | No |  |  |  |  | 1
26 | ISKCON | Payroll & Statutory Compliance | Employee TDS |  | Payroll | Yes | No |  |  |  |  | 1
27 | ISKCON | Payroll & Statutory Compliance | Statutory Compliances (PF / ESI etc) |  | Payroll | Yes | No |  |  |  |  | 1
28 | ISKCON | Payroll & Statutory Compliance | Establishment Acts Compliances |  | ?? | ?? | No |  |  |  |  | 1
29 | ISKCON | Human Resource Management (HRMS) | Attendance Management |  | 0-HRMS | ?? | No | Out of ERP. Attendance output to be uploaded to Payroll |  |  |  | 1
30 | ISKCON | Human Resource Management (HRMS) | Recruitment Management |  | 0-HRMS | ?? | No | Available features of HRMS package to be utilized. Any requirement over and above needs to be customised |  |  |  | 1
31 | ISKCON | Human Resource Management (HRMS) | Performance Management |  | 0-HRMS | ?? | No |  |  |  |  | 1
32 | ISKCON | Human Resource Management (HRMS) | Claims Management |  | 0-HRMS | ?? | No |  |  |  |  | 1
33 | ISKCON | Human Resource Management (HRMS) | Compensation & Benefits |  | 0-HRMS | ?? | No |  |  |  |  | 1
34 | ISKCON | Human Resource Management (HRMS) | Travel Management |  | 0-HRMS | ?? | No |  |  |  |  | 1
35 | ISKCON | Human Resource Management (HRMS) | Employee Self Service |  | 0-HRMS | ?? | No |  |  |  |  | 1
36 | ISKCON | Human Resource Management (HRMS) | Exit Management |  | 0-HRMS | ?? | No |  |  |  |  | 1
37 | ISKCON | Human Resource Management (HRMS) | Balance Score Card |  | 0-HRMS | No | Yes |  |  | 6 |  | 1
38 | ISKCON | Reports / Score Card / Dashboards | MIS Reports & Dashboards |  | ?? | No | Yes |  |  | 10 |  | 1
39 | ISKCON | Facility Maintenance |  |  | Plant Maintenance | Yes | No | Plant maintenance module to be used |  |  |  | 1
40 | ISKCON | Customer Relationship Management | Contact Management |  | ?? | Yes | No |  |  |  |  | 1
41 | ISKCON | Donations Management | Donor Master |  | ?? | ?? | No | Refer point #1 |  |  |  | 1
42 | ISKCON | Donations Management | Patron Master |  | ?? | ?? | No |  |  |  |  | 1
43 | ISKCON | Donations Management | Donation Receipt Processing |  | ?? | ?? | No |  |  |  |  | 1
44 | ISKCON | Donations Management | Bahumana Management |  | ?? | ?? | No |  |  |  |  | 1
45 | ISKCON | Donations Management | Dispatch Management |  | Sales & Receivables | Yes | No |  |  |  |  | 1
46 | ISKCON | Donations Management | Inventory Management |  | Inventory | Yes | No |  |  |  |  | 1
47 | ISKCON | Donations Management | Online Donations Management |  | ?? | ?? | No | Refer point #1 |  |  |  | 1
48 | ISKCON | Donations Management | Donor Relationship Management |  | ?? | Yes | No | To the extent of manageing donar involvement with the temple activities and sending related campaigns |  |  |  | 1
49 | ISKCON | Donations Management | Contact Management |  | ?? | Yes | No |  |  |  |  | 1
50 | ISKCON | Donations Management | Tele Marketing |  | ?? | Yes | No | To do can be maintained in the system |  |  |  | 1
51 | ISKCON | Donations Management | Balance Score Card |  | ?? | No | Yes |  |  | 3 |  | 1
52 | ISKCON | Guest House (Yatri Nivas) | Room Booking |  | ?? | No | Yes |  |  | 30 |  | 1
53 | ISKCON | Guest House (Yatri Nivas) | Check In |  | ?? | No | Yes |  |  |  |  | 1
54 | ISKCON | Guest House (Yatri Nivas) | Room Services |  | ?? | No | Yes |  |  |  |  | 1
55 | ISKCON | Guest House (Yatri Nivas) | Billing |  | ?? | No | Yes |  |  |  |  | 1
56 | ISKCON | Guest House (Yatri Nivas) | Patron Privilege Management |  | ?? | No | Yes |  |  |  |  | 1
57 | ISKCON | Guest House (Yatri Nivas) | Balance Score Card |  | ?? | No | Yes |  |  |  |  | 1
58 | TSF-GIFT | Accounts & Finance | Fixed Assets Accounting |  | Fixed Asset | Yes | No |  | 120 |  |  | 2
59 | TSF-GIFT | Accounts & Finance | General Ledger |  | General Ledger | Yes | No |  |  |  |  | 2
60 | TSF-GIFT | Accounts & Finance | Accounts Payable |  | Purchase & Payables | Yes | No |  |  |  |  | 2
61 | TSF-GIFT | Accounts & Finance | Budget and MIS |  | Financial Management | Yes | No |  |  |  |  | 2
62 | TSF-GIFT | Accounts & Finance | Audit (Internal and External) |  | ?? | ?? | No |  |  |  |  | 2
63 | TSF-GIFT | Accounts & Finance | Taxation |  | India Localization | Yes | No |  |  |  |  | 2
64 | TSF-GIFT | Accounts & Finance | Sales & Accounts Receivable |  | Sales & Receivables | Yes | No |  |  |  |  | 2
65 | TSF-GIFT | Sales Forecasting | Cash Sales Forecasting (Internal) |  | Indent Mgmt | Yes | No |  |  |  |  | 2
66 | TSF-GIFT | Sales Forecasting | Credit Sales Forecasting (External) |  | Indent Mgmt | Yes | No |  |  |  |  | 2
67 | TSF-GIFT | Procurement Planning | Material Planning |  | Purchase & Payables | Yes | No |  |  |  |  | 2
68 | TSF-GIFT | Procurement to Payment | Quotation |  | Purchase & Payables | Yes | No |  |  |  |  | 2
69 | TSF-GIFT | Procurement to Payment | Purchase Order |  | Purchase & Payables | Yes | No |  |  |  |  | 2
70 | TSF-GIFT | Procurement to Payment | Supplier Returns |  | Purchase & Payables | Yes | No |  |  |  |  | 2
71 | TSF-GIFT | Procurement to Payment | Bill of Materials |  | Inventory | Yes | No |  |  |  |  | 2
72 | TSF-GIFT | Procurement to Payment | Job Order |  | Sub-contract | Yes | No |  |  |  |  | 2
73 | TSF-GIFT | Procurement to Payment | Sub Contract Work Order |  | Sub-contract | Yes | No |  |  |  |  | 2
74 | TSF-GIFT | Procurement to Payment | Purchase Inward Note |  | Inventory | Yes | No | GRN to be used |  |  |  | 2
75 | TSF-GIFT | Procurement to Payment | Payment Advice |  | Financial Management | Yes | No |  |  |  |  | 2
76 | TSF-GIFT | Inventory Management | GRN |  | Inventory | Yes | No |  |  |  |  | 2
77 | TSF-GIFT | Inventory Management | Quality Inspection |  | QC Module | Yes | No |  |  |  |  | 2
78 | TSF-GIFT | Inventory Management | Rejections & Acceptance |  | QC Module | Yes | No |  |  |  |  | 2
79 | TSF-GIFT | Inventory Management | Item Conversion |  | Inventory | Yes | No |  |  |  |  | 2
80 | TSF-GIFT | Inventory Management | Transfers (within Stores & Sub Stores) |  | Inventory | Yes | No |  |  |  |  | 2
81 | TSF-GIFT | Inventory Management | Issues (Delivery Challan / Packing Slips) |  | Sales & Receivables | Yes | No |  |  |  |  | 2
82 | TSF-GIFT | Inventory Management | Supplier Returns |  | Sales & Receivables | Yes | No |  |  |  |  | 2
83 | TSF-GIFT | Retail Sales | Counter Issues |  | Inventory | Yes | No |  |  |  |  | 2
84 | TSF-GIFT | Retail Sales | Counter Returns |  | Inventory | Yes | No |  |  |  |  | 2
85 | TSF-GIFT | Retail Sales | Counter Transfers |  | Inventory | Yes | No |  |  |  |  | 2
86 | TSF-GIFT | Credit Sales & Exports | Marketing |  | Contact Management | Yes | No |  |  |  |  | 2
87 | TSF-GIFT | Credit Sales & Exports | Quotation |  | Sales & Receivables | Yes | No |  |  |  |  | 2
88 | TSF-GIFT | Credit Sales & Exports | Sample / Complimentary Issues |  | Sales & Receivables | Yes | No |  |  |  |  | 2
89 | TSF-GIFT | Credit Sales & Exports | Customer Order |  | Sales & Receivables | Yes | No |  |  |  |  | 2
90 | TSF-GIFT | Credit Sales & Exports | Customer Order Delivery |  | Sales & Receivables | Yes | No |  |  |  |  | 2
91 | TSF-GIFT | Credit Sales & Exports | Sales Return |  | Sales & Receivables | Yes | No |  |  |  |  | 2
92 | TSF-GIFT | Credit Sales & Exports | Payment Follow-up |  | Sales & Receivables | Yes | No |  |  |  |  | 2
93 | TSF-GIFT | Credit Sales & Exports | Customer Feedback |  | Sales & Receivables | Yes | No |  |  |  |  | 2
94 | TSF-GIFT | Master Data Management | Item Master |  | Inventory | Yes | No |  |  |  |  | 2
95 | TSF-GIFT | Master Data Management | Supplier Master |  | Purchase & Payables | Yes | No |  |  |  |  | 2
96 | TSF-GIFT | Master Data Management | Customer Master |  | Sales & Receivables | Yes | No |  |  |  |  | 2
97 | TSF-GIFT | Master Data Management | BOM Creation |  | Inventory | Yes | No |  |  |  |  | 2
99 | TSF-GIFT | Reports / Score Card / Dashboards | Balance Score Card |  | 0-Reporting | No | Yes |  |  | 3 |  | 2
100 | TSF-GIFT | Job Activities for Magazine Printing | Planning (Quantity to be Printed) |  | ?? | No | Yes | Magazine subscription module to be customised. Content outsourcing will be out of ERP |  | 30 |  | 1
101 | TSF-GIFT | Job Activities for Magazine Printing | Advertisements |  | ?? | No | Yes |  |  |  |  | 1
102 | TSF-GIFT | Job Activities for Magazine Printing | Content Sourcing |  | ?? | No | Yes |  |  |  |  | 1
103 | TSF-GIFT | Job Activities for Magazine Printing | Print Order |  | ?? | No | Yes |  |  |  |  | 1
104 | TSF-GIFT | Job Activities for Magazine Printing | Postal Deliveries |  | ?? | No | Yes |  |  |  |  | 1
105 | TSF-GIFT | Job Activities for Magazine Printing | GRN Receipts |  | ?? | No | Yes |  |  |  |  | 1
106 | TSF-GIFT | Job Activities for Magazine Printing | Inventory Management |  | ?? | No | Yes |  |  |  |  | 1
107 | TSF-GIFT | Subscription Management for Magazines | Subscription Management |  | ?? | No | Yes |  |  |  |  | 1
108 | TSF-GIFT | Subscription Management for Magazines | Label Printing |  | ?? | No | Yes |  |  |  |  | 1
109 | TSF-GIFT | Subscription Management for Magazines | Magazine Dispatch |  | ?? | No | Yes |  |  |  |  | 1
110 | TSF-GIFT | Subscription Management for Magazines | Customer Complaints |  | ?? | No | Yes |  |  |  |  | 1
111 | TSF-GIFT | Subscription Management for Magazines | Marketing (Direct / Tele Marketing) |  | ?? | No | Yes |  |  |  |  | 1
112 | TSF-GIFT | Subscription Management for Magazines | Complimentary Gifts |  | ?? | No | Yes |  |  |  |  | 1
113 | TSF-GIFT | Subscription Management for Magazines | Adyathmika Vidya Dana |  | ?? | No | Yes |  |  |  |  | 1
114 | TSF-GIFT | Reports / Score Card / Dashboards | MIS Reports & Dashboards |  | 0-Reporting | No | Yes |  |  |  |  | 1
115 | TSF-FOOD | Accounts & Finance | Fixed Assets Accounting |  | Fixed Asset | Yes | No |  | 150 |  |  | 2
116 | TSF-FOOD | Accounts & Finance | General Ledger |  | General Ledger | Yes | No |  |  |  |  | 2
117 | TSF-FOOD | Accounts & Finance | Accounts Payable |  | Purchase & Payables | Yes | No |  |  |  |  | 2
118 | TSF-FOOD | Accounts & Finance | Budget and MIS |  | Financial Management | Yes | No |  |  |  |  | 2
119 | TSF-FOOD | Accounts & Finance | Audit (Internal and External) |  | ?? | ?? | No |  |  |  |  | 2
120 | TSF-FOOD | Accounts & Finance | Taxation |  | India Localization | Yes | No |  |  |  |  | 2
121 | TSF-FOOD | Forecast | Catering / Retail / Events |  | Indent Mgmt | Yes | No |  |  |  |  | 2
122 | TSF-FOOD | Retail Sales | Cash Sales |  | Sales & Receivables | Yes | No |  |  |  |  | 2
123 | TSF-FOOD | Retail Sales | Credit Sales |  | Sales & Receivables | Yes | No |  |  |  |  | 2
124 | TSF-FOOD | Retail Sales | Wastage |  | Inventory | Yes | No |  |  |  |  | 2
125 | TSF-FOOD | Retail Sales | Indents |  | Indent Mgmt | No | Yes | Refer Point # 12 & 13 |  |  |  | 2
126 | TSF-FOOD | Retail Sales | Sales Returns |  | Sales & Receivables | Yes | No |  |  |  |  | 2
127 | TSF-FOOD | Retail Sales | Stock Returns |  | Sales & Receivables | Yes | No |  |  |  |  | 2
128 | TSF-FOOD | Retail Sales | Cash Collections |  | Sales & Receivables | Yes | No |  |  |  |  | 2
129 | TSF-FOOD | Retail Sales | Cash Settlement |  | Financial Management | Yes | No |  |  |  |  | 2
130 | TSF-FOOD | Retail Sales | Discount Approvals |  | Sales & Receivables | Yes | No |  |  |  |  | 2
131 | TSF-FOOD | Credit Sales | Customer Order (Catering / Events / Cakes) |  | Sales & Receivables | Yes | No |  |  |  |  | 2
132 | TSF-FOOD | Credit Sales | Indents |  | Indent Mgmt | No | Yes | Refer Point # 12 & 13 |  |  |  | 2
133 | TSF-FOOD | Credit Sales | Order Fulfilment |  | ?? | ?? | No |  |  |  |  | 2
134 | TSF-FOOD | Retail Sales / Credit Sales | Customer Feedback |  | Sales & Receivables | Yes | No |  |  |  |  | 2
135 | TSF-FOOD | Stores (FGA) | Order Consolidation |  | Indent Mgmt | No | Yes | Refer Point # 12 & 13 |  |  |  | 2
136 | TSF-FOOD | Stores (FGA) | Production Indent |  | Indent Mgmt | No | Yes |  |  |  |  | 2
137 | TSF-FOOD | Stores (FGA) | Item Issues |  | Indent Mgmt | No | Yes |  |  |  |  | 2
138 | TSF-FOOD | Stores (FGA) | Item Receipts |  | Indent Mgmt | No | Yes |  |  |  |  | 2
139 | TSF-FOOD | Stores (FGA) | Wastage |  | Inventory | Yes | No |  |  |  |  | 2
140 | TSF-FOOD | Stores (FGA) | Internal Transfers |  | Inventory | Yes | No |  |  |  |  | 2
141 | TSF-FOOD | Production Planning | Material Planning |  | Manufacturing | Yes | No |  |  |  |  | 2
142 | TSF-FOOD | Production Planning | Production Orders |  | Manufacturing | Yes | No |  |  |  |  | 2
143 | TSF-FOOD | Production Planning | Production Indent to Stores |  | Indent Mgmt | No | Yes | Refer Point # 12 & 13 |  |  |  | 2
144 | TSF-FOOD | Production Planning | Bill of Materials |  | Inventory | Yes | No |  |  |  |  | 2
145 | TSF-FOOD | Production Planning | Receipts against indents |  | Inventory | Yes | No |  |  |  |  | 2
146 | TSF-FOOD | Production Planning | Rejection & Damages |  | Inventory | Yes | No |  |  |  |  | 2
147 | TSF-FOOD | Inventory Management | Indent Consolidation |  | Indent Mgmt | No | yes | Refer Point # 12 & 13 |  |  |  | 2
148 | TSF-FOOD | Inventory Management | Purchase Request |  | Indent Mgmt | No | yes |  |  |  |  | 2
149 | TSF-FOOD | Inventory Management | Receipt of Goods (GRN) |  | Inventory | Yes | No |  |  |  |  | 2
150 | TSF-FOOD | Inventory Management | Quality Inspection (FSMS standard) |  | QC Module | Yes | No |  |  |  |  | 2
151 | TSF-FOOD | Inventory Management | Rejections & Acceptance |  | QC Module | Yes | No |  |  |  |  | 2
152 | TSF-FOOD | Inventory Management | Raw Material Issues |  | Inventory | Yes | No |  |  |  |  | 2
153 | TSF-FOOD | Procurement Planning | Quotations |  | Purchase & Payables | Yes | No |  |  |  |  | 2
154 | TSF-FOOD | Procurement Planning | Purchase Order |  | Purchase & Payables | Yes | No |  |  |  |  | 2
155 | TSF-FOOD | Procurement Planning | Payment Advice |  | Financial Management | Yes | No |  |  |  |  | 2
156 | TSF-FOOD | Procurement Planning | Gate Entry |  | Gate Entry | Yes | No |  |  |  |  | 2
157 | TSF-FOOD | Procurement Planning | Supplier Returns |  | Purchase & Payables | Yes | No |  |  |  |  | 2
158 | TSF-FOOD | Master Data Management | Item Master |  | Inventory | Yes | No |  |  |  |  | 2
159 | TSF-FOOD | Master Data Management | Supplier Master |  | Purchase & Payables | Yes | No |  |  |  |  | 2
160 | TSF-FOOD | Master Data Management | Customer Master |  | Sales & Receivables | Yes | No |  |  |  |  | 2
161 | TSF-FOOD | Master Data Management | BOM Creation |  | Manufacturing | Yes | No |  |  |  |  | 2
162 | TSF-FOOD | Reports / Score Card / Dashboards | Balance Score Card |  | ?? | No | Yes |  |  | 3 |  | 2
163 | TSF-FOOD | Reports / Score Card / Dashboards | MIS Reports & Dashboards |  | 0-Reporting | No | Yes |  |  | 5 |  | 2
164 | GST | Accounts & Finance | General Ledger |  | General Ledger | Yes | No |  | 100 |  |  | 1
165 | GST | Accounts & Finance | Fixed Assets Accounting |  | Fixed Asset | Yes | No |  |  |  |  | 1
166 | GST | Accounts & Finance | Domestic Sales |  | Sales & Receivables | Yes | No |  |  |  |  | 1
167 | GST | Accounts & Finance | E-BRC |  | ?? | ?? | No |  |  |  |  | 1
168 | GST | Accounts & Finance | Export and Deemed Export |  | ?? | ?? | No | Documentation to be maintained outside ERP |  |  |  | 1
169 | GST | Accounts & Finance | Duty Drawback & other Export Compliances |  | ?? | ?? | No | Documentation to be maintained outside ERP |  |  |  | 1
170 | GST | Accounts & Finance | Budget and MIS |  | Financial Management | Yes | No | Budget Vs Actul to be utilized |  |  |  | 1
171 | GST | Accounts & Finance | Accounts Payable |  | Purchase & Payables | Yes | No |  |  |  |  | 1
172 | GST | Accounts & Finance | Accounts Receivables |  | Sales & Receivables | Yes | No |  |  |  |  | 1
173 | GST | Accounts & Finance | Audit (Internal and External) |  | ?? | ?? | No |  |  |  |  | 1
174 | GST | Accounts & Finance | Taxation |  | India Localization | Yes | No |  |  |  |  | 1
175 | GST | Procurement Planning | Purchase Requisition |  | Indent Mgmt | No | Yes | Refer Point # 12 & 13 |  |  |  | 1
176 | GST | Procurement Planning | Material Indent |  | Indent Mgmt | No | Yes |  |  |  |  | 1
177 | GST | Procurement Planning | Quotation |  | Purchase & Payables | Yes | No |  |  |  |  | 1
178 | GST | Procurement Planning | Rate Contract |  | Purchase & Payables | Yes | No |  |  |  |  | 1
179 | GST | Procurement Planning | Purchase Order (Tolerance Limits) |  | Purchase & Payables | Yes | No | P.O Amendment to be used |  |  |  | 1
180 | GST | Procurement Planning | Purchase Voucher |  | Purchase & Payables | Yes | No |  |  |  |  | 1
181 | GST | Procurement Planning | Payments |  | Purchase & Payables | Yes | No |  |  |  |  | 1
Approve Invoice
Relase Cheque
182 | GST | Inventory Management | Main Store and Sub Store Management |  | Inventory | Yes | No |  |  |  |  | 1
183 | GST | Inventory Management | Receipt of Goods (GRN) |  | Inventory | Yes | No |  |  |  |  | 1
184 | GST | Inventory Management | Material Issues |  | Manufacturing | Partial | Yes | Partial customisation is required |  | 4 |  | 1
185 | GST | Inventory Management | Quality Inspection & Control |  | QC Module | Yes | No |  |  |  |  | 1
186 | GST | Inventory Management | Re-order Level, MOQ & UOM conversions |  | Inventory | Yes | No |  |  |  |  | 1
187 | GST | Inventory Management | Bundling of SKU (Combo Packs) |  | Inventory | Yes | No | Use Assembly BOM |  |  |  | 1
188 | GST | Sales Management | Point of Sales |  | ?? | No | No | Separate POS |  |  |  | 1
189 | GST | Sales Management | Export Sales & Compliances |  | Sales & Receivables | Partial | Yes | Documentation to be maintained outside ERP |  | 3 |  | 1
190 | GST | Sales Management | Online Sales |  | Sales & Receivables | No | Yes | Web order Integration with NAV recommended |  | 22 |  | 1
191 | GST | Reports / Score Card / Dashboards | Balance Score Card |  | ?? | No | Yes |  |  | 3 |  | 1
192 | GST | Reports / Score Card / Dashboards | MIS Reports & Dashboards |  | 0-Reporting | No | Yes |  |  | 10 |  | 1
|  |  | TOTAL EFFORT | [5 empty] | 490 | 170
Note on D2: (identify the sub processes for each of the process listed here… you can add more rows for each sub process)
Note on G2: Name of Module available in ERP to fit this process
Note on D67: We will receive the sales forecast from our temple counters, mobile vans (BM) and the magazine division. Based on this requirement the procurement is planned.
Note on D68: Based on the expected customer order, the sales team forecasts the requirements which is given as input to procurement planning. This is not based on delivery date promised to customer.
Note on D69: The forecast information received from sales team (for cash sales and credit sales) become input for planning the procurement of materials. Based on this purchase indents are made and sent to procurement team.
Note on C85: Temple Counters / Mobile Vans / Online Sales / External
Note on C86: Temple Counters / Mobile Vans / Online Sales / External
Note on C87: Temple Counters / Mobile Vans / Online Sales / External
Note on D88: Marketing team meets customers and generate enquiries.
Note on D89: For the enquiries received, Sales Executives prepare quotation and send to customer.
Note on D90: Samples are issued to the marketing team for showing to customers. Sometimes they can also give it to customer as a compliment.
Note on D91: Customer order is received by sales executives. Without sending quotations, sometimes we receive order from existing customers also.
Note on D92: Stores will prepare outward Delivery challan (DC) and Packing Slip (in case of external customers) - invoice is generated based on the DC - the material is delivered and an acknowledgement taken in copy of invoice.
Note on D93: Against an invoice the items returned by the customer are taken back.
Note on D94: Based on the credit terms with customer sales team follows up for the payments.
Note on D123: Internal / Retail Shops / Restaurant / Catering / Events
Note on D124: Catering / Events / Packed Products / Cakes

## Gap-Pivot
Row Labels | Count of S.No.
Accounts & Finance | 35
Accounts Payable | 4
Accounts Receivables | 1
Audit (Internal and External) | 4
Balance Score Card | 1
Budget and MIS | 4
Chart of Accounts | 1
Domestic Sales | 1
Donation Accounting | 1
Duty Drawback & other Export Compliances | 1
E-BRC | 1
Export and Deemed Export | 1
Fixed Assets Accounting | 4
General Ledger | 4
Kalyana Mantapa Income Accounting | 1
Sales & Accounts Receivable | 1
Taxation | 4
Ticket and Other Incomes Accounting | 1
Credit Sales | 3
Customer Order (Catering / Events / Cakes) | 1
Indents | 1
Order Fulfilment | 1
Credit Sales & Exports | 8
Customer Feedback | 1
Customer Order | 1
Customer Order Delivery | 1
Marketing | 1
Payment Follow-up | 1
Quotation | 1
Sales Return | 1
Sample / Complimentary Issues | 1
Customer Relationship Management | 1
Contact Management | 1
Donations Management | 11
Bahumana Management | 1
Balance Score Card | 1
Contact Management | 1
Dispatch Management | 1
Donation Receipt Processing | 1
Donor Master | 1
Donor Relationship Management | 1
Inventory Management | 1
Online Donations Management | 1
Patron Master | 1
Tele Marketing | 1
Facility Maintenance | 1
(blank) | 1
Forecast | 1
Catering / Retail / Events | 1
Guest House (Yatri Nivas) | 6
Balance Score Card | 1
Billing | 1
Check In | 1
Patron Privilege Management | 1
Room Booking | 1
Room Services | 1
Human Resource Management (HRMS) | 9
Attendance Management | 1
Balance Score Card | 1
Claims Management | 1
Compensation & Benefits | 1
Employee Self Service | 1
Exit Management | 1
Performance Management | 1
Recruitment Management | 1
Travel Management | 1
Inventory & Stores Management | 5
Main Store and Sub Store Management | 1
Material Issues | 1
Quality Inspection & Control | 1
Receipt of Goods (GRN) | 1
Re-order Level, MOQ & UOM conversions | 1
Inventory Management | 19
Bundling of SKU (Combo Packs) | 1
GRN | 1
Indent Consolidation | 1
Issues (Delivery Challan / Packing Slips) | 1
Item Conversion | 1
Main Store and Sub Store Management | 1
Material Issues | 1
Purchase Request | 1
Quality Inspection | 1
Quality Inspection & Control | 1
Quality Inspection (FSMS standard) | 1
Raw Material Issues | 1
Receipt of Goods (GRN) | 2
Rejections & Acceptance | 2
Re-order Level, MOQ & UOM conversions | 1
Supplier Returns | 1
Transfers (within Stores & Sub Stores) | 1
Job Activities for Magazine Printing | 7
Advertisements | 1
Content Sourcing | 1
GRN Receipts | 1
Inventory Management | 1
Planning (Quantity to be Printed) | 1
Postal Deliveries | 1
Print Order | 1
Master Data Management | 8
BOM Creation | 2
Customer Master | 2
Item Master | 2
Supplier Master | 2
Material Management | 1
Balance Score Card | 1
Payroll & Statutory Compliance | 4
Employee TDS | 1
Establishment Acts Compliances | 1
Payroll | 1
Statutory Compliances (PF / ESI etc) | 1
Procurement Planning | 13
Gate Entry | 1
Material Indent | 1
Material Planning | 1
Payment Advice | 1
Payments | 1
Purchase Order | 1
Purchase Order (Tolerance Limits) | 1
Purchase Requisition | 1
Purchase Voucher | 1
Quotation | 1
Quotations | 1
Rate Contract | 1
Supplier Returns | 1
Procurement to Payment | 15
Bill of Materials | 1
Job Order | 1
Material Indent | 1
Payment Advice | 1
Payments | 1
Purchase Inward Note | 1
Purchase Order | 1
Purchase Order (Tolerance Limits) | 1
Purchase Requisition | 1
Purchase Voucher | 1
Quotation | 2
Rate Contract | 1
Sub Contract Work Order | 1
Supplier Returns | 1
Production Planning | 6
Bill of Materials | 1
Material Planning | 1
Production Indent to Stores | 1
Production Orders | 1
Receipts against indents | 1
Rejection & Damages | 1
Reports / Score Card / Dashboards | 7
Balance Score Card | 3
MIS Reports & Dashboards | 4
Retail Sales | 3
Counter Issues | 1
Counter Returns | 1
Counter Transfers | 1
Retail Sales | 9
Cash Collections | 1
Cash Sales | 1
Cash Settlement | 1
Credit Sales | 1
Discount Approvals | 1
Indents | 1
Sales Returns | 1
Stock Returns | 1
Wastage | 1
Retail Sales / Credit Sales | 1
Customer Feedback | 1
Sales Forecasting | 2
Cash Sales Forecasting (Internal) | 1
Credit Sales Forecasting (External) | 1
Sales Management | 3
Export Sales & Compliances | 1
Online Sales | 1
Point of Sales | 1
Stores (FGA) | 6
Internal Transfers | 1
Item Issues | 1
Item Receipts | 1
Order Consolidation | 1
Production Indent | 1
Wastage | 1
Subscription Management for Magazines | 7
Adyathmika Vidya Dana | 1
Complimentary Gifts | 1
Customer Complaints | 1
Label Printing | 1
Magazine Dispatch | 1
Marketing (Direct / Tele Marketing) | 1
Subscription Management | 1
Grand Total | 191

## Business Processes
| TSF G | TSF F | SST | BBT
Procurement to Payment
Procurement Planning | MANUAL | MANUAL | NA | MANUAL
Purchase Indents | MANUAL | MANUAL | NA | MANUAL
Supplier Quotation | DESTINY | MANUAL | NA | DESTINY
Supplier Order | DESTINY | PRISM | DESTINY | DESTINY
Gate Pass Entry | MANUAL | MANUAL | MANUAL | MANUAL
Goods Receipts | DESTINY | PRISM | DESTINY | DESTINY
Supplier Returns | DESTINY | PRISM | NA | DESTINY
Purchase Inward Notes | DESTINY | NA | DESTINY | DESTINY
Payment Advice | MANUAL | MANUAL | MANUAL | MANUAL
Payment Processing | TALLY | TALLY | TALLY | TALLY
Quality Control
Quality Inspection | DESTINY | MANUAL | DESTINY | DESTINY
Quality Acceptance | DESTINY | MANUAL | DESTINY | DESTINY
Quality Rejection | DESTINY | MANUAL | DESTINY | DESTINY
Quality Rework | MANUAL | NA | MANUAL | MANUAL
Scrap / Waste Management | MANUAL | MANUAL | MANUAL | MANUAL
Second Sales | MANUAL | NA | MANUAL | MANUAL
Cash Sales Management
Customer Order | DESTINY | MANUAL | MANUAL | NA
Cash Invoice | DESTINY | MANUAL | MANUAL | NA
Payment Collections | DESTINY | MANUAL | MANUAL | NA
Credit Sales Management
Sales Forecasting & Planning | MANUAL | MANUAL | NA | MANUAL
Indents | DESTINY | PARTIAL | NA | DESTINY
Customer Order | DESTINY | PARTIAL | NA | DESTINY
Credit Invoice | DESTINY | MANUAL | NA | DESTINY
Customer Returns | DESTINY | MANUAL | NA | DESTINY
Payment Collections | DESTINY | MANUAL | NA | DESTINY
Inventory & Stores
Store Issues | DESTINY | PRISM | DESTINY | DESTINY
Delivery Challan | DESTINY | MANUAL | DESTINY | DESTINY
Packing Slip | DESTINY | MANUAL | DESTINY | DESTINY
Store Receipts | DESTINY | PRISM | DESTINY | DESTINY
Stock Transfers | DESTINY | PRISM | DESTINY | DESTINY
Item Conversions | MANUAL | MANUAL | MANUAL | NA
Counter Returns | DESTINY | MANUAL | NA | NA
Counter Issues | DESTINY | MANUAL | NA | NA
Job Work Issues | DESTINY | NA | NA | NA
Job Work Returns | DESTINY | NA | NA | NA
Production
Production Planning | MANUAL | MANUAL | NA | MANUAL
BOM Creation | MANUAL | MANUAL | NA | NA
Job Work Creation | DESTINY | NA | NA | DESTINY
Production Issues | DESTINY | PARTIAL | NA | DESTINY
Finished Goods Receipts | DESTINY | PRISM | NA | DESTINY
Sub contract work order | DESTINY | NA | NA | DESTINY

## ERP Modules Applicable
ERP MODULES
Cash Management
Chart of Accounts
Contact Management
Financial Management
Fixed Asset
Gate Entry
General Ledger
Indent Mgmt
India Localization
Inventory
Manufacturing
Purchase & Payables
QC Module
Sales & Receivables
Sub-contract

## Build vs. Integration
Integration/Customisation of process
Sl.No. | Gap Fit Ref. | Process | Sub-process | Integration | Configuration or customization
1 | 1 | Accounts & Finance | Donation Accounting | Dhananjaya- in-house built system is currently used, having facilitites to update donor info; schemes, Bahumana, Donation Receipt and reporting functionalities. Link to the financial module is missing and in Finance, separte receipts are put for each donation As ISKCON users are satisfactied with this module and building the same in ERP is time consuming and costly, Its recommended to integrate the same with the Finance module in ERP. | Donation receipt to Financial Ledgers to be integrated
2 | 12 | Procurement-to-payment | Purchase Requisition | In MBS Dynamics Nav, Requisitions are independent (cannot be consolidated) and linked to the P.O. As ISKCON wants to consolidate the Indents and then raise the P.O and tracking of material issue against the indents, customization is recommended | Customization
3 | 13 | Procurement to Payment | Material Indent
4 | 21 | Inventory & Stores Management | Material Issues
5 | 52 | Guest House (Yatri Nivas) | Room Booking | An in-house developed program is used for Guest House Management currently. This is not fulfilling the requirements. Hence its recommended to customise the entire module in ERP so that it can be operated in an integrated manner. | Customization
6 | 53 | Guest House (Yatri Nivas) | Check In
7 | 54 | Guest House (Yatri Nivas) | Room Services
8 | 55 | Guest House (Yatri Nivas) | Billing
9 | 56 | Guest House (Yatri Nivas) | Patron Privilege Management
10 | 100 | Job Activities for Magazine Printing | Planning (Quantity to be Printed) | Costing based on various parameters to be customised | Customization
11 | 107-113 | Subscription Management for Magazines | Subscription Management | Magazine subscription module to be customised | Customization
12 | 125 | Retail Sales | Indents | Refer sl. No. 2 of this page | Customization
13 | 132 | Credit Sales | Indents | Refer sl. No. 2 of this page | Customization
14 | 135 | Stores (FGA) | Order Consolidation | Indent and Sales orders would be consolidated and linked to the production order. Issue and receipt against the indents to be done. Customization is recommended. | Customization
15 | 136 | Stores (FGA) | Production Indent
16 | 137 | Stores (FGA) | Item Issues
17 | 138 | Stores (FGA) | Item Receipts
18 | 143 | Production Planning | Production Indent to Stores
19 | 147 | Inventory Management | Indent Consolidation
20 | 148 | Inventory Management | Purchase Request
21 | 175 | Procurement Planning | Purchase Requisition
22 | 176 | Procurement Planning | Material Indent
23 | 184 | Inventory Management | Material Issues
24 | 189 | Sales Management | Export Sales & Compliances | Customisation based on specific requirements | Customization
25 | 190 | Sales Management | Online Sales | Sales order information to be downloaded to NAV | Integration of web orders with NAV
27 | 39 | Facility Maintenance | Plant maintenance | Add-On Module yet to be procured | Configuration
28 | 25 | Payroll & Statutory Compliance | Payroll and HR module | Add-On Module yet to be procured | Configuration
29 | 77-78 | Inventory Management | Quality Module | Add-On Module yet to be procured | Configuration
26 |  |  | Point of Sales | To be decided based on the type of POS going to be procured | Integration with NAV

## Users
EMPLOYEE ID | EMPLOYEE NAME | DESIGNATION | TRUST | DIVISION | DEPARTMENT | User CAL
ISK-1414 | BASAVARAJU K S | Executive Assistant | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1360 | CHANDRU K | Executive - Accounts | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1351 | GEETHA R | Executive - Finance | IB | Accounts & Finance | Accounts & Finance | Full User CAL
GSP-0001 | HARISH RAO A | Head - Service Line | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1394 | KOUSHIK C | Sr. Executive - Accounts | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1047 | KRISHNA SAGAR V | Sr. Executive - Accounts | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1275 | KRISHNAMURTHY B G | Deputy Manager - Taxation & Audit | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-0931 | MADHU H R | Executive - Accounts | IB | Accounts & Finance | Accounts & Finance | Full User CAL
MSC-9989 | RAJU DHANASEKARAN | Consultant | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1046 | RAMESH N RAO | Deputy Manager - Banking & Treasury | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-0506 | SANGEETHA RAMESH V | Sr. Executive - Accounts | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1304 | SHALINI M | Jr. Executive - Accounts | IB | Accounts & Finance | Accounts & Finance | Full User CAL
DEV-2362 | SHYAMA VALLABHA DASA | Head - Accounts & Finance | IB | Accounts & Finance | Accounts & Finance | Full User CAL
1900018 | SUDHAKAR REDDY | Audit Trainee | IB | Accounts & Finance | Accounts & Finance | Full User CAL
TSF-0352 | SUJATHA SHUKLA | Executive - Accounts | IB | Accounts & Finance | Accounts & Finance | Full User CAL
GSP-0002 | UMESH P R | Unit Head - Banking & Treasury | IB | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1231 | YUVARAJ | Sr. Executive - Accounts | IB | Accounts & Finance | Accounts & Finance | Full User CAL
DEV-2171 | PATITA PAVANA DASA | Sub-editor - Content Development | IB | Bhaktivedanta Darshana | Bhaktivedanta Darshana | Limited User CAL
DEV-2129 | SHUKADEVA DASA | Devotee | IB | Brahmachari Ashram Mgmt. | Brahmachari Ashram Mgmt.
ISK-0189 | SREENIVASULU B | Asst. Ashram | IB | Brahmachari Ashram Mgmt. | Brahmachari Ashram Mgmt. | Limited User CAL
DEV-2145 | VAMSIDHARA DASA | Temple Commander | IB | Brahmachari Ashram Mgmt. | Brahmachari Ashram Mgmt. | Limited User CAL
DEV-2309 | VEDAVYASA DASA | Devotee | IB | Brahmachari Ashram Mgmt. | Brahmachari Ashram Mgmt.
DEV-1003 | BHAKTI LATHA DEVI DASI | - | IB | Creative Architecture Services | Creative Architecture Services
ISK-0024 | LOKESH KUMAR R | Executive - Graphics | IB | Creative Services | Creative Services
ISK-0010 | RAVI PAWAR | Executive - Graphics | IB | Creative Services | Creative Services
ISK-0066 | SACHIN SOMASUNDARAN N | 2D Visualizer | IB | Creative Services | Creative Services
ISK-0042 | SATYANARAYANA P H | Photographer | IB | Creative Services | Creative Services
ISK-1037 | SUDHAKARA D | Executive - Graphics | IB | Creative Services | Creative Services
ISK-0004 | SURESH RAI | Unit Head - Graphics | IB | Creative Services | Creative Services
ISK-0005 | BABU THIPPESWAMY | Team Lead - Promotion & Sales | IB | Cultural Education Services | Cultural Education Services | Limited User CAL
ISK-0737 | MANJUNATH R | Sr. Event Co-ordinator | IB | Cultural Education Services | Cultural Education Services | Limited User CAL
ISK-1203 | MOHITH ARORA | Executive | IB | Cultural Education Services | Cultural Education Services | Limited User CAL
ISK-1143 | RAMESH N KULKARNI | Executive | IB | Cultural Education Services | Cultural Education Services | Limited User CAL
ISK-0836 | SHUBANGA CHAITANYA DASA | Unit Head - CES | IB | Cultural Education Services | Cultural Education Services | Full User CAL
ISK-0657 | SUDHIR S | Team Lead - Content Development | IB | Cultural Education Services | Cultural Education Services
1000372 | SUNDER VADIVELU | Sr. Executive - Marketing | IB | Cultural Education Services | Cultural Education Services | Limited User CAL
ISK-0078 | ABHIRAMA DASA | Unit Head - Service | IB | Dhananjaya | Dhananjaya | Full User CAL
DEV-2147 | ACHARYA RATNA DASA | Public Relations Officer | IB | Dhananjaya | Dhananjaya
ISK-0424 | ASHA P | Communication | IB | Dhananjaya | Dhananjaya
ISK-0307 | AVINASH A T | Executive - FOLK Operations | IB | Dhananjaya | Dhananjaya
ISK-0854 | GUNDAPPA PUJARI | Executive | IB | Dhananjaya | Dhananjaya
DEV-2329 | HEMANGA CHAITANYA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2185 | ISHVARA PURI DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
ISK-0163 | KANTHARAJU S | Office Assistant | IB | Dhananjaya | Dhananjaya
DEV-2178 | KRISHNA SAKHA DASA | Division Head - Dhananjaya | IB | Dhananjaya | Dhananjaya
ISK-0561 | KUSUMA S | Tele Caller | IB | Dhananjaya | Dhananjaya
DEV-2333 | LAKSHMANA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2089 | LALITHAASHRAYA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2041 | MADHAVA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2035 | MAHAVISHNU DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2106 | MEGHASHYAM DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2060 | NADIYA VIHARI DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2331 | NANDA KISHORE DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
ISK-0638 | NATARAJ | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2141 | NILOTPALA SHYAMA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2038 | NITYA TRIPTA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
ISK-1132 | NITYANANDA RAMA DASA | Emp-Preacher | IB | Dhananjaya | Dhananjaya
DEV-2074 | PANKAJA NABHA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2140 | PRACHETHA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2080 | PRANA CHAITANYA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
ISK-0530 | PRASHANTH K | Data Entry Operator | IB | Dhananjaya | Dhananjaya
ISK-0831 | RAGHAVENDRA RAO S | Manager - Operations | IB | Dhananjaya | Dhananjaya | Full User CAL
DEV-2154 | RAGHUKULA NANDANA DASA | Public Relations Officer | IB | Dhananjaya | Dhananjaya
ISK-0164 | RAJESH | Office Assistant | IB | Dhananjaya | Dhananjaya
ISK-0570 | ROOPA DEVI N | Tele Caller | IB | Dhananjaya | Dhananjaya
ISK-0135 | SHEELA K | Sr. Associate | IB | Dhananjaya | Dhananjaya
ISK-1411 | SHIVA KUMAR B M | Office Assistant | IB | Dhananjaya | Dhananjaya
ISK-0047 | SHIVA MURTHY V K | Sr. Executive | IB | Dhananjaya | Dhananjaya
ISK-0601 | SHUBHA C | Tele Caller | IB | Dhananjaya | Dhananjaya
DEV-2247 | SITAKANTA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
DEV-2039 | SRIDHAM KRISHNA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
ISK-0660 | SRINIVASA D | Executive | IB | Dhananjaya | Dhananjaya
ISK-1377 | SRINIVASA K | Office Assistant | IB | Dhananjaya | Dhananjaya
ISK-0090 | SUSHMA BHUSHAN | Executive - Secretary | IB | Dhananjaya | Dhananjaya
ISK-0136 | USHA BAI R | Tele Caller | IB | Dhananjaya | Dhananjaya
ISK-1013 | UTTAM MADHAVA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
ISK-0055 | VANITHA B U | Sr. Executive - Front Desk | IB | Dhananjaya | Dhananjaya
DEV-2016 | VARADA SIMHA DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
ISK-0400 | VIBHA V | Sr. Executive | IB | Dhananjaya | Dhananjaya
DEV-2107 | VRINDAVAN DHAM DASA | LLP Preacher | IB | Dhananjaya | Dhananjaya
GSP-0005 | KARUNAKARAN K | Deputy Manager - Projects | IB | Engineering & Constructions | Vaikuntha Hill | Full User CAL
GSP-0004 | SATYAMEDHA DASA | Sr. General Manager - Projects | IB | Engineering & Constructions | Vaikuntha Hill | Full User CAL
ISK-0832 | AGRANI KRISHNA DASA | Sr. Executive | IB | e-Presence | e-Presence
ISK-1075 | AKSHAR BRAHMA DASA | Unit Head - Visuals / Events | IB | e-Presence | e-Presence
ISK-1378 | APARNA G | Jr. Executive - Web Administration | IB | e-Presence | e-Presence
ISK-1385 | BHAGYALAKSHMI V | Executive - Social Media | IB | e-Presence | e-Presence
DEV-1004 | CHITRA DEVI DASI | Executive - Content Development | IB | e-Presence | e-Presence
ISK-1298 | DEEPAK V C | Graphics Designer cum Video Editor | IB | e-Presence | e-Presence
ISK- 1412 | DHANUSH M | Administrative Assistance | IB | e-Presence | e-Presence
ISK-1279 | GOPINATH R DAMALE | Executive - Content Development | IB | e-Presence | e-Presence
DEV-2218 | JAGAT JIVAN DASA | Content Writer | IB | e-Presence | e-Presence
ISK-1402 | JITHENDRA BABU HB | Graphics Designer | IB | e-Presence | e-Presence
ISK-1263 | KANHU CHRAN GOUDA | Executive - Web Administration | IB | e-Presence | e-Presence
ISK-1257 | LAKSHMANA N R | SEO Executive | IB | e-Presence | e-Presence
ISK-0015 | MANJUNATH N | Co-ordinator | IB | e-Presence | e-Presence
ISK-1312 | PREM KUMAR | Image Content Developer | IB | e-Presence | e-Presence
FTCISK-034 | SUPREET M DURGAD | Graphic Designer cum Video editor | IB | e-Presence | e-Presence
ISK-1071 | APPANNA S K | Manager - Kalyana Mantapa | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
ISK-1341 | BHAGYALAKSHMI R | Executive - Secretary | IB | Facilities & Utilities | Facilities & Utilities | Limited User CAL
ISK-0193 | DHANDAPANI S |  | IB | Facilities & Utilities | Facilities & Utilities
ISK-0167 | JAGADISH S | Office Assistant | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
ISK-0425 | KARNA | CCTV Operator | IB | Facilities & Utilities | Facilities & Utilities
DEV-2160 | LAKSHMISHA DASA | Unit Head - Maintenance | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
DEV-2220 | MAHAPRABHU GAURANGA DASA | LLP Preacher | IB | Facilities & Utilities | Facilities & Utilities
ISK-1283 | MOHAN S | - | IB | Facilities & Utilities | Facilities & Utilities
ISK-1251 | MURALI T M | Site Engineer | IB | Facilities & Utilities | Facilities & Utilities | Limited User CAL
FTCISK-016 | NARAYAN M |  | IB | Facilities & Utilities | Facilities & Utilities
DEV-2225 | PRAHLADEESHA DASA | Division Head - Facilities | IB | Facilities & Utilities | Facilities & Utilities | Limited User CAL
ISK-1106 | PRAKASH D | Manager - Transport | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
ISK-1134 | PUSHPA SRINATH | Executive - Front Desk | IB | Facilities & Utilities | Facilities & Utilities | Limited User CAL
ISK-0742 | SANJAY KUMAR BHALLA | Chief Security Officer | IB | Facilities & Utilities | Facilities & Utilities
ISK-1258 | SELVAM V | Executive - House Keeping | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
ISK-0187 | SHASHIDHAR | Supervisor - Maintanance & Facility | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
ISK-0039 | SHIVA KUMAR | Executive - Facilities and Utilities | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
OTH-0006 | SREE RAMAIAH | Associate | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
ISK-1369 | SURESH R | Manager - House Keeping | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
ISK-0245 | VASUDEVAN P S | Official Mail ID for Control Room | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
ISK-0227 | VEERENDRA N C | Assistant - Transport | IB | Facilities & Utilities | Facilities & Utilities | Full User CAL
ISK-1005 | SAVITHA B | RECEPTIONIST | IB | Hospitality | Hospitality | Limited User CAL
ISK-1151 | BASAVARAJA H | Executive - HR Operations | IB | Human Resources | Human Resources | Full User CAL
ISK-1407 | DEEPAK KUMAR H | Management Trainee - HR | IB | Human Resources | Human Resources | Full User CAL
FTCTSG-005 | HARI PRIYA | Consultant - Talent Management | IB | Human Resources | Human Resources | Full User CAL
ISK-1418 | HARISH S S | Sr. Excecutive - HR | IB | Human Resources | Human Resources | Full User CAL
ISK-1255 | KIRAN KUMAR | Secretary - HR | IB | Human Resources | Human Resources | Full User CAL
ISK-1406 | MANUKAR SATHYAKANTH | Management Trainee - HR | IB | Human Resources | Human Resources | Full User CAL
DEV-2018 | NANDANANDANA DASA | Group Head - HR | IB | Human Resources | Human Resources | Full User CAL
ISK-1387 | POOJA M | Sr. Excecutive - HR | IB | Human Resources | Human Resources | Full User CAL
ISK-1397 | RAMYA R | Trainee - Management | IB | Human Resources | Human Resources | Full User CAL
ISK-1113 | RAVI SHANKAR S | Office Assistant | IB | Human Resources | Human Resources | Full User CAL
ISK-1434 | SHEEBA SAPNA R | Executive-HR Helpesk | IB | Human Resources | Human Resources | Full User CAL
FTCISK-033 | SUBRAMANI S | Consultant | IB | Human Resources | Human Resources | Full User CAL
ISK-0100 | AYYAPPA DASIKA | Project Manager - IT | IB | Information Technology | Information Technology | Full User CAL
ISK-1321 | BHEEMASENA RAO | Server Administrator | IB | Information Technology | Information Technology | Full User CAL
ISK-0664 | JANAKI VALLABHA DASA | Division Head - IT | IB | Information Technology | Information Technology | Full User CAL
ISK-1267 | KARTHIK ANAND | IT Support Engineer | IB | Information Technology | Information Technology | Full User CAL
ISK-1172 | KUMARASWAMY M M | Executive - Stores | IB | Information Technology | Information Technology | Full User CAL
ISK-1313 | NIPUN C RAO | Network Administrator | IB | Information Technology | Information Technology
ISK-0495 | PAVAN KUMAR G | Executive - Software Support | IB | Information Technology | Information Technology | Full User CAL
ISK-1314 | PRADEEP STHS | Executive - Software Support | IB | Information Technology | Information Technology | Full User CAL
TSF-0289 | RAJESH KUMAR B | IT Support Engineer | IB | Information Technology | Information Technology | Full User CAL
ISK-1405 | RATIKANTA MALLIK |  | IB | Information Technology | Information Technology
TSG-0095 | RAVINDRA PATIL | IT Support Engineer | IB | Information Technology | Information Technology | Full User CAL
ISK-1399 | SIREESHA L | Service Desk Executive | IB | Information Technology | Information Technology | Full User CAL
ISK-0118 | SREEDHAR SASALA | Asst. Manager - Software | IB | Information Technology | Information Technology | Full User CAL
ISK-1316 | VIJAYA BANU | IT Secretary | IB | Information Technology | Information Technology | Full User CAL
ISK-1166 | VISHNU PRATAP | Trainee IT Support Engineer | IB | Information Technology | Information Technology | Full User CAL
ISK-1319 | VIVEKANANDHAN S | Servicedesk Analyst | IB | Information Technology | Information Technology | Full User CAL
DEV-2014 | AMITASANA DASA | Executive Council Member | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
DEV-2252 | ANANTHA KIRTHI DASA | Devotee | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
DEV-1002 | CHAMARI DEVI DASI | Executive Council Member | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
DEV-2100 | CHANCHALAPATHI DASA | Executive Council Member | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
DEV-2111 | MADHU PANDIT DASA | President | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
DEV-2043 | RADHAKANTA DASA | Executive Council Member | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
DEV-2338 | RASESHWARA DASA | - | IB | ISKCON Bangalore | ISKCON Bangalore
DEV-2006 | STOKA KRISHNA DASA | Executive Council Member | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
ISK-0950 | SUBRAMANYA S | Executive Assistant | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
ISK-0016 | USHA GURURAJ | Secretary - VP's Office | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
DEV-2042 | VASUDEV KESHAV DASA | Executive Council Member | IB | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
DEV-2263 | RASAJNA DASA | FOLK Guide | IB | ISKCON Whitefield | ISKCON Whitefield
DEV-2296 | SHYAMA KRISHNA DASA | FOLK Guide | IB | ISKCON Whitefield | ISKCON Whitefield
OTH-0005 | TIRU DASA | Division Head - Krishna Kalakshetra | IB | Krishna Kalakshetra | Krishna Kalakshetra | Full User CAL
DEV-2150 | AKINCHANA CHAITANYA DASA | Division Head - Krishnamrita | IB | Krishnamrita | Krishnamrita | Full User CAL
ISK-0595 | ASWATHRAJ V R | Sr. Executive - Purchase | IB | Krishnamrita | Krishnamrita | Full User CAL
ISK-0731 | BHASKAR |  | IB | Krishnamrita | Krishnamrita
ISK-1070 | MURALIDHAR B E | Asst. Manager | IB | Krishnamrita | Krishnamrita | Full User CAL
ISK-0909 | SOMASHEKAR G | Sr. Executive - Stores | IB | Krishnamrita | Krishnamrita | Full User CAL
ISK-1147 | LAKSHMAN V | Executive - Stores | IB | Material Management | Material Management | Full User CAL
ISK-1315 | MANIKANDAN T |  | IB | Material Management | Material Management | Full User CAL
ISK-0174 | MANJUNATH L | Stores Assitant | IB | Material Management | Material Management | Full User CAL
FTCISK-014 | PRABHU R | Store Planner | IB | Material Management | Material Management | Full User CAL
ISK-0216 | RAJ SHEKAR | Assistant - Stores | IB | Material Management | Material Management | Full User CAL
ISK-0028 | UMA S | Asst. Manager - Purchase | IB | Material Management | Material Management | Full User CAL
ISK-0125 | AMIT A KARNIK | Co-ordinator - Communications & Media | IB | Public Relations | Public Relations | Limited User CAL
ISK-1373 | ASHWIN NAIK R | Asst.PRO | IB | Public Relations | Public Relations | Limited User CAL
DEV-2091 | BHARATARSHABHA DASA | Service Line Head | IB | Public Relations | Public Relations | Limited User CAL
ISK-0011 | GAYATHRI S V | Sr. Co-ordinator | IB | Public Relations | Public Relations | Limited User CAL
ISK-0018 | GOPINATH M K | Co-ordinator - Public Relations | IB | Public Relations | Public Relations | Limited User CAL
ISK-1290 | HANUMANTHARAJU A S | Executive | IB | Public Relations | Public Relations | Limited User CAL
ISK-1102 | JYOTHI AMINAGAD | Secretary | IB | Public Relations | Public Relations | Limited User CAL
DEV-2048 | KULASHEKARA CHAITANYA DASA | Public Relations Officer | IB | Public Relations | Public Relations | Limited User CAL
ISK-1357 | MAYURJAIN K S | Executive | IB | Public Relations | Public Relations | Limited User CAL
DEV-2146 | NAVEENA NEERADA DASA | Public Relations Officer | IB | Public Relations | Public Relations | Limited User CAL
DEV-2234 | SUGUNA KRISHNA DASA | Public Relations Officer | IB | Public Relations | Public Relations | Limited User CAL
ISK-1000 | DEBENDRA NATH | Associate | IB | Temple Management | Temple Services | Limited User CAL
DEV-2057 | GUNABHADRA DASA | Unit Head - Deity Department | IB | Temple Management | Temple Services | Full User CAL
DEV-2132 | SRIPATHI DASA |  | IB | Temple Service | Temple Services
DEV-2181 | AMOGHALILA DASA | Devotee | IB | Temple Services | Temple Services
DEV-2242 | ARAVINDAKSHA DASA | Devotee | IB | Temple Services | Temple Services
DEV-2116 | RADHE SHYAM DASA |  | IB | Temple Services | Temple Services
ISK-1352 | VEERENDRA POLKONDWAR | Secretary | IB | Temple Services | Temple Services | Limited User CAL
GSP-0009 | BHASKARA RAO P | Sr. Executive - Accounts | IB | Vaikuntha Hill | Vaikuntha Hill | Full User CAL
GSP-0003 | GEETHA PRASAD C Y | Asst. Manager - Finance and Accounts | IB | Vaikuntha Hill | Vaikuntha Hill | Full User CAL
DEV-2054 | SACHI TANYA DASA | Asst. Temple Commander | IB | Vaikuntha Hill | Vaikuntha Hill | Full User CAL
GSP-0013 | VINAYAK HUDDAR | Executive - Accounts | IB | Vaikuntha Hill | Vaikuntha Hill | Full User CAL
ISK-1349 | ABHAY TIWARI | Values Mentor | IB | Values Plus | Values Plus
ISK-1388 | ADITI CHOUDARY | Values Mentor | IB | Values Plus | Values Plus
ISK-0896 | AMBARISH NAGANNA | Executive - Operations | IB | Values Plus | Values Plus
FTCISK-031 | DEEPA SATTA | Instructional Designer | IB | Values Plus | Values Plus
ISK-1307 | DEVLEENA DAS | Values Mentor | IB | Values Plus | Values Plus
ISK-0797 | GIRIJA RAMANAN | Sr. Values Mentor | IB | Values Plus | Values Plus
ISK-0411 | JAYA BHUWANA N | Instructional Designer | IB | Values Plus | Values Plus
ISK-1376 | JAYARAM S | Content Developer | IB | Values Plus | Values Plus
ISK-1413 | KRISHMA C R | Values Mentor | IB | Values Plus | Values Plus
ISK-1194 | LOKESH B D | Office Assistant | IB | Values Plus | Values Plus
ISK-1291 | MAMTA MAHANTY | Sr. Values Mentor | IB | Values Plus | Values Plus
ISK-1398 | NEHUL CHOUDHARY | Values Mentor | IB | Values Plus | Values Plus
FTCISK-001 | PAYASVINI RADHA DD | Instructional Designer | IB | Values Plus | Values Plus
ISK-0119 | PRAMUKH THARESH | Team Lead | IB | Values Plus | Values Plus
ISK-0625 | RAJINI V B | Sr. Values Mentor | IB | Values Plus | Values Plus
ISK-0300 | RAMYA RAJ KUMAR | Sr. Executive | IB | Values Plus | Values Plus
ISK-1288 | SAPTHAGIRI L | Sr. Values Mentor | IB | Values Plus | Values Plus
ISK-0751 | SHILPA P S | Jr. Executive | IB | Values Plus | Values Plus
ISK-1317 | SHIVA KUMAR S | Sr. Values Mentor | IB | Values Plus | Values Plus
ISK-1199 | SRIRANJANI R V | Sr. Values Mentor | IB | Values Plus | Values Plus
ISK-1214 | SUBASH B N | Sr. Instructional Designer | IB | Values Plus | Values Plus
ISK-1328 | SURAJ M SATTA | Team Lead - Marketing | IB | Values Plus | Values Plus
ISK-1330 | TRISHA CHATTERJEE | Content Developer | IB | Values Plus | Values Plus
ISK-0077 | LALITHA VISHAKA DEVI DASI | Manager - Hospitality | IB | Yatri Nivas | Yatri Nivas | Full User CAL
ISK-735 | RAGHUNANDAN B K | Associate - Stores | IB | Yatri Nivas | Yatri Nivas | Full User CAL
ISK-0368 | SUMANTA CHATTERJEE | Supervisor - Guest House | IB | Yatri Nivas | Yatri Nivas | Limited User CAL
ISK-1433 | GIRISH G | Executive - Telecaller | IB | Youth Preaching | Youth Preaching
DEV-2260 | GUNAKARA RAMA DASA | Team Lead - Youth Programs | IB | Youth Preaching | Youth Preaching
ISK-1404 | HARSH MALIK | Executive - Perspective Development | IB | Youth Preaching | Youth Preaching
DEV-2257 | KALAKANTA DASA | Team Lead - Youth Programs | IB | Youth Preaching | Youth Preaching
DEV-2298 | KALANIDHI DASA | FOLK Guide | IB | Youth Preaching | Youth Preaching
ISK-1033 | KRISHNA SAGAR N L | Executive - FOLK Operations | IB | Youth Preaching | Youth Preaching
DEV-2284 | MAHOTSAHA CHAITANYA DASA | FOLK Guide | IB | Youth Preaching | Youth Preaching
ISK-1393 | MAYANK AGRAWAL | Executive - Public Relations | IB | Youth Preaching | Youth Preaching
DEV-2354 | MOHANA CHAITANYA DASA | FOLK Guide | IB | Youth Preaching | Youth Preaching
ISK-1090 | PRATHAP K | Executive - Operations | IB | Youth Preaching | Youth Preaching
DEV-2364 | SADANANDA DASA | FOLK Guide | IB | Youth Preaching | Youth Preaching
DEV-2179 | SAMPATI DASA | Division Head - FOLK | IB | Youth Preaching | Youth Preaching
ISK-0622 | SIDDALINGA SWAMY | Jr. Content Writer | IB | Youth Preaching | Youth Preaching
ISK-0676 | SRI VIGRAHA DASA | Team Lead - Youth Programs | IB | Youth Preaching | Youth Preaching
ISK-1072 | THOMAS M | Sr. Executive - Data Management and Communication | IB | Youth Preaching | Youth Preaching
DEV-2285 | VAINATEYA DASA | FOLK Guide | IB | Youth Preaching | Youth Preaching
DEV-2305 | VILASA VIGRAHA DASA | FOLK Guide | IB | Youth Preaching | Youth Preaching
OTH-0003 | SESHASTUTA GOVINDA DASA | General Manager - IHT | IB
OTH-0004 | VASUDEVA PRAN DASA | Event Co-ordinator | IB
TSG-0229 | BALAKRISHNA B AITHAL | Deputy Manager - Accounts Payables | IC | Accounts & Finance | Accounts & Finance | Full User CAL
TSF-0303 | SANJEEVI SREEKANTH | Sr. Executive - Accounts | IC | Accounts & Finance | Accounts & Finance | Full User CAL
TSF-0299 | VENKATESH V | Sr. Manager - HR | IC | Human Resources | Human Resources | Full User CAL
DEV-2075 | KODANDARAMA DASA | Secretary - President's Office | IC | ISKCON Bangalore | ISKCON Bangalore | Limited User CAL
EXT-0013 | AMAZON |  | IC | TSF - Prasadam | TSF - Prasadam
TSF-0246 | ANANDA DEVADIGA | Sr. Executive - Quality Assurance | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0023 | ASHOKA C J | Cashier - Annakuta | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0178 | BEERE GOWDA S | Lead Incharge - FGA | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0001 | CHITRA V V |  | IC | TSF - Prasadam | TSF - Prasadam
TSF-0012 | CHITTAIAH |  | IC | TSF - Prasadam | TSF - Prasadam
TSG-0230 | DINESH V | Executive - Purchase | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0013 | GOPI KRISHNAN J | Unit Head - Annakuta | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
DEV-2066 | GOVINDA DATTA DASA | Production Manager | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0008 | GURU MURTHY | Cashier - Annakuta | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0061 | JAGADISH Y | Store Keeper | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
DEV-2098 | KAIVALYAPATI DASA | Division Head - TSF Prasadam | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0278 | KANNAN ADITHIYA K K | Executive - Purchase | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
ISK-0392 | KARTHIK SAMPRATHI | Executive - MIS | IC | TSF - Prasadam | TSF - Prasadam | Limited User CAL
DEV-2094 | MAHAJAN DASA | Incharge - Counter | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0045 | MANDANNA M S | Asst. Manager - Catering | IC | TSF - Prasadam | TSF - Prasadam | Limited User CAL
TSF-0043 | MAQBOOL AHMED | Restaurant Manager | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
ICH-0368 | MARISWAMY SHIVALINGE GOWDA | Executive - Marketing | IC | TSF - Prasadam | TSF - Prasadam | Limited User CAL
EXT-0014 | MPHASIS |  | IC | TSF - Prasadam | TSF - Prasadam
TSF-0295 | NAVEEN KUMAR V N | Manager - Purchase | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
DEV-2124 | PANKAJANGHRI DASA | Manager - Purchase | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0258 | RAGHAVENDRA RAO Y | Executive - MIS | IC | TSF - Prasadam | TSF - Prasadam | Limited User CAL
TSF-0225 | RAGHU B C | Executive - Stores | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0325 | RAJANNA B G | Executive - Stores | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0156 | RAJESH B | Executive - Stores | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0177 | RASHMI N | Process - Analyst | IC | TSF - Prasadam | TSF - Prasadam | Limited User CAL
TSG-0216 | SAMAL KALPATARU | Supervisor | IC | TSF - Prasadam | TSF - Prasadam
TSF-0273 | SANTHOSH V | Manager - Stores | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0067 | SANTOSH P | Executive - Stores | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
IFP-0028 | SIDDESHWARA T S | Executive - MIS | IC | TSF - Prasadam | TSF - Prasadam | Limited User CAL
TSF-0281 | SIDDHARTHA SINHA | Production Manager | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0263 | SOMA SHEKAR REDDY | Supervisor - Maintanance & Facility | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0192 | SURESH C | Baking Master | IC | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0149 | SWAROP BASU | Lead Incharge - FGA | IC | TSF - Prasadam | TSF - Prasadam
TSF-0176 | UMADEVI DESAI | Manager - FGA | IC | TSF - Prasadam | TSF - Prasadam
TSF-0297 | VIJAY KUMAR R | Executive | IC | TSF - Prasadam | TSF - Prasadam
TSF-0235 | VIJAY RAJESH KUMAR | Asst. Manager - Sales | IC | TSF - Prasadam | TSF - Prasadam | Limited User CAL
TSF-0319 | KANNAN G V | Supervisor | IF | TSF - Prasadam | TSF - Prasadam
5000184 | SHWETHA H M | Executive - Accounts | IF | TSF - Prasadam | TSF - Prasadam | Full User CAL
PRASAHANTH | PRASHANT KADKOL |  | IHF | Creative Architecture Services | Creative Architecture Services
TSG-0044 | ALUMELAMMA B G | Sr. Executive - Accounts | SST | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1326 | BASAVARAJ BASAPPA DODDAMANI | Deputy Manager - Accounts Receivables | SST | Accounts & Finance | Accounts & Finance | Full User CAL
TSG-0001 | GOWRI R | Deputy Manager - MIS & Financial Planning | SST | Accounts & Finance | Accounts & Finance | Full User CAL
TSG-0056 | PREETHI SINHA S | Sr. Executive - Accounts | SST | Accounts & Finance | Accounts & Finance | Full User CAL
FTCSST-001 | GAYATHRI DEVI | Translator | SST | Bhaktivedanta Darshana | Bhaktivedanta Darshana
SST-0002 | KRISHNAPPA H V | Sr. Executive - Publications | SST | Bhaktivedanta Darshana | Bhaktivedanta Darshana
SST-0038 | LATHA D C | Jr. Executive - Publications | SST | Bhaktivedanta Darshana | Bhaktivedanta Darshana
SST-0096 | LATHA S NARAYANA | Executive | SST | Bhaktivedanta Darshana | Bhaktivedanta Darshana
TSG-0163 | JAGADEESH T G | Unit Head - Back End Support | SST | Human Resources | Human Resources | Full User CAL
TSG-0105 | VINITA BANSAL | Executive - HR | SST | Human Resources | Human Resources | Full User CAL
TSG-0010 | ANANTH NARAYAN | Inward Incharge | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0066 | ANILKUMAR MR | Supervisor - BBT Stores | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0006 | BALAKRISHNA A | Associate - Purchase | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0020 | BHARATH LINGAPPA | Cashier | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0089 | GANESH M S | Automation Manager | SST | TSF - Matchless Gift | TSF - Matchless Gift
TSG-0164 | GAYATRI MOHAN | Business Analyst | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
SST-0737 | GOPI V |  | SST | TSF - Matchless Gift | TSF - Matchless Gift
SST-0850 | KAMAKSHI B |  | SST | TSF - Matchless Gift | TSF - Matchless Gift
TSG-0113 | KRISHNA G |  | SST | TSF - Matchless Gift | TSF - Matchless Gift
TSG-0016 | KRISHNA R | Executive - Purchase | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0038 | MADHU N M | Deputy Manager - Materials | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0025 | MAHADEVA SWAMY K G | Retail - Supervisor | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
SST-0017 | MANJUNATH DV | Sr. Executive - Marketing | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0032 | MOHAN M S | Outward Incharge | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0049 | NAGARAJ K V | Executive - Purchase | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0150 | NAGARATNA RAGHU | Consultant | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0007 | NANJUNDA SWAMY | Store Planner | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0041 | NEELAKANTAPPA HC | Cashier | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
SST-0018 | RAGHAVENDRA GANIGA | Sr. Executive - Sponsership | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0051 | RAGHUPATHI D | Executive - Vigilence | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0004 | RAGU R | Deputy Manager - Sales | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0061 | RAJU ACHARYA | Supervisor | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0002 | RANGANATH B S | Deputy Manager - Purchase | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0088 | RANJANI K | Purchase Assistant | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
SST-0784 | RAVI J | Back Office Assistant | SST | TSF - Matchless Gift | TSF - Matchless Gift
TSG-0071 | RAVI K R | Sr. Manager - Operations | SST | TSF - Matchless Gift | TSF - Matchless Gift
TSG-0079 | RAVIKUMAR C B | Jr. Executive - Operations | SST | TSF - Matchless Gift | TSF - Matchless Gift
TSG-0036 | SHAMEENA SHETTY | Sr. Executive - Purchase | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
SST-0889 | SHASHI KUMAR | Manager - BVD | SST | TSF - Matchless Gift | TSF - Matchless Gift
TSG-0147 | SRINIVASA KARANTH | Asst. Manager - Marketing | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0050 | SUBHASHISH BHUSAN | Executive - Quality | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
SST-0037 | SUJATHA RAMCHANDRAN | Back Office Assistant | SST | TSF - Matchless Gift | TSF - Matchless Gift
TSG-0060 | SUNIL PREM KUMAR | Sales - Supervisor | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0008 | THIPPANNA T | Section Incharge - Stores | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0003 | UDAY KUMAR SANU | Executive - Sales | SST | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0046 | UNNIKRISHNAN N | Supervisor - Stores | SST | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSF-0426 | SHANT KUMAR | Asst. Manager - Accounts | TSF | Accounts & Finance | Accounts & Finance | Full User CAL
TSF-0171 | ARJUN PULIGAR | Executive - Purchase | TSF | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0014 | HARISH KUMAR B | Executive - Stores | TSF | TSF - Matchless Gift | TSF - Matchless Gift | Full User CAL
TSG-0245 | KRISHNA CHAITANYA MARUVADA | Product Designer | TSF | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0205 | REKHA P K | Manager - Supply Chain | TSF | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0247 | SARALA DEVI | Manager - External Sales | TSF | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0206 | SHWETA UPADHYAY | Manager - Products | TSF | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0013 | SIVAKUMAR M | Supervisor - Production | TSF | TSF - Matchless Gift | TSF - Matchless Gift | Limited User CAL
TSG-0246 | SOMU KEERAN S | Graphic Designer | TSF | TSF - Matchless Gift | TSF - Matchless Gift
8000100 | SUKANYA R | Executive | TSF | TSF - Matchless Gift | TSF - Matchless Gift
TSG-0208 | SUNIL V BIJAPUR | Event Co-ordinator | TSF | TSF - Matchless Gift | TSF - Matchless Gift
TSF-0055 | BALAJI KANNAN A | Head Chef | TSF | TSF - Prasadam | TSF - Prasadam
TSG-0220 | DEVENDRA PRADHAN | Supervisor | TSF | TSF - Prasadam | TSF - Prasadam | Limited User CAL
TSF-0070 | KSHIROD KUMAR SAMAL | Cashier | TSF | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0345 | MAHENDRA V | Sr. Associate | TSF | TSF - Prasadam | TSF - Prasadam | Limited User CAL
6000286 | MOHAN C M | Executive - QA | TSF | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0306 | NANJUNDA B N | Executive - MIS | TSF | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0391 | PRADEEP KUMAR M | Executive - QA | TSF | TSF - Prasadam | TSF - Prasadam | Full User CAL
8000402 | SUMITHRA R | Executive - QA | TSF | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSF-0351 | VIDYA P G | Executive | TSF | TSF - Prasadam | TSF - Prasadam | Full User CAL
TSG-0115 | PRASSANNA KUMARI | Executive - Accounts |  | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1367 | ROOPA MANAKUR | Executive - Accounts |  | Accounts & Finance | Accounts & Finance | Full User CAL
ISK-1295 | SURESH J | Jr Executive - Accounts |  | Accounts & Finance | Accounts & Finance | Full User CAL
OTH-0001 | IT SERVERS |  |  | Information Technology | Information Technology | Full User CAL
TSG-0209 | MUKUNDAN T | Event Co-ordinator |  | TSF - Matchless Gift | TSF - Matchless Gift
GSP-0017 | AMBIKA KEELARA | Sr. Architect | GSPL | Creative Architecture Services | Creative Architecture Services
GSP-0010 | GAJANAND A PATIL | Sr. 3D Artist | GSPL | Creative Architecture Services | Creative Architecture Services
GSP-0011 | PREETHI N M | Jr. 3D Artist | GSPL | Creative Architecture Services | Creative Architecture Services
OTH-0007 | CHARU KRISHNA DASA |  | GSPL | Goloka Seva Trust | Goloka Seva Trust
GSP-0016 | GOVINDASWAMY V H | Stores Officer | GSPL | Vaikuntha Hill | Vaikuntha Hill | Full User CAL
GSP-0006 | MADHUSUDAN REDDY M N | Asst. Manager | GSPL | Vaikuntha Hill | Vaikuntha Hill | Limited User CAL
GSP-0008 | MANJULA MAHESH | Deputy Manager Procurement | GSPL | Vaikuntha Hill | Vaikuntha Hill | Full User CAL
GSP-0015 | SEETHARAMAN S | Consultant | GSPL | Vaikuntha Hill | Vaikuntha Hill | Full User CAL
GSP-0014 | SRINIVASAN T M | Deputy Manager | GSPL | Vaikuntha Hill | Vaikuntha Hill | Full User CAL
GSP-0007 | SWAMINATHAN K | Consultant | GSPL | Vaikuntha Hill | Vaikuntha Hill | Full User CAL
GST-0016 | SURYA PRAKASH | Excecutive - Accounts | GST | Accounts | Goloka Seva Trust | Full User CAL
GST-0012 | LILAVATAR DASA | Manager | GST | Goloka Seva Trust | Goloka Seva Trust | Full User CAL
GST-0020 | MANJULA | Sales Excecutive | GST | Goloka Seva Trust | Goloka Seva Trust | Limited User CAL