## Pivot
Information from Proposal
|  | Sub-contract | 2
Row Labels | Count of Process | Contact Management | 1
?? | 18 | ?? | 46
0-HRMS | 7 | 0-HRMS | 9
0-Reporting | 3 | 0-Reporting | 4
0-Subprocess not clear | 7
Attendance Management | 1
Cash Management | 1 | Cash Management | 1
Chart of Accounts | 1 | Chart of Accounts | 1
Financial Management | 7 | Financial Management | 7
Fixed Assets | 4 | Fixed Asset | 4
Gate Entry | 1 | Gate Entry | 1
General Ledger | 4 | General Ledger | 4
Indent Mgmt | 17 | Indent Mgmt | 17
India Localization | 4 | India Localization | 4
Inventory | 27 | Inventory | 27
Manufacturing | 3 | Manufacturing | 4
Payroll | 3 | Payroll | 3
Plant Maintenance | 1 | Plant Maintenance | 1
Purchase & Payables | 22 | Purchase & Payables | 22
QC Module | 6 | QC Module | 6
Sales & Receivables | 26 | Sales & Receivables | 27
Grand Total | 163

## Process-Map-Table
ABS # | Entity | Process | Sub Process (identify the sub processes for each of the process listed here… you can add more rows for each sub process) | Name of Module available in ERP to fit this process | Recommendation for process changes as per industry standards to make this a direct fit
1 | ISKCON | Accounts & Finance | Donation Accounting | ?? | Integration with Donation Mgmt. system is recommended to pull the receipt data to finance
2 | ISKCON | Accounts & Finance | Ticket and Other | Sales & Receivables
3 | ISKCON | Accounts & Finance | Kalyana Mandapa | Sales & Receivables
4 | ISKCON | Accounts & Finance | Fixed Assets Accounting | Fixed Assets
5 | ISKCON | Accounts & Finance | General Ledger | General Ledger
6 | ISKCON | Accounts & Finance | Accounts Payable | Purchase & Payables
7 | ISKCON | Accounts & Finance | Budget and MIS | Financial Management
8 | ISKCON | Accounts & Finance | Audit (Internal and External) | 0-Subprocess not clear | Will be done as per standard feature available
9 | ISKCON | Accounts & Finance | Taxation | India Localization
10 | ISKCON | Accounts & Finance | Chart of Accounts | Chart of Accounts
12 | ISKCON | Procurement to Payment | Purchase Requisition | Indent Mgmt | Consolidation of Indent, Purchase Request & Issue based on indent to be customised
13 | ISKCON | Procurement to Payment | Material Indent | Indent Mgmt
14 | ISKCON | Procurement to Payment | Quotation | Purchase & Payables
15 | ISKCON | Procurement to Payment | Rate Contract | Purchase & Payables
16 | ISKCON | Procurement to Payment | Purchase Order (Tolerance Limits) | Purchase & Payables | P.O Amedment to be used
17 | ISKCON | Procurement to Payment | Purchase Voucher | Purchase & Payables
18 | ISKCON | Procurement to Payment | Payments | Cash Management
19 | ISKCON | Inventory & Stores Management | Main Store and Sub Store Management | Inventory | Locations to be used
20 | ISKCON | Inventory & Stores Management | Receipt of Goods (GRN) In | Inventory
21 | ISKCON | Inventory & Stores Management | Material Issues | Indent Mgmt | Refer point #12 & 13
22 | ISKCON | Inventory & Stores Management | Quality Inspection & Control | QC Module
23 | ISKCON | Inventory & Stores Management | Re-order Level, MOQ & UOM conversions | Inventory
25 | ISKCON | Payroll & Statutory Compliance | Payroll | Payroll
26 | ISKCON | Payroll & Statutory Compliance | Employee TDS | Payroll
27 | ISKCON | Payroll & Statutory Compliance | Statutory Compliances (PF / ESI etc) | Payroll
28 | ISKCON | Payroll & Statutory Compliance | Establishment Acts Compliances | 0-Subprocess not clear
29 | ISKCON | Human Resource Management (HRMS) | Attendance Management Out of ERP. | Attendance Management | output to be uploaded to Payroll
30 | ISKCON | Human Resource Management (HRMS) | Recruitment Management | 0-HRMS | Available features of HRMS package to be utilized. Any requirement over and above needs to be customised
31 | ISKCON | Human Resource Management (HRMS) | Performance Management | 0-HRMS
32 | ISKCON | Human Resource Management (HRMS) | Claims Management | 0-HRMS
33 | ISKCON | Human Resource Management (HRMS) | Compensation & Benefits | 0-HRMS
34 | ISKCON | Human Resource Management (HRMS) | Travel Management | 0-HRMS
35 | ISKCON | Human Resource Management (HRMS) | Employee Self Service | 0-HRMS
36 | ISKCON | Human Resource Management (HRMS) | Exit Management | 0-HRMS
38 | ISKCON | Reports / Score Card / Dashboards | MIS Reports & Dashboards | 0-Reporting
39 | ISKCON | Facility Maintenance |  | Plant Maintenance | Plant maintenance module to be used
40 | ISKCON | Customer Relationship Management | Contact Management | ??
41 | ISKCON | Donations Management | Donor Master | ?? | Refer point #1
42 | ISKCON | Donations Management | Patron Master | ??
43 | ISKCON | Donations Management | Donation Receipt Processin | ??
44 | ISKCON | Donations Management | Bahumana Management | ??
45 | ISKCON | Donations Management | Dispatch Management | Sales & Receivables
46 | ISKCON | Donations Management | Inventory Management | Inventory
47 | ISKCON | Donations Management | Online Donations Managemen | ?? | Refer point #1
48 | ISKCON | Donations Management | Donor Relationship Managemen | ?? | To the extent of manageing donar involvement with the temple activities and sending related campaigns
49 | ISKCON | Donations Management | Contact Management | ??
50 | ISKCON | Donations Management | Tele Marketing | ?? | To do can be maintained in the system
58 | TSF-GIFT | Accounts & Finance | Fixed Assets Accounting | Fixed Assets
59 | TSF-GIFT | Accounts & Finance | General Ledger | General Ledger
60 | TSF-GIFT | Accounts & Finance | Accounts Payable | Purchase & Payables
61 | TSF-GIFT | Accounts & Finance | Budget and MIS | Financial Management
62 | TSF-GIFT | Accounts & Finance | Audit (Internal and External) | 0-Subprocess not clear | Will be done as per standard feature available
63 | TSF-GIFT | Accounts & Finance | Taxation | India Localization
64 | TSF-GIFT | Accounts & Finance | Sales & Accounts Receivable | Sales & Receivables
65 | TSF-GIFT | Sales Forecasting | Cash Sales Forecasting | Indent Mgmt
66 | TSF-GIFT | Sales Forecasting | Credit Sales Forecasting | Indent Mgmt
67 | TSF-GIFT | Procurement Planning | Material Planning | Purchase & Payables
68 | TSF-GIFT | Procurement to Payment | Quotation | Purchase & Payables
69 | TSF-GIFT | Procurement to Payment | Purchase Order | Purchase & Payables
70 | TSF-GIFT | Procurement to Payment | Supplier Returns | Purchase & Payables
71 | TSF-GIFT | Procurement to Payment | Bill of Materials | Inventory
72 | TSF-GIFT | Procurement to Payment | Job Order Sub-contract | ??
73 | TSF-GIFT | Procurement to Payment | Sub Contract Work Order Sub-contract | ??
74 | TSF-GIFT | Procurement to Payment | Purchase Inward Note Inventory GRN | Inventory
75 | TSF-GIFT | Procurement to Payment | Payment Advice | Financial Management
76 | TSF-GIFT | Inventory Management | GRN | Inventory
77 | TSF-GIFT | Inventory Management | Quality Inspection | QC Module
78 | TSF-GIFT | Inventory Management | Rejections & Acceptance | QC Module
79 | TSF-GIFT | Inventory Management | Item Conversion | Inventory
80 | TSF-GIFT | Inventory Management | Transfers (within Stores & Sub Stores) | Inventory
81 | TSF-GIFT | Inventory Management | Issues (Delivery Challan / Packing Slips) | Sales & Receivables
82 | TSF-GIFT | Inventory Management | Supplier Returns | Sales & Receivables
83 | TSF-GIFT | Retail Sales Counter | Issues | Inventory
84 | TSF-GIFT | Retail Sales | Counter Returns | Inventory
85 | TSF-GIFT | Retail Sales Counter | Transfers | Inventory | GRN to be used
86 | TSF-GIFT | Credit Sales & Exports Marketing | Contact management | ??
87 | TSF-GIFT | Credit Sales & Exports | Quotation | Sales & Receivables
88 | TSF-GIFT | Credit Sales & Exports | Sample / Complimentary Issues | Sales & Receivables
89 | TSF-GIFT | Credit Sales & Exports | Customer Order | Sales & Receivables
90 | TSF-GIFT | Credit Sales & Exports | Customer Order Delivery | Sales & Receivables
91 | TSF-GIFT | Credit Sales & Exports | Sales Return | Sales & Receivables
92 | TSF-GIFT | Credit Sales & Exports | Payment Follow-up | Sales & Receivables
93 | TSF-GIFT | Credit Sales & Exports | Customer Feedback | Sales & Receivables
94 | TSF-GIFT | Master Data Management | Item Master | Inventory
95 | TSF-GIFT | Master Data Management | Supplier Master | Purchase & Payables
96 | TSF-GIFT | Master Data Management | Customer Master | Sales & Receivables
97 | TSF-GIFT | Master Data Management | BOM Creation | Inventory
98 | TSF-GIFT | Master Data Management | Quotation Already Quotation for Purchase & Sales are mentioned in line 70 & 89 | ??
115 | TSF-FOOD | Accounts & Finance | Fixed Assets Accounting | Fixed Assets
116 | TSF-FOOD | Accounts & Finance | General Ledger | General Ledger
117 | TSF-FOOD | Accounts & Finance | Accounts Payable | Purchase & Payables
118 | TSF-FOOD | Accounts & Finance | Budget and MIS | Financial Management
119 | TSF-FOOD | Accounts & Finance | Audit (Internal and External) | 0-Subprocess not clear | Will be done as per standard feature available
120 | TSF-FOOD | Accounts & Finance | Taxation | India Localization
121 | TSF-FOOD | Forecast | Catering / Retail / Events | Indent Mgmt
122 | TSF-FOOD | Retail Sales | Cash Sales | Sales & Receivables
123 | TSF-FOOD | Retail Sales | Credit Sales | Sales & Receivables
124 | TSF-FOOD | Retail Sales | Wastage | Inventory
125 | TSF-FOOD | Retail Sales | Indents | Indent Mgmt | Refer Point # 12 & 13
126 | TSF-FOOD | Retail Sales | Sales Returns | Sales & Receivables
127 | TSF-FOOD | Retail Sales | Stock Returns | Sales & Receivables
128 | TSF-FOOD | Retail Sales | Cash Collections | Sales & Receivables
129 | TSF-FOOD | Retail Sales | Cash Settlement | Financial Management
130 | TSF-FOOD | Retail Sales | Discount Approvals | Sales & Receivables
131 | TSF-FOOD | Credit Sales | Customer Order (Catering / Events / Cakes) | Sales & Receivables
132 | TSF-FOOD | Credit Sales | Indents | Indent Mgmt | Refer Point # 12 & 13
133 | TSF-FOOD | Credit Sales | Order Fulfilment | 0-Subprocess not clear | Will be done as per standard feature available
134 | TSF-FOOD | Retail Sales / Credit Sales | Customer Feedback | Sales & Receivables
135 | TSF-FOOD | Stores (FGA) | Order Consolidation | Indent Mgmt | Refer Point # 12 & 13
136 | TSF-FOOD | Stores (FGA) | Production Indent | Indent Mgmt
137 | TSF-FOOD | Stores (FGA) | Item Issues | Indent Mgmt
138 | TSF-FOOD | Stores (FGA) | Item Receipts | Indent Mgmt
139 | TSF-FOOD | Stores (FGA) | Wastage | Inventory
140 | TSF-FOOD | Stores (FGA) | Internal Transfers | Inventory
141 | TSF-FOOD | Production Planning | Material Planning | Manufacturing
142 | TSF-FOOD | Production Planning | Production Orders | Manufacturing
143 | TSF-FOOD | Production Planning | Production Indent to Stores | Indent Mgmt | Refer Point # 12 & 13
144 | TSF-FOOD | Production Planning | Bill of Materials | Inventory
145 | TSF-FOOD | Production Planning | Receipts against indents | Inventory
146 | TSF-FOOD | Production Planning | Rejection & Damages | Inventory
147 | TSF-FOOD | Inventory Management | Indent Consolidation Indent Mgmt Refer Poi | Indent Mgmt | Refer Point # 12 & 13
148 | TSF-FOOD | Inventory Management | Purchase Request | Indent Mgmt
149 | TSF-FOOD | Inventory Management | Receipt of Goods (GRN) | Inventory
150 | TSF-FOOD | Inventory Management | Quality Inspection (FSMS standard) | QC Module
151 | TSF-FOOD | Inventory Management | Rejections & Acceptance | QC Module
152 | TSF-FOOD | Inventory Management | Raw Material Issues | Inventory
153 | TSF-FOOD | Procurement Planning | Quotations | Purchase & Payables
154 | TSF-FOOD | Procurement Planning | Purchase Order | Purchase & Payables
155 | TSF-FOOD | Procurement Planning | Payment Advice | Financial Management
156 | TSF-FOOD | Procurement Planning | Gate Entry | Gate Entry
157 | TSF-FOOD | Procurement Planning | Supplier Returns | Purchase & Payables
158 | TSF-FOOD | Master Data Management | Item Master | Inventory
159 | TSF-FOOD | Master Data Management | Supplier Master | Purchase & Payables
160 | TSF-FOOD | Master Data Management | Customer Master | Sales & Receivables
161 | TSF-FOOD | Master Data Management | BOM Creation | Manufacturing
163 | TSF-FOOD | Reports / Score Card / Dashboards | MIS Reports & Dashboards | 0-Reporting
164 | GST | Accounts & Finance | General Ledger | General Ledger
165 | GST | Accounts & Finance | Fixed Assets Accounting | Fixed Assets
166 | GST | Accounts & Finance | Domestic Sales | Sales & Receivables
167 | GST | Accounts & Finance | E-BRC | 0-Subprocess not clear | Will be done as per standard feature available
168 | GST | Accounts & Finance | Export and Deemed Export | ?? | Documentation to be maintained outside ERP
169 | GST | Accounts & Finance | Duty Drawback & other Export Compliance | ?? | Documentation to be maintained outside ERP
170 | GST | Accounts & Finance | Budget and MIS | Financial Management | Budget Vs Actul to be utilized
171 | GST | Accounts & Finance | Accounts Payable | Purchase & Payables
172 | GST | Accounts & Finance | Accounts Receivables | Sales & Receivables
173 | GST | Accounts & Finance | Audit (Internal and External) | 0-Subprocess not clear | Will be done as per standard feature
174 | GST | Accounts & Finance | Taxation | India Localization
175 | GST | Procurement Planning | Purchase Requisition | Indent Mgmt | Refer Point # 12 & 13
176 | GST | Procurement Planning | Material Indent | Indent Mgmt
177 | GST | Procurement Planning | Quotation | Purchase & Payables
178 | GST | Procurement Planning | Rate Contract | Purchase & Payables
179 | GST | Procurement Planning | Purchase Order (Tolerance Limits) | Purchase & Payables | P.O Amendment to be used
180 | GST | Procurement Planning | Purchase Voucher | Purchase & Payables
181 | GST | Procurement Planning | Payments | Purchase & Payables
182 | GST | Inventory Management | Main Store and Sub Store Management | Inventory
183 | GST | Inventory Management | Receipt of Goods (GRN) | Inventory
184 | GST | Inventory Management | Material Issues Manufacturin | ?? | Partial customisation is required
185 | GST | Inventory Management | Quality Inspection & Control | QC Module
186 | GST | Inventory Management | Re-order Level, MOQ & UOM conversions | Inventory
187 | GST | Inventory Management | Bundling of SKU (Combo Packs) | Inventory | Use Assembly BOM
188 | GST | Sales Management | Point of Sale | ?? | Separate POS
189 | GST | Sales Management | Export Sales & Compliances | Sales & Receivables | Documentation to be maintained outside ERP
192 | GST | Reports / Score Card / Dashboards | MIS Reports & Dashboard | 0-Reporting

## SSC
Name | ITTI |  | ABS
Cost | 3000000 |  | 4675000
Duration | 6 Months |  | 12 Months
Phases |  |  | 4
Efforts
Resources
Methodology | Detailed Agile |  |  |  |  | Big | Seq
Assumptions |  |  | Identified |  |  | 32 | 46
Out of Scope |  |  | Identified |  |  | 8 | 11.5
Reports | 10 |  | 30
Extra Report Rate |  |  | 8500/ report |  |  | 6 | 9
Extra Customization Rate (Reports) |  |  | 8500/ report
Support | 30 Days |  | 15 Days |  |  | 1 PM, 2FC, 1.5TC
Post Implementation Training |  |  | 5 Days
Training Material |  |  | 12500 /day |  |  |  | Cust, Report, installation etc. inisitation app server
Resource Profile |  |  | 1 PM + 2 FC
Implementation Location | at ISKCON |  | at ABS
Development Location | at ITTI |  | at ABS
Payment T&C | Milestone wise |  | Month wise
MS | Weeks | Days | MS | Weeks | Days
Milestone 1: Agile Preparation | 1 | 4
Milestone 2: (GST along with UAT and Training) | 9 | 42 | GST | 9 | 45
Milestone 3: (TSF-Food along with UAT and Training) | 10 | 56 | ISKCON | 10 | 50
Milestone 4: (TSF-Gifts along with UAT and Training) | 9 | 42 | TFS | 18 | 90
Milestone 5: (ISKCON along with UAT and Training) | 10 | 60 | SST | 9 | 45
Milestone 6: Consolidation | 3 | 20
Total | 42 | 224 | Total | 46 | 230

## ITTI-MS
|  | Sprint | Weeks | Weeks | Days
Milestone 1 |  | Sprint 0 | 1 | 1 | 4
Milestone 2 | Gokula Seva Trus t ( GST ) | Sprint 1 | 2 | 9 | 42
|  | Sprint 2 | 2
|  | Sprint 3 | 2
|  | Sprint 4 | 2
|  | Sprint 5 | 1
Milestone 3 | Foods (TFS) | Sprint 1 | 2 | 10 | 56
|  | Sprint 2 | 2
|  | Sprint 3 | 2
|  | Sprint 4 | 2
|  | Sprint5 | 2
|  | Sprint 6 | 1
Milestone 4 | Gifts (TFS) | Sprint 1 | 2 | 9 | 42
|  | Sprint 2 | 2
|  | Sprint 3 | 2
|  | Sprint 4 | 2
|  | Sprint 5 | 1
Milestone 5 | ISKCON | Sprint 1 | 2 | 10 | 60
|  | Sprint 2 | 2
|  | Sprint 3 | 2
|  | Sprint 4 | 2
|  | Sprint 5 | 2
Milestone 6 | Consolidation | Sprint 6 | 1 | 20 | 20
Total |  |  |  | 59 | 224

## Assumptions
ABS
Employees of ISKCON will be involved in the project. The availability of these employees as per the stages of the project would be critical to ensure there are no delays in the schedule proposed.
It is assumed that all the required information would be provided by ISKCON during the requirements gathering phase, and necessary help will be provided by these employees of in this phase, without which the rest of the phases will be delayed.
It is assumed that all approvals for each of the project phases would be available on time from ISKCON to ensure minimal delays.
It is assumed that ISKCON would procure the required software and hardware for the project and make it available to ABS during the implementation phase at the client site. The hardware and software required at ABS Development Center for ABS employees working on this project would be provided by ABS.
All prices are exclusive of sales Tax, VAT and other Taxes and duties that may be applicable. All such Taxes and duties are to be borne by ISKCON
Any change management requests shall be handled on a Time & Material basis. For all Time and Material projects. For additional work currently not scoped in this proposal, separate estimates shall be submitted providing staffing, timelines and pricing details.
Payment should be done within 3 days from the receipt of the invoices.
The proposal is based on the data provided by ISKCON on the nature and scope of project.
Any data included in the proposal but which is not a part of the project proposed by ISKCON would be corrected at the scope definition stage of the project.
The information used here would be the basis for project
Training Material will not be prepared by ABS
Broadband connectivity for 5 people of ABS
Templates for loading all the master data (chart of accounts, items, vendors, customers, bills of material etc) will be provided by ABS along with sample data to facilitate smooth upload
Operating Software, Database and any other Middle ware that may be required like SQL Server, Windows Server, SharePoint Portal, and Performance Point Server etc. will need to be procured separately by ISKCON.
availability of the client team and users associated with the project for various activities including workshops, meetings and approvals.
No Past transactional data will be taken into the system
Provision of all the required data, testing of all the transactions, Validations of all the transactions and the Reports are ISKCON’s responsibility
Any reconciliations arising out of wrong data entry, or comparisons between the old data and the new system generated data or need arises during the parallel runs is ISKCON’s Responsibility
All data entry & testing is ISKCON’s responsibility
To avoid this ABS strongly recommends ISKCON to standardize on the Printers, size of paper and the formats
Implementation for HR & Payroll and Quality Module requires Licenses to be procured by ISKCON
Plant Module (which is not part of current implementation scope) licenses to be procured by ISKCON
Modules (ITTI) | Modules (ABS)
Phase 1
Accounts and Finance | • Finance & Accounts
Procurement to Payment | • Sales
Procurement Planning | • Procurement
Asset Management ( Fixed Assets ) | • Donations Management
Purchasing | • Inventory & Stores
Inventory | • Production
Production Planning ( Basic Production and Direct Costs) | • HRMS & Payroll
Sales Forecasting | • Quality
Consignment Sales | • Configuration and Development
Subscription Management for Magazines.
Sales Management ( Exports / Distributors/ Retail / Online )
Stores Management
Quality Control (raw materials / production plants / finished goods stores)
Donation Management
Convention Halls
Facility Maintenance
Phase 2
Customer Relationship Management
Payroll & Human Resources Management
Project Management.
Retail Sales ( Temple Counters / Mobile Vans / Online Sales / Export )
Automating the job activities connected to magazine printing
Subscription Management for Magazines
Detailed production
Retail Store using POS

## DeptWiseModules
Gokula Seva Trust (GST)
Finance & Accounts
Procurement Planning
Inventory Management
Sales Management ( Exports / Distributors / Retail and Online)
Quality
Stores Management
Touchstone Foundation (Gifts)
Finance & Accounts
Procurement Planning
Inventory Management
Sales Forecasting and Consignment Sales
Quality
Stores Management
Touchstone Foundation (Foods)
Finance & Accounts
Procurement Planning
Inventory Management
Sales Management (Temple Counters / Outlets / Restaurants / Catering Orders)
Production Planning
Quality
Stores Management
ISKCON
Finance & Accounts
Procurement to Payment
Inventory Management
Quality
Stores Management
Donation Management ( Integration with 3rd party application )
Kalyana Mantapa (Convention Halls)

## OutOfScope
ABS
• Implementation of additional Companies (other than what is the scope of this proposal)
• Consolidation of Multiple Databases
• Integration with Principal/Head Quarters/subsidiaries
• Integration with third-party solutions like Portals, POS, Barcode, etc.,
• Balanced Scorecard Reports for all modules ,Web Sales Order Integration with NAV, Magazine Printing Module , Guest House Management (Yatri Nivas) Module has been excluded based from scope based on the request from ISKCON
• Features and functionalities other than what is explicitly mentioned
Post implementation first month book closure for reconcilation