## GST
ISKCON- MS DYNAMICS NAV 2013 R2 IMPLEMENTATION PROJECT PLAN- ENTITY: GOLOKA SEVA TRUST (GST)
MODULES COVERED - FINANCE, SALES & PURCHASE, INVENTORY, PRODUCTION & FIXED ASSETS
| Phase | Title | Activities | Deliverable | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | Status | Remarks
INITIATION
| INITIATION | KICK-OFF MEETING | KICK-OFF AND INITIAL INTRODUCTION
PRESENTATION OF IMPLEMENTATION METHODOLOGY
REVIEW OF AVAILABLE RESOURCES-TEAM IDENTIFICATION (PROCESS OWNERS, PROJECT MANAGER, SIGNING AUTHORITY)
NOMINATE PROCESS OWNERS, PROJECT MANAGER & SIGN OFF AUTHORITY
OVERVIEW OF BUSINESS AS IS AT A MACRO LEVEL
|  |  | PRESENTATION & APPROVAL OF PROJECT PLAN | PROJECT PLAN
ANALYSIS & DESIGN
| ANALYSIS & DESIGN | REQUIREMENT ANALYSIS | WORKSHOP FOR FUNCTION WISE BUSINESS PROCESS STUDY & COLLECTION OF REQUIREMENTS
DATABASE-COMPANY STRUCTURE AWARENESS SESSION TO THE KEY USER GROUP
PRODUCT CAPABILITY & UTILIZATION AWARENESS TO THE KEY USER GROUP
BUSINESS PROCESS & DOCUMENTS PRESENTATION
INVENTORY MANAGEMENT & PROCUREMENT ANALYSIS
PACKING PROCESS & RELATED ENTRIES & DOCUMENTS
PURCHASE PROCESS
FINANCIAL MANAGEMENT & ACCOUNTING STRUCTURE INCL. CHART OF ACCOUNTS, GENERAL ACCOUNTING & JOURNAL BATCHES - REQ.
BANK ACCOUNTS, VARIOUS TYPES OFTRANSACTIONS, CURRENCIES, EXCHANGE RATE & BRS REQ.
PURCHASE PROCESS, DUTIES & TAXES
SALES PROCESS DUTIES & TAXES
AP & AR
FIXED ASSETS
FINANCIAL STATEMENTS & PERIODIC REPORTS- REQ
CUSTOMER ENTITY- CREATION - GENERAL INFORMATION AND SET UP- REQ.
VENDOR & ITEM CREATION- SET UP & REQ
FINALYZING DIMENSIONS, POSTING GROUPS, TAX COMPONENTS
BOM & PACKING PROCESS SET UP
PROCESS FINALIZATION WORKSHOP
DATA CONVERSION & VOLUME MATRIX( OPB)
COLLECT VARIOUS TEST CASES & DOCUMENT FORMATS
FINANCIAL VOUCHERS, ADVICE, DRN & CRN
SALES- TEST CASES & DOCUMENT FORMATS
PURCHASE- TEST CASES & DOCUMENT FORMATS
|  | FUNCTIONAL REQ. DOCUMENTATION | FRD & FIT GAP
PREPARATION OF FRD (FUNCTIONAL REQUIREMENT DOCUMENT)
PREPARE GAP-FIT DOCUMENT (INCLUDING REPORTING REQUIREMENTS)
|  |  | FRD PRESENTATION | FRD
FRD SIGN OFF
GAP - FIT RESOLUTION WORKSHOP (PROCESS CONFIRMATION)
|  |  | PREPARE LIST OF CUSTOMISED DELIVERABLES (INCLUDING REPORTING REQUIREMENTS) | LIST OF DELIVERABLES
REVIEW IMPACT OF GAP-FIT RESOLUTION ON PROJECT PLAN
|  | SOLUTION DESIGN | CUSTOMISATION - TO BE BUILD
SOLUTION DESIGN WORKSHOP
IDENTIFY LIMITATIONS IN THE OUT-OF-BOX SOLUTION AND DISCUSS WORK AROUND
PREPARATION OF ENTERPRISE DESIGN DOCUMENT (EDD)
|  |  | PRESENTATION OF EDD | EDD
CUSTOMISATION BUILD - TO BE
REPORTS (TO BE BUILD)
DATA CONVERSION AND DESIGN BUILD
PREPARATION OF TEST CASES (ISKCON TO PROVIDE INFO)
UNIT TESTING
|  |  | COMPLETION OF STATEMENT OF WORK | TEST CASES
CONFIGURATION
4.3.3 | CONFIGURATION | INSTALLATION & SYSTEM INITIALIZATION | INSTALLATION, DATABASE SETUP AND CONFIGURATION
SERVER SETUP WITH MS DYNAMICS NAV INSTALLATION
|  | CREATE DB | CREATE NEW DB AND COMPANIES (LEGAL ENTITIES)
|  | MIGRATE MASTER DATA | SETTING UP COMPANIES
UPLOAD MASTERS- CUSTOMER, VENDOR, ITEM, BANK, ACCOUNTS, FA, DIMENSION, POSTING GROUPS, & SET UP
|  |  | ALL MASTERS VERIFICATION | RECORD STATISTICS
|  | VALIDITY CHECK | CHECK THE VALIDITY OF THE DATA CREATED/IMPORTED
ROLE AND USER MATRIX FINALIZATION
|  |  | CUSTOMER CONFIRMATION ON MASTERDATA & SET UP | CONFIRMATION FROM CUSTOMER
|  | CRP | CRP WORKSHOP- PROCESS & TRANSACTIONS
CRP-WORKSHOP- REPORTS
|  |  | OBTAIN CUSTOMER CONFIRMATION | CONFIRMATION FROM CUSTOMER
|  | OPB TEMPLATES | PROVIDING TEMPLATES FOR VARIOUS OPENING BALANCES
PREPARATION OF USER MANUAL
DEPLOYMENT
4.3.4 | DEPLOYMENT | TRAINING | TRAINING FOR USERS ON THE CUSTOMISED FINAL PRODUCT | USER MANUAL
USER TRAINING
|  | USER ACCEPTANCE TEST | USER ACCEPTANCE TESTING OF SAMPLE SCENARIOS
UAT INSTANCE SET UP
|  |  | INTERAGATION TESTING | TESTING STRATEGY DOCUMENT, LIST OF FUNCTIONALITIES, TRANSACTIONS & REPORTS
PERFORM UAT
GENERATE REPORTS
REVIEW RESULTS AND OBTAIN SIGN OFF
GO-LIVE
4.3.5 | GO-LIVE | SYSTEM READINESS | GO-LIVE SET UP
PRODUCTION INSTANCE SET
ROLE AND USER MATRIX SET UP
REPORTS
FINALYZE CUT OVER AND GO-LIVE
|  |  | UPLOADING OPB | BALANCE CONFIRMATION FROM CUSTOMER
|  |  | FINAL SET UP TESTING / CHECK UP | E MAIL CONFIRMATION FROM CUSTOMER
|  | GO LIVE | GO LIVE - LIVE TRANSACTIONS
LIVE TRANSACTION SUPPORT - ON SITE
|  | SIGN OFF | PROJECT SIGN OFF & HAND OVER TO SUPPORT | SIGN OFF SHEET
|  |  | TOTAL NO. OF CAL DAYS | 45

## ISKCON
ISKCON- MS DYNAMICS NAV 2013 R2 IMPLEMENTATION PROJECT PLAN- ENTITY: ISKCON
MODULES COVERED - FINANCE, PURCHASE, INVENTORY & FIXED ASSETS
| Phase | Title | Activities | Deliverable | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | Status | Remarks
INITIATION
| INITIATION | KICK-OFF MEETING | KICK-OFF AND INITIAL INTRODUCTION
PRESENTATION OF IMPLEMENTATION METHODOLOGY
REVIEW OF AVAILABLE RESOURCES-TEAM IDENTIFICATION (PROCESS OWNERS, PROJECT MANAGER, SIGNING AUTHORITY)
NOMINATE PROCESS OWNERS, PROJECT MANAGER & SIGN OFF AUTHORITY
OVERVIEW OF BUSINESS AS IS AT A MACRO LEVEL
|  |  | PRESENTATION & APPROVAL OF PROJECT PLAN | PROJECT PLAN
ANALYSIS & DESIGN
| ANALYSIS & DESIGN | REQUIREMENT ANALYSIS | WORKSHOP FOR FUNCTION WISE BUSINESS PROCESS STUDY & COLLECTION OF REQUIREMENTS
DATABASE-COMPANY STRUCTURE AWARENESS SESSION TO THE KEY USER GROUP
PRODUCT CAPABILITY & UTILIZATION AWARENESS TO THE KEY USER GROUP
BUSINESS PROCESS & DOCUMENTS PRESENTATION
INVENTORY MANAGEMENT & PROCUREMENT ANALYSIS
PURCHASE PROCESS & INVENTORY ISSUE
FINANCIAL MANAGEMENT & ACCOUNTING STRUCTURE INCL. CHART OF ACCOUNTS, GENERAL ACCOUNTING & JOURNAL BATCHES - REQ.
BANK ACCOUNTS, VARIOUS TYPES OFTRANSACTIONS, CURRENCIES, EXCHANGE RATE & BRS REQ.
PURCHASE PROCESS, DUTIES & TAXES
DONATION ACCOUNTING
ACCOUNTING OF VARIOUS OTHER INCOME
AP & AR
FIXED ASSETS
FINANCIAL STATEMENTS & PERIODIC REPORTS- REQ
CUSTOMER ENTITY- CREATION - GENERAL INFORMATION AND SET UP- REQ.
VENDOR & ITEM CREATION- SET UP & REQ
FINALYZING DIMENSIONS, POSTING GROUPS, TAX COMPONENTS
PROCESS FINALIZATION WORKSHOP
DATA CONVERSION & VOLUME MATRIX( OPB)
COLLECT VARIOUS TEST CASES & DOCUMENT FORMATS
FINANCIAL VOUCHERS, ADVICE, DRN & CRN
DONATION RECEIPTS & OTHER INCOME
PURCHASE- TEST CASES & DOCUMENT FORMATS
|  | FUNCTIONAL REQ. DOCUMENTATION | FRD & FIT GAP
PREPARATION OF FRD (FUNCTIONAL REQUIREMENT DOCUMENT)
PREPARE GAP-FIT DOCUMENT (INCLUDING REPORTING REQUIREMENTS)
|  |  | FRD PRESENTATION | FRD
FRD SIGN OFF
GAP - FIT RESOLUTION WORKSHOP (PROCESS CONFIRMATION)
|  |  | PREPARE LIST OF CUSTOMISED DELIVERABLES (INCLUDING REPORTING REQUIREMENTS) | LIST OF DELIVERABLES
REVIEW IMPACT OF GAP-FIT RESOLUTION ON PROJECT PLAN
|  | SOLUTION DESIGN | CUSTOMISATION - TO BE BUILD
SOLUTION DESIGN WORKSHOP
IDENTIFY LIMITATIONS IN THE OUT-OF-BOX SOLUTION AND DISCUSS WORK AROUND
PREPARATION OF ENTERPRISE DESIGN DOCUMENT (EDD)
|  |  | PRESENTATION OF EDD | EDD
CUSTOMISATION BUILD - TO BE
REPORTS (TO BE BUILD)
DATA CONVERSION AND DESIGN BUILD
PREPARATION OF TEST CASES (ISKCON TO PROVIDE INFO)
UNIT TESTING
|  |  | COMPLETION OF STATEMENT OF WORK | TEST CASES
CONFIGURATION
4.3.3 | CONFIGURATION | INSTALLATION & SYSTEM INITIALIZATION | INSTALLATION, DATABASE SETUP AND CONFIGURATION
|  | CREATE DB | CREATE COMPANY (LEGAL ENTITY)
|  | MIGRATE MASTER DATA | SETTING UP COMPANY
UPLOAD MASTERS- CUSTOMER, VENDOR, ITEM, BANK, ACCOUNTS, FA, DIMENSION, POSTING GROUPS, & SET UP
|  |  | ALL MASTERS VERIFICATION | RECORD STATISTICS
|  | VALIDITY CHECK | CHECK THE VALIDITY OF THE DATA CREATED/IMPORTED
ROLE AND USER MATRIX FINALIZATION
|  |  | CUSTOMER CONFIRMATION ON MASTERDATA & SET UP | CONFIRMATION FROM CUSTOMER
|  | CRP | CRP WORKSHOP- PROCESS & TRANSACTIONS
CRP-WORKSHOP- REPORTS
|  |  | OBTAIN CUSTOMER CONFIRMATION | CONFIRMATION FROM CUSTOMER
|  | OPB TEMPLATES | PROVIDING TEMPLATES FOR VARIOUS OPENING BALANCES
PREPARATION OF USER MANUAL
DEPLOYMENT
4.3.4 | DEPLOYMENT | TRAINING | TRAINING FOR USERS ON THE CUSTOMISED FINAL PRODUCT | USER MANUAL
USER TRAINING
|  | USER ACCEPTANCE TEST | USER ACCEPTANCE TESTING OF SAMPLE SCENARIOS
UAT INSTANCE SET UP
|  |  | INTERAGATION TESTING | TESTING STRATEGY DOCUMENT, LIST OF FUNCTIONALITIES, TRANSACTIONS & REPORTS
PERFORM UAT
GENERATE REPORTS
REVIEW RESULTS AND OBTAIN SIGN OFF
GO-LIVE
4.3.5 | GO-LIVE | SYSTEM READINESS | GO-LIVE SET UP
PRODUCTION INSTANCE SET
ROLE AND USER MATRIX SET UP
REPORTS
FINALYZE CUT OVER AND GO-LIVE
|  |  | UPLOADING OPB | BALANCE CONFIRMATION FROM CUSTOMER
|  |  | FINAL SET UP TESTING / CHECK UP | E MAIL CONFIRMATION FROM CUSTOMER
|  | GO LIVE | GO LIVE - LIVE TRANSACTIONS
LIVE TRANSACTION SUPPORT - ON SITE
|  | SIGN OFF | PROJECT SIGN OFF & HAND OVER TO SUPPORT | CONCLUSION LETTER
|  |  | TOTAL NO. OF CAL DAYS | 50

## TSF
ISKCON- MS DYNAMICS NAV 2013 R2 IMPLEMENTATION PROJECT PLAN- ENTITY: TOUCHSTONE FOUNDATION (TSF)
MODULES COVERED - FINANCE, SALES & PURCHASE, INVENTORY, PRODUCTION & FIXED ASSETS
| Phase | Title | Activities | Deliverable | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | week 13 | week 14 | week 15 | week 16 | Wek 17 | Week 18 | Status | Remarks
INITIATION
| INITIATION | KICK-OFF MEETING | KICK-OFF AND INITIAL INTRODUCTION
PRESENTATION OF IMPLEMENTATION METHODOLOGY
REVIEW OF AVAILABLE RESOURCES-TEAM IDENTIFICATION (PROCESS OWNERS, PROJECT MANAGER, SIGNING AUTHORITY)
NOMINATE PROCESS OWNERS, PROJECT MANAGER & SIGN OFF AUTHORITY
OVERVIEW OF BUSINESS AS IS AT A MACRO LEVEL
|  |  | PRESENTATION & APPROVAL OF PROJECT PLAN | PROJECT PLAN
ANALYSIS & DESIGN
| ANALYSIS & DESIGN | REQUIREMENT ANALYSIS | WORKSHOP FOR FUNCTION WISE BUSINESS PROCESS STUDY & COLLECTION OF REQUIREMENTS
DATABASE-COMPANY STRUCTURE AWARENESS SESSION TO THE KEY USER GROUP
PRODUCT CAPABILITY & UTILIZATION AWARENESS TO THE KEY USER GROUP
BUSINESS PROCESS & DOCUMENTS PRESENTATION: GIFT DIVISION
INVENTORY MANAGEMENT & LOCATIONS
PHOTO ASSEMBLY & BOOKS KIT MAKING
PROCUREMENT PLANNING
PURCHASE PROCESS, APPROVAL & AMENDMENT
SALES PLANNING, SALES PROCESS
BUSINESS PROCESS & DOCUMENTS PRESENTATION: FOOD DIVISION
INVENTORY MANAGEMENT & LOCATIONS
PROCUREMENT PLANNING
PURCHASE PROCESS, APPROVAL & AMENDMENT
BOM,PRODUCTION PLANNING & PROCESS,
QC PROCESS
FG INVENTORY & DISTRIBUTION
SALES PLANNING, SALES PROCESS
FG COSTING AND ACCOUNTING
FINANCIAL MANAGEMENT & ACCOUNTING STRUCTURE INCL. CHART OF ACCOUNTS, GENERAL ACCOUNTING & JOURNAL BATCHES - REQ.
BANK ACCOUNTS, VARIOUS TYPES OFTRANSACTIONS, CURRENCIES, EXCHANGE RATE & BRS REQ.
PURCHASE PROCESS, DUTIES & TAXES
SALES PROCESS DUTIES & TAXES
AP & AR
FIXED ASSETS
FINANCIAL STATEMENTS & PERIODIC REPORTS- REQ
CUSTOMER ENTITY- CREATION - GENERAL INFORMATION AND SET UP- REQ.
VENDOR & ITEM CREATION- SET UP & REQ WITH PRICING
FINALYZING DIMENSIONS, POSTING GROUPS, TAX COMPONENTS
PROCESS FINALIZATION WORKSHOP
DATA CONVERSION & VOLUME MATRIX( OPB)
COLLECT VARIOUS TEST CASES & DOCUMENT FORMATS
FINANCIAL VOUCHERS, ADVICE, DRN & CRN
PURCHASE- TEST CASES & DOCUMENT FORMATS
BOM, CONSUMPTION, QC & OUTPUT ENTRIES
SALES- TEST CASES & DOCUMENT FORMATS
|  | FUNCTIONAL REQ. DOCUMENTATION | FRD & FIT GAP
PREPARATION OF FRD (FUNCTIONAL REQUIREMENT DOCUMENT)
PREPARE GAP-FIT DOCUMENT (INCLUDING REPORTING REQUIREMENTS)
|  |  | FRD PRESENTATION | FRD
FRD SIGN OFF
GAP - FIT RESOLUTION WORKSHOP (PROCESS CONFIRMATION)
|  |  | PREPARE LIST OF CUSTOMISED DELIVERABLES (INCLUDING REPORTING REQUIREMENTS) | LIST OF DELIVERABLES
REVIEW IMPACT OF GAP-FIT RESOLUTION ON PROJECT PLAN
|  | SOLUTION DESIGN | CUSTOMISATION - TO BE BUILD
SOLUTION DESIGN WORKSHOP
IDENTIFY LIMITATIONS IN THE OUT-OF-BOX SOLUTION AND DISCUSS WORK AROUND
PREPARATION OF ENTERPRISE DESIGN DOCUMENT (EDD)
|  |  | PRESENTATION OF EDD | EDD
CUSTOMISATION BUILD - TO BE
REPORTS (TO BE BUILD)
DATA CONVERSION AND DESIGN BUILD
PREPARATION OF TEST CASES (ISKCON TO PROVIDE INFO)
UNIT TESTING
|  |  | COMPLETION OF STATEMENT OF WORK | TEST CASES
CONFIGURATION
4.3.3 | CONFIGURATION | INSTALLATION & SYSTEM INITIALIZATION | INSTALLATION, DATABASE SETUP AND CONFIGURATION
|  | CREATE DB | CREATE COMPANY (LEGAL ENTITY)
|  | MIGRATE MASTER DATA | SETTING UP COMPANY
UPLOAD MASTERS- CUSTOMER, VENDOR, ITEM, BANK, ACCOUNTS, FA, DIMENSION, POSTING GROUPS, & SET UP
|  |  | ALL MASTERS VERIFICATION | RECORD STATISTICS
|  | VALIDITY CHECK | CHECK THE VALIDITY OF THE DATA CREATED/IMPORTED
ROLE AND USER MATRIX FINALIZATION
|  |  | CUSTOMER CONFIRMATION ON MASTERDATA & SET UP | CONFIRMATION FROM CUSTOMER
|  | CRP | CRP WORKSHOP- PROCESS & TRANSACTIONS
CRP-WORKSHOP- REPORTS
|  |  | OBTAIN CUSTOMER CONFIRMATION | CONFIRMATION FROM CUSTOMER
|  | OPB TEMPLATES | PROVIDING TEMPLATES FOR VARIOUS OPENING BALANCES
PREPARATION OF USER MANUAL
DEPLOYMENT
4.3.4 | DEPLOYMENT | TRAINING | TRAINING FOR USERS ON THE CUSTOMISED FINAL PRODUCT | USER MANUAL
USER TRAINING
|  | USER ACCEPTANCE TEST | USER ACCEPTANCE TESTING OF SAMPLE SCENARIOS
UAT INSTANCE SET UP
|  |  | INTERAGATION TESTING | TESTING STRATEGY DOCUMENT, LIST OF FUNCTIONALITIES, TRANSACTIONS & REPORTS
PERFORM UAT
GENERATE REPORTS
REVIEW RESULTS AND OBTAIN SIGN OFF
GO-LIVE
4.3.5 | GO-LIVE | SYSTEM READINESS | GO-LIVE SET UP
PRODUCTION INSTANCE SET
ROLE AND USER MATRIX SET UP
REPORTS
FINALYZE CUT OVER AND GO-LIVE
|  |  | UPLOADING OPB | BALANCE CONFIRMATION FROM CUSTOMER
|  |  | FINAL SET UP TESTING / CHECK UP | E MAIL CONFIRMATION FROM CUSTOMER
|  | GO LIVE | GO LIVE - LIVE TRANSACTIONS
LIVE TRANSACTION SUPPORT - ON SITE
|  | SIGN OFF | PROJECT SIGN OFF & HAND OVER TO SUPPORT | CONCLUSION LETTER
|  |  | TOTAL NO. OF CAL DAYS | 90

## SST
ISKCON- MS DYNAMICS NAV 2013 R2 IMPLEMENTATION PROJECT PLAN- ENTITY: SANKIRTHAN SEVA TRUST ( SST)
MODULES COVERED - FINANCE, PURCHASE, SALES, INVENTORY & FIXED ASSETS
| Phase | Title | Activities | Deliverable | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | Status | Remarks
INITIATION
| INITIATION | KICK-OFF MEETING | KICK-OFF AND INITIAL INTRODUCTION
PRESENTATION OF IMPLEMENTATION METHODOLOGY
REVIEW OF AVAILABLE RESOURCES-TEAM IDENTIFICATION (PROCESS OWNERS, PROJECT MANAGER, SIGNING AUTHORITY)
NOMINATE PROCESS OWNERS, PROJECT MANAGER & SIGN OFF AUTHORITY
OVERVIEW OF BUSINESS AS IS AT A MACRO LEVEL
|  |  | PRESENTATION & APPROVAL OF PROJECT PLAN | PROJECT PLAN
ANALYSIS & DESIGN
| ANALYSIS & DESIGN | REQUIREMENT ANALYSIS | WORKSHOP FOR FUNCTION WISE BUSINESS PROCESS STUDY & COLLECTION OF REQUIREMENTS
DATABASE-COMPANY STRUCTURE AWARENESS SESSION TO THE KEY USER GROUP
PRODUCT CAPABILITY & UTILIZATION AWARENESS TO THE KEY USER GROUP
BUSINESS PROCESS & DOCUMENTS PRESENTATION
MAGAZINE OUTSOURCING- ORDERS & ENTIRES
INVENTORY MANAGEMENT & PROCUREMENT ANALYSIS
PURCHASE PROCESS & INVENTORY ISSUE
MAGAZINE DISTRIBUTION RELATED ENTRIES
FINANCIAL MANAGEMENT & ACCOUNTING STRUCTURE INCL. CHART OF ACCOUNTS, GENERAL ACCOUNTING & JOURNAL BATCHES - REQ.
BANK ACCOUNTS, VARIOUS TYPES OFTRANSACTIONS, CURRENCIES, EXCHANGE RATE & BRS REQ.
PURCHASE PROCESS, DUTIES & TAXES
AP & AR
FIXED ASSETS
FINANCIAL STATEMENTS & PERIODIC REPORTS- REQ
CUSTOMER ENTITY- CREATION - GENERAL INFORMATION AND SET UP- REQ.
VENDOR & ITEM CREATION- SET UP & REQ
FINALYZING DIMENSIONS, POSTING GROUPS, TAX COMPONENTS
PROCESS FINALIZATION WORKSHOP
DATA CONVERSION & VOLUME MATRIX( OPB)
COLLECT VARIOUS TEST CASES & DOCUMENT FORMATS
FINANCIAL VOUCHERS, ADVICE, DRN & CRN
MAGAZINE ACCOUNTING ( REVENUE & COST)
PURCHASE- TEST CASES & DOCUMENT FORMATS
|  | FUNCTIONAL REQ. DOCUMENTATION | FRD & FIT GAP
PREPARATION OF FRD (FUNCTIONAL REQUIREMENT DOCUMENT)
PREPARE GAP-FIT DOCUMENT (INCLUDING REPORTING REQUIREMENTS)
|  |  | FRD PRESENTATION | FRD
FRD SIGN OFF
GAP - FIT RESOLUTION WORKSHOP (PROCESS CONFIRMATION)
|  |  | PREPARE LIST OF CUSTOMISED DELIVERABLES (INCLUDING REPORTING REQUIREMENTS) | LIST OF DELIVERABLES
REVIEW IMPACT OF GAP-FIT RESOLUTION ON PROJECT PLAN
|  | SOLUTION DESIGN | CUSTOMISATION - TO BE BUILD
SOLUTION DESIGN WORKSHOP
IDENTIFY LIMITATIONS IN THE OUT-OF-BOX SOLUTION AND DISCUSS WORK AROUND
PREPARATION OF ENTERPRISE DESIGN DOCUMENT (EDD)
|  |  | PRESENTATION OF EDD | EDD
CUSTOMISATION BUILD - TO BE
REPORTS (TO BE BUILD)
DATA CONVERSION AND DESIGN BUILD
PREPARATION OF TEST CASES (ISKCON TO PROVIDE INFO)
UNIT TESTING
|  |  | COMPLETION OF STATEMENT OF WORK | TEST CASES
CONFIGURATION
4.3.3 | CONFIGURATION | INSTALLATION & SYSTEM INITIALIZATION | INSTALLATION, DATABASE SETUP AND CONFIGURATION
|  | CREATE DB | CREATE COMPANY (LEGAL ENTITY)
|  | MIGRATE MASTER DATA | SETTING UP COMPANY
UPLOAD MASTERS- CUSTOMER, VENDOR, ITEM, BANK, ACCOUNTS, FA, DIMENSION, POSTING GROUPS, & SET UP
|  |  | ALL MASTERS VERIFICATION | RECORD STATISTICS
|  | VALIDITY CHECK | CHECK THE VALIDITY OF THE DATA CREATED/IMPORTED
ROLE AND USER MATRIX FINALIZATION
|  |  | CUSTOMER CONFIRMATION ON MASTERDATA & SET UP | CONFIRMATION FROM CUSTOMER
|  | CRP | CRP WORKSHOP- PROCESS & TRANSACTIONS
CRP-WORKSHOP- REPORTS
|  |  | OBTAIN CUSTOMER CONFIRMATION | CONFIRMATION FROM CUSTOMER
|  | OPB TEMPLATES | PROVIDING TEMPLATES FOR VARIOUS OPENING BALANCES
PREPARATION OF USER MANUAL
DEPLOYMENT
4.3.4 | DEPLOYMENT | TRAINING | TRAINING FOR USERS ON THE CUSTOMISED FINAL PRODUCT | USER MANUAL
USER TRAINING
|  | USER ACCEPTANCE TEST | USER ACCEPTANCE TESTING OF SAMPLE SCENARIOS
UAT INSTANCE SET UP
|  |  | INTERAGATION TESTING | TESTING STRATEGY DOCUMENT, LIST OF FUNCTIONALITIES, TRANSACTIONS & REPORTS
PERFORM UAT
GENERATE REPORTS
REVIEW RESULTS AND OBTAIN SIGN OFF
GO-LIVE
4.3.5 | GO-LIVE | SYSTEM READINESS | GO-LIVE SET UP
PRODUCTION INSTANCE SET
ROLE AND USER MATRIX SET UP
REPORTS
FINALYZE CUT OVER AND GO-LIVE
|  |  | UPLOADING OPB | BALANCE CONFIRMATION FROM CUSTOMER
|  |  | FINAL SET UP TESTING / CHECK UP | E MAIL CONFIRMATION FROM CUSTOMER
|  | GO LIVE | GO LIVE - LIVE TRANSACTIONS
LIVE TRANSACTION SUPPORT - ON SITE
|  | SIGN OFF | PROJECT SIGN OFF & HAND OVER TO SUPPORT | CONCLUSION LETTER
|  |  | TOTAL NO. OF CAL DAYS | 45