## 05
Topics
S. No. | Course | Module | Topics Covered | Phase | Day | Status | (Re) Planned Date | Actual Date
617 | Finance Essentials | Chart of Accounts | Chart of Accounts Overview | 1 | Day-01 | Completed | 2015-03-17 | 2015-03-17
618 | Finance Essentials | Chart of Accounts | G/L Account Card | 1 | Day-01 | Completed | 2015-03-17 | 2015-03-17
607 | Finance Essentials | Finance Management Setup | General Ledger Setup | 1 | Day-01 | Completed | 2015-03-17 | 2015-03-17
608 | Finance Essentials | Finance Management Setup | Accounting Periods | 1 | Day-01 | Completed | 2015-03-17 | 2015-03-17
2000 | Fixed Assets | Fixed Assets Setup | Fixed Assets Overview | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1413 | Trade | Analysis and Reporting | Sales and Purchase Budgets | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1397 | Trade | Assembly Management | Reservations and Item Tracking | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1316 | Trade | Customer Service Features | Item Substitutions | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1317 | Trade | Customer Service Features | Item Cross References | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1355 | Trade | Item Charges | Sales Item Charges | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1329 | Trade | Purchase Order Management | Manage Purchase Transactions | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1330 | Trade | Purchase Order Management | Purchase Prices and Discounts | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1331 | Trade | Purchase Order Management | Purchase Prices | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1332 | Trade | Purchase Order Management | Invoice and Line Discounts | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1345 | Trade | Requisition Management | Requisition Management Setup | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1346 | Trade | Requisition Management | Requisition Worksheet | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1386 | Trade | Returns Managements | Manage Customer Returns | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1286 | Trade | Sales Order Management | Set Up Sales Order Management | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1287 | Trade | Sales Order Management | Manage Sales Transactions | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1288 | Trade | Sales Order Management | Item Reservation | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1289 | Trade | Sales Order Management | Posting Orders | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1304 | Trade | Sales Prices and Discounts | Sales Prices | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1305 | Trade | Sales Prices and Discounts | Maintain Sales Prices | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1306 | Trade | Sales Prices and Discounts | Sales Line Discounts | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1307 | Trade | Sales Prices and Discounts | Invoice Discounts | 1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
870 | Finance Advance | Budgets | Creating Budgets | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
871 | Finance Advance | Budgets | Copying Budgets | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
872 | Finance Advance | Budgets | Exporting and Importing Budgets | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
850 | Finance Advance | Multicurrency | Currency Card and Exchange Rates | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
851 | Finance Advance | Multicurrency | Set Up Multicurrency for Customers, Vendors, and Bank Accounts | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
642 | Finance Essentials | Cash Management - Receivables and Payables | Bank Account Overview | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
643 | Finance Essentials | Cash Management - Receivables and Payables | Customer Overview | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
644 | Finance Essentials | Cash Management - Receivables and Payables | Vendor Overview | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
645 | Finance Essentials | Cash Management - Receivables and Payables | Cash Receipt Journal and Payment Journal Overview | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
646 | Finance Essentials | Cash Management - Receivables and Payables | Suggest Vendor Payments | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
647 | Finance Essentials | Cash Management - Receivables and Payables | Print and Post Payables Checks | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
648 | Finance Essentials | Cash Management - Receivables and Payables | Voiding Checks | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
649 | Finance Essentials | Cash Management - Receivables and Payables | Applying Payments | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
650 | Finance Essentials | Cash Management - Receivables and Payables | Unapply Customer and Vendor Ledger Entries | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
651 | Finance Essentials | Cash Management - Receivables and Payables | Reversal of Posted Journals | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
675 | Finance Essentials | Cash Management - Reconciliation | Bank Reconciliation | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
676 | Finance Essentials | Cash Management - Reconciliation | Complete a Bank Reconciliation | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
619 | Finance Essentials | Chart of Accounts | G/L Account Card Ribbon | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
628 | Finance Essentials | General Journals | Creating and Posting Journal Entries | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
629 | Finance Essentials | General Journals | Standard Journals | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
630 | Finance Essentials | General Journals | Recurring Journals | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
631 | Finance Essentials | General Journals | Processing Recurring Journals | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
682 | Finance Essentials | Receivables and Paybales Management | Set Up Payment Discounts | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
683 | Finance Essentials | Receivables and Paybales Management | Process Payment Discounts | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
684 | Finance Essentials | Receivables and Paybales Management | Set Up and Process Payment Tolerances | 1 | Day-03 | Parked | 2015-03-19 | 2015-03-19
685 | Finance Essentials | Receivables and Paybales Management | Review the Posted Payment Discount Tolerance and the Payment Tolerance Entries | 1 | Day-03 | Parked | 2015-03-19 | 2015-03-19
686 | Finance Essentials | Receivables and Paybales Management | Review Customer and Vendor Statistics | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
769 | Finance Essentials | Year End Procedures | Closing a Fiscal Year | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
2001 | Finance Advance | Cost Accounting | Cost Accounting Overview | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
852 | Finance Advance | Multicurrency | Process Documents and Journals | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
853 | Finance Advance | Multicurrency | Adjust Exchange Rates Batch Job for Customers, Vendors, and Bank Accounts | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
854 | Finance Advance | Multicurrency | Reporting Currency | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
855 | Finance Advance | Multicurrency | View the Exchange Rate Adjustment Register | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
856 | Finance Advance | Multicurrency | Summary of Currency Exchange Rates | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
737 | Finance Essentials | Prepayments | Setting Up Prepayments | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
738 | Finance Essentials | Prepayments | Set Up Prepayment Percentages for Customers and Vendors | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
739 | Finance Essentials | Prepayments | Set Up Prepayment % for Customer-Item & Vendor-Item Combinations | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
740 | Finance Essentials | Prepayments | Set Up Prepayments Verification | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
741 | Finance Essentials | Prepayments | Prepayments Processing Flows | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
742 | Finance Essentials | Prepayments | Prepayment Sales and Purchase Orders Overview | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
743 | Finance Essentials | Prepayments | Process Prepayment Sales and Purchase Orders | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
744 | Finance Essentials | Prepayments | Prepayment Sales and Purchase Invoices | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
745 | Finance Essentials | Prepayments | Prepayment Purchase Order Process | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
699 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Reminder Terms | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
700 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Number Series for Reminders and Issue Reminders | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
701 | Finance Essentials | Receivables and Paybales Management | Create and Issue Reminders | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
702 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Finance Charge Terms | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
703 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Number Series for Finance Charge Terms | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
704 | Finance Essentials | Receivables and Paybales Management | Create and Issue Finance Charge Memos | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
705 | Finance Essentials | Receivables and Paybales Management | Calculate Interest on Reminders | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1411 | Trade | Analysis and Reporting | Analysis Views and Reports | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1412 | Trade | Analysis and Reporting | Analysis by Dimensions | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1395 | Trade | Assembly Management | Assembly Items and Assembly Bill of Materials | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1396 | Trade | Assembly Management | Assemble to Order | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1398 | Trade | Assembly Management | Selling ATO Items and Inventory Items Together | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1399 | Trade | Assembly Management | Assemble-to-Order Shipments | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1318 | Trade | Customer Service Features | Set Up and Create Nonstock Items | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1319 | Trade | Customer Service Features | Sell Nonstock Items | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1354 | Trade | Item Charges | Purchase Item Charges | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1356 | Trade | Item Charges | Purchase and Sales Allowances | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1328 | Trade | Purchase Order Management | Purchase Order Management Setup | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1333 | Trade | Purchase Order Management | Vendor Prepayments | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1347 | Trade | Requisition Management | Additional Worksheet Features | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1385 | Trade | Returns Managements | Returns Management Setup | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1387 | Trade | Returns Managements | Manage Returns to Vendors | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1290 | Trade | Sales Order Management | Drop Shipments | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1291 | Trade | Sales Order Management | Customer Prepayments | 1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
138 | Config-Func | Set Up Dimensions | Dimensions and Dimension Values | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
139 | Config-Func | Set Up Dimensions | Setting Up Dimensions in General Ledger Setup | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
140 | Config-Func | Set Up Dimensions | Dimension Combinations | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
141 | Config-Func | Set Up Dimensions | Default Dimensions and Account Type Default Dimensions | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
142 | Config-Func | Set Up Dimensions | Default Dimension Priority | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
143 | Config-Func | Set Up Dimensions | Conflicting Default Dimensions | 1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
2002 | Finance Advance | Cash Flow Forecast | Cash Flow Forecast Overview | 1 | Day 04 | Completed | 2015-03-19 | 2015-03-19
2003 | Indian Localization | Structure | Overview of structure | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2004 | Indian Localization | Structure | Basic Setup | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2005 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Purchase Order with Structure | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2006 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Sales Order with Structure | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2007 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Purchase Return Order with Structure | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2008 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Sales Return Order with Structure | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2078 | Indian Localization | VAT / Sales Tax | Overview of Value Added Tax (VAT) | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2079 | Indian Localization | VAT / Sales Tax | Basic Setup | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2080 | Indian Localization | VAT / Sales Tax | Calculating VAT on purchase of goods | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2083 | Indian Localization | VAT / Sales Tax | Calculating VAT able Purchase Tax on CST | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2084 | Indian Localization | VAT / Sales Tax | Calculating VAT if Purchases are meant for Export or Deemed Export | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2087 | Indian Localization | VAT / Sales Tax | Calculating VAT in case of Sales Order | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
885 | Finance Advance | Cost Accounting | Cost Entries | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
887 | Finance Advance | Cost Accounting | Cost Allocation | 2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
928 | Finance Advance | Financial Reporting and Analysis | Analyze the Chart of Accounts | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
929 | Finance Advance | Financial Reporting and Analysis | Account Schedules | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
930 | Finance Advance | Financial Reporting and Analysis | Analysis by Dimensions | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
931 | Finance Advance | Financial Reporting and Analysis | Export Analysis Views to Microsoft Excel | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
932 | Finance Advance | Financial Reporting and Analysis | Dimension-Based Reports | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
933 | Finance Advance | Financial Reporting and Analysis | Combine Analysis Views with Account Schedules | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1077 | Fixed Assets | Fixed Asset Insurance | Setting Up Insurance Information | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1078 | Fixed Assets | Fixed Asset Insurance | Attaching Assets to Insurance Policies | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1079 | Fixed Assets | Fixed Asset Insurance | Monitoring Insurance Coverage | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1080 | Fixed Assets | Fixed Asset Insurance | Updating Insurance Information | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1050 | Fixed Assets | Fixed Asset Reclassification | Asset Transfers | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1051 | Fixed Assets | Fixed Asset Reclassification | Combining Assets | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1001 | Fixed Assets | Fixed Asset Transactions | Journals for Fixed Assets | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1002 | Fixed Assets | Fixed Asset Transactions | Purchase Fixed Assets | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1003 | Fixed Assets | Fixed Asset Transactions | Calculate and Post Depreciation | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1004 | Fixed Assets | Fixed Asset Transactions | Write-down and Appreciation of Fixed Assets | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1005 | Fixed Assets | Fixed Asset Transactions | Fixed Asset Disposals | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1006 | Fixed Assets | Fixed Asset Transactions | Correct an Entry | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1007 | Fixed Assets | Fixed Asset Transactions | Document Fixed Asset Transactions | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1008 | Fixed Assets | Fixed Asset Transactions | Fixed Asset Reports | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1009 | Fixed Assets | Fixed Asset Transactions | Budget Fixed Asset Transactions | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1012 | Fixed Assets | Fixed Asset Transactions | Minor Assets | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1064 | Fixed Assets | Fixed Assets Maintenance | Setting Up Maintenance Information | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1065 | Fixed Assets | Fixed Assets Maintenance | Maintenance Registration and Costs | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1066 | Fixed Assets | Fixed Assets Maintenance | Maintenance Cost Reporting | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
975 | Fixed Assets | Fixed Assets Setup | Fixed Assets Process Flow | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
976 | Fixed Assets | Fixed Assets Setup | Fixed Assets Setup | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
977 | Fixed Assets | Fixed Assets Setup | Fixed Assets Posting Groups | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
978 | Fixed Assets | Fixed Assets Setup | Depreciation Books | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
979 | Fixed Assets | Fixed Assets Setup | Fixed Asset Card | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
980 | Fixed Assets | Fixed Assets Setup | Fixed Asset Allocation Keys | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
981 | Fixed Assets | Fixed Assets Setup | Main Assets and Asset Components | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
983 | Fixed Assets | Fixed Assets Setup | Make Duplicate Entries | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
984 | Fixed Assets | Fixed Assets Setup | Copy Fixed Assets and FA Ledger Entries | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1365 | Trade | Order Promising | Sales Order Promising Definitions and Calculations | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1366 | Trade | Order Promising | Date Calculation Setup for Sales Orders | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1367 | Trade | Order Promising | Promising Sales Order Delivery | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1368 | Trade | Order Promising | Purchase Order Promising Definitions and Calculations | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1369 | Trade | Order Promising | Date Calculation Setup for Purchase Orders | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1370 | Trade | Order Promising | Estimating Purchase Order Receipts | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1371 | Trade | Order Promising | Estimate a Transfer Order Receipt | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1372 | Trade | Order Promising | Calendars | 2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
2097 | Indian Localization | VAT / Sales Tax | Entering VAT opening in case of capital goods containing VAT deferment with Settled Period | 2 |  | Parked
2098 | Indian Localization | VAT / Sales Tax | Entering VAT opening in case of capital goods containing VAT deferment without Settled period | 2 |  | Parked
934 | Finance Advance | Financial Reporting and Analysis | Finance Performance Charts | 2
1010 | Fixed Assets | Fixed Asset Transactions | Cost Accounting Depreciation | 2
2040 | Indian Localization | Service Tax | Overview of Service Tax | 2
2041 | Indian Localization | Service Tax | Basic Setup | 2
2042 | Indian Localization | Service Tax | Calculating Service Tax and TDS using Journal Voucher | 2
2043 | Indian Localization | Service Tax | Service Tax Implication while Making Payment to Vendor against Invoice | 2
2044 | Indian Localization | Service Tax | Calculating Service Tax and TDS using Bank Payment Voucher for Advance Payments | 2
2045 | Indian Localization | Service Tax | Service Tax Implication while creating Invoice against Advance Payment | 2
2046 | Indian Localization | Service Tax | Service Tax Implication by Applying Advance Payment and Invoice from Vendor Ledger Entry | 2
2047 | Indian Localization | Service Tax | Service Tax Implication by Applying Normal Payment and Invoice from Vendor Ledger Entry | 2
2048 | Indian Localization | Service Tax | Reversal of Bank Payment Voucher which includes Service Tax | 2
2049 | Indian Localization | Service Tax | Purchase Invoice with CENVAT taken on Inputs | 2
2050 | Indian Localization | Service Tax | Purchase Invoice with CENVAT taken on Capital Goods | 2
2051 | Indian Localization | Service Tax | Credit Received from Inter Unit Transfer by a LTU | 2
2052 | Indian Localization | Service Tax | Purchase Invoice with Service Tax in case of Input Service Distributor | 2
2053 | Indian Localization | Service Tax | Service Tax Distribution | 2
2054 | Indian Localization | Service Tax | GTA Transaction in case of Service Receiver | 2
2055 | Indian Localization | Service Tax | Refund of Advance Payment from Vendor with Service Tax | 2
2056 | Indian Localization | Service Tax | Purchase Credit Memo with Service Tax | 2
2057 | Indian Localization | Service Tax | Calculating Service Tax using Journal Voucher | 2
2058 | Indian Localization | Service Tax | Service Tax Implication while Receiving Payment from Customer | 2
2059 | Indian Localization | Service Tax | Calculating Service Tax on Advance Payment Received from Customer | 2
2060 | Indian Localization | Service Tax | Service Tax Implication while creating Invoice against Advance Payment | 2
2061 | Indian Localization | Service Tax | Service Tax Implication by Applying Advance Payment and Invoice from Customer Ledger Entry | 2
2062 | Indian Localization | Service Tax | Service Tax Implication by Applying Normal Payment and Invoice from Customer Ledger Entry | 2
2063 | Indian Localization | Service Tax | Reversal of Bank Receipt Voucher which includes Service Tax | 2
2064 | Indian Localization | Service Tax | Export of Services using Sales Invoice | 2
2065 | Indian Localization | Service Tax | Sale of Exempted Services | 2
2066 | Indian Localization | Service Tax | ST Pure Agent | 2
2067 | Indian Localization | Service Tax | Calculating Service Tax with Abatement Percentage | 2
2068 | Indian Localization | Service Tax | Refund of Advance Payment to Customer with Service Tax | 2
2069 | Indian Localization | Service Tax | Sales Credit Memo with Service Tax | 2
2070 | Indian Localization | Service Tax | Calculation of Service Tax on Direct Payments/Receipts | 2
2071 | Indian Localization | Service Tax | Service Tax Implication while applying Invoice and Payment with different Currency Exchange Rates | 2
2072 | Indian Localization | Service Tax | Service Tax Opening | 2
2073 | Indian Localization | Service Tax | Service Tax Adjustment | 2
2074 | Indian Localization | Service Tax | Adjust Service Tax Credit | 2
2075 | Indian Localization | Service Tax | Service Tax Payment | 2
2076 | Indian Localization | Service Tax | ST3 Removed as such/LTU Dtls | 2
2077 | Indian Localization | Service Tax | Service Tax Reports | 2
2081 | Indian Localization | VAT / Sales Tax | Calculating VAT if vendor has opted for Composition scheme | 2
2082 | Indian Localization | VAT / Sales Tax | Calculating VAT if Retention limit is defined in the Tax Jurisdiction setup with Non ITC claimable Usage% defined | 2
2085 | Indian Localization | VAT / Sales Tax | Calculating VAT in case of capital item if deferment period is 1Y in the States setup with a checkmark in the Financial Year field | 2
2086 | Indian Localization | VAT / Sales Tax | Calculating VAT in Purchase Credit Memo in case of normal item | 2
2088 | Indian Localization | VAT / Sales Tax | Calculating VAT if standard deduction% is defined in the Tax Detail setup | 2
2089 | Indian Localization | VAT / Sales Tax | Calculating VAT on sale of goods in case of VAT exempted or Export or Deemed Export | 2
2090 | Indian Localization | VAT / Sales Tax | Calculating CST on sale of goods using sales order | 2
2091 | Indian Localization | VAT / Sales Tax | Calculating VAT as per multiple tax jurisdictions in case of normal item | 2
2092 | Indian Localization | VAT / Sales Tax | Adjustment of VAT (Lot no. wise) in case of normal item when VAT Adjustment type is Lost/Destroy | 2
2093 | Indian Localization | VAT / Sales Tax | Adjustment of VAT (Serial No. Wise) in case of normal item When VAT Adjustment type is Consumed | 2
2094 | Indian Localization | VAT / Sales Tax | Adjustment of VAT in case of Partial Branch Transfers through VAT Adjustment Journal | 2
2095 | Indian Localization | VAT / Sales Tax | Adjustment of VAT in case of change in usage through VAT Adjustment Journal | 2
2100 | Indian Localization | VAT / Sales Tax | Calculating VAT through Purchase Credit Memo in case of Fixed Asset | 2
2101 | Indian Localization | VAT / Sales Tax | Calculating VAT through Sales Credit Memo | 2
2102 | Indian Localization | VAT / Sales Tax | VAT Settlement | 2
2103 | Indian Localization | VAT / Sales Tax | VAT Reporting | 2
909 | Finance Advance | Cash Flow Forecast | Functions of the Cash Flow Forecast | 2
910 | Finance Advance | Cash Flow Forecast | Setting Up Cash Flow Forecasts | 2
911 | Finance Advance | Cash Flow Forecast | Creating Cash Flow Forecasts | 2
912 | Finance Advance | Cash Flow Forecast | Cash Flow Forecast Reporting | 2
883 | Finance Advance | Cost Accounting | Workflow in Cost Accounting | 2
884 | Finance Advance | Cost Accounting | Setting Up Cost Accounting | 2
886 | Finance Advance | Cost Accounting | Cost Budgets | 2
888 | Finance Advance | Cost Accounting | Cost Accounting History | 2
889 | Finance Advance | Cost Accounting | Cost Accounting Reporting | 2
890 | Finance Advance | Cost Accounting | Tips and Tricks | 2
73 | Config-Tech | Manage User Rights and Profiles | Authentication | 3
74 | Config-Tech | Manage User Rights and Profiles | Set Up User Rights | 3
75 | Config-Tech | Manage User Rights and Profiles | Create a New Permission Set | 3
76 | Config-Tech | Manage User Rights and Profiles | Apply Security Filters | 3
77 | Config-Tech | Manage User Rights and Profiles | User-Specific Setup | 3
78 | Config-Tech | Manage User Rights and Profiles | User Profile Setup | 3
79 | Config-Tech | Manage User Rights and Profiles | Best Practices | 3
54 | Config-Tech | Set Up a Company by Using RapidStart Services | Manual Setup vs RapidStart Services | 3
55 | Config-Tech | Set Up a Company by Using RapidStart Services | Rapid Start Services Process Flow | 3
56 | Config-Tech | Set Up a Company by Using RapidStart Services | Create and Export a Configuration Package | 3
57 | Config-Tech | Set Up a Company by Using RapidStart Services | Configure a New Company by Using RapidStart Services | 3
58 | Config-Tech | Set Up a Company by Using RapidStart Services | Data Migration by Using Rapid Start Services | 3
59 | Config-Tech | Set Up a Company by Using RapidStart Services | Transfer Opening Balances by Using RapidStart Services | 3
160 | Config-Tech | Set Up and Manage Document Approvals | Set Up Document Approvals | 3
161 | Config-Tech | Set Up and Manage Document Approvals | Set Up the Notification System | 3
162 | Config-Tech | Set Up and Manage Document Approvals | Set Up a Sales Document Approvals System | 3
163 | Config-Tech | Set Up and Manage Document Approvals | Use the Document Approval System | 3
109 | Config-Tech | Set Up General Journals Templates and Batches | Journal Templates, Batches, and Lines | 3
110 | Config-Tech | Set Up General Journals Templates and Batches | Create Journal Templates and Batches | 3
95 | Config-Func | Set Up Number Series | Number Series | 3
117 | Config-Func | Set Up Posting Groups | Specific Posting Groups | 3
118 | Config-Func | Set Up Posting Groups | General Posting Groups | 3
119 | Config-Func | Set Up Posting Groups | General Posting Setup | 3
120 | Config-Func | Set Up Posting Groups | VAT Posting Groups | 3
121 | Config-Func | Set Up Posting Groups | VAT Posting Setup | 3
122 | Config-Func | Set Up Posting Groups | Best Practices | 3
123 | Config-Func | Set Up Posting Groups | Post and Review a Sales Transaction | 3
103 | Config-Func | Set Up Trail Codes | Source Code and Reason Codes | 3
104 | Config-Func | Set Up Trail Codes | Navigate the Audit Trail | 3
1081 | Fixed Assets | Fixed Asset Insurance | Indexing Insurance | NA | NA | Not Applicable
1011 | Fixed Assets | Fixed Asset Transactions | Indexation | NA | NA | Not Applicable
982 | Fixed Assets | Fixed Assets Setup | Record Open Transactions | NA | NA | Remove this
2096 | Indian Localization | VAT / Sales Tax | Entering VAT opening in case of normal item | NA | NA | Not Applicable
2099 | Indian Localization | VAT / Sales Tax | Entering VAT opening on sale of goods | NA | NA | Not Applicable
833 | Finance Advance | Intrastat | Set up Intrastat | NA | NA | Not Applicable
834 | Finance Advance | Intrastat | Report Intrastat | NA | NA | Not Applicable
841 | Finance Advance | VAT Rate Change | Prepare for VAT Rate Change Tool | NA | NA | Not Applicable
842 | Finance Advance | VAT Rate Change | Set Up Using VAT Rate Change Tool | NA | NA | Not Applicable
843 | Finance Advance | VAT Rate Change | Perform VAT Rate Conversions | NA | NA | Not Applicable
954 | Finance Advance | XBRL | XBRL Terminology | NA | NA | Not Applicable
955 | Finance Advance | XBRL | XBRL Specifications and Taxonomies | NA | NA | Not Applicable
956 | Finance Advance | XBRL | Work with Linkbases | NA | NA | Not Applicable
957 | Finance Advance | XBRL | Enter XBRL Line Definitions | NA | NA | Not Applicable
958 | Finance Advance | XBRL | Export the XBRL Lines | NA | NA | Not Applicable
718 | Finance Essentials | VAT | VAT Calculation Types | NA | NA | Not Applicable
719 | Finance Essentials | VAT | Display VAT Amounts in Sales and Purchase Documents | NA | NA | Not Applicable
720 | Finance Essentials | VAT | Manually Adjust VAT Amounts in Sales and Purchase Documents and Journals | NA | NA | Not Applicable
721 | Finance Essentials | VAT | Unrealized VAT | NA | NA | Not Applicable
722 | Finance Essentials | VAT | VAT Statements | NA | NA | Not Applicable
723 | Finance Essentials | VAT | VAT Settlement | NA | NA | Not Applicable
1232 | Manufacturing | Advanced Capacity | Explains how to set up work centers and machine centers | NA | NA | Not Applicable
1233 | Manufacturing | Advanced Capacity | Shows how to set up shop calendars and capacity calendars | NA | NA | Not Applicable
1234 | Manufacturing | Advanced Capacity | Describes registered absences and how to use them | NA | NA | Not Applicable
1235 | Manufacturing | Advanced Capacity | Explains how to use capacity journals | NA | NA | Not Applicable
1117 | Manufacturing | Basic Capacities and Routings | Explains how to set up capacity | NA | NA | Not Applicable
1118 | Manufacturing | Basic Capacities and Routings | Shows how to create routings | NA | NA | Not Applicable
1119 | Manufacturing | Basic Capacities and Routings | Describes the advanced features for routings | NA | NA | Not Applicable
1120 | Manufacturing | Basic Capacities and Routings | Reviews the standard capacity and routing reports | NA | NA | Not Applicable
1169 | Manufacturing | Forecasting and Planning | Describe the production forecast functionality | NA | NA | Not Applicable
1170 | Manufacturing | Forecasting and Planning | Explain the integration between production forecasting and planning | NA | NA | Not Applicable
1171 | Manufacturing | Forecasting and Planning | Show how actual demand is netted against forecast demand | NA | NA | Not Applicable
1172 | Manufacturing | Forecasting and Planning | Describe forecasting by location, order tracking as it relates to forecasting, and forecasting setup | NA | NA | Not Applicable
1173 | Manufacturing | Forecasting and Planning | Review the forecast reports | NA | NA | Not Applicable
1253 | Manufacturing | Manufacturing - Additional Topics | Describes standard tasks and how to use them | NA | NA | Not Applicable
1254 | Manufacturing | Manufacturing - Additional Topics | Explains stop codes and how to use them | NA | NA | Not Applicable
1255 | Manufacturing | Manufacturing - Additional Topics | Reviews the various options for recording scrap and the relationships between the options | NA | NA | Not Applicable
1256 | Manufacturing | Manufacturing - Additional Topics | Defines non-productive time and shows how to use it in a production order | NA | NA | Not Applicable
1257 | Manufacturing | Manufacturing - Additional Topics | Shows how to reduce lead time | NA | NA | Not Applicable
1258 | Manufacturing | Manufacturing - Additional Topics | Consumption journal entries and output journal entries for multilevel production orders | NA | NA | Not Applicable
1259 | Manufacturing | Manufacturing - Additional Topics | Defines production families and shows how to use them in a production order | NA | NA | Not Applicable
1260 | Manufacturing | Manufacturing - Additional Topics | Describes standard tasks and how to use them | NA | NA | Not Applicable
1261 | Manufacturing | Manufacturing - Additional Topics | Explains stop codes and how to use them | NA | NA | Not Applicable
1262 | Manufacturing | Manufacturing - Additional Topics | Reviews the various options for recording scrap and the relationships between the options | NA | NA | Not Applicable
1263 | Manufacturing | Manufacturing - Additional Topics | Defines non-productive time and shows how to use it in a production order | NA | NA | Not Applicable
1264 | Manufacturing | Manufacturing - Additional Topics | Shows how to reduce lead time | NA | NA | Not Applicable
1265 | Manufacturing | Manufacturing - Additional Topics | Consumption journal entries and output journal entries for multilevel production orders | NA | NA | Not Applicable
1266 | Manufacturing | Manufacturing - Additional Topics | Defines production families and shows how to use them in a production order | NA | NA | Not Applicable
1182 | Manufacturing | Planning | Describes the general concepts of the planning system | NA | NA | Not Applicable
1183 | Manufacturing | Planning | Introduces the planning worksheet and related functions | NA | NA | Not Applicable
1184 | Manufacturing | Planning | Explains how to use regenerative planning | NA | NA | Not Applicable
1185 | Manufacturing | Planning | Shows how to use net change planning | NA | NA | Not Applicable
1186 | Manufacturing | Planning | Describes how parameters affect the planning process | NA | NA | Not Applicable
1187 | Manufacturing | Planning | Explains how to use order tracking and action messages | NA | NA | Not Applicable
1188 | Manufacturing | Planning | Describes the general concepts of the planning system | NA | NA | Not Applicable
1189 | Manufacturing | Planning | Introduces the planning worksheet and related functions | NA | NA | Not Applicable
1190 | Manufacturing | Planning | Explains how to use regenerative planning | NA | NA | Not Applicable
1191 | Manufacturing | Planning | Shows how to use net change planning | NA | NA | Not Applicable
1192 | Manufacturing | Planning | Describes how parameters affect the planning process | NA | NA | Not Applicable
1193 | Manufacturing | Planning | Explains how to use order tracking and action messages | NA | NA | Not Applicable
1196 | Manufacturing | Planning - Additional Topics | Defines item variants | NA | NA | Not Applicable
1197 | Manufacturing | Planning - Additional Topics | Explains how to use locations in planning | NA | NA | Not Applicable
1198 | Manufacturing | Planning - Additional Topics | Shows how to perform transfers between locations | NA | NA | Not Applicable
1199 | Manufacturing | Planning - Additional Topics | Describes how to use blanket sales orders in planning | NA | NA | Not Applicable
1200 | Manufacturing | Planning - Additional Topics | Explains how to use multilevel production orders | NA | NA | Not Applicable
1201 | Manufacturing | Planning - Additional Topics | Reviews how to filter the planning worksheet | NA | NA | Not Applicable
1202 | Manufacturing | Planning - Additional Topics | Shows how to change the replenishment system for a planning line | NA | NA | Not Applicable
1203 | Manufacturing | Planning - Additional Topics | Describes how to refresh planning lines | NA | NA | Not Applicable
1204 | Manufacturing | Planning - Additional Topics | Identifies the available planning reports | NA | NA | Not Applicable
1108 | Manufacturing | Production Bill of Materials | Describes the production BOM structure and its basic features | NA | NA | Not Applicable
1109 | Manufacturing | Production Bill of Materials | Explains and demonstrates production BOM advanced features | NA | NA | Not Applicable
1110 | Manufacturing | Production Bill of Materials | Shows production BOM reports | NA | NA | Not Applicable
1143 | Manufacturing | Production Order Processing | Reviews the flow of events as production orders move from release until they are finished | NA | NA | Not Applicable
1144 | Manufacturing | Production Order Processing | Options and procedures related to material consumption and production output | NA | NA | Not Applicable
1145 | Manufacturing | Production Order Processing | Shows how to pick components and put away finished goods in the warehouse | NA | NA | Not Applicable
1146 | Manufacturing | Production Order Processing | Explains the uses of the consumption journal, output journal, and production journal | NA | NA | Not Applicable
1128 | Manufacturing | Production Orders | Describes the different production order statuses | NA | NA | Not Applicable
1129 | Manufacturing | Production Orders | Explains how to create and schedule a production order | NA | NA | Not Applicable
1130 | Manufacturing | Production Orders | Different types of changes that you can make to a production order | NA | NA | Not Applicable
1131 | Manufacturing | Production Orders | Shows how to use the Production Order batch job | NA | NA | Not Applicable
1133 | Manufacturing | Production Orders | Reviews the production order listings and reports | NA | NA | Not Applicable
1132 | Manufacturing | Production Orders - Additional Topics | Reservations, statistics, phantom BOMs, and manufacturing batch units of measure | NA | NA | Not Applicable
1162 | Manufacturing | Sales Order Interface and Order Planning | Describes and demonstrates all aspects of sales order planning | NA | NA | Not Applicable
1163 | Manufacturing | Sales Order Interface and Order Planning | Explains and demonstrates all aspects of order planning | NA | NA | Not Applicable
1098 | Manufacturing | Sample Company Structure | Explains how to set the working date | NA | NA | Not Applicable
1099 | Manufacturing | Sample Company Structure | Shows how to change the default profile to Production Planner | NA | NA | Not Applicable
1100 | Manufacturing | Sample Company Structure | Describes license information | NA | NA | Not Applicable
1243 | Manufacturing | Shop Loading | Describes the basic tools that are used to manage shop loading | NA | NA | Not Applicable
1244 | Manufacturing | Shop Loading | Explains how to manage shop loading by assuming infinite capacity | NA | NA | Not Applicable
1245 | Manufacturing | Shop Loading | Shows how to manage shop loading by using finite capacity | NA | NA | Not Applicable
1246 | Manufacturing | Shop Loading | Reviews the reports that are related to shop loading | NA | NA | Not Applicable
1247 | Manufacturing | Shop Loading | Describes the basic tools that are used to manage shop loading | NA | NA | Not Applicable
1248 | Manufacturing | Shop Loading | Explains how to manage shop loading by assuming infinite capacity | NA | NA | Not Applicable
1249 | Manufacturing | Shop Loading | Shows how to manage shop loading by using finite capacity | NA | NA | Not Applicable
1250 | Manufacturing | Shop Loading | Reviews the reports that are related to shop loading | NA | NA | Not Applicable
1217 | Manufacturing | Subcontracting | Describes how to set up a subcontractor and define subcontractor costs | NA | NA | Not Applicable
1218 | Manufacturing | Subcontracting | Shows how to assign a subcontractor work center to a routing operation | NA | NA | Not Applicable
1219 | Manufacturing | Subcontracting | Explains how to use the subcontracting worksheet to issue purchase orders to subcontractors | NA | NA | Not Applicable
1220 | Manufacturing | Subcontracting | Describes how to post subcontracting purchase orders | NA | NA | Not Applicable
1221 | Manufacturing | Subcontracting | Shows how to review subcontracting ledger entries | NA | NA | Not Applicable
1222 | Manufacturing | Subcontracting | Reviews the Subcontractor – Dispatch List report | NA | NA | Not Applicable
1154 | Manufacturing | System Setup | Describes all fields on the Manufacturing Setup page | NA | NA | Not Applicable
1155 | Manufacturing | System Setup | Explains all fields on the item card that affect manufacturing | NA | NA | Not Applicable
1156 | Manufacturing | System Setup | Reviews all fields on the stock keeping unit card that affect manufacturing | NA | NA | Not Applicable
1157 | Manufacturing | System Setup | Describe all fields on the Manufacturing Setup page | NA | NA | Not Applicable
1158 | Manufacturing | System Setup | Explain all fields on the item card that affect manufacturing | NA | NA | Not Applicable
1159 | Manufacturing | System Setup | Review all fields on the stock keeping unit card that affect manufacturing | NA | NA | Not Applicable
1097 | Overview | Sample Company Structure | Overview of the demo company, CRONUS International | NA | NA | Not Applicable
2009 | Indian Localization | Excise | Overview of Excise | NA | NA | Not Applicable
2010 | Indian Localization | Excise | Basic Setup | NA | NA | Not Applicable
2011 | Indian Localization | Excise | Excise Calculation in Purchase order or Purchase Return order for CENVAT Items | NA | NA | Not Applicable
2012 | Indian Localization | Excise | Excise Calculation in case of Capital Goods | NA | NA | Not Applicable
2013 | Indian Localization | Excise | Excise calculation in case of Imported goods in Purchase Invoice and Return Order | NA | NA | Not Applicable
2014 | Indian Localization | Excise | Excise Refund and Excise loading on Inventory | NA | NA | Not Applicable
2015 | Indian Localization | Excise | Output entries for finished goods | NA | NA | Not Applicable
2016 | Indian Localization | Excise | Excise calculation in Sales order or Sales invoice | NA | NA | Not Applicable
2017 | Indian Localization | Excise | Supplementary Invoice | NA | NA | Not Applicable
2018 | Indian Localization | Excise | Sales Cancellation | NA | NA | Not Applicable
2019 | Indian Localization | Excise | Excise Calculation in Case of Sale of Capital Goods | NA | NA | Not Applicable
2020 | Indian Localization | Excise | Excise Calculation in free sample given to Customer | NA | NA | Not Applicable
2021 | Indian Localization | Excise | Sale of Goods which are Returned | NA | NA | Not Applicable
2022 | Indian Localization | Excise | Depositing of PLA amount and creating of excise charge liability using the Tax Journal | NA | NA | Not Applicable
2023 | Indian Localization | Excise | Direct debit to PLA/RG in Sales Invoice | NA | NA | Not Applicable
2024 | Indian Localization | Excise | Excise Calculation in case Goods removed as such | NA | NA | Not Applicable
2025 | Indian Localization | Excise | Excise Calculation in Sales Invoice as per MRP Provision of the Excise Act | NA | NA | Not Applicable
2026 | Indian Localization | Excise | Transfer of Intermediate Goods from one Location to another Location | NA | NA | Not Applicable
2027 | Indian Localization | Excise | Transfer of Raw material from one Location to another Location | NA | NA | Not Applicable
2028 | Indian Localization | Excise | Calculation of Excise duty in case of Captive Consumption | NA | NA | Not Applicable
2029 | Indian Localization | Excise | Purchase Invoice with Service Tax Credit taken on Input service | NA | NA | Not Applicable
2030 | Indian Localization | Excise | Service tax Credit utilized for Excise payment | NA | NA | Not Applicable
2031 | Indian Localization | Excise | Excise Payment | NA | NA | Not Applicable
2032 | Indian Localization | Excise | Update ER 1 PLA Payments Type | NA | NA | Not Applicable
2033 | Indian Localization | Excise | Excise calculation in Purchase order or Purchase Return order for CENVAT Items in case of Trading | NA | NA | Not Applicable
2034 | Indian Localization | Excise | Excise calculation in Sales order or Sales Return order for CENVAT Items in case of Trading | NA | NA | Not Applicable
2035 | Indian Localization | Excise | Transfer of Goods from Trading location to Manufacturing Location | NA | NA | Not Applicable
2036 | Indian Localization | Excise | Transfer of goods from manufacturing location to trading location | NA | NA | Not Applicable
2037 | Indian Localization | Excise | Identifying the Principal Item | NA | NA | Not Applicable
2038 | Indian Localization | Excise | Opening Entry | NA | NA | Not Applicable
2039 | Indian Localization | Excise | Excise Reports | NA | NA | Not Applicable