## Slide 1: CPM & CCM Critical Path & Critical Chain
Hari P. Thapliyal
MCA, MBA (Operations), PGDFM, ZED Master Trainer, PMP, MCITP,
PMI-ACP, PRINCE2 Practitioner, SCT, CSM, MCT, SDC, SCM, SPOC, SAMC

## Slide 2: Disclaimer
We are not perfect being. Be are striving for the perfection.
We are first time trying to visualize the entire project in the form of critical path and critical chain. Therefore there are many opportunities for the improvements. Let’s start doing it and on the way if any opportunity is identified we can incorporate the inputs.
There are many ways of estimating efforts, duration, resources, cost and many ways to optimize the schedule some will be discussed in this workshop of 4 hours but many others will not be discussed.
Feel free to share your inputs today or anytime in future.

## Slide 3
This is not
  A Meeting
  A Lecture of a professor
  A Speech of some senior person
  One more training in your hectic routine
This is a workshop to reset our style of estimating, scheduling and making/taking commitment to/from our stakeholders (management, customer, vendors, team members). Here we are trying to understand how to make commitment where chances of failure can be minimized drastically.

## Slide 4: Agenda
What do you estimate?
Why do you estimate?
How do you estimate?
Range of Estimate & Basis of Estimate
Confidence Level of Estimate
What is critical in CPM?
What is CPM?
What is CCM?
What is buffer? What is float?
Contingency Reserve vs Management Reserve
Some diseases of project network path
Process of Scheduling

## Slide 5: How do you estimate?
Analogous Estimate
Parametric Estimate
3 Point Estimate
Bottom-up Estimate
Published Estimating Data

## Slide 6: Project Schedule Management

## Slide 7: Project Schedule Management
  Plan Schedule Management [PLANNING]
  Define Activities [PLANNING]
  Sequence Activities [PLANNING]
  Estimate Activity Resources [PLANNING]
  Estimate Activity Durations [PLANNING]
  Develop Schedule [PLANNING]
  Control Schedule [M&C]

## Slide 8: Plan Schedule Management
Establishing the policies, procedures and documentation for planning, developing, managing, executing, and controlling the project schedule

## Slide 9: Schedule Management Plan
It includes
  Scheduling tools to be used
  Level of accuracy
  Units of measure for each resource
  Organizational procedure links
  Process of updating the progress in schedule model
  Control thresholds
  Rules of performance measurement (baselines, %complete, fixed formula etc.)
  Define scheduling reporting format

## Slide 10: Define Activities
Identifying the specific actions to be performed to produce the project deliverables

## Slide 11: Define Activities
.1 Expert judgment
.2 Decomposition
.3 Rolling wave planning
.4 Meetings
.1 Project management plan
.2 EEFs
.3 OPAs
.1 Activity list
.2 Activity attributes
.3 Milestone list
PScM
PLAN

## Slide 12: Activity Attributes
Dependency
Location of performance
Type of dependency
Level of efforts (work contour)
Efforts required
Related Deadline
Related WBS account
Critical activity
Type of task (fixed duration, resources, work)
Resource & skills required
Duration
Lead & Lag

## Slide 13: Sequence Activities
Identifying and documenting relationships among the project activities.

## Slide 14: Sequence Activities
.1 Precedence diagramming method
.2 Dependency determination and integration
.3 Leads and lags
.4 PMIS
.1 Schedule management plan
.2 Project documents
  • Activity attributes
  • Activity list
  • Assumption log
  • Milestone list
.3 EEFs
.4 OPAs
.1 Project schedule network diagrams
.2 Project documents updates
  • Activity attributes
  • Activity list
  • Assumption log
  • Milestone list
PScM
PLAN

## Slide 15: Discussion
Sequence Previously activities of your project write FS, SF, FF, SS after the activities
FS- (Finish first to start the next) Documentation & Review, Design & Development
FF- (Finish next to finish the previous) Product Documentation & Product System Testing
SF- (Start next to finish the previous) Shift working environment, changing motor, shifting applications from servers A to B, shifting work environment from A to B.
SS- (Start next to start previous) Listening & Speaking, Start meeting & Start a topic to discuss, Listening & Making Notes, Requirement Gathering & Requirement Analysis

## Slide 16: Precedence Diagramming Method (PDM)
Also known as Activity on Nodes (AON)
Notes: 16

## Slide 17: Activity Type
Fixed Work
  Effort driven. Can change the duration by adding/ removing resources. E.g. To attempt 60 questions 60 min required. If you distributed between people duration can be altered.
Fixed Duration
  Time driven. Can not change the duration by adding/removing resources. E.g. Duration of the training does not depend upon # of participants. It is fixed.
Fixed Units
  Resource driven. Cannot change the duration by adding/removing resources. In fact altering number/type of resources make activity undoable. e.g Remove one person from review process where min 2 people are required.

## Slide 18: Time Constraints
ASAP
ALAP
SNET
SNLT
FNLT
FNET
MFO
MSO

## Slide 19: Network Development
Precedence Diagramming Method (AON)
Start
D
E
F
A
B
C
Finish

## Slide 20: Network Development
Precedence Diagramming Method (AOA)
Start
Finish
A
B
C
D
E
F

## Slide 21: Estimate Activity Durations
Approximating the number of work periods needed to complete individual activities with estimated resources.

## Slide 22: Estimate Activity Durations
.1 Expert judgment
.2 Analogous estimating
.3 Parametric estimating
.4 Three-point estimating
.5 Bottom-up estimating
.6 Data analysis
  • Alternatives analysis
  • Reserve analysis
.1• Schedule management plan
  • Scope baseline
.2 Project documents
  • Activity attributes
  • Activity list
  • Assumption log
  • Lessons learned register
  • Milestone list
  • Project team assignments
  • Resource breakdown structure
  • Resource calendars
  • Resource requirements
  • Risk register
.3 EEFs
.4 OPAs
.1 Duration estimates
.2 Basis of estimates
.3 Project documents updates
  • Activity attributes
  • Assumption log
  • Lessons learned register
PScM
PLAN

## Slide 23: PERT – Program Evaluation and Review Technique
Beta Distribution
  PERT Estimate tE= (Optimistic + 4 * Most Likely + Pessimistic)/6
Triangular Distribution
  tE= (Optimistic + Most Likely + Pessimistic)/3
Standard Deviation (using PERT) = (Pessimistic-Optimistic)/6
Variance (using PERT) = ( (Pessimistic - Optimistic)/6)2

## Slide 24: Develop Schedule
Analyzing activity sequences, durations, resource requirements and schedule constraints to create the project schedule.

## Slide 25: Develop Schedule
.1 Schedule network analysis
.2 Critical path method
.3 Resource optimization
.4 Data analysis
  • What-if scenario analysis
  • Simulation
.5 Leads and lags
.6 Schedule compression
.7 PMISs
.8 Agile release planning
.1• Schedule management plan
  • Scope baseline
.2 Project documents
  • Activity attributes
  • Activity list
  • Assumption log
  • Basis of estimates
  • Duration estimates
  • Lessons learned register
  • Milestone list
  • Project schedule network diagrams
  • Project team assignments
  • Resource calendars
  • Resource requirements
  • Risk register
.3 Agreements
.4 EEFs
.5 OPAs
.1 Schedule baseline
.2 Project schedule
.3 Schedule data
.4 Project calendars
.5 Change requests
.
PScM
PLAN

## Slide 26: Schedule Compression Techniques

## Slide 27: Resource Optimization techniques
Resource Levelling
  Ensure resource are not allocated more than their availability for the given project. Can lead to change in critical path.
Resource Smoothing
  Adjust activities in such a way that resources requirement do not exceed than defined limit. No change in critical path. Activities can be delayed within their float (free/total).

## Slide 28: Modeling Techniques
What if scenario analysis
  Assess the feasibility of project schedule under adverse conditions. Prepare a contingency plan to overcome the problems. Or prepare mitigation plan to reduce the impact of unexpected situations.
Simulation
  Calculate multiple project duration using tools like Monte Carlo Simulation. In this case use assumptions and distribution constructed using 3 Point estimates.

## Slide 29: Control Schedule
Monitoring the status of the project to update project progress and manage changes to the schedule baseline

## Slide 30: Control Schedule
.1 Data analysis
  • Earned value analysis
  • Iteration burndown chart
  • Performance reviews
  • Trend analysis
  • Variance analysis
  • What-if scenario analysis
.2 Critical path method
.3 Project management
  information system
.4 Resource optimization
.6 Leads and lags
.7 Schedule compression
.1• Schedule management plan
  • Schedule baseline
  • Scope baseline
  • Performance measurement baseline
.2 Project documents
  • Lessons learned register
  • Project calendars
  • Project schedule
  • Resource calendars
  • Schedule data
.3 Work performance data
.4 OPAs
.1 Work performance information
.2 Schedule forecasts
.3 Change requests
.4 Project management plan updates
  • Schedule management plan
  • Schedule baseline
  • Cost baseline
  • Performance measurement
  baseline
.5 Project documents updates
  • Assumption log
  • Basis of estimates
  • Lessons learned register
  • Project schedule
  • Resource calendars
  • Risk register
  • Schedule data
PScM
M&C

## Slide 31: Product Vision, Release, Iteration Planning

## Slide 32: Burndown Chart

## Slide 33: Critical Path Method (CPM)

## Slide 34: Critical Path Method (CPM)
Critical Path method is a planning technique that is used to demonstrate and view the chronological activities of a program or project, and identifies any possible timing risks and can be used to establish the least amount of time to complete a project.

## Slide 35: Critical Path
ES EF
ES EF
ES EF
LS LF
Start
Finish
Duration 7 Task A
LS LF
Duration 6 Task C
LS LF
Duration 3 Task G
LS LF
Duration 2 Task H
ES EF
LS LF
Duration 3 Task B
ES EF
LS LF
Duration 3 Task D
ES EF
LS LF
Duration 3 Task E
ES EF
LS LF
Duration 2 Task F
ES EF
ES EF
ES EF
ES EF

## Slide 36: Critical Path – Longest Path, Zero Float
LS LF
Start
Finish
0
0
7
7
ES EF
LS LF
7
7
13
13
ES EF
LS LF
13
13
16
16
ES EF
LS LF
16
16
18
18
ES EF
LS LF
Duration 3 Task B
0
7
10
3
ES EF
LS LF
Duration 3 Task D
3
10
13
6
ES EF
LS LF
Duration 3 Task E
6
13
16
9
ES EF
LS LF
Duration 2 Task F
3
11
13
5
ES EF
0
0
0
7
7
7
8
0
Duration 7 Task A
Duration 6 Task C
Duration 3 Task G
Duration 2 Task H

## Slide 37: Discussion/Excertise-16
Start
Finish
Duration 4 Task A
ES EF
LS LF
Duration 4 Task B
ES EF
LS LF
Duration 3 Task C
ES EF
LS LF
Duration 10 Task G
ES EF
LS LF
Duration 5 Task E
ES EF
LS LF
Duration 5 Task F
ES EF
LS LF
Duration 7 Task D
ES EF
LS LF
5 Minutes

## Slide 38: Network Exercise - solution
Start
Finish
Duration 4 Task A
0
0
4
4
ES EF
LS LF
Duration 4 Task B
4
7
11
8
ES EF
LS LF
Duration 3 Task C
11
11
14
14
ES EF
LS LF
Duration 10 Task G
14
14
24
24
ES EF
LS LF
Duration 5 Task E
0
4
9
5
ES EF
LS LF
Duration 5 Task F
5
9
14
10
ES EF
LS LF
Duration 7 Task D
4
4
11
11
ES EF
LS LF
Critical Path : ADCG
Notes: Free float: An activity can be delayed without impacting the start of next activity
Total float: As many alternative path that many total float. Total float is available on non critical path. Activities can be delayed without delaying project
Free float on critical path activities is Zero

## Slide 39: Facts/Tips for Critical Path
Total Float is the amount of time the task can delayed without delaying the project finish date.
Free float is the amount of time a task can slip without delaying the early start of any task that immediately follows it
It is possible that a zero float activity may not be on critical path
Longest path & shortest time possible to complete the project
A project can multiple critical paths
Difference between late and early is float
Positive float (the activity can wait to start even after previous activity finishes)
Negative float (the activity must start before previous finishes)
Zero float (the activity must immediately start after the finish of previous one)
Crashing activities to short the overall duration of project
Fast-tracking activities to short the overall duration of project
Be cautious that non-critical activity is not being delayed than the allowed free float
Take care of sub-critical path or non-critical path
Manage critical path resources very closely
Do not overload critical path activity resources
Avoid multitasking for resources working on critical path activities

## Slide 40: Benefits of PERT/CPM
It Provides following information
Expected Project completion time
Probability of completion before a specified date
The critical path activities that directly impact the completion time
The activities that have slack time and that can lend resources to critical path activities
Activity start and end dates

## Slide 41: Critical Chain Method (CCM)

## Slide 42: Background
Eliyahu Goldratt proposed CCM
This is developed based on the TOC framework

## Slide 43: Why CCM is needed?
You have CPM available why CCM is needed?
  You can manage the delays on non-critical path using buffers/floats. BUT
  How do you manage the delays on critical path?

## Slide 44: Principles Behind CCM
Delays accumulate; gains don't advantage
  Sequential Steps: Resources are not available to start early
  Parallel Steps: Three activity each takes 5 days time start in parallel. If one activity takes 10 days and other finish on time, early activities will not be able to take advantage.
  If above sequential and parallel activities are dependent then affect is magnified
Other Time Wasters
  Multitasking
  Student Syndrome
  Parkinson's Law

## Slide 45: Critical Chain Method
CPM is developed using the believe that book as many resource as in advance and they will be available when need because it has been promised
CCM says that if a resource is over booked on any activity he will not be available to work on that activity therefore level the resource on the project activities. Thus resource constrained critical path is critical chain.
CPM is about hoarding, greed. Therefore over-estimation and project management laws like Parkinson law, Murphy law, Student syndrome applies here.
CCM is about believe and assumption that it will available when needed but we need to have proper alert system in place.

## Slide 46: CCM Concepts
Resource Buffer: Notify dependent task resources that when I will finish my work on regularly basis and final notification 1-2 days before. So that resource is available to start the work.
Safety or project buffer should be added at the end of critical-chain as non-activity buffer
Feeding buffer: Add buffer where chain of non-critical activity joins the critical path. This way non critical task can be avoided being critical

## Slide 47: How to estimate in CCM
Resource will give t80, t90 estimate.
Half them to get t50 estimate.
Do not put end date to task and let people finish the task as early as possible.
No penalty for finish beyond t50.
Project Buffer should be 50% of the buffer removed from activity.

## Slide 48: Buffer Types

## Slide 49: Where to put Buffer

## Slide 50: How to manage CCM
If activity finishes late time is borrowed from project buffer.
If activity finishes early, gained time is added to project buffer

## Slide 51: Microsoft Project Demo

## Slide 52
Am I missing anything?
Do you have any question?

## Slide 53: Next Program
Project Risk Management
Who should Participate: All who face risk of failure. I think HOD, PM, PMT
Time : 13-Dec, Tuesday 10.00am – 12am.
Location: Admin Block Training Room

## Slide 54
Hari P Thapliyal,
PMO Architect & Project Management Trainer & Coach
Vedavit Project Solutions
Reach Me:
hari.prasad@vedavit-ps.com
Skype: hari.thapliyal, YM: hari_thapliyal, Twitter: harithapliyal
Mobile: +91 9535999336
Profile: http://in.linkedin.com/in/harithapliyal
Blog: http://pmlogy.com/