## Slide 1: KANBAN
Hari P. Thapliyal
MCA, MBA (Operations), PGDFM, ZED Master Trainer, PMP, MCITP,
PMI-ACP, PRINCE2 Practitioner, SCT, CSM, MCT, SDC, SCM, SPOC, SAMC

## Slide 2: Disclaimer
We are not perfect being. Be are striving for the perfection.
We are trying to set a Kanban board first time at the project level. Therefore there are opportunities of improvements. Let’s start doing it and on the way if any opportunity is identified we can incorporate the inputs.
There are many ways of designing Kanban board we have chosen one.
Feel free to share inputs to design a best project Kanban board. Today or anytime in future.

## Slide 3: Agenda
What is Kanban?
Why Kanban?
How to plan activities?
How to update Kanban?
Questions & Answers (QA) session. -15 min

## Slide 4: What is Kanban
Literally signboard or billboard in Chinese and Japanese
Early adoption in Toyota Production
Earlier it was managed manually
Nowadays it is Automatic
Your inputs…………..

## Slide 5: Why Kanban
Commitment Known to everybody
Dependency is visible to everybody
Availability and workload of department/people on any particular day is visible
Can visualize the bottleneck
Can prioritize the work everyday morning
Can plan alternative resource
Assign impediment resolution owner & the deadline
Work on high impact/high value work first
Anything else??????

## Slide 6: How to plan activities
Use your baselined plan. Baselined plan is available with Project Manager
Project Management Team (PMT) creates detail plan for each delivery (if it is not baselined)
Project Manager inserts detail plan in the high level baseline plan
PMT: creates Task Card and put in the task column on the Kanban board.
Task cards need to be created for the week.
You can create these cards anytime before the next week starts
Ideally tasks in the task card should be taken from baseline plan

## Slide 7: How Task Card Looks Like?
These are colorful cards. Placed on the Kanban board
Use only that color which is assigned for your department to create a task card
One Task card should have one task only
Task card should have Owner, Hours, Due Date & Task Name on it.
Card on task should be assignable to one person
Duration of any task card should be ideally 1-5 day
Owner | Hours | Due Date Revised Finish
Task Name/Description |  | 

## Slide 8: How to update Kanban?
Update the Kanban on daily basis. As many times as possible. Do not wait for 5:30 pm.
If new task is identified please free to create that on behalf of your department
When updating Kanban board also check work of the day and week of other department
Kanban board must be up to date before daily standup meeting starts
Kanban board must be updated after standup meeting (if any change happen during the standup)

## Slide 9: Where is our Kanban Board?
Kanban Board is in the PMO (Project Management Office) Area.

## Slide 10
Am I missing anything?
Do you have any question?

## Slide 11: Next Program
What is daily standup meant for & How to do?
Time : 30-Nov (Tomorrow) 2pm.
Location: This Room

## Slide 12
Hari P Thapliyal,
PMO Architect & Project Management Trainer & Coach
Vedavit Project Solutions
Reach Me:
hari.prasad@vedavit-ps.com
Skype: hari.thapliyal, YM: hari_thapliyal, Twitter: harithapliyal
Mobile: +91 9535999336
Profile: http://in.linkedin.com/in/harithapliyal
Blog: http://pmlogy.com/