## RiskDB
Source | Risk Name | Probability | Impact | Avoidance Plan | Mitigation Plan | Transfernace Plan
Material | Poor quality material may be received
Material Tech Specs may not match at the delivery time
There may be Material Shortage
Material may be received late
Material may not be available in the market
Procurement | There may be delay in Custom office
There may be accident during transportation
There may shortfall of material quantity
Wrong material may be ordered
Mateial price may increase
Material grade not commercially available
Drawing may change aferr raw material procured
Material may not be delivered as per drawing
Production | Fabrication may be of poor quality
There may not be sufficient workspace to continue production
Procured material may not serve the purpose
Drawing | Drawing may change during fabrication
There may be a dimension error
Design | There may be over design of equipment
Technical details may be missed in drawing
Designed submitted late
Finance | Double payment may be done to vendor
LC may not open on time
Bank guarantee may not be issued on time
Estimation | Duration Estimates may be wrong
Resource Estimates may be wrong
Calculation error may be in estimation
Process | Process may change during execution
Management | Decision not made on time
Communication | Stakeholders not informed on time
Information not fully available
Communication not happened to right person
Communication happened to wrong person
Environment | There may be rain or cyclone
Human | There may be mistake due to multitasking
Person is not available due to sickness
Incompetent resource may be assigned to a work
Critical machine may break down
Infra | File server may be down during work
Mail server may be down during work
Communication network may be down for communication
There may be man-power shortage
Requirement | Client may change requirement