## Sheet1
Project Schedule Review Checklist
| Template Version | v0.1
Project Manager Name
Reviewer Name
Project Code
Review Date
|  | Answer | Remarks
Project Level
1 | Team_Stand_Calendar is set at project level. | Not Checked
2 | Start date of project is set correctly. | Not Checked
3 | Project summary task turned on and check project name is correct. | Not Checked
In Project Organizer
1 | No extra/local fields for Task & Resource | Not Checked
2 | No local table | Not Checked
3 | No local view | Not Checked
4 | No local filter | Not Checked
5 | Only these Calendar Team_Stand_Calendar, Team_2Shift_Calendar, TEAM_Night_Calendar | Not Checked
| Resource Level | Not Checked
1 | No local resource in the project schedule | Not Checked
2 | Name of resources should be same as in global checklist | Not Checked
Task level
1 | Check calendar of the tasks (If production task then 2shift calendar else stand calendar) | Not Checked
2 | Check task type (it should be fixed duration mostly) | Not Checked
3 | Project should have marked some activities as milestone (Ticked) | Not Checked
4 | Check dependency are correctly defined (FS, SS, FF, SF should be correctly set) | Not Checked
5 | No dependency should be assigned to a summary task. | Not Checked
6 | Summary task should not have any resources assigned. | Not Checked
7 | Every activity should have resource. | Not Checked
8 | Check number of resources required for an activity correctly assigned. | Not Checked
9 | Lead & Lag is wait / overlap time and it is not estimate of duration. Ensure this is NOT part of the duration/work estimate | Not Checked
10 | Lead & Lag time is correctly set to an activity. | Not Checked
11 | Duration of every activities are correctly estimated and assigned. Use the benckmark estimate provided by Production. | Not Checked
12 | Unit number of resources assigned to a task multiplied by the duration should be tallied to the work. | Not Checked
13 | If required estimate the "work" column again. | Not Checked
14 | No task should have constraint other than ASAP (As Soon As Possible), unless there is some genuine reason | Not Checked
15 | No task should have estimated work / duration with question mark (?), unless there is some reason. | Not Checked
16 | No manually entered date in Start, Finish date field of any task | Not Checked
There are 10 views in Microsoft Project. Ensure the data required for project is complete and correctly entered against the column shown in those views
1 | TEAM-BudgetInfo-View | Not Checked
2 | TEAM-Despatch-View | Not Checked
3 | TEAM-Finance-View | Not Checked
4 | TEAM-GenInfo-View | Not Checked
5 | TEAM-ProposedSchedule-Analysis-View | Not Checked
6 | TEAM-Purchase-Dept-View | Not Checked
7 | TEAM-Resource-View | Not Checked
8 | TEAM-Work-Tracking-View | Not Checked
9 | TEAM-Work-Tracking-View-2 | Not Checked
10 | TEAM-Temp | Not Checked