## Prabhakar-WBS
Departmnet | Work | Work 1
Project work | Specs Sheet of equipment
Purchase work | Enquiry floating to vendors
Purchase work | Recive Quoations from vendor
Project/Purchase | Vendor finalization
Purchase work | Placing Order
Project work | Receive Equipment Drawing (R0)
Project work | Send corrected drawing to vendors
Project work | Receive Equipment Drawing (R1) |  | Bottelneck
Project work | Send corrected drawing to vendors (if required)
Project work | Receive Equipment Drawing (R2)
Project work | Freeze the drawings
Project work | Vendor Work Starts
Vendor work |  | Purchase Raw material
Vendor work |  | Material inspection by third party
Vendor work |  | Fabrication starts
Vendor work |  | Final inspection by third party
Vendor work |  | Despatch equipment
Store Dept | Store owner receives equpment
Account Dept | Create GRN
Store Dept | Issue equipment for plan utilization
Project work | Erection of equipment
Project work | Handover the equipment to process