## Slide 1
Project Management Training
Tagros Chemicals
Hari Prasad Thapliyal
PMP, PMI-ACP, CSM, MBA, MCA, PGDOM, PGDFM, CIC, PRINCE2-Practitioner
PMO Architect & Project Management Evangelist
Vedavit Project Solutions
Cell: +91-95-3599-9336
Email: hari.Prasad@vedavit-ps.com
Website: www.pmlogy.com
'PMI-ACP', 'PMI', PMP, and 'ACP' are a registered marks of the Project Management Institute, Inc.

## Slide 2: General

## Slide 3: General Understanding
Project, Program, Portfolio and Interdependencies
Project Left Cycle: Phases, Milestones, Deliverables
Project Boundary
Project Constraints
Project Management Office (PMO)
Project Management Methodologies
Organization Process Assets
Enterprise Environmental Factors
Knowledge Area & Process Groups
Process Groups & Level of Activities
Organization Types & Project Success

## Slide 4: General Understanding Cont…
Enterprise Environmental Factors
Organization Process Assets
Project Success Criteria
Stakeholders Register
Project Charter
Cost of Change & Degree of Risk
Typical Costing and Staffing Across PLC
Project Manager: Skills, R&R, Authority

## Slide 5: Project Management Planning Documents
Integration Planning
Configuration Management Plan
Scope Management Plan
Requirement Management Plan
Schedule Management Plan
Cost Management Plan
Quality Management Plan
Process Improvement Plan
Communication Management Plan
Human Resource Management Plan
Risk Management Plan
Procurement Management Plan
Stakeholder Management Plan
Scope Baseline
Cost Baseline
Schedule Baseline

## Slide 6: Project Documents
Project Charter
Business Case
Agreements
Stakeholder Register
WBS
Estimation (Duration, Resources)
Milestones
Project Schedule
Funding Requirement
Quality Checklists
Risk Register
Requirement Traceability Matrix
Project RACI Chart

## Slide 7: Logs/ Register
Change Log
Lessons Log
Issue Log
Action Register

## Slide 8: Project Reports
Forecast Reports
Progress Reports
Status Report

## Slide 9: Procurement Documents
Procurement SOW
Procurement Plan
Procurement Source Selection Criteria
Make and Buy Decision Document
Quotations
Agreements
Sellers Proposals

## Slide 10: Planning

## Slide 11: Estimation Techniques
Analogous Estimation
Parametric Estimation
3 Point Estimation (PERT Estimation)
Wide band Delphi Estimation
Bottom up Estimation
Published Estimating Data

## Slide 12: Things to Take Care to Baselines
Schedule and cost should be as per the project charter
If not then analyze cost, duration, dependency, lead, lag, resources, determine project critical path, Free Float and Total float of activities, add resources to critical activities, think about outsourcing, check risk, know the buffer to make cost/schedule close to numbers in project charter
Resource should be leveled and they should not be overloaded
Productivity cannot be 100%, create and use project calendar, do not force resource in planning but try to negotiate
Schedule, cost, scope, quality expectations should be understood by all stakeholders and negotiated
Buffers should be managed separately
Contingency reserve (buffer) should part of cost baseline
Check you funding requirements and negotiate those
Know your management reserve. It is not part of cost baseline.

## Slide 13: Organization Process Assets (OPA)
Create OPA by
  regular introspections with the team
  Refining previous projects templates/checklist etc.
  Adopting industry best practices
Dedicate efforts towards making people aware about existing OPA
Use OPA whenever you are starting a new project
Refer to OPA regularly whenever you need new insight
Using OPA is better than guessing

## Slide 14: Tools/Techniques for Collecting Requirements
Interviews
Focus Groups
Facilitated Workshops
Group Creativity Technique
Group Decision Making Techniques
Questionnaires and Surveys
Observations
Prototypes
Benchmarking
Context diagrams
Document Analysis

## Slide 15: Steps of Project Scheduling
Define activities
Sequence activities as Activity Attributes
Estimate Activity Resources
Estimate Activity Duration
Develop Schedule
Baseline Schedule

## Slide 16: Know Activity Attributes - Impacts Schedule/Cost
  Name,
  Location,
  Department,
  Dependency,
  Activity Type,
  Constraints,
  Tracking Method,
  WBS Code,
  Cost,
  Duration,
  Resource Requirement,
  % Complete

## Slide 17: Estimate Activity Duration
Consider risk around activities
Establish your project calendar (work timings, days in a week, off days of week, holidays, working hours everyday)
Consider availability of resources. Sometimes they are available but not 100%.
Consider productivity of resources. It is never 100%.
Know you are estimating ideal duration, not the actual duration, not the effort
Understand that every activity’s duration cannot be crashed by adding resources.
PERT method help you in knowing confidence of your schedule

## Slide 18: Facts/Tips for Critical Path
Total Float is the amount of time the task can delayed without delaying the project finish date.
Free float is the amount of time a task can slip without delaying the early start of any task that immediately follows it
It is possible that a zero float activity may not be on critical path
Longest path & shortest time possible to complete the project
A project can multiple critical paths
Difference between late and early is float
Positive float (the activity can wait to start even after previous activity finishes)
Negative float (the activity must start before previous finishes)
Zero float (the activity must immediately start after the finish of previous one)
Crashing activities to short the overall duration of project
Fast-tracking activities to short the overall duration of project
Be cautious that non-critical activity is not being delayed than the allowed free float
Take care of sub-critical path or non-critical path
Manage critical path resources very closely
Do not overload critical path activity resources
Avoid multitasking for resources working on critical path activities

## Slide 19: Cost Planning
Estimate Cost of Each Activities (EC)
Document assumptions of estimation
Consider risks while estimating cost
Develop project funding requirements (DB)
Consider cash flow and payout while developing funding requirements
Baseline Project Cost

## Slide 20: Project Cost Estimation Ranges
Cost estimation may include only indirect Cost along with direct Costs
Class Name | % | Range
Definitive | - 5 -> +5% | 10%
Capital Cost | -15 -> +10% | 25%
Appropriation | -25 -> +15% | 40%
Budget Estimates | -10 -> +25% | 35%
Feasibility | -35 -> +25% | 60%
Order of Magnitude | -50 -> +50% | 100%

## Slide 21: Quality Definitions from Quality Gurus
Deming says “Quality is Predictability”
Crosby says “Conformance to requirements”
Juran says “Fitness for use”
Feigenbaum says “Customer’s opinion”
Conformance to “Valid Requirements“.
Best value for money.

## Slide 22: Project Quality Planning
Quality is related to the satisfaction of stakeholders.
Generally quality is implicit requirements therefore spend time to understand quality expectation of all relevant stakeholders and ensure how will you deliver those
Develop Quality Checklist
Understand Cost of Quality
Identify Quality Metrics to measure, improve project/product quality
Develop Quality Assurance Plan & Process
Develop Quality Management Plan & Process (QMP)

## Slide 23: Project Human Resource Planning
Establish Project Calendar
Create Role & Responsibilities based on skills required to perform project activities
Develop RACI Chart
Establish/Refine Job Description
Establish Project Organization Chart
Establish Performance Appraisal Systems
Establish Conflict Management System
Establish Staffing Management Plan
Establish Team Building Plan
Identify type of trainings required to ensure people understand processes, they understand temperaments and work style of fellow team members, expectations from them. Establish Training Need and Training Plan
Establish Hiring Systems

## Slide 24: Project Communication Management
Understand communication need of different stakeholders
Group stakeholders based on their communication need
Understand number of communication channels involved
Identify possible communication technologies and their benefits and cost of setup and operation
Define Roles & Responsibilities for managing communication
Make decision about communication technologies to be used
Establish how will you ensure effectiveness of communication
Establish communication metrics
Put all above information in Communication Management Plan (CoMP)

## Slide 25: Risk Management Planning
Identify who is responsible for risk management
Establish tools/template to capture risk
R&R for Risk Assessment, Audit
Risk appetite of stakeholders
Develop impact table
Develop probability and impact table
Methods of risk categorization

## Slide 26: Risk Management
Risk Identification is everybody’s responsibility. We should be conscious about what we are doing and what is the impact of something unexpected happening
Project Manager can use contingency reserve (CR) without approval
For using management reserve (MR) management approval is required
CR is for Known-Unknown Risks
MR is for Unknown-Unknown Risks
Use CR for the purpose it is has been kept. Do not use it for other work

## Slide 27: 4 Ways to response to Risks
Negative Risk | Positive Risk
Avoid | Exploit
Mitigate | Enhance
Transfer | Share
Accept | Accept

## Slide 28: Steps of Risk Management
Identify Risks
Assess Probability of Risks Identified
Assess Impact of Risks Identified
Assess Urgency of Risks Identified
Establish which risk must have response plan
Assign Risk Owner
Establish Risk Response Plan for High Exposure Risk
Assign Risk Actionee
Categorize Risks
Establish contingency funds

## Slide 29: Project Execution

## Slide 30: Project Execution
Direct and Manage Project Work (DMPW)
Perform Quality Assurance (PQA)
Acquire Project Team (APT)
Develop Project Team (DPT)
Manage Project Team (MPT)
Manage Communications (MC)
Conduct Procurement (CoP)
Manage Stakeholder Engagement (MSE)

## Slide 31: Direct and Manage Project Work
Execute Project as per the Baselined Project Management Plan
Produce only those deliverables which are valued by customer
For any deviation use only “Approved” Change Requests
If work is not possible as per the baselined plan then team should make Project Manager aware about it. This is change request.
As a practice project manager should not make decision about deviation from baselined plan immediately.
Change request should be evaluated based on the urgency and then decision is either made by project change control board or Project Manager depending on impact and urgency.
Project work progress data, any issue, impediments should be captured on daily basis. Automate this step as much possible so that your get correct data
Coordinate project related dependencies between departments, agencies, consultants, experts, management and other stakeholders on daily basis.

## Slide 32: Perform Quality Assurance
A mechanism to determine that everybody including the project manager is following processes
Deviation from the plan is acceptable but deviation from the process is compliance issue and taken very seriously by management, regulators, customer etc.
Project manager should perform quality assurance for his team
External to project (Auditor) who has knowledge about audit process and project processes should perform regular audit. Project Manager should plan for this in his plan. A surprise audit asked by management, regulator or customer is also possible.
Auditors should identify area of improvement, provide recommendation, appreciate best practices, take best practices at organization level. (Change Request)
Auditors should make stakeholders aware about non-compliance
An auditor must use project’s project plan, project reports, quality report to perform the audit

## Slide 33: Acquire Project Team
Hire right people on right time and assign them the work as per their capability
Negotiate role, responsibilities, work time, position, compensation, reporting relationship, joining time, location of work and agree before you confirm any person in the project team
Interview every person you are taking on the project based on the level of expertise and skills expected for the project work

## Slide 34: Develop Project Team
In a project chemistry is more important than physics
Project is delivered by team not by individuals
Conduct trainings
Conduct team building activities
Define ground rules as a team
Develop binding between virtual teams
Evaluate continually that how team is maturing

## Slide 35: Manage Project Team
Do not monitor and control people. Be objective and manage your team using project objectives.
Appraise and provide feedback on regular basis
Identify improvement need of individuals and team (Change Request)
Maintain issue log of team conflicts and keep resolving it based of priority
Assign only those people for conflict management who have competency
Help individuals in owning the responsibility of conflict resolution

## Slide 36: Sources of conflict
Schedules
Project Priorities
Technical Issues
Personality Conflict
Cost
Scarce resources
Personal work styles
Administrative Procedures

## Slide 37: Characteristics of conflict
Conflict is team issue
Conflict is natural and forces a search for alternatives
Openness resolves conflict
Conflict resolution should focus on issues, not personalities
Conflict resolution should focus on the present not on the past

## Slide 38: Key to Successful Team Management
Listens to subordinates to diagnose or solve problems
Sets goals and develops short- and long- range action plans
Gives directions about who is to do which tasks to what standards
Provides feedback on task performance
Rewards
Develops subordinates
Understanding that team is an Integral Unit of Organization
A team mission, objective, goals, strategy and role definition
A leader and an organizational support system
Managers responsive to needs of team members
Encourage participation and effective communication
Foster an atmosphere of trust among team members
Provide feedback effectively
A collective culture and style
Motivate team members with challenges & rewards

## Slide 39: Project Governance

## Slide 40: Project Governance
Monitor & Control Project Work (MCPW)
Perform Integrated Change Control (PICC)
Validate Scope (VC)
Control Scope (CS)
Control Schedule (CSc)
Control Cost (CC)
Control Quality (CQ)
Control Communications (CCom)
Control Risks (CR)
Control Procurements (CnP)
Control Stakeholders Engagements (CSE)

## Slide 41: Earned Value Management
Budget at Completion
Planned Value
Actual Cost
Earned Value
Cost Variance
Cost Performance Index
Schedule Variance
Schedule Performance Index
Estimate to Complete
Estimate at Completion
Variance at Completion

## Slide 42: Project Closure

## Slide 43: Close Project or Phase
Must be performed at the end of every phase or at project closure
This is the final step and formal step. No work is produced for the customer here, no testing no negotiation.
Prepare a handover report
Handover the final product to customer
Ensure all the agreement clauses are fulfilled. Close the contract.
Lessons learned exercise should be performed with team and lessons learned should be documented
Team should be informed and disbanded
Stakeholders should be communicated
Department should be communicated

## Slide 44: Close Procurements
Procurement may be closed
  Either all the items has been delivered or
  Product/Services not required
  Product/Services are not of good quality
Audit all procurements
Settle payments with supplier
Conduct lessons learned exercise for each procurement, document lessons learned and share with organization
Inform to your accounting and legal departments