## IP
Project Management Methodology
Processes Tailored

## ConMP
Config. Item | PMP Doc | CI | Naming | Permission | Dir Struc | Storage
Yes |  | Drawing | DW-Deparment-v-0.1
Yes |  | Specifications
Yes |  | PO
Yes |  | Govt Apprval
Yes |  | Comparision
Yes |  | BOQ
Yes | Yes | Indent
No |  | Reports
No |  | MoM
No |  | Action Register
No |  | Change Logs
No |  | Issue Logs
No |  | Bills
No |  | Challans
No |  | GRN

## ScopeMP
Requirement Collection Methods
Requirement Validation Process
Requirement Control Process
Scope Change Management Process
Requirment Related Metrics & Control Limits

## ReqMP
RTM Structure

## ComMP
Stakeholders
Reproting need | PM
Report Temp | PC | Report | Periodicity | Prep Resp | Sending/Sharing Reposn | To whom
How report will be shared | PM | Report 1
Reporting Metrics |  | Report 2
Report 3
Report 4
Report 5
Report 6

## RiskMP
Identify Source of Risk | Team
Prepare a risk register | PM | 2015-03-02 |  | Impact Table
Risk Identification | Team | Regular |  |  | 0.05 | 0.1 | 0.2 | 0.4 | 0.8
Risk prioritization | RM | Regular |  |  | VL | L | M | H | VH
Risk assignment | PM | Regular |  | Cost | <2% | <=2% < 4% | >=4 <8% | >8% < 10% | >10%
Risk Reponse Plan | RiskOwner | Regular |  | Schedule | 1 day | 2 day | 5 day | 10 day | >10 day
Risk Reporting | RM | Weekly |  | Quality
Develop Impact Matrix | PM | 2015-03-02 |  | Scope
Develop PI Matrix | PM & Stakeholder | 2015-03-05
Probablity & Impact Matrix for Schedule
|  |  | Impact | 0.9 | 0.09 | 0.18 | 0.27 | 0.36 | 0.45 | 0.54 | 0.63 | 0.72 | 0.81
|  |  |  | 0.8 | 0.08 | 0.16 | 0.24 | 0.32 | 0.4 | 0.48 | 0.56 | 0.64 | 0.72
|  |  |  | 0.7 | 0.07 | 0.14 | 0.21 | 0.28 | 0.35 | 0.42 | 0.49 | 0.56 | 0.63
|  |  |  | 0.6 | 0.06 | 0.12 | 0.18 | 0.24 | 0.3 | 0.36 | 0.42 | 0.48 | 0.54
|  |  |  | 0.5 | 0.05 | 0.1 | 0.15 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4 | 0.45
|  |  |  | 0.4 | 0.04 | 0.08 | 0.12 | 0.16 | 0.2 | 0.24 | 0.28 | 0.32 | 0.36
|  |  |  | 0.3 | 0.03 | 0.06 | 0.09 | 0.12 | 0.15 | 0.18 | 0.21 | 0.24 | 0.27
|  |  |  | 0.2 | 0.02 | 0.04 | 0.06 | 0.08 | 0.1 | 0.12 | 0.14 | 0.16 | 0.18
|  |  |  | 0.1 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09
[5 empty] | 0.1 | 0.2 | 0.3 | 0.4 | 0.5 | 0.6 | 0.7 | 0.8 | 0.9
Probability