## Lists
EEF Sources
Political
Environmental
Social
Technology
Legal
Government
Project Management Practics
Org Business Process

## Master
# | Document Name
1 | Project Charter
2 | Stakeholder Register
3 | Enterprise Environmental Factors
4 | Organization Process Assets
5 | WBS
6 | Estimation (Duration, Resources)
7 | Milestones
8 | Project Schedule
9 | Funding Requirement
10 | Quality Checklists
11 | Risk Register
12 | Requirement Tracebility Matrix
13 | Project RACI Chart
14 | Overall Project Status
25 | Lessons Learned

## 1
Project Charter
Objective | To produce 40 ton / sulfo. To launch a new molecule for which currently there are limited manufacturer and wide market.
High level requirments | 100 sq meter plant. Storage facility for 15 days inventory 20 equipment Utility faciltiy Misc Facility
High level risk | Govt may restrict project progress Monsoon may affect contrstruction Fund may not be available Culture may affect productivy Surplus material may not be avaiable Manpower/skills may not be available Comptetion can come up in the market before us
High level milestones | Drawing approval (1 months) Statutory approval (2 months) Civil work / P&ID completion / equpmnt layout (10 months) Material procurment & receipt (11 months) Erection commissioning (12 months)
Initial assumptions | Satutotry approvla will happen on time Receiving all metrials of time Surplus fund flow is available
High level budget | 50 cr +/- 5%
High level timeline | 1 year +/-2 weeks
Approval required | Environment clearnce - MOEF / GPCB EB Sanction - SEGEB Bioloer Approla - IB
Project Manager | E Kannapran
Project Sponsor | AJ

## 2
Stakeholder Register
General | [8 empty] | Contact |  |  | Management
ID | Name | I/E | Role/Title | Organization | Department | When | Internal/External | Manager | Phone | Email-id | City | Expectations | Influence | Interest | Current Position | Needed Position | Personal Attributes | Engagement Plan | Reporting Need
| Director | E | Director |  | MOEF | [7 empty] | 10 | 1 |  |  | Tough IAS officor, Biding all rules | Parties, Gifts, MS | Template Name1
| AJ | I | Director |  | Management | [7 empty] | 10 | 10 |  |  | Quick decision maker, | Provide minimum document and interested information.
Note on G3: (Start, Phase1, Phase2, Phase3, Throughout)

## 3
Enterprise Environmental Factors
Political | Name
Environmental | Monsoon
Environmental | Skilled manpower
Political | local politics
Environmental | road and building avialablity
Social | local festivals
Government | govt evironmental policies
Environmental | power supplies
Environmental | market demant change

## 4
Organizational Process Assets
S.No | Repository Owner | Dept | Type | Doc Group | Doc Name | Temp-ID | Lifecycle Phase | Responsibility | Project Name
1 |  | Tech |  | CAPEX |  |  | Intiation
2 |  | Tech |  |  | Capacity working | TECH-CAP | Intiation | Process Eng
3 |  | Tech |  |  | Budget | TECH-BUD | Intiation | Process Eng
4 |  | Tech |  |  | Schedule | TECH-SCH | Intiation | Process Eng
5 |  | Tech |  |  | Fund flow | TECH-FF | Intiation | PM
6 |  | Tech |  | Specification Sheets |  |  | Planning
7 |  | Tech |  |  | Individual Equip Specs | TECH-IES | Planning | PE
8 |  | Tech |  | Govt Approval Req |  |  | Planning
9 |  | Tech |  |  | Assessments | TECH-AS | Planning | PM
10 |  | Tech |  |  | Necessary Format Prep | TECH-NFP | Planning | PE
11 |  | Tech |  | Drawings |  |  | Planning
12 |  | Tech |  |  | P&I Diagram |  | Planning | Process Eng
13 |  | Tech |  |  | Equipment Layout |  | Planning | PM
14 |  | Tech |  |  | Piping Layout |  | Planning | Project Eng
15 |  | Tech |  |  | E&I Layout |  | Planning | Project Eng
16 |  | Tech |  |  | Equipment Drawing Review |  | Execution | Project Eng
17 |  | Tech |  |  | Equipment Drawing Approval |  | Execution | PM
18 |  | Tech |  |  | Civil Drawing |  | Execution | PM
19 |  | Tech
20 |  | Tech |  | Project & Activity Diagram |  |  | Planning
21 |  | Tech |  |  | Macro Scheduling |  | Planning | PM
22 |  | Tech |  |  | Critical Items Micro Schedule |  | Execution | PM
23 |  | Tech
24 |  | Tech |  | Project Report |  |  | Execution
25 |  | Tech |  |  | Progress Report |  | Execution | Project Eng
26 |  | Tech |  |  | Budget vs Actual Report |  | Execution | Project Eng
27 |  | Tech |  |  | Daily Project Reviews |  | Execution | Project Eng
28 |  | Tech
29 |  | Tech |  | Commissioning Report
30 |  | Tech |  |  | Test Certificate from Vendor |  | End | Vendor Eng
31 |  | Tech |  |  | Trial Run Report |  | End | Project Eng
32 |  | Tech |  | Misc Docs
33 |  | Tech |  |  | Completion Report |  | End | Project Eng
34 |  | Purc |  |  | Purchase Order Register |  | Weekly | Purchase Officer
35 |  | Purc |  |  | Purchase Order |  | Weekly | Purchase Officer
36 |  | Purc |  |  | Order Ack |  | Weekly | Purchase Officer
37 |  | Purc |  |  | Despatch Shipment Detail Format |  | Weekly | Purchase Officer
38 |  | Purc |  |  | Third Party Inspection Call/Report |  | Weekly | Purchase Officer
39 |  | Purc |  |  | Pending Order Report |  | Weekly | Purchase Officer
40 |  | Purc |  |  | Pending Indent Report |  | Weekly | Purchase Officer
41 |  | Purc |  |  | Pending GRN/Billing YTB accounted report |  | Weekly | Purchase Officer
42 |  | Purc |  |  | Overall Project Report Budget vs Actual and Status |  | Monthly | Purchase Manager
43 |  | Purc |  |  | Fund Requirments |  | Weekly | Purchase Manager
44 |  | Purc |  |  | Payment Request |  | Weekly/As Required | Purchase Officer
45 |  | Purc |  |  | Comparion Chart |  | Intiation | Purchase Officer
46 |  | Purc |  |  | Enquiry Document |  | Intiation | Purchase Officer
47 | PMO | PM |  | Project Management
48 | PMO | PM |  |  | Risk Register
49 | PMO | PM |  |  | Issue Register
50 | PMO | PM |  |  | Lessons Learned
51 | PMO | PM |  |  | Risk Database
52 | PMO | PM |  |  | Resource Utilization Reports
53 | PMO | PM |  |  | Quality Report
54 | PMO | PM |  |  | Communication Management Plan
55 | PMO | PM |  |  | Communciation Related Metrics
56 | PMO | PM |  |  | Stakeholder Register & Mgmt Plan
57 | PMO | PM |  |  | Project Life Cycle & Tailoring
58 | PMO | PM |  |  | Quality Checklists
59 | PMO | PM |  |  | Integrated Project Schedule
60 | PMO | PM |  |  | Project Critical Path/ Schedule
61 | PMO | PM |  |  | Project Charter
62 | PMO | PM |  |  | Configuration Management Plan
63 | PMO | PM |  |  | Procurement Management Plan
64 | ?? | Store |  |  | Inventory Status
65 | PMO | PM |  |  | Quality Policy Enforcement
66 | PMO | PM |  |  | Resource Assignment
67 | PMO | PM |  |  | Project Earned Value Report
68 | PMO | PM |  |  | Staffing Plan
69 | PMO | PM |  |  | Project Estimates
Historical Data
Standard darwing of equipment
Specificaiton sheets
BOM
Civil data
Vendor List
PO
Comparision of offers
Delivery Chart
Lessons Learned
Drawing vs physical condition mismatch equpment.
Due to extended monsson civil work delayed.
Non available of civil drawing on time
Delay in timely supervision of equpments
Standards
Comparision format
Order formats
Budget vs acutal report
Status report
P&ID tempatate
Specs tempalte
project charter
process log sheets
BOM

## 5
Work Breakdown Structure
Level 1 WBS | Level 2 WBS
Basic Engineering
Capacity working
Equipment Sizing
Macro sizing
Detail Engineering
P&ID
Civil drawing
Equipment layout
Specs of equipments
Take Approvals
Environment clearnce
EB Sanction
Boiler Approval
Execution Civil
Archi vendor finaization
Drawing release
procrement of cement and steel
Construction
Procure
Enqiry floating
Receiving quoation & comparision & finalization
Apprval of drawing
inspection & receipt of material
Intatallation
Erection of equpment
piping
electrical
insturctmentation
insullation and painting
Commissiong
pressure test
trial run
load test
water trial

## 6
Estimation Sheet
Level 1 WBS | Level 2 WBS | Duration | Resources
Basic Engineering
Capacity working
Equipment Sizing
Macro sizing
Detail Engineering
P&ID
Civil drawing
Equipment layout
Specs of equipments
Take Approvals
Environment clearnce
EB Sanction
Boiler Approval
Execution Civil
Archi vendor finaization
Drawing release
procrement of cement and steel
Construction
Procure
Enqiry floating
Note on C2: Hari Thapliyal: Break WBS Item if duration is more than 80 hours

## 7
Milestone List
# | Name | Date
1 | Basic Eng Completion | 2015-04-04
2 | Detail Eng completion | 2015-06-01

## 8
Prepare in MSP

## 9
Funding Requirements
Month | Fund Reqirment | Accumulative | Date
Mar'15 | 10000000 | 10000000
Apr'15 | 10000000 | 20000000
May'15 | 20000000 | 40000000

## 10
Quality Checklists Required
# | Name of Checklist | Purpose | Responsibility to Use | Checklist File Name
1 | Safety Checklist | Zero Accident | Safety Officer | safety-checklist.xls
2 | QAP Checklist | To maintain product standard & scheduled manufactoring stages | Third party inspector Project Manager | qap-checklist.xls

## 11
Risk Register
Risk Id | Risk Name | Risk Source | Risk Description | Probability | Impact | Impact Description | Exposure | Identifier | Owner | Assignee | Identification Date | Updation Date | Latest Status | Mitigation Plan | Contingency Plan
RK-01 | MOEF Approval | Govt | MOEF Approval requirment may change | 0.3 | 0.8 | Project will get delayed by 3 month | 0.24 | Raja | TRP | EK | 2015-03-10 | 2015-03-20 | Open | Preconsulting to govt official | Revisit project plan & nego baselines
RK-02 |  |  |  | 0.1 | 0.9 |  | 0.09 | [6 empty] | Meeting similar MOEF applied people

## 12
Requirement Tracablity Matrix
Req Id | HLR | Basic Design | Detail Desing | Implementation | Requirment Provider | Acceptance Criteria | Priority | Status
1 | Utility Facility

## 13
| Partiban | Linda | EK | KPS | Ashish | Marda
Basic design | A | R | C | C
Detail design | R | A | C | I
Procurment |  |  |  |  | A | R
Capcity calculation | R

## 14
Project-Code | Project Name | Sponsor | Project Manager | Schedule | Cost | Quality | Scope
| ABC | Krishna | Ram | Red | Red | Red | Red
| XYZ | Krishna | Mohan | Green | Red | Red | Red
| PQR | Krishna | Hari | Red | Red | Red | Red
| STU | Krishna | Shiva | Red | Green | Red | Red
| ABS | Krishna | John | Red | Red | Amber | Red

## 25
Lessons Learned
Phase | Date of LL Exercise | LL